## README
SYNTHETIC RFI / CHANGE ORDER DATASET – Sound Transit East Link (Bellevue/Overlake) & Downtown Redmond Link
Purpose: test whether categorizing RFIs by content can produce a meaningful importance ranking. ALL RFIs, change orders, amounts, dates and outcomes are synthetic (randomly generated with a fixed seed, 20261012). They are not Sound Transit records.
WHAT IS REAL (anchors from official/public sources)
• Downtown Redmond Link: 3.4 mi, 2 stations (Marymoor Village, Downtown Redmond), ~1,400-stall garage; baseline budget $1.53B (Board R2018-37, Oct 2018); single design-build contract; baseline NTP Q3 2019; opened May 10, 2025; Stacy Witbeck/Kuney JV; $25M contingency motion M2025-09 (Feb 2025, project 97% complete).
• East Link: baseline $3.677B (2015), later raised to $3.82B; civil packages E130/E320/E330/E335/E340/E360 plus E750 Systems; construction began 2016; 2 Line South Bellevue–Redmond Technology opened April 2024.
• E330 Bellevue tunnel: Atkinson low bid $121,446,551; authorized $133,591,206 (10% contingency). E360: Kiewit-Hoffman East Link Constructors, $225,336,088 base, $247,869,697 authorized, NTP June 2016. E340: Max J. Kuney, authorized cap $107,487,012 (M2021-06). E335: Stacy and Witbeck/Atkinson JV GC/CM (Feb 2017), +$10M contingency (M2021-05), board cited numerous design-related issues. E750: LTK Engineering is DSDC (M2020-19).
• Sound Transit reported East Link float was consumed by delays (E335/E750 area most); DRLE retained schedule float. The generator reflects this: higher critical-path delay and slower responses on E335/E750, lighter on DRLE.
WHAT IS ESTIMATED / SYNTHETIC
• Contract base values for E320, E335, E750, DRLE and the E320/E750 contractor names are NOT in the sources reviewed – see Contracts!source_status. Replace with Board motion values if you need exact figures.
• RFI counts (1,370), RFI text, dates, response times, cost and delay distributions are modeled. Total RFI-linked approved cost is calibrated to a % of contract base per package (see Contracts column and Summary sheet): E320 5.5%, E330 7%, E335 9%, E340 6%, E360 6.5%, E750 8%, DRLE 3%. These percentages are my modeling assumptions, not published figures.
HOW THE DATA WAS GENERATED
1. Each package gets RFIs spread over its construction window (bell-shaped intensity, weekdays only) with a category mix that fits its scope (e.g., E330 heavy on ground conditions, E750 on systems interfaces).
2. Each content category has its own probabilities/size for cost claims, schedule claims, critical-path exposure, response time and change-order conversion (Data_Dictionary + Summary show the resulting rates).
3. Contractor priority flag is deliberately NOISY (weakly correlated with true impact) so it does not trivially solve the ranking problem.
4. RFIs that convert are grouped into change orders (1–4 RFIs each, same package/category within ~90 days), then given outcomes: negotiated reduction, as requested, global settlement, rejected, withdrawn, partial, or DRB-escalated, with realistic cycle times.
5. true_priority_tier / rank / impact_score are GROUND TRUTH built from actual outcomes (approved cost 50%, critical-path delay 30%, float consumed 10%, time granted 10%). Tiers by rank: P1 top 8%, P2 next 17%, P3 next 30%, P4 rest.
HOW TO RUN YOUR TEST
• Use only columns flagged "Y" under available_at_submittal in Data_Dictionary as features (content category, location, spec section, package, discipline, contractor flags, description text). Exclude response/outcome/cost columns – they would leak the answer.
• Compare: (a) baseline = contractor_priority_flag, (b) category-only ranking, (c) category + location + critical-path flag, (d) text model on description. Evaluate against true_priority_tier (e.g., precision@P1/P2, Spearman vs true_priority_rank).
• Caveat: the category effects were built in by design, so a positive result confirms the pipeline works, not that real Sound Transit RFIs behave this way. Validate on real data before relying on it.
SHEETS: Contracts · RFIs · Change_Orders · CO_Outcomes · RFI_CO_Link · Data_Dictionary · Summary (live formulas). CSV copies provided separately. Cost fields in USD (year of expenditure, nominal).

## Summary
Summary by package (live formulas)
Package | RFIs | Change orders | % RFIs → CO | Avg initial response (days) | % on time | Total critical-path delay (days) | Approved RFI-linked cost ($) | Contract base ($) | Approved % of base | Total time granted (days)
E320 | 150 | 44 | 36% | 7.9067 | 77.33% | 283 | 10450200 | 190000000 | 5.5% | 178
E330 | 170 | 48 | 39.41% | 7.4647 | 78.82% | 197 | 8501200 | 121446551 | 7% | 131
E335 | 260 | 59 | 28.85% | 9.5615 | 68.85% | 492 | 25650000 | 285000000 | 9% | 294
E340 | 90 | 28 | 35.56% | 9.0556 | 72.22% | 172 | 5700100 | 95000000 | 6% | 73
E360 | 140 | 40 | 30.71% | 8.9286 | 72.14% | 262 | 14646900 | 225336088 | 6.5% | 133
E750 | 220 | 42 | 21.82% | 12.0864 | 74.55% | 486 | 28800000 | 360000000 | 8% | 331
DRLE | 340 | 67 | 23.53% | 7.3529 | 63.53% | 236 | 21600300 | 720000000 | 3% | 135
Total | 1370 | 328 |  |  |  | 2128 | 115348700 | 1996782639 | 5.777% | 1275
Summary by content category (the signal under test)
Category | RFIs | % RFIs → CO | Avg approved cost / RFI ($) | Avg critical-path delay (days) | Avg initial response (days) | % rated P1/P2 | % flagged Urgent by contractor
Third-Party / Permit / ROW Requirement | 131 | 18.32% | 26266.4122 | 1.8244 | 12.3435 | 16.79% | 16.79%
Architectural / Finishes / Station Elements | 74 | 4.054% | 1039.1892 | 0 | 5.3919 | 2.703% | 9.459%
Design Conflict / Constructability | 199 | 41.71% | 139631.6583 | 1.3518 | 8.7889 | 36.68% | 23.62%
Differing Site Conditions / Geotechnical | 144 | 65.97% | 202361.1111 | 2.7222 | 7.5556 | 54.17% | 21.53%
Environmental / Stormwater / Critical Areas | 68 | 14.71% | 21086.7647 | 0.5 | 10.6176 | 11.76% | 19.12%
Fire-Life-Safety / MEP / Tunnel Systems | 103 | 17.48% | 60204.8544 | 1.0388 | 10.5146 | 15.53% | 22.33%
Material / Submittal / Substitution | 72 | 4.167% | 1126.3889 | 0.19444 | 6.7778 | 4.167% | 15.28%
Staging / MOT / Access / Sequencing | 90 | 15.56% | 14980 | 1.4667 | 4.4556 | 13.33% | 22.22%
Spec / Drawing Clarification | 53 | 3.774% | 928.3019 | 0 | 4.2453 | 3.774% | 15.09%
Systems Interface (TPSS/OCS/Signals/Comms) | 172 | 22.09% | 79876.7442 | 3.314 | 13.3779 | 20.35% | 18.02%
Trackwork / Track-Structure Interface | 68 | 7.353% | 6750 | 0.19118 | 7.6471 | 5.882% | 17.65%
Utility Conflict / Relocation | 196 | 53.06% | 161188.2653 | 1.8265 | 8.0204 | 44.39% | 18.37%

## Contracts
package_id | project | package_name | contractor | delivery_method | contract_base_usd | authorized_incl_contingency_usd | synthetic_rfi_count | rfi_window_start | rfi_window_end | required_response_days | rfi_linked_approved_cost_target_pct_of_base | source_status
E320 | East Link Extension | South Bellevue (Station, garage, Bellevue Way/112th Ave SE road-over-rail) | E320 contractor (not named in sources) | Design-Bid-Build | 190000000 |  | 150 | 2016-03-01 | 2021-06-30 | 10 | 0.055 | Estimated (value not in sources)
E330 | East Link Extension | Downtown Bellevue Tunnel (SEM tunnel, 110th Ave NE) | Atkinson Construction (Guy F. Atkinson) | Design-Bid-Build | 121446551 | 133591206 | 170 | 2016-02-01 | 2021-03-31 | 10 | 0.07 | Base and authorized amounts verified (TunnelTalk, Nov 2015 bid result)
E335 | East Link Extension | Downtown Bellevue to Spring District (4 stations, I-405 bridge) | Stacy and Witbeck/Atkinson, JV | GC/CM (Heavy Civil) | 285000000 |  | 260 | 2017-02-01 | 2023-06-30 | 10 | 0.09 | Estimated; board motions confirm GC/CM award (Feb 2017), +$10M contingency (M2021-05), many design-related issues
E340 | East Link Extension | Bel-Red (130th Station, at-grade/aerial guideway) | Max J. Kuney Company | Design-Bid-Build | 95000000 | 107487012 | 90 | 2017-03-01 | 2021-06-30 | 10 | 0.06 | Authorized amount verified (M2021-06 cap $107,487,012); base estimated
E360 | East Link Extension | SR 520 to Overlake Transit Center (Overlake Village & Redmond Tech stations, 2 ped bridges) | Kiewit-Hoffman East Link Constructors | Design-Build | 225336088 | 247869697 | 140 | 2016-07-01 | 2021-09-30 | 10 | 0.065 | Base and authorized verified (Motion M2016-48; NTP June 2016)
E750 | East Link Extension | Systems (traction power, OCS, signals, communications, tunnel systems) | E750 Systems contractor (not named in sources) | Design-Bid-Build (DSDC: LTK Engineering) | 360000000 |  | 220 | 2018-01-15 | 2024-04-15 | 14 | 0.08 | Estimated; LTK DSDC and systems scope verified (Motion M2020-19)
DRLE | Downtown Redmond Link Extension | Downtown Redmond Link (3.4 mi, Marymoor Village & Downtown Redmond stations, 1,400-stall garage) | Stacy Witbeck/Kuney, JV | Design-Build (single contract) | 720000000 |  | 340 | 2019-09-01 | 2025-04-30 | 7 | 0.03 | Contractor verified (Railway News); contract value estimated; project budget $1.53B verified

## RFIs
rfi_id | package_id | project | contractor | location | content_category_code | content_category | discipline | spec_section | subject | description | submitted_by | submitted_date | required_response_days | contractor_priority_flag | contractor_claims_cost_impact | contractor_claims_schedule_impact | on_critical_path_at_submittal | attachments | assigned_reviewer | num_reviewers | response_date | response_days_initial | response_on_time | days_overdue_initial | revision_cycles | closed_date | response_days_final | status | schedule_impact_days_claimed | critical_path_delay_days_actual | float_consumed_days_actual | contractor_est_cost_low_usd | contractor_est_cost_high_usd | led_to_change_order | linked_co_ids | linked_requested_cost_usd | linked_approved_cost_usd | linked_time_granted_days | impact_score_0_100 | true_priority_rank | true_priority_tier
E320-RFI-0001 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | WSDOT comment on right-of-way use permit – Bellevue Way SE retained cut | WSDOT review comments on the right-of-way use permit require changes to the column reinforcement at Bellevue Way SE retained cut. Request direction on scope impacts and whether comments are within the contract requirements. | Project Engineer | 2016-08-18 | 10 | Urgent | Y | N | N | 8 | WSDOT / ST Third-Party Mgmt | 3 | 2016-08-30 | 12 | N | 2 | 1 | 2016-08-30 | 12 | Closed | 0 | 0 | 0 | 8000 | 15000 | N |  | 0 | 0 | 0 | 0 | 840 | P4 – Low
E320-RFI-0002 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Bellevue Way SE trench: petroleum-stained soil with odor | During excavation at Bellevue Way SE trench (Sta. 1148+29) the contractor encountered petroleum-stained soil with odor, not shown on the GBR or S-800. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Project Manager | 2016-08-29 | 10 | Routine | N | N | N | 7 | DSDC – HJH JV | 2 | 2016-09-08 | 10 | Y | 0 | 1 | 2016-09-08 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 841 | P4 – Low
E320-RFI-0003 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | City of Bellevue comment on building permit – 112th Ave SE road-over-rail structure | City of Bellevue review comments on the building permit require changes to the column reinforcement at 112th Ave SE road-over-rail structure. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2016-10-13 | 10 | Routine | N | N | N | 0 | City of Bellevue / ST Third-Party Mgmt | 3 | 2016-10-31 | 16 | N | 6 | 1 | 2016-10-31 | 16 | Closed | 0 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 692 | P3 – Medium
E320-RFI-0004 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | City of Bellevue comment on clearing and grading permit – Bellevue Way SE trench | City of Bellevue review comments on the clearing and grading permit require changes to the drilled shaft cap at Bellevue Way SE trench. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2016-11-07 | 10 | Routine | Y | N | N | 8 | WSDOT / ST Third-Party Mgmt | 1 | 2016-11-17 | 10 | Y | 0 | 1 | 2016-11-17 | 10 | Closed | 0 | 0 | 0 | 73000 | 136000 | Y | E320-CO-001 | 103900 | 44100 | 0 | 36.9 | 292 | P2 – High
E320-RFI-0005 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Art embed coordination – South Bellevue Station | Request to clarify finish/connection detail on C-536 at South Bellevue Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Manager | 2016-11-11 | 10 | Urgent | Y | Y | N | 7 | DSDC – HJH JV | 1 | 2016-11-15 | 4 | Y | 0 | 1 | 2016-11-15 | 4 | Closed | 2 | 0 | 1 | 26000 | 48000 | N |  | 0 | 0 | 0 | 0.2 | 761 | P4 – Low
E320-RFI-0006 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bellevue Way SE retained cut: perched groundwater | During excavation at Bellevue Way SE retained cut (Sta. 1312+21) the contractor encountered perched groundwater at approx. elevation 120 ft, not shown on the GBR or A-192. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Scheduler | 2016-12-28 | 10 | Routine | Y | Y | N | 7 | DSDC – HJH JV | 2 | 2017-01-04 | 7 | Y | 0 | 1 | 2017-01-04 | 7 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 842 | P4 – Low
E320-RFI-0007 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Art embed coordination – Mercer Slough interface | Request to clarify finish/connection detail on C-658 at Mercer Slough interface. Includes coordination with art program embeds and handrail sleeves as applicable. | Superintendent | 2017-01-10 | 10 | Routine | N | N | N | 7 | DSDC – HJH JV | 2 | 2017-01-18 | 8 | Y | 0 | 1 | 2017-01-18 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 843 | P4 – Low
E320-RFI-0008 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – Bellevue Way SE retained cut | Civil and systems drawings differ on grounding/bonding of column reinforcement for stray-current control at Bellevue Way SE retained cut. Request governing detail and responsibility for installation. | Scheduler | 2017-01-13 | 10 | Routine | N | Y | N | 3 | DSDC – HJH JV | 4 | 2017-01-25 | 12 | N | 2 | 1 | 2017-01-25 | 12 | Closed | 6 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 762 | P4 – Low
E320-RFI-0009 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 30-in. storm drain at South Bellevue parking garage | Potholing at Sta. 1181+44 located a 30-in. storm drain in conflict with the proposed guideway girder diaphragm. Utility is not shown on A-492. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Field Engineer | 2017-01-16 | 10 | Routine | Y | N | N | 5 | DSDC – HJH JV | 1 | 2017-01-30 | 13 | N | 3 | 1 | 2017-01-30 | 13 | Closed | 0 | 0 | 0 | 163000 | 305000 | Y | E320-CO-002 | 162700 | 0 | 0 | 0 | 844 | P4 – Low
E320-RFI-0010 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – station canopy support sequence at Bellevue Way SE trench | Erection of the station canopy support as drawn conflicts with adjacent work and access limits at Bellevue Way SE trench. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Superintendent | 2017-01-16 | 10 | Routine | N | Y | N | 1 | DSDC – HJH JV | 5 | 2017-01-27 | 11 | N | 1 | 1 | 2017-01-27 | 11 | Closed | 6 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 617 | P3 – Medium
E320-RFI-0011 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | SPC | Spec / Drawing Clarification | General | 01 25 00 Substitution Procedures | Drawing/spec discrepancy – South Bellevue Station | Request clarification of 01 25 00 Substitution Procedures and M-284: dimension/notes appear inconsistent or omitted for the work at South Bellevue Station. | Project Manager | 2017-01-20 | 10 | Routine | N | N | N | 6 | DSDC – HJH JV | 3 | 2017-01-23 | 3 | Y | 0 | 1 | 2017-01-23 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 845 | P4 – Low
E320-RFI-0012 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Drawing/spec discrepancy – Mercer Slough interface | Request clarification of 01 33 00 Submittal Procedures and A-227: dimension/notes appear inconsistent or omitted for the work at Mercer Slough interface. | Scheduler | 2017-01-23 | 10 | Routine | N | N | N | 5 | DSDC – HJH JV | 1 | 2017-01-30 | 5 | Y | 0 | 1 | 2017-01-30 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 846 | P4 – Low
E320-RFI-0013 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | SPC | Spec / Drawing Clarification | General | 01 25 00 Substitution Procedures | Clarify spec requirement – 112th Ave SE road-over-rail structure | Request clarification of 01 25 00 Substitution Procedures and C-720: dimension/notes appear inconsistent or omitted for the work at 112th Ave SE road-over-rail structure. | Project Engineer | 2017-02-20 | 10 | Routine | N | N | N | 2 | ST Design Management | 4 | 2017-02-28 | 8 | Y | 0 | 1 | 2017-02-28 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 847 | P4 – Low
E320-RFI-0014 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Mercer Slough interface: buried concrete debris and an old foundation | During excavation at Mercer Slough interface (Sta. 2086+58) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or S-666. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Project Manager | 2017-02-28 | 10 | Routine | Y | N | Y | 5 | DSDC – HJH JV | 2 | 2017-03-06 | 4 | Y | 0 | 1 | 2017-03-06 | 4 | Closed | 0 | 0 | 0 | 7000 | 12000 | Y | E320-CO-003 | 7860 | 4000 | 0 | 28.6 | 347 | P3 – Medium
E320-RFI-0015 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Bellevue Way SE retained cut: loose granular fill below planned bearing elevation | During excavation at Bellevue Way SE retained cut (Sta. 1413+01) the contractor encountered loose granular fill below planned bearing elevation, not shown on the GBR or M-184. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Design Manager | 2017-03-07 | 10 | Routine | N | Y | Y | 7 | DSDC – HJH JV | 1 | 2017-03-20 | 13 | N | 3 | 1 | 2017-03-20 | 13 | Closed | 30 | 23 | 0 |  |  | N |  | 0 | 0 | 0 | 23 | 354 | P3 – Medium
E320-RFI-0016 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Night work and noise variance – 112th Ave SE road-over-rail structure | Contractor requests approval of an alternate traffic/staging plan at 112th Ave SE road-over-rail structure: temporary lane shift. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Project Manager | 2017-03-09 | 10 | Expedite | N | Y | N | 7 | DSDC – HJH JV | 1 | 2017-03-14 | 5 | Y | 0 | 1 | 2017-03-14 | 5 | Closed | 10 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 618 | P3 – Medium
E320-RFI-0017 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Night work and noise variance – Mercer Slough interface | Contractor requests approval of an alternate traffic/staging plan at Mercer Slough interface: extended night closure. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Design Manager | 2017-03-27 | 10 | Routine | N | N | N | 2 | DSDC – HJH JV | 1 | 2017-04-03 | 7 | Y | 0 | 1 | 2017-04-03 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 848 | P4 – Low
E320-RFI-0018 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at South Bellevue parking garage: loose granular fill below planned bearing elevation | During excavation at South Bellevue parking garage (Sta. 1803+71) the contractor encountered loose granular fill below planned bearing elevation, not shown on the GBR or M-661. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Project Manager | 2017-03-29 | 10 | Routine | Y | N | N | 7 | DSDC – HJH JV | 2 | 2017-04-10 | 12 | N | 2 | 1 | 2017-04-10 | 12 | Closed | 0 | 0 | 0 | 128000 | 239000 | Y | E320-CO-003 | 179040 | 91100 | 0 | 39.4 | 248 | P2 – High
E320-RFI-0019 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Crane staging in right-of-way – Bellevue Way SE retained cut | Contractor requests approval of an alternate traffic/staging plan at Bellevue Way SE retained cut: temporary lane shift. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Field Engineer | 2017-04-14 | 10 | Routine | N | Y | N | 8 | DSDC – HJH JV | 1 | 2017-04-17 | 3 | Y | 0 | 1 | 2017-04-17 | 3 | Closed | 26 | 0 | 14 |  |  | N |  | 0 | 0 | 0 | 3.1 | 468 | P3 – Medium
E320-RFI-0020 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – guideway girder diaphragm at South Bellevue Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-200 for egress width at South Bellevue Station. Request direction on compliant detail. | Superintendent | 2017-04-17 | 10 | Expedite | Y | N | N | 8 | DSDC – HJH JV | 5 | 2017-04-25 | 8 | Y | 0 | 1 | 2017-04-25 | 8 | Closed | 0 | 0 | 0 | 41000 | 76000 | Y | E320-CO-004 | 33200 | 15600 | 0 | 33.3 | 325 | P2 – High
E320-RFI-0021 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Haul route revision – 112th Ave SE road-over-rail structure | Contractor requests approval of an alternate traffic/staging plan at 112th Ave SE road-over-rail structure: revised haul route. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Field Engineer | 2017-05-08 | 10 | Routine | N | Y | N | 0 | DSDC – HJH JV | 3 | 2017-05-12 | 4 | Y | 0 | 2 | 2017-05-29 | 19 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 849 | P4 – Low
E320-RFI-0022 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Property owner access/restoration requirement – South Bellevue parking garage | Adjacent property owner has requested additional restoration and access provisions at South Bellevue parking garage beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Superintendent | 2017-05-15 | 10 | Routine | N | N | Y | 2 | Puget Sound Energy / ST Third-Party Mgmt | 3 | 2017-05-26 | 11 | N | 1 | 1 | 2017-05-26 | 11 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 850 | P4 – Low
E320-RFI-0023 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Rail Bonding location conflict at Sta. 2245+62 | Proposed rail bonding foundation location at Sta. 2245+62 conflicts with stair core wall; offset of 3 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2017-05-29 | 10 | Routine | N | Y | N | 1 | DSDC – HJH JV | 1 | 2017-06-05 | 6 | Y | 0 | 2 | 2017-06-20 | 22 | Closed | 7 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 693 | P3 – Medium
E320-RFI-0024 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Grounding/bonding and stray-current detail – Bellevue Way SE retained cut | Civil and systems drawings differ on grounding/bonding of pedestrian ramp for stray-current control at Bellevue Way SE retained cut. Request governing detail and responsibility for installation. | Project Manager | 2017-06-26 | 10 | Expedite | N | N | Y | 6 | DSDC – HJH JV | 2 | 2017-07-17 | 21 | N | 11 | 2 | 2017-07-26 | 30 | Closed | 0 | 4 | 0 |  |  | N |  | 0 | 0 | 0 | 4 | 449 | P3 – Medium
E320-RFI-0025 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Bellevue Way SE trench | Systems contractor requires 4-in. PVC conduit stub-ups for OCS pole at Bellevue Way SE trench not provided in civil M-820. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Project Manager | 2017-07-14 | 10 | Routine | N | N | N | 4 | ST Design Management | 2 | 2017-07-31 | 15 | N | 5 | 1 | 2017-07-31 | 15 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 851 | P4 – Low
E320-RFI-0026 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at 112th Ave SE road-over-rail structure: an unmapped abandoned storm line | During excavation at 112th Ave SE road-over-rail structure (Sta. 1590+90) the contractor encountered an unmapped abandoned storm line, not shown on the GBR or M-433. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Project Engineer | 2017-07-26 | 10 | Routine | N | Y | N | 4 | DSDC – HJH JV | 1 | 2017-07-31 | 4 | Y | 0 | 1 | 2017-07-31 | 4 | Closed | 3 | 0 | 2 |  |  | Y | E320-CO-005 | 17400 | 11100 | 1 | 32.9 | 329 | P2 – High
E320-RFI-0027 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with PSE distribution duct bank at 112th Ave SE road-over-rail structure | Potholing at Sta. 1114+61 located a PSE distribution duct bank in conflict with the proposed column reinforcement. Utility is not shown on A-225. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Field Engineer | 2017-08-07 | 10 | Urgent | Y | Y | Y | 0 | DSDC – HJH JV | 2 | 2017-08-21 | 12 | N | 2 | 1 | 2017-08-21 | 12 | Closed | 9 | 7 | 0 | 286000 | 534000 | Y | E320-CO-006 | 309830 | 309830 | 11.2 | 54.3 | 27 | P1 – Critical
E320-RFI-0028 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Lane closure window request – South Bellevue parking garage | Contractor requests approval of an alternate traffic/staging plan at South Bellevue parking garage: extended night closure. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Scheduler | 2017-08-28 | 10 | Urgent | Y | Y | Y | 8 | DSDC – HJH JV | 4 | 2017-09-04 | 7 | Y | 0 | 1 | 2017-09-04 | 7 | Closed | 31 | 14 | 0 | 35000 | 65000 | N |  | 0 | 0 | 0 | 14 | 373 | P3 – Medium
E320-RFI-0029 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 24-in. sanitary sewer at South Bellevue parking garage | Potholing at Sta. 1494+74 located a 24-in. sanitary sewer in conflict with the proposed stair core wall. Utility is not shown on M-865. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Engineer | 2017-09-04 | 10 | Expedite | Y | Y | N | 4 | DSDC – HJH JV | 2 | 2017-09-07 | 3 | Y | 0 | 2 | 2017-09-25 | 19 | Closed | 9 | 0 | 3 | 242000 | 451000 | Y | E320-CO-006 | 213470 | 213470 | 7.8 | 45.6 | 129 | P2 – High
E320-RFI-0030 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at South Bellevue parking garage: abandoned timber piles | During excavation at South Bellevue parking garage (Sta. 1096+62) the contractor encountered abandoned timber piles, not shown on the GBR or M-189. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Scheduler | 2017-09-06 | 10 | Routine | Y | Y | N | 6 | ST Design Management | 4 | 2017-09-14 | 8 | Y | 0 | 1 | 2017-09-14 | 8 | Closed | 12 | 0 | 8 | 120000 | 224000 | Y | E320-CO-007 | 95150 | 95150 | 6.9 | 43.6 | 166 | P2 – High
E320-RFI-0031 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Direct fixation fastener spacing at Sta. 1723+12 | Track layout at Sta. 1723+12 (Bellevue Way SE retained cut) differs from the track-structure interface drawing A-374. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2017-09-13 | 10 | Urgent | Y | Y | N | 1 | DSDC – HJH JV | 4 | 2017-09-15 | 2 | Y | 0 | 1 | 2017-09-15 | 2 | Closed | 5 | 0 | 1 | 869000 | 1623000 | N |  | 0 | 0 | 0 | 0.2 | 763 | P4 – Low
E320-RFI-0032 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – 112th Ave SE road-over-rail structure | A-143 shows a 25 ft-1 in. dimension for the column reinforcement; structural sheet S-460 shows a different value. Request clarification before fabrication/rebar release. | Design Manager | 2017-09-13 | 10 | Routine | N | N | N | 0 | DSDC – HJH JV | 1 | 2017-09-21 | 8 | Y | 0 | 1 | 2017-09-21 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 852 | P4 – Low
E320-RFI-0033 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Mercer Slough interface: abandoned timber piles | During excavation at Mercer Slough interface (Sta. 2061+44) the contractor encountered abandoned timber piles, not shown on the GBR or E-170. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Superintendent | 2017-09-15 | 10 | Routine | Y | Y | N | 6 | DSDC – HJH JV | 1 | 2017-09-22 | 7 | Y | 0 | 1 | 2017-09-22 | 7 | Closed | 5 | 0 | 2 | 74000 | 138000 | Y | E320-CO-007 | 56250 | 56250 | 4.1 | 39.5 | 247 | P2 – High
E320-RFI-0034 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – pedestrian ramp sequence at Bellevue Way SE trench | Erection of the pedestrian ramp as drawn conflicts with adjacent work and access limits at Bellevue Way SE trench. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2017-10-13 | 10 | Expedite | Y | N | N | 8 | DSDC – HJH JV | 1 | 2017-10-23 | 8 | Y | 0 | 1 | 2017-10-23 | 8 | Closed | 0 | 0 | 0 | 40000 | 75000 | Y | E320-CO-008 | 32200 | 19000 | 0 | 34 | 321 | P2 – High
E320-RFI-0035 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at Mercer Slough interface, citing procurement lead time. Product data attached. | Design Manager | 2017-10-17 | 10 | Urgent | Y | Y | N | 8 | DSDC – HJH JV | 1 | 2017-10-26 | 9 | Y | 0 | 1 | 2017-10-26 | 9 | Closed | 5 | 0 | 2 | 21000 | 39000 | N |  | 0 | 0 | 0 | 0.4 | 694 | P3 – Medium
E320-RFI-0036 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | In-water work window – South Bellevue parking garage | Field conditions at South Bellevue parking garage require changes to temporary erosion and sediment control or stormwater facility per E-821. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2017-10-23 | 10 | Routine | N | N | Y | 4 | DSDC – HJH JV | 2 | 2017-11-23 | 31 | N | 21 | 1 | 2017-11-23 | 31 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 853 | P4 – Low
E320-RFI-0037 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – guideway girder diaphragm and retaining wall footing at Bellevue Way SE trench | Interference between guideway girder diaphragm and retaining wall footing at Bellevue Way SE trench per C-850. Required clearance of 7 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Scheduler | 2017-10-24 | 10 | Expedite | N | Y | Y | 5 | DSDC – HJH JV | 1 | 2017-10-27 | 3 | Y | 0 | 2 | 2017-11-08 | 15 | Closed | 17 | 12 | 0 |  |  | N |  | 0 | 0 | 0 | 12 | 376 | P3 – Medium
E320-RFI-0038 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at 112th Ave SE road-over-rail structure: glacially deposited boulders exceeding 36 in. | During excavation at 112th Ave SE road-over-rail structure (Sta. 2200+81) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or E-343. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Field Engineer | 2017-10-30 | 10 | Routine | Y | Y | Y | 1 | DSDC – HJH JV | 5 | 2017-11-06 | 7 | Y | 0 | 1 | 2017-11-06 | 7 | Closed | 28 | 16 | 0 | 1081000 | 2019000 | Y | E320-CO-012 | 2358420 | 2063530 | 22.7 | 73.6 | 4 | P1 – Critical
E320-RFI-0039 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – Bellevue Way SE retained cut | Systems contractor requires 3-in. PVC conduit stub-ups for SCADA cabinet at Bellevue Way SE retained cut not provided in civil C-108. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2017-11-08 | 10 | Routine | Y | Y | Y | 2 | DSDC – HJH JV | 2 | 2017-11-27 | 18 | N | 8 | 2 | 2017-12-12 | 34 | Closed | 6 | 8 | 0 | 132000 | 246000 | Y | E320-CO-010 | 114600 | 114600 | 5 | 49.8 | 62 | P1 – Critical
E320-RFI-0040 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – Mercer Slough interface | E-158 shows a 27 ft-3 in. dimension for the column reinforcement; structural sheet S-664 shows a different value. Request clarification before fabrication/rebar release. | Superintendent | 2017-11-10 | 10 | Routine | Y | N | N | 6 | DSDC – HJH JV | 2 | 2017-11-15 | 5 | Y | 0 | 1 | 2017-11-15 | 5 | Closed | 0 | 0 | 0 | 62000 | 116000 | Y | E320-CO-009 | 34500 | 23800 | 0 | 34.7 | 317 | P2 – High
E320-RFI-0041 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Clarify spec requirement – 112th Ave SE road-over-rail structure | Request clarification of 01 25 00 Substitution Procedures and C-767: dimension/notes appear inconsistent or omitted for the work at 112th Ave SE road-over-rail structure. | Scheduler | 2017-11-13 | 10 | Routine | N | N | N | 8 | DSDC – HJH JV | 2 | 2017-11-20 | 5 | Y | 0 | 1 | 2017-11-20 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 854 | P4 – Low
E320-RFI-0042 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 24-in. sanitary sewer at South Bellevue Station | Potholing at Sta. 1529+20 located a 24-in. sanitary sewer in conflict with the proposed column reinforcement. Utility is not shown on A-430. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Project Engineer | 2017-12-18 | 10 | Expedite | Y | Y | Y | 0 | DSDC – HJH JV | 2 | 2017-12-25 | 5 | Y | 0 | 1 | 2017-12-25 | 5 | Closed | 28 | 14 | 0 | 201000 | 374000 | Y | E320-CO-011 | 275210 | 175760 | 11.4 | 59.4 | 18 | P1 – Critical
E320-RFI-0043 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with PSE distribution duct bank at 112th Ave SE road-over-rail structure | Potholing at Sta. 1037+17 located a PSE distribution duct bank in conflict with the proposed guideway girder diaphragm. Utility is not shown on C-310. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2017-12-25 | 10 | Expedite | Y | N | N | 6 | DSDC – HJH JV | 2 | 2018-01-01 | 5 | Y | 0 | 1 | 2018-01-01 | 5 | Closed | 0 | 0 | 0 | 71000 | 133000 | Y | E320-CO-011 | 111390 | 71140 | 4.6 | 40 | 235 | P2 – High
E320-RFI-0044 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – guideway girder diaphragm and column reinforcement at South Bellevue Station | Interference between guideway girder diaphragm and column reinforcement at South Bellevue Station per A-680. Required clearance of 4 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2018-01-05 | 10 | Routine | N | Y | Y | 0 | DSDC – HJH JV | 1 | 2018-01-12 | 7 | Y | 0 | 1 | 2018-01-12 | 7 | Closed | 10 | 8 | 0 |  |  | N |  | 0 | 0 | 0 | 8 | 406 | P3 – Medium
E320-RFI-0045 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – bearing pad/embed plate and duct bank encasement at South Bellevue parking garage | Interference between bearing pad/embed plate and duct bank encasement at South Bellevue parking garage per C-287. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2018-01-05 | 10 | Routine | N | Y | Y | 0 | DSDC – HJH JV | 3 | 2018-01-26 | 21 | N | 11 | 2 | 2018-02-16 | 42 | Closed | 15 | 9 | 0 |  |  | N |  | 0 | 0 | 0 | 9 | 397 | P3 – Medium
E320-RFI-0046 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | In-water work window – Bellevue Way SE trench | Field conditions at Bellevue Way SE trench require changes to temporary erosion and sediment control or stormwater facility per M-673. Request direction considering critical-areas conditions and permit requirements. | Scheduler | 2018-01-16 | 10 | Expedite | Y | N | N | 5 | DSDC – HJH JV | 1 | 2018-01-30 | 14 | N | 4 | 2 | 2018-02-12 | 27 | Closed | 0 | 0 | 0 | 147000 | 275000 | N |  | 0 | 0 | 0 | 0 | 855 | P4 – Low
E320-RFI-0047 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Bellevue Way SE trench: glacially deposited boulders exceeding 36 in. | During excavation at Bellevue Way SE trench (Sta. 969+12) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or C-682. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Superintendent | 2018-01-17 | 10 | Routine | Y | Y | N | 3 | DSDC – HJH JV | 5 | 2018-01-25 | 8 | Y | 0 | 1 | 2018-01-25 | 8 | Closed | 4 | 0 | 1 | 454000 | 848000 | Y | E320-CO-012 | 448780 | 392670 | 4.3 | 46 | 122 | P2 – High
E320-RFI-0048 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – 112th Ave SE road-over-rail structure | Civil and systems drawings differ on grounding/bonding of station canopy support for stray-current control at 112th Ave SE road-over-rail structure. Request governing detail and responsibility for installation. | Design Manager | 2018-01-29 | 10 | Expedite | N | Y | N | 4 | DSDC – HJH JV | 2 | 2018-02-05 | 6 | Y | 0 | 1 | 2018-02-05 | 6 | Closed | 10 | 0 | 7 |  |  | N |  | 0 | 0 | 0 | 1.6 | 547 | P3 – Medium
E320-RFI-0049 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – platform edge slab sequence at Bellevue Way SE trench | Erection of the platform edge slab as drawn conflicts with adjacent work and access limits at Bellevue Way SE trench. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Field Engineer | 2018-02-01 | 10 | Routine | Y | N | N | 1 | DSDC – HJH JV | 1 | 2018-02-08 | 7 | Y | 0 | 1 | 2018-02-08 | 7 | Closed | 0 | 0 | 0 | 45000 | 84000 | Y | E320-CO-013 | 42100 | 13900 | 0 | 32.9 | 330 | P2 – High
E320-RFI-0050 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Embedded conduit stub-ups – South Bellevue parking garage | Systems contractor requires 3-in. PVC conduit stub-ups for signal case at South Bellevue parking garage not provided in civil S-281. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Scheduler | 2018-02-05 | 10 | Expedite | Y | N | N | 2 | DSDC – HJH JV | 3 | 2018-02-15 | 10 | Y | 0 | 2 | 2018-03-05 | 27 | Closed | 0 | 0 | 0 | 133000 | 248000 | N |  | 0 | 0 | 0 | 0 | 856 | P4 – Low
E320-RFI-0051 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Puget Sound Energy comment on building permit – Bellevue Way SE trench | Puget Sound Energy review comments on the building permit require changes to the pedestrian ramp at Bellevue Way SE trench. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2018-02-19 | 10 | Routine | N | Y | N | 5 | Puget Sound Energy / ST Third-Party Mgmt | 2 | 2018-03-07 | 16 | N | 6 | 1 | 2018-03-07 | 16 | Closed | 34 | 0 | 15 |  |  | N |  | 0 | 0 | 0 | 3.3 | 466 | P3 – Medium
E320-RFI-0052 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – stair core wall and drilled shaft cap at South Bellevue Station | Interference between stair core wall and drilled shaft cap at South Bellevue Station per A-627. Required clearance of 2 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2018-02-20 | 10 | Routine | N | N | N | 7 | DSDC – HJH JV | 1 | 2018-02-28 | 8 | Y | 0 | 1 | 2018-02-28 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 857 | P4 – Low
E320-RFI-0053 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – South Bellevue parking garage | A-873 shows a 42 ft-0 in. dimension for the column reinforcement; structural sheet S-221 shows a different value. Request clarification before fabrication/rebar release. | Design Manager | 2018-03-02 | 10 | Urgent | Y | N | Y | 0 | DSDC – HJH JV | 2 | 2018-03-12 | 9 | Y | 0 | 1 | 2018-03-12 | 9 | Closed | 0 | 0 | 0 | 286000 | 535000 | N |  | 0 | 0 | 0 | 0 | 858 | P4 – Low
E320-RFI-0054 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Track slab/expansion joint interface – Mercer Slough interface | Track layout at Sta. 1806+05 (Mercer Slough interface) differs from the track-structure interface drawing M-333. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Engineer | 2018-03-09 | 10 | Routine | N | N | N | 4 | DSDC – HJH JV | 1 | 2018-03-16 | 7 | Y | 0 | 2 | 2018-04-05 | 27 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 859 | P4 – Low
E320-RFI-0055 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Bellevue Way SE trench: petroleum-stained soil with odor | During excavation at Bellevue Way SE trench (Sta. 2031+24) the contractor encountered petroleum-stained soil with odor, not shown on the GBR or S-230. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Project Engineer | 2018-03-12 | 10 | Routine | Y | N | Y | 3 | DSDC – HJH JV | 1 | 2018-03-19 | 5 | Y | 0 | 1 | 2018-03-19 | 5 | Closed | 0 | 0 | 0 | 402000 | 751000 | Y | E320-CO-014 | 463100 | 157000 | 0 | 41.2 | 214 | P2 – High
E320-RFI-0056 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Property owner access/restoration requirement – Bellevue Way SE trench | Adjacent property owner has requested additional restoration and access provisions at Bellevue Way SE trench beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Project Manager | 2018-03-15 | 10 | Expedite | Y | Y | N | 2 | WSDOT / ST Third-Party Mgmt | 2 | 2018-04-02 | 16 | N | 6 | 1 | 2018-04-02 | 16 | Closed | 13 | 0 | 5 | 81000 | 152000 | N |  | 0 | 0 | 0 | 1.1 | 571 | P3 – Medium
E320-RFI-0057 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Crane staging in right-of-way – Bellevue Way SE retained cut | Contractor requests approval of an alternate traffic/staging plan at Bellevue Way SE retained cut: revised haul route. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Scheduler | 2018-03-19 | 10 | Urgent | N | Y | Y | 1 | DSDC – HJH JV | 2 | 2018-03-26 | 5 | Y | 0 | 1 | 2018-03-26 | 5 | Closed | 13 | 10 | 0 |  |  | N |  | 0 | 0 | 0 | 10 | 393 | P3 – Medium
E320-RFI-0058 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – retaining wall footing sequence at Bellevue Way SE trench | Erection of the retaining wall footing as drawn conflicts with adjacent work and access limits at Bellevue Way SE trench. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Scheduler | 2018-03-27 | 10 | Routine | Y | Y | N | 5 | DSDC – HJH JV | 2 | 2018-04-09 | 13 | N | 3 | 2 | 2018-04-30 | 33 | Closed | 3 | 0 | 3 | 59000 | 110000 | Y | E320-CO-015 | 120600 | 84200 | 1 | 40.1 | 232 | P2 – High
E320-RFI-0059 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – guideway girder diaphragm and column reinforcement at South Bellevue parking garage | Interference between guideway girder diaphragm and column reinforcement at South Bellevue parking garage per A-179. Required clearance of 6 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Field Engineer | 2018-04-10 | 10 | Routine | N | N | Y | 8 | DSDC – HJH JV | 3 | 2018-04-18 | 8 | Y | 0 | 1 | 2018-04-18 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 860 | P4 – Low
E320-RFI-0060 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – Bellevue Way SE retained cut | S-278 shows a 27 ft-3 in. dimension for the retaining wall footing; structural sheet S-313 shows a different value. Request clarification before fabrication/rebar release. | Superintendent | 2018-04-11 | 10 | Expedite | N | Y | N | 2 | ST Design Management | 1 | 2018-04-16 | 5 | Y | 0 | 2 | 2018-05-04 | 23 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 764 | P4 – Low
E320-RFI-0061 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Mercer Slough interface: abandoned timber piles | During excavation at Mercer Slough interface (Sta. 1591+32) the contractor encountered abandoned timber piles, not shown on the GBR or E-712. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Design Manager | 2018-04-16 | 10 | Routine | N | N | N | 5 | ST Design Management | 3 | 2018-04-23 | 7 | Y | 0 | 2 | 2018-05-14 | 26 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 861 | P4 – Low
E320-RFI-0062 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – column reinforcement and guideway girder diaphragm at South Bellevue parking garage | Interference between column reinforcement and guideway girder diaphragm at South Bellevue parking garage per A-185. Required clearance of 4 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2018-04-20 | 10 | Routine | Y | N | N | 1 | DSDC – HJH JV | 4 | 2018-04-25 | 5 | Y | 0 | 1 | 2018-04-25 | 5 | Closed | 0 | 0 | 0 | 53000 | 99000 | Y | E320-CO-016 | 34800 | 28500 | 0 | 35.4 | 309 | P2 – High
E320-RFI-0063 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | City of Bellevue comment on street improvement permit – Mercer Slough interface | City of Bellevue review comments on the street improvement permit require changes to the pedestrian ramp at Mercer Slough interface. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2018-05-01 | 10 | Routine | Y | Y | N | 4 | WSDOT / ST Third-Party Mgmt | 3 | 2018-05-16 | 15 | N | 5 | 2 | 2018-05-30 | 29 | Closed | 3 | 0 | 2 | 276000 | 515000 | Y | E320-CO-018 | 265800 | 212200 | 2 | 43.4 | 170 | P2 – High
E320-RFI-0064 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – column reinforcement sequence at South Bellevue parking garage | Erection of the column reinforcement as drawn conflicts with adjacent work and access limits at South Bellevue parking garage. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2018-05-01 | 10 | Routine | Y | Y | Y | 0 | DSDC – HJH JV | 2 | 2018-05-07 | 5 | Y | 0 | 1 | 2018-05-07 | 5 | Closed | 13 | 4 | 0 | 22000 | 40000 | Y | E320-CO-017 | 38200 | 35100 | 7 | 42.4 | 191 | P2 – High
E320-RFI-0065 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Bellevue Way SE trench | A-124 shows a 37 ft-10 in. dimension for the drilled shaft cap; structural sheet S-580 shows a different value. Request clarification before fabrication/rebar release. | Project Manager | 2018-05-04 | 10 | Expedite | N | N | N | 0 | DSDC – HJH JV | 2 | 2018-05-15 | 11 | N | 1 | 1 | 2018-05-15 | 11 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 862 | P4 – Low
E320-RFI-0066 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Drawing/spec discrepancy – Bellevue Way SE trench | Request clarification of 01 33 00 Submittal Procedures and M-154: dimension/notes appear inconsistent or omitted for the work at Bellevue Way SE trench. | Superintendent | 2018-05-16 | 10 | Urgent | N | N | N | 7 | ST Design Management | 5 | 2018-05-22 | 6 | Y | 0 | 1 | 2018-05-22 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 863 | P4 – Low
E320-RFI-0067 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Night work and noise variance – South Bellevue Station | Contractor requests approval of an alternate traffic/staging plan at South Bellevue Station: extended night closure. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Design Manager | 2018-06-06 | 10 | Urgent | Y | Y | Y | 5 | DSDC – HJH JV | 2 | 2018-06-08 | 2 | Y | 0 | 2 | 2018-06-25 | 18 | Closed | 39 | 33 | 0 | 50000 | 93000 | Y | E320-CO-019 | 65130 | 0 | 0 | 30 | 342 | P2 – High
E320-RFI-0068 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Night work and noise variance – South Bellevue parking garage | Contractor requests approval of an alternate traffic/staging plan at South Bellevue parking garage: temporary lane shift. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Project Manager | 2018-06-08 | 10 | Routine | Y | N | Y | 4 | DSDC – HJH JV | 3 | 2018-06-11 | 2 | Y | 0 | 2 | 2018-06-25 | 17 | Closed | 0 | 3 | 0 | 85000 | 158000 | Y | E320-CO-019 | 110670 | 0 | 0 | 3 | 472 | P3 – Medium
E320-RFI-0069 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Canopy/glazing connection – Bellevue Way SE trench | Request to clarify finish/connection detail on M-500 at Bellevue Way SE trench. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Manager | 2018-06-11 | 10 | Routine | N | N | N | 6 | DSDC – HJH JV | 3 | 2018-06-18 | 6 | Y | 0 | 1 | 2018-06-18 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 864 | P4 – Low
E320-RFI-0070 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Direct fixation fastener spacing at Sta. 1629+81 | Track layout at Sta. 1629+81 (Bellevue Way SE retained cut) differs from the track-structure interface drawing S-573. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Superintendent | 2018-06-13 | 10 | Routine | N | Y | N | 2 | DSDC – HJH JV | 2 | 2018-07-04 | 21 | N | 11 | 1 | 2018-07-04 | 21 | Closed | 9 | 0 | 9 |  |  | N |  | 0 | 0 | 0 | 2 | 510 | P3 – Medium
E320-RFI-0071 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – drilled shaft cap at 112th Ave SE road-over-rail structure | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-469 for emergency stair pressurization at 112th Ave SE road-over-rail structure. Request direction on compliant detail. | Project Manager | 2018-06-18 | 10 | Urgent | N | Y | N | 6 | DSDC – HJH JV | 2 | 2018-06-25 | 7 | Y | 0 | 1 | 2018-06-25 | 7 | Closed | 7 | 0 | 6 |  |  | N |  | 0 | 0 | 0 | 1.3 | 562 | P3 – Medium
E320-RFI-0072 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Clarify spec requirement – South Bellevue Station | Request clarification of 01 25 00 Substitution Procedures and M-700: dimension/notes appear inconsistent or omitted for the work at South Bellevue Station. | Field Engineer | 2018-06-29 | 10 | Urgent | N | Y | N | 2 | DSDC – HJH JV | 2 | 2018-07-03 | 4 | Y | 0 | 1 | 2018-07-03 | 4 | Closed | 1 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 765 | P4 – Low
E320-RFI-0073 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at South Bellevue Station: an unmapped abandoned storm line | During excavation at South Bellevue Station (Sta. 2074+37) the contractor encountered an unmapped abandoned storm line, not shown on the GBR or E-792. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Superintendent | 2018-08-10 | 10 | Expedite | Y | Y | Y | 6 | ST Design Management | 1 | 2018-08-20 | 8 | Y | 0 | 2 | 2018-08-27 | 16 | Closed | 20 | 9 | 0 | 301000 | 562000 | Y | E320-CO-021 | 395550 | 298590 | 7.4 | 54.9 | 25 | P1 – Critical
E320-RFI-0074 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Crane staging in right-of-way – South Bellevue Station | Contractor requests approval of an alternate traffic/staging plan at South Bellevue Station: extended night closure. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Design Manager | 2018-09-03 | 10 | Routine | Y | N | N | 7 | DSDC – HJH JV | 2 | 2018-09-06 | 3 | Y | 0 | 1 | 2018-09-06 | 3 | Closed | 0 | 0 | 0 | 739000 | 1380000 | N |  | 0 | 0 | 0 | 0 | 865 | P4 – Low
E320-RFI-0075 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | SPC | Spec / Drawing Clarification | General | 01 25 00 Substitution Procedures | Missing dimension on C-279 | Request clarification of 00 72 00 General Conditions and C-279: dimension/notes appear inconsistent or omitted for the work at South Bellevue Station. | Scheduler | 2018-09-06 | 10 | Urgent | N | N | N | 7 | DSDC – HJH JV | 1 | 2018-09-10 | 3 | Y | 0 | 1 | 2018-09-10 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 866 | P4 – Low
E320-RFI-0076 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – pedestrian ramp at South Bellevue parking garage | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-112 for fire alarm device layout at South Bellevue parking garage. Request direction on compliant detail. | Design Manager | 2018-09-12 | 10 | Routine | N | N | N | 0 | ST Design Management | 3 | 2018-09-19 | 7 | Y | 0 | 1 | 2018-09-19 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 867 | P4 – Low
E320-RFI-0077 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at South Bellevue Station: glacially deposited boulders exceeding 36 in. | During excavation at South Bellevue Station (Sta. 1374+95) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or E-542. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Scheduler | 2018-09-13 | 10 | Urgent | Y | Y | Y | 7 | ST Design Management | 2 | 2018-09-17 | 3 | Y | 0 | 2 | 2018-10-02 | 19 | Closed | 8 | 4 | 0 | 493000 | 920000 | Y | E320-CO-021 | 404450 | 305310 | 7.6 | 50.1 | 55 | P1 – Critical
E320-RFI-0078 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with fiber communications duct bank at Bellevue Way SE trench | Potholing at Sta. 1350+76 located a fiber communications duct bank in conflict with the proposed retaining wall footing. Utility is not shown on C-532. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Project Engineer | 2018-09-13 | 10 | Expedite | Y | Y | Y | 3 | DSDC – HJH JV | 2 | 2018-09-19 | 6 | Y | 0 | 1 | 2018-09-19 | 6 | Closed | 4 | 2 | 0 | 52000 | 97000 | Y | E320-CO-020 | 134600 | 97800 | 1 | 41.9 | 201 | P2 – High
E320-RFI-0079 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with fiber communications duct bank at Mercer Slough interface | Potholing at Sta. 2346+39 located a fiber communications duct bank in conflict with the proposed pedestrian ramp. Utility is not shown on A-244. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Scheduler | 2018-09-24 | 10 | Routine | N | N | Y | 6 | DSDC – HJH JV | 1 | 2018-10-09 | 15 | N | 5 | 1 | 2018-10-09 | 15 | Closed | 0 | 1 | 0 |  |  | N |  | 0 | 0 | 0 | 1 | 603 | P3 – Medium
E320-RFI-0080 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Night work and noise variance – Bellevue Way SE retained cut | Contractor requests approval of an alternate traffic/staging plan at Bellevue Way SE retained cut: crane pick over active roadway. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Superintendent | 2018-10-08 | 10 | Urgent | N | N | N | 7 | ST Design Management | 2 | 2018-10-15 | 6 | Y | 0 | 1 | 2018-10-15 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 868 | P4 – Low
E320-RFI-0081 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – bearing pad/embed plate and drilled shaft cap at 112th Ave SE road-over-rail structure | Interference between bearing pad/embed plate and drilled shaft cap at 112th Ave SE road-over-rail structure per E-184. Required clearance of 2 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2018-10-12 | 10 | Expedite | Y | Y | Y | 4 | DSDC – HJH JV | 2 | 2018-10-22 | 8 | Y | 0 | 2 | 2018-11-12 | 29 | Closed | 4 | 3 | 0 | 225000 | 420000 | Y | E320-CO-023 | 252200 | 155700 | 1 | 44.5 | 148 | P2 – High
E320-RFI-0082 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 12-in. ductile iron water main at 112th Ave SE road-over-rail structure | Potholing at Sta. 2189+54 located a 12-in. ductile iron water main in conflict with the proposed guideway girder diaphragm. Utility is not shown on C-397. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Design Manager | 2018-10-12 | 10 | Expedite | Y | Y | Y | 7 | DSDC – HJH JV | 2 | 2018-10-19 | 7 | Y | 0 | 2 | 2018-11-06 | 25 | Closed | 7 | 4 | 0 | 96000 | 179000 | Y | E320-CO-022 | 124600 | 89900 | 3 | 44.3 | 154 | P2 – High
E320-RFI-0083 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Special trackwork layout – Bellevue Way SE trench | Track layout at Sta. 949+73 (Bellevue Way SE trench) differs from the track-structure interface drawing C-398. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2018-10-22 | 10 | Routine | N | N | N | 0 | DSDC – HJH JV | 1 | 2018-10-30 | 8 | Y | 0 | 1 | 2018-10-30 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 869 | P4 – Low
E320-RFI-0084 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – South Bellevue parking garage | C-736 shows a 57 ft-3 in. dimension for the duct bank encasement; structural sheet S-878 shows a different value. Request clarification before fabrication/rebar release. | Design Manager | 2018-10-26 | 10 | Routine | N | Y | N | 7 | DSDC – HJH JV | 2 | 2018-11-05 | 10 | Y | 0 | 1 | 2018-11-05 | 10 | Closed | 3 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 695 | P3 – Medium
E320-RFI-0085 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – alternate epoxy-coated rebar supplier | Contractor requests approval to substitute alternate epoxy-coated rebar supplier for specified epoxy-coated rebar on work at Bellevue Way SE retained cut, citing procurement lead time. Product data attached. | Design Manager | 2018-11-02 | 10 | Routine | N | N | N | 3 | DSDC – HJH JV | 2 | 2018-11-08 | 6 | Y | 0 | 1 | 2018-11-08 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 870 | P4 – Low
E320-RFI-0086 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 12-in. ductile iron water main at South Bellevue parking garage | Potholing at Sta. 1167+14 located a 12-in. ductile iron water main in conflict with the proposed platform edge slab. Utility is not shown on E-310. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Engineer | 2018-11-05 | 10 | Urgent | N | Y | N | 6 | DSDC – HJH JV | 2 | 2018-11-16 | 11 | N | 1 | 1 | 2018-11-16 | 11 | Closed | 4 | 0 | 1 |  |  | Y | E320-CO-024 | 61010 | 37930 | 1.5 | 37.1 | 285 | P2 – High
E320-RFI-0087 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – retaining wall footing at 112th Ave SE road-over-rail structure | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-813 for fire alarm device layout at 112th Ave SE road-over-rail structure. Request direction on compliant detail. | Project Engineer | 2018-11-09 | 10 | Expedite | Y | Y | N | 3 | ST Design Management | 1 | 2018-11-16 | 7 | Y | 0 | 1 | 2018-11-16 | 7 | Closed | 8 | 0 | 3 | 75000 | 141000 | N |  | 0 | 0 | 0 | 0.7 | 652 | P3 – Medium
E320-RFI-0088 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with PSE distribution duct bank at South Bellevue Station | Potholing at Sta. 1847+24 located a PSE distribution duct bank in conflict with the proposed guideway girder diaphragm. Utility is not shown on E-411. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Engineer | 2018-12-07 | 10 | Expedite | Y | Y | N | 1 | DSDC – HJH JV | 4 | 2018-12-12 | 5 | Y | 0 | 1 | 2018-12-12 | 5 | Closed | 5 | 0 | 2 | 28000 | 53000 | Y | E320-CO-024 | 58490 | 36370 | 1.5 | 37.1 | 286 | P2 – High
E320-RFI-0089 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at 112th Ave SE road-over-rail structure, citing procurement lead time. Product data attached. | Superintendent | 2018-12-10 | 10 | Routine | N | N | N | 6 | DSDC – HJH JV | 2 | 2018-12-17 | 5 | Y | 0 | 1 | 2018-12-17 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 871 | P4 – Low
E320-RFI-0090 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | Puget Sound Energy comment on building permit – South Bellevue Station | Puget Sound Energy review comments on the building permit require changes to the stair core wall at South Bellevue Station. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2019-01-08 | 10 | Routine | N | N | N | 3 | Puget Sound Energy / ST Third-Party Mgmt | 3 | 2019-01-15 | 7 | Y | 0 | 2 | 2019-01-30 | 22 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 872 | P4 – Low
E320-RFI-0091 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 8-in. high-pressure gas main at 112th Ave SE road-over-rail structure | Potholing at Sta. 1516+59 located a 8-in. high-pressure gas main in conflict with the proposed stair core wall. Utility is not shown on C-625. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Superintendent | 2019-01-15 | 10 | Urgent | N | N | Y | 4 | ST Design Management | 3 | 2019-01-21 | 5 | Y | 0 | 1 | 2019-01-21 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 873 | P4 – Low
E320-RFI-0092 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with fiber communications duct bank at South Bellevue Station | Potholing at Sta. 1373+75 located a fiber communications duct bank in conflict with the proposed pedestrian ramp. Utility is not shown on M-413. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Scheduler | 2019-01-23 | 10 | Expedite | Y | Y | Y | 1 | DSDC – HJH JV | 1 | 2019-01-28 | 4 | Y | 0 | 1 | 2019-01-28 | 4 | Closed | 29 | 27 | 0 | 3356000 | 6264000 | Y | E320-CO-025 | 2685700 | 1478500 | 15 | 81 | 1 | P1 – Critical
E320-RFI-0093 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Rail Bonding location conflict at Sta. 1182+22 | Proposed rail bonding foundation location at Sta. 1182+22 conflicts with stair core wall; offset of 2 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Project Engineer | 2019-02-13 | 10 | Routine | N | N | Y | 6 | DSDC – HJH JV | 2 | 2019-02-21 | 8 | Y | 0 | 1 | 2019-02-21 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 874 | P4 – Low
E320-RFI-0094 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – platform edge slab sequence at South Bellevue Station | Erection of the platform edge slab as drawn conflicts with adjacent work and access limits at South Bellevue Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Project Manager | 2019-03-05 | 10 | Urgent | N | N | N | 8 | DSDC – HJH JV | 1 | 2019-03-13 | 8 | Y | 0 | 1 | 2019-03-13 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 875 | P4 – Low
E320-RFI-0095 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 8-in. high-pressure gas main at 112th Ave SE road-over-rail structure | Potholing at Sta. 2009+45 located a 8-in. high-pressure gas main in conflict with the proposed drilled shaft cap. Utility is not shown on M-761. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Scheduler | 2019-03-07 | 10 | Routine | N | Y | N | 0 | DSDC – HJH JV | 1 | 2019-03-18 | 11 | N | 1 | 1 | 2019-03-18 | 11 | Closed | 12 | 0 | 7 |  |  | N |  | 0 | 0 | 0 | 1.6 | 548 | P3 – Medium
E320-RFI-0096 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Mercer Slough interface: soft lacustrine silt below design subgrade | During excavation at Mercer Slough interface (Sta. 2044+22) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or C-277. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Project Engineer | 2019-03-07 | 10 | Urgent | Y | Y | N | 2 | ST Design Management | 1 | 2019-03-13 | 6 | Y | 0 | 1 | 2019-03-13 | 6 | Closed | 3 | 0 | 2 | 13000 | 25000 | Y | E320-CO-027 | 12690 | 2980 | 0.4 | 28.1 | 348 | P3 – Medium
E320-RFI-0097 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 12-in. ductile iron water main at Mercer Slough interface | Potholing at Sta. 1143+86 located a 12-in. ductile iron water main in conflict with the proposed pedestrian ramp. Utility is not shown on M-260. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Field Engineer | 2019-03-25 | 10 | Urgent | N | N | N | 3 | ST Design Management | 4 | 2019-04-05 | 11 | N | 1 | 1 | 2019-04-05 | 11 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 876 | P4 – Low
E320-RFI-0098 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – alternate epoxy-coated rebar supplier | Contractor requests approval to substitute alternate epoxy-coated rebar supplier for specified epoxy-coated rebar on work at Bellevue Way SE retained cut, citing procurement lead time. Product data attached. | Superintendent | 2019-04-10 | 10 | Expedite | N | N | N | 0 | DSDC – HJH JV | 2 | 2019-04-15 | 3 | Y | 0 | 1 | 2019-04-15 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 877 | P4 – Low
E320-RFI-0099 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Haul route revision – South Bellevue parking garage | Contractor requests approval of an alternate traffic/staging plan at South Bellevue parking garage: extended night closure. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Design Manager | 2019-04-19 | 10 | Routine | N | N | N | 4 | DSDC – HJH JV | 1 | 2019-04-24 | 5 | Y | 0 | 1 | 2019-04-24 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 878 | P4 – Low
E320-RFI-0100 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at South Bellevue Station: petroleum-stained soil with odor | During excavation at South Bellevue Station (Sta. 1152+88) the contractor encountered petroleum-stained soil with odor, not shown on the GBR or M-296. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Superintendent | 2019-04-19 | 10 | Routine | Y | Y | N | 1 | DSDC – HJH JV | 1 | 2019-05-06 | 17 | N | 7 | 1 | 2019-05-06 | 17 | Closed | 4 | 0 | 5 | 17000 | 31000 | Y | E320-CO-027 | 22210 | 5220 | 0.6 | 30.8 | 340 | P2 – High
E320-RFI-0101 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 8-in. high-pressure gas main at Bellevue Way SE retained cut | Potholing at Sta. 928+56 located a 8-in. high-pressure gas main in conflict with the proposed station canopy support. Utility is not shown on E-650. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Scheduler | 2019-04-22 | 10 | Routine | Y | Y | N | 1 | DSDC – HJH JV | 3 | 2019-05-03 | 11 | N | 1 | 1 | 2019-05-03 | 11 | Closed | 1 | 0 | 0 | 97000 | 182000 | Y | E320-CO-026 | 211700 | 0 | 0 | 0 | 879 | P4 – Low
E320-RFI-0102 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Lane closure window request – South Bellevue parking garage | Contractor requests approval of an alternate traffic/staging plan at South Bellevue parking garage: temporary lane shift. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Project Engineer | 2019-04-23 | 10 | Routine | N | Y | N | 4 | DSDC – HJH JV | 1 | 2019-05-01 | 8 | Y | 0 | 1 | 2019-05-01 | 8 | Closed | 1 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 880 | P4 – Low
E320-RFI-0103 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – duct bank encasement sequence at Mercer Slough interface | Erection of the duct bank encasement as drawn conflicts with adjacent work and access limits at Mercer Slough interface. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Project Manager | 2019-05-02 | 10 | Urgent | Y | Y | Y | 1 | DSDC – HJH JV | 2 | 2019-05-15 | 13 | N | 3 | 1 | 2019-05-15 | 13 | Closed | 15 | 9 | 0 | 43000 | 81000 | Y | E320-CO-028 | 117200 | 53100 | 5 | 48.2 | 89 | P1 – Critical
E320-RFI-0104 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Canopy/glazing connection – Bellevue Way SE trench | Request to clarify finish/connection detail on E-876 at Bellevue Way SE trench. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2019-05-03 | 10 | Routine | N | Y | N | 7 | ST Design Management | 2 | 2019-05-09 | 6 | Y | 0 | 2 | 2019-05-22 | 19 | Closed | 3 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 766 | P4 – Low
E320-RFI-0105 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 12-in. ductile iron water main at Bellevue Way SE trench | Potholing at Sta. 1439+18 located a 12-in. ductile iron water main in conflict with the proposed duct bank encasement. Utility is not shown on C-671. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Manager | 2019-05-09 | 10 | Routine | Y | N | N | 3 | ST Design Management | 1 | 2019-05-27 | 16 | N | 6 | 1 | 2019-05-27 | 16 | Closed | 0 | 0 | 2 | 141000 | 264000 | N |  | 0 | 0 | 0 | 0.4 | 696 | P3 – Medium
E320-RFI-0106 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – galvanized steel handrail | Contractor requests approval to substitute galvanized steel handrail for stainless steel handrail on work at Bellevue Way SE retained cut, citing procurement lead time. Product data attached. | Design Manager | 2019-05-21 | 10 | Routine | N | N | Y | 6 | DSDC – HJH JV | 3 | 2019-05-27 | 5 | Y | 0 | 1 | 2019-05-27 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 881 | P4 – Low
E320-RFI-0107 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – column reinforcement and stair core wall at 112th Ave SE road-over-rail structure | Interference between column reinforcement and stair core wall at 112th Ave SE road-over-rail structure per C-160. Required clearance of 8 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Scheduler | 2019-06-05 | 10 | Expedite | Y | Y | N | 1 | ST Design Management | 2 | 2019-06-19 | 14 | N | 4 | 1 | 2019-06-19 | 14 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 882 | P4 – Low
E320-RFI-0108 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Track slab/expansion joint interface – Bellevue Way SE retained cut | Track layout at Sta. 2103+10 (Bellevue Way SE retained cut) differs from the track-structure interface drawing E-386. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Scheduler | 2019-06-26 | 10 | Routine | N | N | Y | 5 | DSDC – HJH JV | 4 | 2019-07-01 | 4 | Y | 0 | 1 | 2019-07-01 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 883 | P4 – Low
E320-RFI-0109 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – platform edge slab at Bellevue Way SE retained cut | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-340 for fire alarm device layout at Bellevue Way SE retained cut. Request direction on compliant detail. | Field Engineer | 2019-07-09 | 10 | Urgent | Y | N | Y | 2 | DSDC – HJH JV | 2 | 2019-07-19 | 10 | Y | 0 | 1 | 2019-07-19 | 10 | Closed | 0 | 0 | 0 | 55000 | 102000 | N |  | 0 | 0 | 0 | 0 | 884 | P4 – Low
E320-RFI-0110 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – recycled-content fly ash blend | Contractor requests approval to substitute recycled-content fly ash blend for Type IL cement mix on work at 112th Ave SE road-over-rail structure, citing procurement lead time. Product data attached. | Project Manager | 2019-07-18 | 10 | Routine | N | N | N | 4 | DSDC – HJH JV | 1 | 2019-07-24 | 6 | Y | 0 | 1 | 2019-07-24 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 885 | P4 – Low
E320-RFI-0111 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Mercer Slough interface: soft lacustrine silt below design subgrade | During excavation at Mercer Slough interface (Sta. 1692+64) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or A-764. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Design Manager | 2019-08-12 | 10 | Expedite | Y | Y | N | 3 | DSDC – HJH JV | 2 | 2019-08-23 | 11 | N | 1 | 1 | 2019-08-23 | 11 | Closed | 7 | 0 | 6 | 403000 | 753000 | Y | E320-CO-029 | 721100 | 546600 | 5 | 48.5 | 84 | P1 – Critical
E320-RFI-0112 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Night work and noise variance – 112th Ave SE road-over-rail structure | Contractor requests approval of an alternate traffic/staging plan at 112th Ave SE road-over-rail structure: extended night closure. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Design Manager | 2019-08-12 | 10 | Routine | N | N | N | 4 | DSDC – HJH JV | 2 | 2019-08-19 | 5 | Y | 0 | 1 | 2019-08-19 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 886 | P4 – Low
E320-RFI-0113 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Property owner access/restoration requirement – 112th Ave SE road-over-rail structure | Adjacent property owner has requested additional restoration and access provisions at 112th Ave SE road-over-rail structure beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Design Manager | 2019-08-16 | 10 | Expedite | N | Y | Y | 4 | WSDOT / ST Third-Party Mgmt | 3 | 2019-08-23 | 7 | Y | 0 | 1 | 2019-08-23 | 7 | Closed | 16 | 7 | 0 |  |  | N |  | 0 | 0 | 0 | 7 | 416 | P3 – Medium
E320-RFI-0114 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Missing dimension on S-409 | Request clarification of 00 72 00 General Conditions and S-409: dimension/notes appear inconsistent or omitted for the work at Bellevue Way SE retained cut. | Design Manager | 2019-08-22 | 10 | Routine | N | N | N | 2 | DSDC – HJH JV | 4 | 2019-08-26 | 3 | Y | 0 | 1 | 2019-08-26 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 887 | P4 – Low
E320-RFI-0115 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Special trackwork layout – 112th Ave SE road-over-rail structure | Track layout at Sta. 1254+70 (112th Ave SE road-over-rail structure) differs from the track-structure interface drawing E-233. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Engineer | 2019-09-02 | 10 | Routine | Y | Y | Y | 0 | ST Design Management | 1 | 2019-09-09 | 6 | Y | 0 | 1 | 2019-09-09 | 6 | Closed | 10 | 6 | 0 | 15000 | 27000 | N |  | 0 | 0 | 0 | 6 | 419 | P3 – Medium
E320-RFI-0116 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Station finish detail – Mercer Slough interface | Request to clarify finish/connection detail on E-767 at Mercer Slough interface. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2019-09-23 | 10 | Routine | N | N | N | 7 | ST Design Management | 3 | 2019-09-27 | 4 | Y | 0 | 1 | 2019-09-27 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 888 | P4 – Low
E320-RFI-0117 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at 112th Ave SE road-over-rail structure: petroleum-stained soil with odor | During excavation at 112th Ave SE road-over-rail structure (Sta. 965+07) the contractor encountered petroleum-stained soil with odor, not shown on the GBR or M-846. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Project Engineer | 2019-10-07 | 10 | Urgent | Y | Y | N | 8 | DSDC – HJH JV | 2 | 2019-10-09 | 2 | Y | 0 | 1 | 2019-10-09 | 2 | Closed | 7 | 0 | 4 | 664000 | 1240000 | N |  | 0 | 0 | 0 | 0.9 | 619 | P3 – Medium
E320-RFI-0118 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Embedded conduit stub-ups – Mercer Slough interface | Systems contractor requires 2-in. PVC conduit stub-ups for SCADA cabinet at Mercer Slough interface not provided in civil A-580. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Project Engineer | 2019-10-08 | 10 | Routine | N | Y | Y | 8 | DSDC – HJH JV | 3 | 2019-10-14 | 6 | Y | 0 | 1 | 2019-10-14 | 6 | Closed | 14 | 9 | 0 |  |  | N |  | 0 | 0 | 0 | 9 | 398 | P3 – Medium
E320-RFI-0119 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Grounding/bonding and stray-current detail – South Bellevue Station | Civil and systems drawings differ on grounding/bonding of bearing pad/embed plate for stray-current control at South Bellevue Station. Request governing detail and responsibility for installation. | Field Engineer | 2019-11-25 | 10 | Urgent | Y | Y | N | 0 | ST Design Management | 4 | 2019-12-02 | 6 | Y | 0 | 1 | 2019-12-02 | 6 | Closed | 5 | 0 | 2 | 114000 | 213000 | N |  | 0 | 0 | 0 | 0.4 | 697 | P3 – Medium
E320-RFI-0120 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – bearing pad/embed plate sequence at South Bellevue Station | Erection of the bearing pad/embed plate as drawn conflicts with adjacent work and access limits at South Bellevue Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2019-11-27 | 10 | Routine | Y | N | N | 3 | DSDC – HJH JV | 3 | 2019-12-04 | 7 | Y | 0 | 1 | 2019-12-04 | 7 | Closed | 0 | 0 | 0 | 40000 | 74000 | Y | E320-CO-030 | 43400 | 30100 | 0 | 35.5 | 308 | P2 – High
E320-RFI-0121 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 8-in. high-pressure gas main at Bellevue Way SE retained cut | Potholing at Sta. 1229+61 located a 8-in. high-pressure gas main in conflict with the proposed station canopy support. Utility is not shown on E-313. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Superintendent | 2019-12-16 | 10 | Urgent | Y | Y | Y | 0 | ST Design Management | 1 | 2019-12-19 | 3 | Y | 0 | 1 | 2019-12-19 | 3 | Closed | 8 | 5 | 0 | 806000 | 1504000 | Y | E320-CO-031 | 537000 | 405000 | 4 | 50.8 | 49 | P1 – Critical
E320-RFI-0122 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 8-in. high-pressure gas main at Bellevue Way SE retained cut | Potholing at Sta. 2394+50 located a 8-in. high-pressure gas main in conflict with the proposed guideway girder diaphragm. Utility is not shown on A-746. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Superintendent | 2019-12-18 | 10 | Routine | Y | Y | Y | 3 | DSDC – HJH JV | 2 | 2019-12-23 | 4 | Y | 0 | 1 | 2019-12-23 | 4 | Closed | 4 | 1 | 0 | 275000 | 513000 | Y | E320-CO-034 | 384500 | 249900 | 1 | 44.2 | 157 | P2 – High
E320-RFI-0123 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Crane staging in right-of-way – Mercer Slough interface | Contractor requests approval of an alternate traffic/staging plan at Mercer Slough interface: temporary lane shift. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Superintendent | 2019-12-24 | 10 | Routine | Y | Y | N | 3 | DSDC – HJH JV | 3 | 2019-12-27 | 3 | Y | 0 | 1 | 2019-12-27 | 3 | Closed | 7 | 0 | 2 | 55000 | 103000 | Y | E320-CO-032 | 68700 | 39600 | 4 | 38.3 | 269 | P2 – High
E320-RFI-0124 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | WSDOT comment on street improvement permit – 112th Ave SE road-over-rail structure | WSDOT review comments on the street improvement permit require changes to the bearing pad/embed plate at 112th Ave SE road-over-rail structure. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2019-12-27 | 10 | Routine | Y | Y | N | 5 | City of Bellevue / ST Third-Party Mgmt | 1 | 2020-01-02 | 6 | Y | 0 | 2 | 2020-01-10 | 14 | Closed | 8 | 0 | 3 | 58000 | 107000 | Y | E320-CO-033 | 38700 | 27500 | 3 | 36.9 | 293 | P2 – High
E320-RFI-0125 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 30-in. storm drain at South Bellevue Station | Potholing at Sta. 2392+14 located a 30-in. storm drain in conflict with the proposed column reinforcement. Utility is not shown on C-824. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Superintendent | 2020-01-02 | 10 | Routine | N | N | N | 7 | DSDC – HJH JV | 2 | 2020-01-14 | 12 | N | 2 | 1 | 2020-01-14 | 12 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 889 | P4 – Low
E320-RFI-0126 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Direct fixation fastener spacing at Sta. 1290+18 | Track layout at Sta. 1290+18 (Bellevue Way SE retained cut) differs from the track-structure interface drawing E-410. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2020-01-09 | 10 | Routine | Y | N | N | 4 | DSDC – HJH JV | 2 | 2020-01-20 | 11 | N | 1 | 1 | 2020-01-20 | 11 | Closed | 0 | 0 | 1 | 69000 | 129000 | Y | E320-CO-035 | 71500 | 50700 | 0 | 37.6 | 282 | P2 – High
E320-RFI-0127 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | SPC | Spec / Drawing Clarification | General | 01 25 00 Substitution Procedures | Drawing/spec discrepancy – 112th Ave SE road-over-rail structure | Request clarification of 01 33 00 Submittal Procedures and A-424: dimension/notes appear inconsistent or omitted for the work at 112th Ave SE road-over-rail structure. | Design Manager | 2020-01-30 | 10 | Routine | N | Y | N | 2 | DSDC – HJH JV | 1 | 2020-02-04 | 5 | Y | 0 | 1 | 2020-02-04 | 5 | Closed | 1 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 767 | P4 – Low
E320-RFI-0128 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Canopy/glazing connection – Bellevue Way SE retained cut | Request to clarify finish/connection detail on S-820 at Bellevue Way SE retained cut. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2020-02-03 | 10 | Routine | N | N | N | 3 | ST Design Management | 1 | 2020-02-11 | 8 | Y | 0 | 1 | 2020-02-11 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 890 | P4 – Low
E320-RFI-0129 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 8-in. high-pressure gas main at South Bellevue parking garage | Potholing at Sta. 1304+39 located a 8-in. high-pressure gas main in conflict with the proposed retaining wall footing. Utility is not shown on M-633. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Design Manager | 2020-02-04 | 10 | Routine | Y | Y | N | 5 | DSDC – HJH JV | 1 | 2020-02-10 | 6 | Y | 0 | 1 | 2020-02-10 | 6 | Closed | 23 | 0 | 11 | 290000 | 541000 | Y | E320-CO-036 | 340900 | 205600 | 12 | 48.6 | 80 | P1 – Critical
E320-RFI-0130 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at South Bellevue parking garage: loose granular fill below planned bearing elevation | During excavation at South Bellevue parking garage (Sta. 2388+06) the contractor encountered loose granular fill below planned bearing elevation, not shown on the GBR or A-127. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Project Manager | 2020-02-06 | 10 | Expedite | N | Y | Y | 1 | ST Design Management | 1 | 2020-02-11 | 5 | Y | 0 | 1 | 2020-02-11 | 5 | Closed | 17 | 9 | 0 |  |  | N |  | 0 | 0 | 0 | 9 | 399 | P3 – Medium
E320-RFI-0131 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – guideway girder diaphragm and duct bank encasement at South Bellevue Station | Interference between guideway girder diaphragm and duct bank encasement at South Bellevue Station per C-164. Required clearance of 7 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Field Engineer | 2020-02-27 | 10 | Routine | Y | Y | N | 4 | DSDC – HJH JV | 1 | 2020-03-05 | 7 | Y | 0 | 1 | 2020-03-05 | 7 | Closed | 5 | 0 | 2 | 157000 | 293000 | Y | E320-CO-037 | 125800 | 0 | 0 | 0.4 | 698 | P3 – Medium
E320-RFI-0132 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – pedestrian ramp and duct bank encasement at South Bellevue Station | Interference between pedestrian ramp and duct bank encasement at South Bellevue Station per S-735. Required clearance of 6 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2020-03-04 | 10 | Routine | Y | Y | N | 6 | DSDC – HJH JV | 2 | 2020-03-09 | 3 | Y | 0 | 1 | 2020-03-09 | 3 | Closed | 4 | 0 | 2 | 356000 | 665000 | Y | E320-CO-039 | 1042790 | 422860 | 2.2 | 45.8 | 126 | P2 – High
E320-RFI-0133 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with PSE distribution duct bank at South Bellevue Station | Potholing at Sta. 2178+27 located a PSE distribution duct bank in conflict with the proposed pedestrian ramp. Utility is not shown on C-379. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Engineer | 2020-03-09 | 10 | Expedite | N | N | N | 2 | DSDC – HJH JV | 4 | 2020-03-16 | 7 | Y | 0 | 1 | 2020-03-16 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 891 | P4 – Low
E320-RFI-0134 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 30-in. storm drain at Mercer Slough interface | Potholing at Sta. 1789+16 located a 30-in. storm drain in conflict with the proposed drilled shaft cap. Utility is not shown on A-622. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Superintendent | 2020-03-31 | 10 | Routine | Y | Y | N | 4 | DSDC – HJH JV | 2 | 2020-04-06 | 5 | Y | 0 | 1 | 2020-04-06 | 5 | Closed | 10 | 0 | 7 | 249000 | 464000 | Y | E320-CO-038 | 268400 | 0 | 0 | 1.6 | 549 | P3 – Medium
E320-RFI-0135 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – station canopy support sequence at South Bellevue parking garage | Erection of the station canopy support as drawn conflicts with adjacent work and access limits at South Bellevue parking garage. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2020-03-31 | 10 | Routine | Y | N | Y | 0 | DSDC – HJH JV | 1 | 2020-04-03 | 3 | Y | 0 | 1 | 2020-04-03 | 3 | Closed | 0 | 0 | 0 | 303000 | 566000 | N |  | 0 | 0 | 0 | 0 | 892 | P4 – Low
E320-RFI-0136 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – column reinforcement at Bellevue Way SE trench | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-659 for emergency stair pressurization at Bellevue Way SE trench. Request direction on compliant detail. | Design Manager | 2020-04-03 | 10 | Expedite | Y | Y | N | 8 | ST Design Management | 3 | 2020-04-06 | 3 | Y | 0 | 1 | 2020-04-06 | 3 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 893 | P4 – Low
E320-RFI-0137 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – Bellevue Way SE trench | M-288 shows a 34 ft-1 in. dimension for the guideway girder diaphragm; structural sheet S-375 shows a different value. Request clarification before fabrication/rebar release. | Scheduler | 2020-04-13 | 10 | Routine | Y | Y | Y | 4 | DSDC – HJH JV | 2 | 2020-04-22 | 9 | Y | 0 | 1 | 2020-04-22 | 9 | Closed | 8 | 4 | 0 | 232000 | 434000 | Y | E320-CO-039 | 351510 | 142540 | 0.8 | 45.2 | 134 | P2 – High
E320-RFI-0138 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – South Bellevue Station | S-609 shows a 50 ft-7 in. dimension for the station canopy support; structural sheet S-641 shows a different value. Request clarification before fabrication/rebar release. | Design Manager | 2020-04-20 | 10 | Expedite | N | Y | N | 6 | DSDC – HJH JV | 1 | 2020-04-27 | 5 | Y | 0 | 1 | 2020-04-27 | 5 | Closed | 4 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 653 | P3 – Medium
E320-RFI-0139 | E320 | East Link Extension | E320 contractor (not named in sources) | Mercer Slough interface | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Wetland/stream buffer protection – Mercer Slough interface | Field conditions at Mercer Slough interface require changes to temporary erosion and sediment control or stormwater facility per C-709. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2020-05-14 | 10 | Urgent | Y | Y | Y | 0 | DSDC – HJH JV | 1 | 2020-05-25 | 10 | Y | 0 | 1 | 2020-05-25 | 10 | Closed | 16 | 7 | 0 | 41000 | 76000 | Y | E320-CO-040 | 86200 | 72900 | 7 | 47.9 | 92 | P1 – Critical
E320-RFI-0140 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – station canopy support and drilled shaft cap at South Bellevue Station | Interference between station canopy support and drilled shaft cap at South Bellevue Station per A-884. Required clearance of 8 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2020-06-09 | 10 | Urgent | N | N | N | 3 | ST Design Management | 1 | 2020-06-15 | 6 | Y | 0 | 2 | 2020-07-06 | 27 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 894 | P4 – Low
E320-RFI-0141 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at 112th Ave SE road-over-rail structure: soft lacustrine silt below design subgrade | During excavation at 112th Ave SE road-over-rail structure (Sta. 975+10) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or A-173. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Field Engineer | 2020-06-16 | 10 | Expedite | N | Y | N | 4 | DSDC – HJH JV | 2 | 2020-06-25 | 9 | Y | 0 | 2 | 2020-07-09 | 23 | Closed | 11 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 654 | P3 – Medium
E320-RFI-0142 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 12-in. ductile iron water main at Bellevue Way SE retained cut | Potholing at Sta. 1441+40 located a 12-in. ductile iron water main in conflict with the proposed platform edge slab. Utility is not shown on C-626. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Field Engineer | 2020-06-23 | 10 | Routine | N | Y | N | 1 | DSDC – HJH JV | 2 | 2020-07-02 | 9 | Y | 0 | 2 | 2020-07-22 | 29 | Closed | 7 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 620 | P3 – Medium
E320-RFI-0143 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE retained cut | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – drilled shaft cap at Bellevue Way SE retained cut | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-356 for smoke control damper at Bellevue Way SE retained cut. Request direction on compliant detail. | Scheduler | 2020-08-06 | 10 | Routine | Y | N | Y | 2 | DSDC – HJH JV | 4 | 2020-08-17 | 9 | Y | 0 | 1 | 2020-08-17 | 9 | Closed | 0 | 2 | 0 | 28000 | 53000 | Y | E320-CO-041 | 63900 | 34500 | 0 | 38 | 273 | P2 – High
E320-RFI-0144 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at South Bellevue Station: petroleum-stained soil with odor | During excavation at South Bellevue Station (Sta. 1345+71) the contractor encountered petroleum-stained soil with odor, not shown on the GBR or C-456. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Superintendent | 2020-08-10 | 10 | Routine | Y | N | N | 3 | DSDC – HJH JV | 1 | 2020-08-31 | 19 | N | 9 | 1 | 2020-08-31 | 19 | Closed | 0 | 0 | 2 | 1029000 | 1921000 | Y | E320-CO-042 | 2333100 | 1239400 | 0 | 48.8 | 74 | P1 – Critical
E320-RFI-0145 | E320 | East Link Extension | E320 contractor (not named in sources) | 112th Ave SE road-over-rail structure | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at 112th Ave SE road-over-rail structure: soft lacustrine silt below design subgrade | During excavation at 112th Ave SE road-over-rail structure (Sta. 1438+40) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or C-697. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Field Engineer | 2020-09-28 | 10 | Urgent | Y | Y | Y | 2 | ST Design Management | 2 | 2020-10-05 | 5 | Y | 0 | 1 | 2020-10-05 | 5 | Closed | 16 | 9 | 0 | 147000 | 275000 | Y | E320-CO-043 | 255900 | 164400 | 6 | 52.4 | 37 | P1 – Critical
E320-RFI-0146 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Haul route revision – Bellevue Way SE trench | Contractor requests approval of an alternate traffic/staging plan at Bellevue Way SE trench: temporary lane shift. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Project Engineer | 2020-10-08 | 10 | Urgent | Y | N | Y | 4 | ST Design Management | 1 | 2020-10-12 | 3 | Y | 0 | 1 | 2020-10-12 | 3 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 895 | P4 – Low
E320-RFI-0147 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Direct fixation fastener spacing at Sta. 1951+62 | Track layout at Sta. 1951+62 (Bellevue Way SE trench) differs from the track-structure interface drawing C-125. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Engineer | 2020-10-16 | 10 | Expedite | N | N | N | 2 | DSDC – HJH JV | 1 | 2020-10-26 | 8 | Y | 0 | 1 | 2020-10-26 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 896 | P4 – Low
E320-RFI-0148 | E320 | East Link Extension | E320 contractor (not named in sources) | Bellevue Way SE trench | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – recycled-content fly ash blend | Contractor requests approval to substitute recycled-content fly ash blend for Type IL cement mix on work at Bellevue Way SE trench, citing procurement lead time. Product data attached. | Project Engineer | 2020-12-07 | 10 | Routine | N | Y | N | 7 | DSDC – HJH JV | 3 | 2020-12-16 | 9 | Y | 0 | 1 | 2020-12-16 | 9 | Closed | 1 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 897 | P4 – Low
E320-RFI-0149 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue parking garage | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at South Bellevue parking garage, citing procurement lead time. Product data attached. | Project Engineer | 2021-02-05 | 10 | Routine | N | N | N | 4 | ST Design Management | 2 | 2021-02-08 | 2 | Y | 0 | 1 | 2021-02-08 | 2 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 898 | P4 – Low
E320-RFI-0150 | E320 | East Link Extension | E320 contractor (not named in sources) | South Bellevue Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – retaining wall footing and bearing pad/embed plate at South Bellevue Station | Interference between retaining wall footing and bearing pad/embed plate at South Bellevue Station per C-851. Required clearance of 7 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Scheduler | 2021-04-06 | 10 | Routine | Y | N | N | 0 | DSDC – HJH JV | 3 | 2021-04-14 | 8 | Y | 0 | 1 | 2021-04-14 | 8 | Closed | 0 | 0 | 0 | 39000 | 74000 | Y | E320-CO-044 | 66200 | 25200 | 0 | 34.9 | 312 | P2 – High
E330-RFI-0001 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 24-in. sanitary sewer at East Main Station interface | Potholing at Sta. 1472+70 located a 24-in. sanitary sewer in conflict with the proposed guideway girder diaphragm. Utility is not shown on A-104. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Design Manager | 2016-05-16 | 10 | Routine | Y | N | Y | 3 | ST Design Management | 2 | 2016-06-01 | 16 | N | 6 | 1 | 2016-06-01 | 16 | Closed | 0 | 0 | 0 | 66000 | 124000 | Y | E330-CO-001 | 83500 | 61700 | 0 | 38 | 274 | P2 – High
E330-RFI-0002 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | City of Bellevue comment on right-of-way use permit – NE 6th St tunnel turn | City of Bellevue review comments on the right-of-way use permit require changes to the column reinforcement at NE 6th St tunnel turn. Request direction on scope impacts and whether comments are within the contract requirements. | Project Engineer | 2016-07-18 | 10 | Routine | Y | Y | N | 7 | WSDOT / ST Third-Party Mgmt | 2 | 2016-07-25 | 7 | Y | 0 | 1 | 2016-07-25 | 7 | Closed | 15 | 0 | 6 | 44000 | 81000 | Y | E330-CO-002 | 75100 | 44200 | 5 | 39.9 | 238 | P2 – High
E330-RFI-0003 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – retaining wall footing at NE 6th St tunnel turn | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-154 for standpipe connection at NE 6th St tunnel turn. Request direction on compliant detail. | Design Manager | 2016-07-19 | 10 | Routine | N | N | N | 1 | DSDC – HJH JV | 1 | 2016-07-25 | 4 | Y | 0 | 1 | 2016-07-25 | 4 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 899 | P4 – Low
E330-RFI-0004 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | City of Bellevue comment on street improvement permit – NE 6th St tunnel turn | City of Bellevue review comments on the street improvement permit require changes to the retaining wall footing at NE 6th St tunnel turn. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2016-08-31 | 10 | Routine | N | Y | N | 6 | WSDOT / ST Third-Party Mgmt | 2 | 2016-09-12 | 12 | N | 2 | 1 | 2016-09-12 | 12 | Closed | 20 | 0 | 12 |  |  | N |  | 0 | 0 | 0 | 2.7 | 492 | P3 – Medium
E330-RFI-0005 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Haul route revision – South portal – 112th Ave SE/Main St | Contractor requests approval of an alternate traffic/staging plan at South portal – 112th Ave SE/Main St: extended night closure. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Field Engineer | 2016-09-01 | 10 | Expedite | Y | N | Y | 6 | DSDC – HJH JV | 1 | 2016-09-05 | 4 | Y | 0 | 1 | 2016-09-05 | 4 | Closed | 0 | 0 | 0 | 20000 | 38000 | N |  | 0 | 0 | 0 | 0 | 900 | P4 – Low
E330-RFI-0006 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Haul route revision – South portal – 112th Ave SE/Main St | Contractor requests approval of an alternate traffic/staging plan at South portal – 112th Ave SE/Main St: extended night closure. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Project Engineer | 2016-10-14 | 10 | Expedite | Y | Y | N | 6 | DSDC – HJH JV | 2 | 2016-10-17 | 3 | Y | 0 | 1 | 2016-10-17 | 3 | Closed | 7 | 0 | 4 | 7000 | 13000 | Y | E330-CO-003 | 9200 | 5400 | 2 | 31.2 | 338 | P2 – High
E330-RFI-0007 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 8-in. high-pressure gas main at Bellevue SEM tunnel – 110th Ave NE | Potholing at Sta. 1859+96 located a 8-in. high-pressure gas main in conflict with the proposed column reinforcement. Utility is not shown on E-601. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Design Manager | 2016-12-02 | 10 | Routine | Y | N | N | 5 | ST Design Management | 1 | 2016-12-12 | 9 | Y | 0 | 1 | 2016-12-12 | 9 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 901 | P4 – Low
E330-RFI-0008 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – stair core wall at North shaft near Bellevue City Hall | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-791 for emergency stair pressurization at North shaft near Bellevue City Hall. Request direction on compliant detail. | Design Manager | 2016-12-09 | 10 | Routine | N | Y | N | 8 | ST Design Management | 2 | 2016-12-12 | 3 | Y | 0 | 1 | 2016-12-12 | 3 | Closed | 26 | 0 | 7 |  |  | N |  | 0 | 0 | 0 | 1.6 | 550 | P3 – Medium
E330-RFI-0009 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – galvanized steel handrail | Contractor requests approval to substitute galvanized steel handrail for stainless steel handrail on work at North shaft near Bellevue City Hall, citing procurement lead time. Product data attached. | Project Manager | 2016-12-19 | 10 | Routine | N | N | N | 0 | DSDC – HJH JV | 4 | 2016-12-23 | 4 | Y | 0 | 1 | 2016-12-23 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 902 | P4 – Low
E330-RFI-0010 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 12-in. ductile iron water main at Bellevue SEM tunnel – 110th Ave NE | Potholing at Sta. 956+36 located a 12-in. ductile iron water main in conflict with the proposed duct bank encasement. Utility is not shown on S-610. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Field Engineer | 2016-12-20 | 10 | Expedite | N | Y | N | 0 | DSDC – HJH JV | 3 | 2016-12-26 | 5 | Y | 0 | 1 | 2016-12-26 | 5 | Closed | 5 | 0 | 3 |  |  | Y | E330-CO-005 | 76420 | 38210 | 0.1 | 37.1 | 287 | P2 – High
E330-RFI-0011 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – duct bank encasement at NE 6th St tunnel turn | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-567 for fire alarm device layout at NE 6th St tunnel turn. Request direction on compliant detail. | Superintendent | 2017-01-02 | 10 | Expedite | N | N | N | 3 | DSDC – HJH JV | 1 | 2017-01-09 | 5 | Y | 0 | 2 | 2017-01-26 | 24 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 903 | P4 – Low
E330-RFI-0012 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Bellevue SEM tunnel – 110th Ave NE: abandoned timber piles | During excavation at Bellevue SEM tunnel – 110th Ave NE (Sta. 1653+78) the contractor encountered abandoned timber piles, not shown on the GBR or E-393. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Project Manager | 2017-01-13 | 10 | Urgent | Y | Y | N | 5 | DSDC – HJH JV | 1 | 2017-01-17 | 4 | Y | 0 | 2 | 2017-01-26 | 13 | Closed | 11 | 0 | 8 | 1020000 | 1904000 | Y | E330-CO-004 | 1239900 | 957100 | 6 | 51.2 | 44 | P1 – Critical
E330-RFI-0013 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Dimensional discrepancy – North shaft near Bellevue City Hall | E-849 shows a 21 ft-2 in. dimension for the platform edge slab; structural sheet S-156 shows a different value. Request clarification before fabrication/rebar release. | Superintendent | 2017-02-06 | 10 | Routine | N | Y | N | 4 | ST Design Management | 2 | 2017-02-13 | 6 | Y | 0 | 1 | 2017-02-13 | 6 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 768 | P4 – Low
E330-RFI-0014 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with fiber communications duct bank at NE 6th St tunnel turn | Potholing at Sta. 1979+00 located a fiber communications duct bank in conflict with the proposed column reinforcement. Utility is not shown on C-237. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Engineer | 2017-02-13 | 10 | Routine | Y | Y | N | 8 | DSDC – HJH JV | 3 | 2017-02-20 | 7 | Y | 0 | 1 | 2017-02-20 | 7 | Closed | 3 | 0 | 2 | 1554000 | 2902000 | Y | E330-CO-005 | 2039580 | 1019790 | 1.9 | 48.8 | 75 | P1 – Critical
E330-RFI-0015 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unexpected ground condition – NE 6th St tunnel turn | During SEM excavation near Sta. 1045+40 at NE 6th St tunnel turn, ground conditions varied from the baseline in the geotechnical baseline report (observed buried concrete debris and an old foundation). Contractor requests direction on dewatering approach and discharge treatment and confirmation of whether this constitutes a differing site condition. See M-496. | Project Engineer | 2017-03-07 | 10 | Urgent | Y | N | Y | 0 | DSDC – HJH JV | 2 | 2017-03-09 | 2 | Y | 0 | 1 | 2017-03-09 | 2 | Closed | 0 | 0 | 0 | 381000 | 711000 | Y | E330-CO-006 | 498420 | 375080 | 0 | 44.2 | 158 | P2 – High
E330-RFI-0016 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Bellevue SEM tunnel – 110th Ave NE: perched groundwater | During excavation at Bellevue SEM tunnel – 110th Ave NE (Sta. 1305+33) the contractor encountered perched groundwater at approx. elevation 149 ft, not shown on the GBR or E-253. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Project Manager | 2017-03-16 | 10 | Routine | Y | N | N | 0 | DSDC – HJH JV | 2 | 2017-03-23 | 7 | Y | 0 | 1 | 2017-03-23 | 7 | Closed | 0 | 0 | 0 | 8000 | 15000 | Y | E330-CO-006 | 16590 | 12480 | 0 | 32.5 | 332 | P2 – High
E330-RFI-0017 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unexpected ground condition – NE 6th St tunnel turn | During SEM excavation near Sta. 1799+29 at NE 6th St tunnel turn, ground conditions varied from the baseline in the geotechnical baseline report (observed loose granular fill below planned bearing elevation). Contractor requests direction on dewatering approach and discharge treatment and confirmation of whether this constitutes a differing site condition. See A-516. | Superintendent | 2017-03-20 | 10 | Routine | Y | N | Y | 0 | ST Design Management | 1 | 2017-03-27 | 6 | Y | 0 | 1 | 2017-03-27 | 6 | Closed | 0 | 0 | 0 | 32000 | 60000 | Y | E330-CO-006 | 25290 | 19030 | 0 | 34 | 322 | P2 – High
E330-RFI-0018 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 8-in. high-pressure gas main at NE 6th St tunnel turn | Potholing at Sta. 2044+83 located a 8-in. high-pressure gas main in conflict with the proposed retaining wall footing. Utility is not shown on A-890. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Project Manager | 2017-03-27 | 10 | Routine | Y | N | Y | 6 | DSDC – HJH JV | 1 | 2017-04-03 | 6 | Y | 0 | 1 | 2017-04-03 | 6 | Closed | 0 | 0 | 0 | 264000 | 492000 | N |  | 0 | 0 | 0 | 0 | 904 | P4 – Low
E330-RFI-0019 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 24-in. sanitary sewer at Bellevue Transit Center interface | Potholing at Sta. 1339+87 located a 24-in. sanitary sewer in conflict with the proposed station canopy support. Utility is not shown on S-390. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2017-04-07 | 10 | Expedite | Y | Y | N | 4 | DSDC – HJH JV | 1 | 2017-04-14 | 7 | Y | 0 | 2 | 2017-04-25 | 18 | Closed | 4 | 0 | 2 | 62000 | 116000 | Y | E330-CO-008 | 130470 | 89600 | 2.6 | 40.6 | 224 | P2 – High
E330-RFI-0020 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | In-water work window – North shaft near Bellevue City Hall | Field conditions at North shaft near Bellevue City Hall require changes to temporary erosion and sediment control or stormwater facility per E-288. Request direction considering critical-areas conditions and permit requirements. | Field Engineer | 2017-04-11 | 10 | Routine | N | Y | N | 3 | DSDC – HJH JV | 1 | 2017-04-21 | 10 | Y | 0 | 1 | 2017-04-21 | 10 | Closed | 10 | 0 | 7 |  |  | N |  | 0 | 0 | 0 | 1.6 | 551 | P3 – Medium
E330-RFI-0021 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with PSE distribution duct bank at South portal – 112th Ave SE/Main St | Potholing at Sta. 2194+35 located a PSE distribution duct bank in conflict with the proposed bearing pad/embed plate. Utility is not shown on C-669. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Scheduler | 2017-04-24 | 10 | Routine | Y | Y | N | 2 | DSDC – HJH JV | 3 | 2017-05-05 | 11 | N | 1 | 1 | 2017-05-05 | 11 | Closed | 11 | 0 | 8 | 104000 | 195000 | N |  | 0 | 0 | 0 | 1.8 | 537 | P3 – Medium
E330-RFI-0022 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with fiber communications duct bank at South portal – 112th Ave SE/Main St | Potholing at Sta. 2065+38 located a fiber communications duct bank in conflict with the proposed station canopy support. Utility is not shown on E-834. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Scheduler | 2017-05-09 | 10 | Routine | Y | Y | N | 0 | ST Design Management | 1 | 2017-05-15 | 6 | Y | 0 | 1 | 2017-05-15 | 6 | Closed | 4 | 0 | 1 | 30000 | 55000 | Y | E330-CO-007 | 69800 | 0 | 0 | 0.2 | 769 | P4 – Low
E330-RFI-0023 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with abandoned utility vault at Bellevue Transit Center interface | Potholing at Sta. 1826+98 located a abandoned utility vault in conflict with the proposed column reinforcement. Utility is not shown on C-893. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Field Engineer | 2017-05-17 | 10 | Expedite | Y | Y | N | 4 | DSDC – HJH JV | 4 | 2017-05-30 | 13 | N | 3 | 2 | 2017-06-14 | 28 | Closed | 5 | 0 | 1 | 57000 | 106000 | Y | E330-CO-008 | 116630 | 80100 | 2.4 | 39.9 | 239 | P2 – High
E330-RFI-0024 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unexpected ground condition – Bellevue SEM tunnel – 110th Ave NE | During SEM excavation near Sta. 2260+61 at Bellevue SEM tunnel – 110th Ave NE, ground conditions varied from the baseline in the geotechnical baseline report (observed loose granular fill below planned bearing elevation). Contractor requests direction on dewatering approach and discharge treatment and confirmation of whether this constitutes a differing site condition. See S-105. | Design Manager | 2017-05-25 | 10 | Routine | Y | N | N | 5 | ST Design Management | 1 | 2017-05-29 | 4 | Y | 0 | 1 | 2017-05-29 | 4 | Closed | 0 | 0 | 0 | 328000 | 613000 | Y | E330-CO-011 | 402100 | 0 | 0 | 0 | 905 | P4 – Low
E330-RFI-0025 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – column reinforcement and drilled shaft cap at Bellevue SEM tunnel – 110th Ave NE | Interference between column reinforcement and drilled shaft cap at Bellevue SEM tunnel – 110th Ave NE per E-318. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Scheduler | 2017-06-01 | 10 | Routine | Y | N | N | 7 | DSDC – HJH JV | 1 | 2017-06-12 | 10 | Y | 0 | 1 | 2017-06-12 | 10 | Closed | 0 | 0 | 0 | 132000 | 247000 | Y | E330-CO-009 | 107500 | 88300 | 0 | 39.2 | 255 | P2 – High
E330-RFI-0026 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | City of Bellevue comment on critical areas permit – Bellevue Transit Center interface | City of Bellevue review comments on the critical areas permit require changes to the pedestrian ramp at Bellevue Transit Center interface. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2017-06-20 | 10 | Expedite | N | Y | N | 2 | Puget Sound Energy / ST Third-Party Mgmt | 3 | 2017-07-06 | 16 | N | 6 | 1 | 2017-07-06 | 16 | Closed | 5 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 699 | P3 – Medium
E330-RFI-0027 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – stair core wall at North shaft near Bellevue City Hall | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-854 for egress width at North shaft near Bellevue City Hall. Request direction on compliant detail. | Superintendent | 2017-07-05 | 10 | Urgent | Y | N | Y | 1 | DSDC – HJH JV | 3 | 2017-07-12 | 7 | Y | 0 | 1 | 2017-07-12 | 7 | Closed | 0 | 0 | 0 | 72000 | 134000 | Y | E330-CO-010 | 98200 | 32300 | 0 | 35.8 | 304 | P2 – High
E330-RFI-0028 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – bearing pad/embed plate at Bellevue SEM tunnel – 110th Ave NE | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-689 for emergency stair pressurization at Bellevue SEM tunnel – 110th Ave NE. Request direction on compliant detail. | Design Manager | 2017-07-07 | 10 | Routine | N | N | N | 6 | DSDC – HJH JV | 1 | 2017-07-24 | 17 | N | 7 | 1 | 2017-07-24 | 17 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 906 | P4 – Low
E330-RFI-0029 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bellevue SEM tunnel – 110th Ave NE: petroleum-stained soil with odor | During excavation at Bellevue SEM tunnel – 110th Ave NE (Sta. 2249+20) the contractor encountered petroleum-stained soil with odor, not shown on the GBR or M-817. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Field Engineer | 2017-07-28 | 10 | Routine | Y | Y | Y | 2 | DSDC – HJH JV | 2 | 2017-08-03 | 6 | Y | 0 | 1 | 2017-08-03 | 6 | Closed | 21 | 11 | 0 | 1936000 | 3614000 | Y | E330-CO-011 | 1509500 | 0 | 0 | 11 | 384 | P3 – Medium
E330-RFI-0030 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Night work and noise variance – East Main Station interface | Contractor requests approval of an alternate traffic/staging plan at East Main Station interface: extended night closure. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Project Engineer | 2017-08-01 | 10 | Routine | N | N | N | 5 | ST Design Management | 2 | 2017-08-07 | 5 | Y | 0 | 1 | 2017-08-07 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 907 | P4 – Low
E330-RFI-0031 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – column reinforcement at NE 6th St tunnel turn | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-778 for standpipe connection at NE 6th St tunnel turn. Request direction on compliant detail. | Field Engineer | 2017-08-01 | 10 | Routine | N | Y | N | 7 | DSDC – HJH JV | 2 | 2017-08-07 | 4 | Y | 0 | 1 | 2017-08-07 | 4 | Closed | 13 | 0 | 8 |  |  | N |  | 0 | 0 | 0 | 1.8 | 538 | P3 – Medium
E330-RFI-0032 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unexpected ground condition – East Main Station interface | During SEM excavation near Sta. 957+89 at East Main Station interface, ground conditions varied from the baseline in the geotechnical baseline report (observed perched groundwater at approx. elevation 49 ft). Contractor requests direction on dewatering approach and discharge treatment and confirmation of whether this constitutes a differing site condition. See M-310. | Project Manager | 2017-08-02 | 10 | Routine | Y | Y | N | 2 | DSDC – HJH JV | 1 | 2017-08-07 | 5 | Y | 0 | 1 | 2017-08-07 | 5 | Closed | 6 | 0 | 1 | 201000 | 376000 | N |  | 0 | 0 | 0 | 0.2 | 770 | P4 – Low
E330-RFI-0033 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | SPC | Spec / Drawing Clarification | General | 01 25 00 Substitution Procedures | Missing dimension on E-642 | Request clarification of 00 72 00 General Conditions and E-642: dimension/notes appear inconsistent or omitted for the work at East Main Station interface. | Field Engineer | 2017-08-04 | 10 | Routine | N | N | N | 3 | DSDC – HJH JV | 2 | 2017-08-08 | 4 | Y | 0 | 2 | 2017-08-22 | 18 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 908 | P4 – Low
E330-RFI-0034 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | SPC | Spec / Drawing Clarification | General | 01 25 00 Substitution Procedures | Drawing/spec discrepancy – Bellevue SEM tunnel – 110th Ave NE | Request clarification of 01 25 00 Substitution Procedures and E-153: dimension/notes appear inconsistent or omitted for the work at Bellevue SEM tunnel – 110th Ave NE. | Field Engineer | 2017-08-11 | 10 | Routine | N | N | N | 4 | DSDC – HJH JV | 1 | 2017-08-14 | 2 | Y | 0 | 1 | 2017-08-14 | 2 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 909 | P4 – Low
E330-RFI-0035 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Wetland/stream buffer protection – Bellevue SEM tunnel – 110th Ave NE | Field conditions at Bellevue SEM tunnel – 110th Ave NE require changes to temporary erosion and sediment control or stormwater facility per E-167. Request direction considering critical-areas conditions and permit requirements. | Project Manager | 2017-08-24 | 10 | Routine | Y | N | N | 6 | DSDC – HJH JV | 2 | 2017-09-04 | 10 | Y | 0 | 2 | 2017-09-15 | 22 | Closed | 0 | 0 | 0 | 93000 | 173000 | Y | E330-CO-012 | 85000 | 39100 | 0 | 36.4 | 300 | P2 – High
E330-RFI-0036 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 12-in. ductile iron water main at East Main Station interface | Potholing at Sta. 2289+52 located a 12-in. ductile iron water main in conflict with the proposed guideway girder diaphragm. Utility is not shown on A-442. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Field Engineer | 2017-09-01 | 10 | Expedite | Y | Y | N | 1 | DSDC – HJH JV | 1 | 2017-09-08 | 7 | Y | 0 | 1 | 2017-09-08 | 7 | Closed | 4 | 0 | 2 | 75000 | 140000 | N |  | 0 | 0 | 0 | 0.4 | 700 | P3 – Medium
E330-RFI-0037 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Bellevue SEM tunnel – 110th Ave NE | S-307 shows a 39 ft-2 in. dimension for the stair core wall; structural sheet S-732 shows a different value. Request clarification before fabrication/rebar release. | Superintendent | 2017-09-11 | 10 | Expedite | Y | N | Y | 1 | DSDC – HJH JV | 1 | 2017-09-13 | 2 | Y | 0 | 2 | 2017-09-20 | 9 | Closed | 0 | 0 | 0 | 48000 | 90000 | N |  | 0 | 0 | 0 | 0 | 910 | P4 – Low
E330-RFI-0038 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at South portal – 112th Ave SE/Main St: abandoned timber piles | During excavation at South portal – 112th Ave SE/Main St (Sta. 2293+84) the contractor encountered abandoned timber piles, not shown on the GBR or S-350. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Scheduler | 2017-09-11 | 10 | Routine | Y | N | N | 5 | DSDC – HJH JV | 1 | 2017-09-14 | 3 | Y | 0 | 1 | 2017-09-14 | 3 | Closed | 0 | 0 | 0 | 71000 | 132000 | Y | E330-CO-013 | 106300 | 78400 | 0 | 38.8 | 258 | P2 – High
E330-RFI-0039 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – Bellevue Transit Center interface | Civil and systems drawings differ on grounding/bonding of bearing pad/embed plate for stray-current control at Bellevue Transit Center interface. Request governing detail and responsibility for installation. | Design Manager | 2017-09-20 | 10 | Urgent | N | Y | Y | 1 | DSDC – HJH JV | 3 | 2017-09-29 | 9 | Y | 0 | 1 | 2017-09-29 | 9 | Closed | 15 | 12 | 0 |  |  | N |  | 0 | 0 | 0 | 12 | 377 | P3 – Medium
E330-RFI-0040 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Crane staging in right-of-way – North shaft near Bellevue City Hall | Contractor requests approval of an alternate traffic/staging plan at North shaft near Bellevue City Hall: extended night closure. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Field Engineer | 2017-10-02 | 10 | Routine | N | Y | N | 4 | DSDC – HJH JV | 1 | 2017-10-05 | 3 | Y | 0 | 1 | 2017-10-05 | 3 | Closed | 3 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 771 | P4 – Low
E330-RFI-0041 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Direct fixation fastener spacing at Sta. 1343+02 | Track layout at Sta. 1343+02 (NE 6th St tunnel turn) differs from the track-structure interface drawing C-317. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2017-10-03 | 10 | Routine | N | N | Y | 0 | DSDC – HJH JV | 1 | 2017-10-05 | 2 | Y | 0 | 1 | 2017-10-05 | 2 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 911 | P4 – Low
E330-RFI-0042 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 8-in. high-pressure gas main at North shaft near Bellevue City Hall | Potholing at Sta. 1062+80 located a 8-in. high-pressure gas main in conflict with the proposed guideway girder diaphragm. Utility is not shown on S-137. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Scheduler | 2017-10-12 | 10 | Urgent | Y | Y | N | 3 | ST Design Management | 2 | 2017-10-16 | 4 | Y | 0 | 1 | 2017-10-16 | 4 | Closed | 8 | 0 | 5 | 103000 | 192000 | Y | E330-CO-014 | 192580 | 112600 | 2.5 | 42 | 199 | P2 – High
E330-RFI-0043 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – retaining wall footing sequence at East Main Station interface | Erection of the retaining wall footing as drawn conflicts with adjacent work and access limits at East Main Station interface. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Superintendent | 2017-10-17 | 10 | Expedite | N | Y | N | 3 | DSDC – HJH JV | 2 | 2017-11-01 | 15 | N | 5 | 1 | 2017-11-01 | 15 | Closed | 4 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 655 | P3 – Medium
E330-RFI-0044 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with PSE distribution duct bank at NE 6th St tunnel turn | Potholing at Sta. 1141+42 located a PSE distribution duct bank in conflict with the proposed drilled shaft cap. Utility is not shown on C-649. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Scheduler | 2017-10-23 | 10 | Routine | N | N | Y | 8 | DSDC – HJH JV | 4 | 2017-11-02 | 10 | Y | 0 | 1 | 2017-11-02 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 912 | P4 – Low
E330-RFI-0045 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – South portal – 112th Ave SE/Main St | A-877 shows a 49 ft-8 in. dimension for the column reinforcement; structural sheet S-130 shows a different value. Request clarification before fabrication/rebar release. | Superintendent | 2017-10-23 | 10 | Urgent | N | N | Y | 8 | DSDC – HJH JV | 1 | 2017-10-31 | 8 | Y | 0 | 2 | 2017-11-14 | 22 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 913 | P4 – Low
E330-RFI-0046 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Bellevue SEM tunnel – 110th Ave NE: glacially deposited boulders exceeding 36 in. | During excavation at Bellevue SEM tunnel – 110th Ave NE (Sta. 1984+55) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or M-363. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Field Engineer | 2017-10-23 | 10 | Urgent | Y | Y | N | 7 | DSDC – HJH JV | 2 | 2017-11-02 | 10 | Y | 0 | 1 | 2017-11-02 | 10 | Closed | 5 | 0 | 2 | 105000 | 197000 | Y | E330-CO-018 | 120130 | 71090 | 2 | 39.6 | 246 | P2 – High
E330-RFI-0047 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with abandoned utility vault at Bellevue Transit Center interface | Potholing at Sta. 930+72 located a abandoned utility vault in conflict with the proposed station canopy support. Utility is not shown on A-811. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Field Engineer | 2017-10-30 | 10 | Urgent | Y | N | N | 1 | DSDC – HJH JV | 3 | 2017-11-06 | 5 | Y | 0 | 1 | 2017-11-06 | 5 | Closed | 0 | 0 | 0 | 79000 | 147000 | Y | E330-CO-014 | 194120 | 113500 | 2.5 | 40.9 | 219 | P2 – High
E330-RFI-0048 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Haul route revision – North shaft near Bellevue City Hall | Contractor requests approval of an alternate traffic/staging plan at North shaft near Bellevue City Hall: temporary lane shift. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Design Manager | 2017-11-03 | 10 | Expedite | N | Y | N | 5 | DSDC – HJH JV | 4 | 2017-11-09 | 6 | Y | 0 | 2 | 2017-11-24 | 21 | Closed | 3 | 0 | 1 |  |  | Y | E330-CO-015 | 40700 | 40700 | 1 | 37.1 | 288 | P2 – High
E330-RFI-0049 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – alternate epoxy-coated rebar supplier | Contractor requests approval to substitute alternate epoxy-coated rebar supplier for specified epoxy-coated rebar on work at NE 6th St tunnel turn, citing procurement lead time. Product data attached. | Project Engineer | 2017-11-13 | 10 | Routine | N | N | N | 4 | ST Design Management | 2 | 2017-11-20 | 7 | Y | 0 | 1 | 2017-11-20 | 7 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 914 | P4 – Low
E330-RFI-0050 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Crane staging in right-of-way – Bellevue Transit Center interface | Contractor requests approval of an alternate traffic/staging plan at Bellevue Transit Center interface: temporary lane shift. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Field Engineer | 2017-11-13 | 10 | Routine | Y | Y | Y | 0 | DSDC – HJH JV | 2 | 2017-11-20 | 7 | Y | 0 | 1 | 2017-11-20 | 7 | Closed | 5 | 3 | 0 | 77000 | 143000 | Y | E330-CO-016 | 56500 | 0 | 0 | 3 | 473 | P3 – Medium
E330-RFI-0051 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Lane closure window request – South portal – 112th Ave SE/Main St | Contractor requests approval of an alternate traffic/staging plan at South portal – 112th Ave SE/Main St: extended night closure. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Design Manager | 2017-11-13 | 10 | Routine | N | N | N | 1 | DSDC – HJH JV | 2 | 2017-11-16 | 3 | Y | 0 | 1 | 2017-11-16 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 915 | P4 – Low
E330-RFI-0052 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – alternate LED luminaire | Contractor requests approval to substitute alternate LED luminaire for specified LED luminaire on work at NE 6th St tunnel turn, citing procurement lead time. Product data attached. | Scheduler | 2017-11-20 | 10 | Expedite | N | N | N | 3 | DSDC – HJH JV | 4 | 2017-11-23 | 3 | Y | 0 | 1 | 2017-11-23 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 916 | P4 – Low
E330-RFI-0053 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unexpected ground condition – East Main Station interface | During SEM excavation near Sta. 2281+87 at East Main Station interface, ground conditions varied from the baseline in the geotechnical baseline report (observed abandoned timber piles). Contractor requests direction on over-excavation limits and replacement fill and confirmation of whether this constitutes a differing site condition. See S-188. | Design Manager | 2017-12-01 | 10 | Routine | N | Y | N | 7 | DSDC – HJH JV | 3 | 2017-12-06 | 5 | Y | 0 | 1 | 2017-12-06 | 5 | Closed | 5 | 0 | 1 |  |  | Y | E330-CO-018 | 56590 | 33490 | 1 | 36.5 | 298 | P2 – High
E330-RFI-0054 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Traction Power Feeder location conflict at Sta. 1071+14 | Proposed traction power feeder foundation location at Sta. 1071+14 conflicts with pedestrian ramp; offset of 6 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Superintendent | 2017-12-04 | 10 | Expedite | Y | Y | N | 0 | DSDC – HJH JV | 5 | 2017-12-18 | 13 | N | 3 | 1 | 2017-12-18 | 13 | Closed | 9 | 0 | 3 | 257000 | 479000 | Y | E330-CO-017 | 263300 | 215500 | 5 | 44.7 | 143 | P2 – High
E330-RFI-0055 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Bellevue SEM tunnel – 110th Ave NE: perched groundwater | During excavation at Bellevue SEM tunnel – 110th Ave NE (Sta. 1307+63) the contractor encountered perched groundwater at approx. elevation 226 ft, not shown on the GBR or S-141. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Project Manager | 2017-12-18 | 10 | Urgent | Y | N | Y | 6 | DSDC – HJH JV | 1 | 2017-12-21 | 3 | Y | 0 | 1 | 2017-12-21 | 3 | Closed | 0 | 0 | 0 | 125000 | 233000 | Y | E330-CO-018 | 179990 | 106520 | 3 | 40.9 | 220 | P2 – High
E330-RFI-0056 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 8-in. high-pressure gas main at NE 6th St tunnel turn | Potholing at Sta. 1974+87 located a 8-in. high-pressure gas main in conflict with the proposed retaining wall footing. Utility is not shown on E-870. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Design Manager | 2017-12-18 | 10 | Routine | Y | N | N | 5 | DSDC – HJH JV | 1 | 2017-12-25 | 5 | Y | 0 | 1 | 2017-12-25 | 5 | Closed | 0 | 0 | 0 | 56000 | 105000 | Y | E330-CO-019 | 112100 | 70100 | 0 | 38.5 | 261 | P2 – High
E330-RFI-0057 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bellevue Transit Center interface: buried concrete debris and an old foundation | During excavation at Bellevue Transit Center interface (Sta. 1203+45) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or E-132. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Field Engineer | 2017-12-25 | 10 | Routine | Y | Y | Y | 5 | DSDC – HJH JV | 2 | 2017-12-28 | 3 | Y | 0 | 1 | 2017-12-28 | 3 | Closed | 20 | 8 | 0 | 135000 | 252000 | N |  | 0 | 0 | 0 | 8 | 407 | P3 – Medium
E330-RFI-0058 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | Stormwater facility revision – South portal – 112th Ave SE/Main St | Field conditions at South portal – 112th Ave SE/Main St require changes to temporary erosion and sediment control or stormwater facility per E-679. Request direction considering critical-areas conditions and permit requirements. | Scheduler | 2018-01-02 | 10 | Routine | N | N | N | 8 | DSDC – HJH JV | 2 | 2018-01-12 | 10 | Y | 0 | 1 | 2018-01-12 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 917 | P4 – Low
E330-RFI-0059 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unexpected ground condition – North shaft near Bellevue City Hall | During SEM excavation near Sta. 1736+49 at North shaft near Bellevue City Hall, ground conditions varied from the baseline in the geotechnical baseline report (observed petroleum-stained soil with odor). Contractor requests direction on testing/disposal protocol and confirmation of whether this constitutes a differing site condition. See M-322. | Project Engineer | 2018-01-02 | 10 | Routine | Y | Y | Y | 1 | DSDC – HJH JV | 3 | 2018-01-11 | 9 | Y | 0 | 1 | 2018-01-11 | 9 | Closed | 13 | 5 | 0 | 285000 | 532000 | Y | E330-CO-020 | 363100 | 265000 | 6 | 50 | 56 | P1 – Critical
E330-RFI-0060 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at South portal – 112th Ave SE/Main St: abandoned timber piles | During excavation at South portal – 112th Ave SE/Main St (Sta. 1187+01) the contractor encountered abandoned timber piles, not shown on the GBR or C-517. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Design Manager | 2018-01-15 | 10 | Routine | Y | Y | Y | 7 | ST Design Management | 4 | 2018-01-22 | 7 | Y | 0 | 1 | 2018-01-22 | 7 | Closed | 15 | 11 | 0 | 9000 | 17000 | N |  | 0 | 0 | 0 | 11 | 385 | P3 – Medium
E330-RFI-0061 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 12-in. ductile iron water main at NE 6th St tunnel turn | Potholing at Sta. 1969+27 located a 12-in. ductile iron water main in conflict with the proposed pedestrian ramp. Utility is not shown on C-141. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Manager | 2018-01-22 | 10 | Expedite | Y | N | N | 1 | DSDC – HJH JV | 2 | 2018-02-06 | 15 | N | 5 | 1 | 2018-02-06 | 15 | Closed | 0 | 0 | 0 | 190000 | 354000 | Y | E330-CO-021 | 283300 | 118100 | 0 | 40.2 | 230 | P2 – High
E330-RFI-0062 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – pedestrian ramp at East Main Station interface | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-716 for egress width at East Main Station interface. Request direction on compliant detail. | Project Engineer | 2018-01-22 | 10 | Urgent | N | N | N | 7 | DSDC – HJH JV | 3 | 2018-01-29 | 5 | Y | 0 | 2 | 2018-02-12 | 21 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 918 | P4 – Low
E330-RFI-0063 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – guideway girder diaphragm at North shaft near Bellevue City Hall | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-666 for smoke control damper at North shaft near Bellevue City Hall. Request direction on compliant detail. | Field Engineer | 2018-01-23 | 10 | Expedite | N | N | N | 4 | DSDC – HJH JV | 3 | 2018-01-31 | 8 | Y | 0 | 1 | 2018-01-31 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 919 | P4 – Low
E330-RFI-0064 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 24-in. sanitary sewer at North shaft near Bellevue City Hall | Potholing at Sta. 1996+04 located a 24-in. sanitary sewer in conflict with the proposed platform edge slab. Utility is not shown on M-756. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Field Engineer | 2018-01-29 | 10 | Expedite | N | N | N | 0 | DSDC – HJH JV | 4 | 2018-02-05 | 5 | Y | 0 | 1 | 2018-02-05 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 920 | P4 – Low
E330-RFI-0065 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unexpected ground condition – South portal – 112th Ave SE/Main St | During SEM excavation near Sta. 1165+83 at South portal – 112th Ave SE/Main St, ground conditions varied from the baseline in the geotechnical baseline report (observed glacially deposited boulders exceeding 36 in.). Contractor requests direction on testing/disposal protocol and confirmation of whether this constitutes a differing site condition. See C-612. | Design Manager | 2018-01-31 | 10 | Expedite | Y | N | Y | 7 | DSDC – HJH JV | 4 | 2018-02-05 | 5 | Y | 0 | 1 | 2018-02-05 | 5 | Closed | 0 | 3 | 0 | 96000 | 179000 | N |  | 0 | 0 | 0 | 3 | 474 | P3 – Medium
E330-RFI-0066 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Canopy/glazing connection – North shaft near Bellevue City Hall | Request to clarify finish/connection detail on M-300 at North shaft near Bellevue City Hall. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2018-02-12 | 10 | Routine | N | N | N | 2 | ST Design Management | 5 | 2018-02-19 | 7 | Y | 0 | 1 | 2018-02-19 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 921 | P4 – Low
E330-RFI-0067 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unexpected ground condition – East Main Station interface | During SEM excavation near Sta. 2080+75 at East Main Station interface, ground conditions varied from the baseline in the geotechnical baseline report (observed abandoned timber piles). Contractor requests direction on testing/disposal protocol and confirmation of whether this constitutes a differing site condition. See S-365. | Field Engineer | 2018-02-13 | 10 | Routine | Y | Y | Y | 7 | DSDC – HJH JV | 1 | 2018-03-01 | 16 | N | 6 | 1 | 2018-03-01 | 16 | Closed | 12 | 8 | 0 | 395000 | 738000 | Y | E330-CO-023 | 564900 | 0 | 0 | 8 | 408 | P3 – Medium
E330-RFI-0068 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – drilled shaft cap sequence at NE 6th St tunnel turn | Erection of the drilled shaft cap as drawn conflicts with adjacent work and access limits at NE 6th St tunnel turn. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Superintendent | 2018-02-20 | 10 | Routine | Y | Y | N | 6 | DSDC – HJH JV | 1 | 2018-02-28 | 8 | Y | 0 | 1 | 2018-02-28 | 8 | Closed | 3 | 0 | 2 | 8000 | 15000 | N |  | 0 | 0 | 0 | 0.4 | 701 | P3 – Medium
E330-RFI-0069 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Bellevue Transit Center interface: glacially deposited boulders exceeding 36 in. | During excavation at Bellevue Transit Center interface (Sta. 1164+45) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or S-696. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Design Manager | 2018-02-21 | 10 | Routine | Y | Y | N | 7 | DSDC – HJH JV | 2 | 2018-03-01 | 8 | Y | 0 | 1 | 2018-03-01 | 8 | Closed | 12 | 0 | 8 | 19000 | 35000 | Y | E330-CO-022 | 9800 | 6900 | 7 | 34.6 | 318 | P2 – High
E330-RFI-0070 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – platform edge slab at North shaft near Bellevue City Hall | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-686 for egress width at North shaft near Bellevue City Hall. Request direction on compliant detail. | Project Manager | 2018-02-22 | 10 | Expedite | N | N | N | 2 | DSDC – HJH JV | 3 | 2018-03-09 | 15 | N | 5 | 1 | 2018-03-09 | 15 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 922 | P4 – Low
E330-RFI-0071 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Drawing/spec discrepancy – NE 6th St tunnel turn | Request clarification of 01 33 00 Submittal Procedures and M-400: dimension/notes appear inconsistent or omitted for the work at NE 6th St tunnel turn. | Design Manager | 2018-03-26 | 10 | Expedite | N | N | N | 4 | DSDC – HJH JV | 1 | 2018-03-28 | 2 | Y | 0 | 2 | 2018-04-09 | 13 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 923 | P4 – Low
E330-RFI-0072 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Bellevue Transit Center interface: abandoned timber piles | During excavation at Bellevue Transit Center interface (Sta. 1636+30) the contractor encountered abandoned timber piles, not shown on the GBR or A-666. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Superintendent | 2018-04-02 | 10 | Routine | N | Y | N | 1 | DSDC – HJH JV | 2 | 2018-04-16 | 13 | N | 3 | 1 | 2018-04-16 | 13 | Closed | 5 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 572 | P3 – Medium
E330-RFI-0073 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Crane staging in right-of-way – NE 6th St tunnel turn | Contractor requests approval of an alternate traffic/staging plan at NE 6th St tunnel turn: revised haul route. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Design Manager | 2018-04-09 | 10 | Routine | N | Y | N | 8 | DSDC – HJH JV | 2 | 2018-04-12 | 3 | Y | 0 | 1 | 2018-04-12 | 3 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 772 | P4 – Low
E330-RFI-0074 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – pedestrian ramp at Bellevue SEM tunnel – 110th Ave NE | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-139 for smoke control damper at Bellevue SEM tunnel – 110th Ave NE. Request direction on compliant detail. | Scheduler | 2018-05-07 | 10 | Routine | N | N | Y | 4 | DSDC – HJH JV | 5 | 2018-05-21 | 12 | N | 2 | 1 | 2018-05-21 | 12 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 924 | P4 – Low
E330-RFI-0075 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at NE 6th St tunnel turn: loose granular fill below planned bearing elevation | During excavation at NE 6th St tunnel turn (Sta. 2292+40) the contractor encountered loose granular fill below planned bearing elevation, not shown on the GBR or M-516. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Project Engineer | 2018-05-11 | 10 | Expedite | Y | N | N | 1 | DSDC – HJH JV | 3 | 2018-05-21 | 10 | Y | 0 | 1 | 2018-05-21 | 10 | Closed | 0 | 0 | 0 | 104000 | 195000 | N |  | 0 | 0 | 0 | 0 | 925 | P4 – Low
E330-RFI-0076 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Lane closure window request – Bellevue SEM tunnel – 110th Ave NE | Contractor requests approval of an alternate traffic/staging plan at Bellevue SEM tunnel – 110th Ave NE: temporary lane shift. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Superintendent | 2018-05-22 | 10 | Routine | Y | N | N | 3 | DSDC – HJH JV | 2 | 2018-05-25 | 3 | Y | 0 | 2 | 2018-06-04 | 12 | Closed | 0 | 0 | 0 | 245000 | 457000 | N |  | 0 | 0 | 0 | 0 | 926 | P4 – Low
E330-RFI-0077 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 12-in. ductile iron water main at South portal – 112th Ave SE/Main St | Potholing at Sta. 913+55 located a 12-in. ductile iron water main in conflict with the proposed stair core wall. Utility is not shown on S-106. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Superintendent | 2018-05-28 | 10 | Routine | Y | Y | Y | 8 | DSDC – HJH JV | 1 | 2018-05-31 | 3 | Y | 0 | 1 | 2018-05-31 | 3 | Closed | 5 | 2 | 0 | 66000 | 124000 | Y | E330-CO-024 | 60630 | 0 | 0 | 2 | 511 | P3 – Medium
E330-RFI-0078 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unexpected ground condition – South portal – 112th Ave SE/Main St | During SEM excavation near Sta. 2023+10 at South portal – 112th Ave SE/Main St, ground conditions varied from the baseline in the geotechnical baseline report (observed an unmapped abandoned storm line). Contractor requests direction on temporary shoring modification and confirmation of whether this constitutes a differing site condition. See A-232. | Scheduler | 2018-06-07 | 10 | Routine | N | N | Y | 2 | DSDC – HJH JV | 4 | 2018-06-20 | 13 | N | 3 | 1 | 2018-06-20 | 13 | Closed | 0 | 1 | 0 |  |  | N |  | 0 | 0 | 0 | 1 | 604 | P3 – Medium
E330-RFI-0079 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unexpected ground condition – North shaft near Bellevue City Hall | During SEM excavation near Sta. 2012+95 at North shaft near Bellevue City Hall, ground conditions varied from the baseline in the geotechnical baseline report (observed glacially deposited boulders exceeding 36 in.). Contractor requests direction on revised bearing elevation and foundation detail and confirmation of whether this constitutes a differing site condition. See S-789. | Scheduler | 2018-06-18 | 10 | Urgent | N | Y | Y | 6 | DSDC – HJH JV | 1 | 2018-06-22 | 4 | Y | 0 | 1 | 2018-06-22 | 4 | Closed | 8 | 6 | 0 |  |  | N |  | 0 | 0 | 0 | 6 | 420 | P3 – Medium
E330-RFI-0080 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 8-in. high-pressure gas main at Bellevue SEM tunnel – 110th Ave NE | Potholing at Sta. 1992+09 located a 8-in. high-pressure gas main in conflict with the proposed duct bank encasement. Utility is not shown on A-678. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Field Engineer | 2018-06-19 | 10 | Routine | Y | N | N | 0 | DSDC – HJH JV | 2 | 2018-06-25 | 4 | Y | 0 | 1 | 2018-06-25 | 4 | Closed | 0 | 0 | 0 | 647000 | 1208000 | Y | E330-CO-024 | 615870 | 0 | 0 | 0 | 927 | P4 – Low
E330-RFI-0081 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at South portal – 112th Ave SE/Main St: soft lacustrine silt below design subgrade | During excavation at South portal – 112th Ave SE/Main St (Sta. 1215+65) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or C-883. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Project Engineer | 2018-06-25 | 10 | Routine | Y | N | Y | 8 | DSDC – HJH JV | 2 | 2018-07-02 | 5 | Y | 0 | 1 | 2018-07-02 | 5 | Closed | 0 | 0 | 0 | 763000 | 1424000 | Y | E330-CO-025 | 781240 | 0 | 0 | 0 | 928 | P4 – Low
E330-RFI-0082 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bellevue SEM tunnel – 110th Ave NE: soft lacustrine silt below design subgrade | During excavation at Bellevue SEM tunnel – 110th Ave NE (Sta. 2122+95) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or E-296. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Scheduler | 2018-06-28 | 10 | Urgent | Y | Y | Y | 8 | DSDC – HJH JV | 3 | 2018-07-03 | 5 | Y | 0 | 1 | 2018-07-03 | 5 | Closed | 7 | 5 | 0 | 159000 | 297000 | Y | E330-CO-027 | 217750 | 0 | 0 | 5 | 431 | P3 – Medium
E330-RFI-0083 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at East Main Station interface: soft lacustrine silt below design subgrade | During excavation at East Main Station interface (Sta. 2286+83) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or A-269. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Superintendent | 2018-07-09 | 10 | Expedite | Y | N | N | 7 | DSDC – HJH JV | 2 | 2018-07-19 | 10 | Y | 0 | 1 | 2018-07-19 | 10 | Closed | 0 | 0 | 0 | 256000 | 477000 | Y | E330-CO-025 | 485760 | 0 | 0 | 0 | 929 | P4 – Low
E330-RFI-0084 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – bearing pad/embed plate and station canopy support at Bellevue SEM tunnel – 110th Ave NE | Interference between bearing pad/embed plate and station canopy support at Bellevue SEM tunnel – 110th Ave NE per M-257. Required clearance of 2 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2018-07-13 | 10 | Routine | Y | N | N | 6 | DSDC – HJH JV | 1 | 2018-07-19 | 6 | Y | 0 | 1 | 2018-07-19 | 6 | Closed | 0 | 0 | 0 | 47000 | 88000 | Y | E330-CO-026 | 64860 | 56700 | 0 | 37.7 | 280 | P2 – High
E330-RFI-0085 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – guideway girder diaphragm sequence at South portal – 112th Ave SE/Main St | Erection of the guideway girder diaphragm as drawn conflicts with adjacent work and access limits at South portal – 112th Ave SE/Main St. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Superintendent | 2018-08-20 | 10 | Routine | Y | N | N | 0 | DSDC – HJH JV | 1 | 2018-08-27 | 7 | Y | 0 | 1 | 2018-08-27 | 7 | Closed | 0 | 0 | 0 | 54000 | 102000 | Y | E330-CO-026 | 44740 | 39100 | 0 | 36.4 | 301 | P2 – High
E330-RFI-0086 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Stormwater facility revision – NE 6th St tunnel turn | Field conditions at NE 6th St tunnel turn require changes to temporary erosion and sediment control or stormwater facility per M-153. Request direction considering critical-areas conditions and permit requirements. | Project Engineer | 2018-09-10 | 10 | Routine | Y | N | N | 8 | DSDC – HJH JV | 2 | 2018-09-19 | 9 | Y | 0 | 1 | 2018-09-19 | 9 | Closed | 0 | 0 | 0 | 17000 | 31000 | N |  | 0 | 0 | 0 | 0 | 930 | P4 – Low
E330-RFI-0087 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bellevue SEM tunnel – 110th Ave NE: petroleum-stained soil with odor | During excavation at Bellevue SEM tunnel – 110th Ave NE (Sta. 1198+21) the contractor encountered petroleum-stained soil with odor, not shown on the GBR or A-777. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Superintendent | 2018-09-10 | 10 | Routine | Y | Y | Y | 1 | DSDC – HJH JV | 2 | 2018-09-18 | 8 | Y | 0 | 1 | 2018-09-18 | 8 | Closed | 11 | 5 | 0 | 826000 | 1543000 | Y | E330-CO-027 | 1074450 | 0 | 0 | 5 | 432 | P3 – Medium
E330-RFI-0088 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – column reinforcement and bearing pad/embed plate at NE 6th St tunnel turn | Interference between column reinforcement and bearing pad/embed plate at NE 6th St tunnel turn per M-272. Required clearance of 8 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Manager | 2018-09-11 | 10 | Routine | N | N | Y | 3 | DSDC – HJH JV | 2 | 2018-09-18 | 7 | Y | 0 | 2 | 2018-10-03 | 22 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 931 | P4 – Low
E330-RFI-0089 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Bellevue SEM tunnel – 110th Ave NE | S-508 shows a 37 ft-9 in. dimension for the column reinforcement; structural sheet S-616 shows a different value. Request clarification before fabrication/rebar release. | Project Manager | 2018-10-02 | 10 | Expedite | Y | N | N | 2 | DSDC – HJH JV | 1 | 2018-10-08 | 6 | Y | 0 | 1 | 2018-10-08 | 6 | Closed | 0 | 0 | 0 | 232000 | 434000 | Y | E330-CO-028 | 103600 | 65500 | 0 | 38.2 | 271 | P2 – High
E330-RFI-0090 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 12-in. ductile iron water main at South portal – 112th Ave SE/Main St | Potholing at Sta. 1309+87 located a 12-in. ductile iron water main in conflict with the proposed bearing pad/embed plate. Utility is not shown on S-843. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Engineer | 2018-10-05 | 10 | Routine | N | Y | N | 5 | DSDC – HJH JV | 1 | 2018-10-16 | 11 | N | 1 | 2 | 2018-10-29 | 23 | Closed | 3 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 702 | P3 – Medium
E330-RFI-0091 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at East Main Station interface: glacially deposited boulders exceeding 36 in. | During excavation at East Main Station interface (Sta. 1122+32) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or S-780. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Design Manager | 2018-10-08 | 10 | Routine | N | Y | Y | 6 | DSDC – HJH JV | 4 | 2018-10-22 | 14 | N | 4 | 1 | 2018-10-22 | 14 | Closed | 14 | 9 | 0 |  |  | N |  | 0 | 0 | 0 | 9 | 400 | P3 – Medium
E330-RFI-0092 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Direct fixation fastener spacing at Sta. 1114+89 | Track layout at Sta. 1114+89 (South portal – 112th Ave SE/Main St) differs from the track-structure interface drawing M-680. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2018-10-10 | 10 | Urgent | Y | N | Y | 3 | ST Design Management | 2 | 2018-10-17 | 7 | Y | 0 | 1 | 2018-10-17 | 7 | Closed | 0 | 0 | 0 | 58000 | 108000 | N |  | 0 | 0 | 0 | 0 | 932 | P4 – Low
E330-RFI-0093 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Bellevue SEM tunnel – 110th Ave NE: petroleum-stained soil with odor | During excavation at Bellevue SEM tunnel – 110th Ave NE (Sta. 2322+28) the contractor encountered petroleum-stained soil with odor, not shown on the GBR or C-418. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Project Engineer | 2018-10-16 | 10 | Routine | Y | Y | Y | 4 | DSDC – HJH JV | 2 | 2018-10-22 | 4 | Y | 0 | 1 | 2018-10-22 | 4 | Closed | 25 | 15 | 0 | 102000 | 191000 | Y | E330-CO-032 | 134700 | 0 | 0 | 15 | 370 | P3 – Medium
E330-RFI-0094 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | In-water work window – East Main Station interface | Field conditions at East Main Station interface require changes to temporary erosion and sediment control or stormwater facility per S-504. Request direction considering critical-areas conditions and permit requirements. | Project Manager | 2018-10-18 | 10 | Routine | N | Y | N | 5 | DSDC – HJH JV | 3 | 2018-10-31 | 13 | N | 3 | 1 | 2018-10-31 | 13 | Closed | 11 | 0 | 9 |  |  | N |  | 0 | 0 | 0 | 2 | 512 | P3 – Medium
E330-RFI-0095 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – retaining wall footing sequence at Bellevue SEM tunnel – 110th Ave NE | Erection of the retaining wall footing as drawn conflicts with adjacent work and access limits at Bellevue SEM tunnel – 110th Ave NE. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2018-10-19 | 10 | Expedite | Y | N | N | 4 | DSDC – HJH JV | 2 | 2018-11-01 | 13 | N | 3 | 2 | 2018-11-16 | 28 | Closed | 0 | 0 | 1 | 88000 | 165000 | Y | E330-CO-029 | 158000 | 115600 | 0 | 40.4 | 228 | P2 – High
E330-RFI-0096 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – platform edge slab and station canopy support at NE 6th St tunnel turn | Interference between platform edge slab and station canopy support at NE 6th St tunnel turn per E-302. Required clearance of 4 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Engineer | 2018-11-01 | 10 | Routine | N | Y | N | 8 | DSDC – HJH JV | 1 | 2018-11-05 | 4 | Y | 0 | 1 | 2018-11-05 | 4 | Closed | 11 | 0 | 8 |  |  | N |  | 0 | 0 | 0 | 1.8 | 539 | P3 – Medium
E330-RFI-0097 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with abandoned utility vault at East Main Station interface | Potholing at Sta. 1011+82 located a abandoned utility vault in conflict with the proposed stair core wall. Utility is not shown on E-889. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Field Engineer | 2018-11-15 | 10 | Routine | Y | Y | N | 1 | DSDC – HJH JV | 3 | 2018-11-19 | 4 | Y | 0 | 1 | 2018-11-19 | 4 | Closed | 5 | 0 | 2 | 19000 | 35000 | Y | E330-CO-030 | 37600 | 26500 | 3 | 36.5 | 299 | P2 – High
E330-RFI-0098 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Traction Power Feeder location conflict at Sta. 2094+23 | Proposed traction power feeder foundation location at Sta. 2094+23 conflicts with guideway girder diaphragm; offset of 8 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Field Engineer | 2018-12-06 | 10 | Urgent | Y | N | N | 7 | DSDC – HJH JV | 2 | 2018-12-14 | 8 | Y | 0 | 1 | 2018-12-14 | 8 | Closed | 0 | 0 | 0 | 61000 | 113000 | N |  | 0 | 0 | 0 | 0 | 933 | P4 – Low
E330-RFI-0099 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unexpected ground condition – Bellevue Transit Center interface | During SEM excavation near Sta. 1088+94 at Bellevue Transit Center interface, ground conditions varied from the baseline in the geotechnical baseline report (observed loose granular fill below planned bearing elevation). Contractor requests direction on over-excavation limits and replacement fill and confirmation of whether this constitutes a differing site condition. See S-874. | Scheduler | 2018-12-10 | 10 | Routine | N | Y | N | 0 | ST Design Management | 3 | 2018-12-18 | 8 | Y | 0 | 2 | 2019-01-07 | 28 | Closed | 4 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 703 | P3 – Medium
E330-RFI-0100 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at South portal – 112th Ave SE/Main St: soft lacustrine silt below design subgrade | During excavation at South portal – 112th Ave SE/Main St (Sta. 1148+97) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or S-723. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Project Engineer | 2018-12-10 | 10 | Routine | Y | Y | N | 0 | DSDC – HJH JV | 2 | 2018-12-24 | 13 | N | 3 | 2 | 2019-01-07 | 27 | Closed | 15 | 0 | 5 | 6481000 | 12097000 | Y | E330-CO-032 | 8407500 | 0 | 0 | 1.1 | 573 | P3 – Medium
E330-RFI-0101 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bellevue Transit Center interface: glacially deposited boulders exceeding 36 in. | During excavation at Bellevue Transit Center interface (Sta. 1268+05) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or C-696. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Field Engineer | 2018-12-24 | 10 | Routine | N | N | N | 1 | DSDC – HJH JV | 3 | 2019-01-07 | 12 | N | 2 | 1 | 2019-01-07 | 12 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 934 | P4 – Low
E330-RFI-0102 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Bellevue SEM tunnel – 110th Ave NE: abandoned timber piles | During excavation at Bellevue SEM tunnel – 110th Ave NE (Sta. 982+73) the contractor encountered abandoned timber piles, not shown on the GBR or A-269. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Design Manager | 2018-12-25 | 10 | Routine | N | Y | N | 1 | DSDC – HJH JV | 1 | 2019-01-01 | 7 | Y | 0 | 1 | 2019-01-01 | 7 | Closed | 5 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 656 | P3 – Medium
E330-RFI-0103 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Crane staging in right-of-way – Bellevue Transit Center interface | Contractor requests approval of an alternate traffic/staging plan at Bellevue Transit Center interface: revised haul route. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Superintendent | 2018-12-31 | 10 | Urgent | Y | N | N | 2 | DSDC – HJH JV | 2 | 2019-01-03 | 3 | Y | 0 | 1 | 2019-01-03 | 3 | Closed | 0 | 0 | 0 | 104000 | 195000 | Y | E330-CO-031 | 154700 | 154700 | 0 | 41.2 | 215 | P2 – High
E330-RFI-0104 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unexpected ground condition – NE 6th St tunnel turn | During SEM excavation near Sta. 2018+78 at NE 6th St tunnel turn, ground conditions varied from the baseline in the geotechnical baseline report (observed perched groundwater at approx. elevation 231 ft). Contractor requests direction on revised bearing elevation and foundation detail and confirmation of whether this constitutes a differing site condition. See C-788. | Scheduler | 2018-12-31 | 10 | Routine | N | N | N | 3 | ST Design Management | 2 | 2019-01-03 | 3 | Y | 0 | 1 | 2019-01-03 | 3 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 935 | P4 – Low
E330-RFI-0105 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – column reinforcement sequence at Bellevue SEM tunnel – 110th Ave NE | Erection of the column reinforcement as drawn conflicts with adjacent work and access limits at Bellevue SEM tunnel – 110th Ave NE. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Project Engineer | 2019-01-03 | 10 | Routine | N | N | N | 8 | DSDC – HJH JV | 1 | 2019-01-14 | 11 | N | 1 | 1 | 2019-01-14 | 11 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 936 | P4 – Low
E330-RFI-0106 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | SPC | Spec / Drawing Clarification | General | 01 25 00 Substitution Procedures | Clarify spec requirement – NE 6th St tunnel turn | Request clarification of 01 25 00 Substitution Procedures and S-146: dimension/notes appear inconsistent or omitted for the work at NE 6th St tunnel turn. | Field Engineer | 2019-01-04 | 10 | Routine | N | N | N | 4 | DSDC – HJH JV | 2 | 2019-01-08 | 4 | Y | 0 | 1 | 2019-01-08 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 937 | P4 – Low
E330-RFI-0107 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – guideway girder diaphragm and retaining wall footing at Bellevue Transit Center interface | Interference between guideway girder diaphragm and retaining wall footing at Bellevue Transit Center interface per M-112. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2019-01-08 | 10 | Routine | Y | Y | N | 1 | DSDC – HJH JV | 2 | 2019-01-14 | 5 | Y | 0 | 2 | 2019-01-31 | 23 | Closed | 5 | 0 | 3 | 40000 | 75000 | N |  | 0 | 0 | 0 | 0.7 | 657 | P3 – Medium
E330-RFI-0108 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Bellevue Transit Center interface: glacially deposited boulders exceeding 36 in. | During excavation at Bellevue Transit Center interface (Sta. 1609+31) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or M-241. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Design Manager | 2019-01-28 | 10 | Routine | Y | Y | N | 7 | DSDC – HJH JV | 1 | 2019-02-04 | 5 | Y | 0 | 1 | 2019-02-04 | 5 | Closed | 12 | 0 | 10 | 49000 | 91000 | Y | E330-CO-034 | 46770 | 22420 | 15.8 | 42 | 200 | P2 – High
E330-RFI-0109 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – Bellevue Transit Center interface | Systems contractor requires 3-in. PVC conduit stub-ups for tunnel emergency phone at Bellevue Transit Center interface not provided in civil C-493. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2019-02-04 | 10 | Urgent | N | Y | Y | 1 | DSDC – HJH JV | 4 | 2019-02-25 | 20 | N | 10 | 1 | 2019-02-25 | 20 | Closed | 24 | 22 | 0 |  |  | N |  | 0 | 0 | 0 | 22 | 355 | P3 – Medium
E330-RFI-0110 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Puget Sound Energy comment on critical areas permit – NE 6th St tunnel turn | Puget Sound Energy review comments on the critical areas permit require changes to the stair core wall at NE 6th St tunnel turn. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2019-02-07 | 10 | Routine | N | Y | N | 4 | WSDOT / ST Third-Party Mgmt | 3 | 2019-02-18 | 9 | Y | 0 | 1 | 2019-02-18 | 9 | Closed | 5 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 704 | P3 – Medium
E330-RFI-0111 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with PSE distribution duct bank at NE 6th St tunnel turn | Potholing at Sta. 1832+11 located a PSE distribution duct bank in conflict with the proposed station canopy support. Utility is not shown on C-656. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Scheduler | 2019-02-07 | 10 | Routine | Y | Y | N | 5 | DSDC – HJH JV | 1 | 2019-02-12 | 5 | Y | 0 | 2 | 2019-03-04 | 24 | Closed | 6 | 0 | 2 | 25000 | 46000 | N |  | 0 | 0 | 0 | 0.4 | 705 | P3 – Medium
E330-RFI-0112 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – platform edge slab at South portal – 112th Ave SE/Main St | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-692 for egress width at South portal – 112th Ave SE/Main St. Request direction on compliant detail. | Design Manager | 2019-02-11 | 10 | Expedite | Y | N | N | 4 | DSDC – HJH JV | 2 | 2019-02-19 | 8 | Y | 0 | 1 | 2019-02-19 | 8 | Closed | 0 | 0 | 0 | 333000 | 621000 | N |  | 0 | 0 | 0 | 0 | 938 | P4 – Low
E330-RFI-0113 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Crane staging in right-of-way – South portal – 112th Ave SE/Main St | Contractor requests approval of an alternate traffic/staging plan at South portal – 112th Ave SE/Main St: revised haul route. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Project Engineer | 2019-02-18 | 10 | Urgent | Y | N | Y | 6 | DSDC – HJH JV | 1 | 2019-02-20 | 2 | Y | 0 | 1 | 2019-02-20 | 2 | Closed | 0 | 0 | 0 | 51000 | 95000 | N |  | 0 | 0 | 0 | 0 | 939 | P4 – Low
E330-RFI-0114 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – guideway girder diaphragm at South portal – 112th Ave SE/Main St | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-790 for fire alarm device layout at South portal – 112th Ave SE/Main St. Request direction on compliant detail. | Design Manager | 2019-03-04 | 10 | Routine | N | N | Y | 7 | DSDC – HJH JV | 3 | 2019-03-11 | 7 | Y | 0 | 1 | 2019-03-11 | 7 | Closed | 0 | 5 | 0 |  |  | Y | E330-CO-033 | 8200 | 3200 | 0 | 32.8 | 331 | P2 – High
E330-RFI-0115 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – East Main Station interface | Civil and systems drawings differ on grounding/bonding of retaining wall footing for stray-current control at East Main Station interface. Request governing detail and responsibility for installation. | Project Engineer | 2019-03-07 | 10 | Urgent | Y | N | N | 5 | DSDC – HJH JV | 2 | 2019-03-19 | 12 | N | 2 | 1 | 2019-03-19 | 12 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 940 | P4 – Low
E330-RFI-0116 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – duct bank encasement and drilled shaft cap at North shaft near Bellevue City Hall | Interference between duct bank encasement and drilled shaft cap at North shaft near Bellevue City Hall per C-796. Required clearance of 7 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Field Engineer | 2019-03-13 | 10 | Routine | Y | Y | N | 7 | DSDC – HJH JV | 1 | 2019-03-20 | 7 | Y | 0 | 1 | 2019-03-20 | 7 | Closed | 6 | 0 | 4 | 52000 | 98000 | N |  | 0 | 0 | 0 | 0.9 | 621 | P3 – Medium
E330-RFI-0117 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – station canopy support at NE 6th St tunnel turn | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-441 for standpipe connection at NE 6th St tunnel turn. Request direction on compliant detail. | Superintendent | 2019-03-14 | 10 | Routine | Y | Y | N | 4 | DSDC – HJH JV | 1 | 2019-03-20 | 6 | Y | 0 | 1 | 2019-03-20 | 6 | Closed | 27 | 0 | 9 | 50000 | 94000 | N |  | 0 | 0 | 0 | 2 | 513 | P3 – Medium
E330-RFI-0118 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Puget Sound Energy comment on street improvement permit – North shaft near Bellevue City Hall | Puget Sound Energy review comments on the street improvement permit require changes to the drilled shaft cap at North shaft near Bellevue City Hall. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2019-03-18 | 10 | Routine | Y | N | N | 6 | WSDOT / ST Third-Party Mgmt | 2 | 2019-03-25 | 6 | Y | 0 | 2 | 2019-04-01 | 12 | Closed | 0 | 0 | 0 | 18000 | 33000 | N |  | 0 | 0 | 0 | 0 | 941 | P4 – Low
E330-RFI-0119 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – guideway girder diaphragm at East Main Station interface | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-556 for fire alarm device layout at East Main Station interface. Request direction on compliant detail. | Project Manager | 2019-03-19 | 10 | Expedite | Y | Y | N | 4 | ST Design Management | 2 | 2019-03-25 | 4 | Y | 0 | 2 | 2019-04-15 | 25 | Closed | 15 | 0 | 5 | 105000 | 196000 | N |  | 0 | 0 | 0 | 1.1 | 574 | P3 – Medium
E330-RFI-0120 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – bearing pad/embed plate at East Main Station interface | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-786 for emergency stair pressurization at East Main Station interface. Request direction on compliant detail. | Field Engineer | 2019-04-01 | 10 | Urgent | Y | N | Y | 7 | DSDC – HJH JV | 2 | 2019-04-04 | 3 | Y | 0 | 1 | 2019-04-04 | 3 | Closed | 0 | 0 | 0 | 88000 | 164000 | Y | E330-CO-035 | 150900 | 150900 | 0 | 41.1 | 217 | P2 – High
E330-RFI-0121 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at North shaft near Bellevue City Hall: perched groundwater | During excavation at North shaft near Bellevue City Hall (Sta. 2115+63) the contractor encountered perched groundwater at approx. elevation 90 ft, not shown on the GBR or E-200. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Field Engineer | 2019-04-02 | 10 | Routine | Y | Y | N | 4 | DSDC – HJH JV | 2 | 2019-04-08 | 5 | Y | 0 | 1 | 2019-04-08 | 5 | Closed | 42 | 0 | 19 | 33000 | 62000 | Y | E330-CO-034 | 33330 | 15980 | 11.2 | 41.3 | 212 | P2 – High
E330-RFI-0122 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with abandoned utility vault at East Main Station interface | Potholing at Sta. 1718+91 located a abandoned utility vault in conflict with the proposed guideway girder diaphragm. Utility is not shown on C-475. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Field Engineer | 2019-04-05 | 10 | Urgent | Y | Y | Y | 3 | DSDC – HJH JV | 1 | 2019-04-12 | 7 | Y | 0 | 1 | 2019-04-12 | 7 | Closed | 26 | 21 | 0 | 12000 | 22000 | N |  | 0 | 0 | 0 | 21 | 357 | P3 – Medium
E330-RFI-0123 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – pedestrian ramp at Bellevue SEM tunnel – 110th Ave NE | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-674 for fire alarm device layout at Bellevue SEM tunnel – 110th Ave NE. Request direction on compliant detail. | Design Manager | 2019-04-12 | 10 | Urgent | N | N | N | 0 | DSDC – HJH JV | 3 | 2019-04-22 | 8 | Y | 0 | 1 | 2019-04-22 | 8 | Closed | 0 | 0 | 0 |  |  | Y | E330-CO-035 | 11800 | 11800 | 0 | 32.3 | 334 | P2 – High
E330-RFI-0124 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – recycled-content fly ash blend | Contractor requests approval to substitute recycled-content fly ash blend for Type IL cement mix on work at Bellevue SEM tunnel – 110th Ave NE, citing procurement lead time. Product data attached. | Design Manager | 2019-04-15 | 10 | Urgent | N | N | N | 5 | DSDC – HJH JV | 2 | 2019-04-19 | 4 | Y | 0 | 2 | 2019-05-02 | 17 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 942 | P4 – Low
E330-RFI-0125 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 8-in. high-pressure gas main at Bellevue Transit Center interface | Potholing at Sta. 1458+36 located a 8-in. high-pressure gas main in conflict with the proposed retaining wall footing. Utility is not shown on C-796. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Design Manager | 2019-04-16 | 10 | Expedite | Y | N | Y | 5 | DSDC – HJH JV | 1 | 2019-04-29 | 11 | N | 1 | 1 | 2019-04-29 | 11 | Closed | 0 | 0 | 0 | 144000 | 268000 | Y | E330-CO-037 | 180700 | 132900 | 0 | 40.7 | 222 | P2 – High
E330-RFI-0126 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – galvanized steel handrail | Contractor requests approval to substitute galvanized steel handrail for stainless steel handrail on work at Bellevue SEM tunnel – 110th Ave NE, citing procurement lead time. Product data attached. | Field Engineer | 2019-04-22 | 10 | Urgent | N | N | Y | 4 | DSDC – HJH JV | 1 | 2019-04-29 | 6 | Y | 0 | 1 | 2019-04-29 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 943 | P4 – Low
E330-RFI-0127 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with abandoned utility vault at Bellevue Transit Center interface | Potholing at Sta. 2311+21 located a abandoned utility vault in conflict with the proposed platform edge slab. Utility is not shown on S-716. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Design Manager | 2019-04-29 | 10 | Urgent | Y | N | Y | 2 | DSDC – HJH JV | 2 | 2019-05-01 | 2 | Y | 0 | 1 | 2019-05-01 | 2 | Closed | 0 | 0 | 0 | 151000 | 281000 | Y | E330-CO-036 | 215300 | 103600 | 0 | 39.8 | 242 | P2 – High
E330-RFI-0128 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at NE 6th St tunnel turn: abandoned timber piles | During excavation at NE 6th St tunnel turn (Sta. 2181+19) the contractor encountered abandoned timber piles, not shown on the GBR or A-587. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Project Engineer | 2019-05-21 | 10 | Expedite | Y | Y | N | 3 | DSDC – HJH JV | 1 | 2019-06-05 | 15 | N | 5 | 1 | 2019-06-05 | 15 | Closed | 10 | 0 | 6 | 91000 | 169000 | Y | E330-CO-039 | 110630 | 66320 | 0.4 | 39.7 | 244 | P2 – High
E330-RFI-0129 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 8-in. high-pressure gas main at East Main Station interface | Potholing at Sta. 1537+96 located a 8-in. high-pressure gas main in conflict with the proposed drilled shaft cap. Utility is not shown on M-707. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2019-06-06 | 10 | Routine | Y | N | Y | 2 | DSDC – HJH JV | 1 | 2019-06-17 | 10 | Y | 0 | 1 | 2019-06-17 | 10 | Closed | 0 | 0 | 0 | 474000 | 884000 | Y | E330-CO-038 | 308910 | 308910 | 2.7 | 44.5 | 149 | P2 – High
E330-RFI-0130 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – drilled shaft cap and column reinforcement at NE 6th St tunnel turn | Interference between drilled shaft cap and column reinforcement at NE 6th St tunnel turn per A-733. Required clearance of 6 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Field Engineer | 2019-06-11 | 10 | Routine | N | N | N | 2 | DSDC – HJH JV | 2 | 2019-06-24 | 11 | N | 1 | 2 | 2019-07-01 | 18 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 944 | P4 – Low
E330-RFI-0131 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Property owner access/restoration requirement – East Main Station interface | Adjacent property owner has requested additional restoration and access provisions at East Main Station interface beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Superintendent | 2019-06-21 | 10 | Routine | N | N | Y | 0 | WSDOT / ST Third-Party Mgmt | 1 | 2019-06-27 | 6 | Y | 0 | 1 | 2019-06-27 | 6 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 945 | P4 – Low
E330-RFI-0132 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | SPC | Spec / Drawing Clarification | General | 01 25 00 Substitution Procedures | Clarify spec requirement – East Main Station interface | Request clarification of 01 25 00 Substitution Procedures and A-759: dimension/notes appear inconsistent or omitted for the work at East Main Station interface. | Superintendent | 2019-06-21 | 10 | Routine | N | N | N | 4 | DSDC – HJH JV | 3 | 2019-06-24 | 2 | Y | 0 | 1 | 2019-06-24 | 2 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 946 | P4 – Low
E330-RFI-0133 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Rail Bonding location conflict at Sta. 2108+42 | Proposed rail bonding foundation location at Sta. 2108+42 conflicts with retaining wall footing; offset of 9 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Project Manager | 2019-07-01 | 10 | Routine | Y | N | N | 5 | DSDC – HJH JV | 1 | 2019-07-10 | 9 | Y | 0 | 2 | 2019-07-19 | 18 | Closed | 0 | 0 | 0 | 60000 | 113000 | N |  | 0 | 0 | 0 | 0 | 947 | P4 – Low
E330-RFI-0134 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – East Main Station interface | M-238 shows a 41 ft-9 in. dimension for the retaining wall footing; structural sheet S-648 shows a different value. Request clarification before fabrication/rebar release. | Field Engineer | 2019-07-16 | 10 | Urgent | N | Y | N | 0 | DSDC – HJH JV | 1 | 2019-07-19 | 3 | Y | 0 | 1 | 2019-07-19 | 3 | Closed | 7 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 658 | P3 – Medium
E330-RFI-0135 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Tunnel Emergency Phone location conflict at Sta. 1487+08 | Proposed tunnel emergency phone foundation location at Sta. 1487+08 conflicts with bearing pad/embed plate; offset of 11 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2019-07-17 | 10 | Routine | N | Y | N | 2 | DSDC – HJH JV | 2 | 2019-07-29 | 10 | Y | 0 | 1 | 2019-07-29 | 10 | Closed | 36 | 0 | 18 |  |  | N |  | 0 | 0 | 0 | 4 | 450 | P3 – Medium
E330-RFI-0136 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Stormwater facility revision – South portal – 112th Ave SE/Main St | Field conditions at South portal – 112th Ave SE/Main St require changes to temporary erosion and sediment control or stormwater facility per E-246. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2019-07-17 | 10 | Routine | Y | Y | N | 1 | ST Design Management | 2 | 2019-07-25 | 8 | Y | 0 | 1 | 2019-07-25 | 8 | Closed | 4 | 0 | 3 | 112000 | 209000 | N |  | 0 | 0 | 0 | 0.7 | 659 | P3 – Medium
E330-RFI-0137 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unexpected ground condition – NE 6th St tunnel turn | During SEM excavation near Sta. 2350+14 at NE 6th St tunnel turn, ground conditions varied from the baseline in the geotechnical baseline report (observed glacially deposited boulders exceeding 36 in.). Contractor requests direction on testing/disposal protocol and confirmation of whether this constitutes a differing site condition. See C-789. | Superintendent | 2019-07-29 | 10 | Urgent | Y | N | Y | 2 | ST Design Management | 2 | 2019-08-05 | 6 | Y | 0 | 1 | 2019-08-05 | 6 | Closed | 0 | 0 | 0 | 261000 | 486000 | Y | E330-CO-039 | 511370 | 306530 | 2 | 44.2 | 159 | P2 – High
E330-RFI-0138 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unexpected ground condition – East Main Station interface | During SEM excavation near Sta. 1737+25 at East Main Station interface, ground conditions varied from the baseline in the geotechnical baseline report (observed loose granular fill below planned bearing elevation). Contractor requests direction on revised bearing elevation and foundation detail and confirmation of whether this constitutes a differing site condition. See E-355. | Scheduler | 2019-07-31 | 10 | Routine | Y | N | Y | 0 | DSDC – HJH JV | 1 | 2019-08-05 | 4 | Y | 0 | 1 | 2019-08-05 | 4 | Closed | 0 | 0 | 0 | 42000 | 79000 | Y | E330-CO-039 | 52570 | 31510 | 0.2 | 35.8 | 305 | P2 – High
E330-RFI-0139 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 24-in. sanitary sewer at East Main Station interface | Potholing at Sta. 1549+74 located a 24-in. sanitary sewer in conflict with the proposed bearing pad/embed plate. Utility is not shown on S-309. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Project Manager | 2019-09-02 | 10 | Routine | Y | Y | N | 6 | DSDC – HJH JV | 1 | 2019-09-10 | 8 | Y | 0 | 1 | 2019-09-10 | 8 | Closed | 5 | 0 | 1 | 21000 | 39000 | Y | E330-CO-038 | 37690 | 37690 | 0.3 | 36.6 | 296 | P2 – High
E330-RFI-0140 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Night work and noise variance – NE 6th St tunnel turn | Contractor requests approval of an alternate traffic/staging plan at NE 6th St tunnel turn: crane pick over active roadway. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Design Manager | 2019-09-04 | 10 | Routine | N | N | Y | 6 | DSDC – HJH JV | 2 | 2019-09-09 | 5 | Y | 0 | 1 | 2019-09-09 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 948 | P4 – Low
E330-RFI-0141 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Art embed coordination – East Main Station interface | Request to clarify finish/connection detail on M-229 at East Main Station interface. Includes coordination with art program embeds and handrail sleeves as applicable. | Superintendent | 2019-09-26 | 10 | Routine | Y | N | N | 8 | ST Design Management | 2 | 2019-10-04 | 8 | Y | 0 | 1 | 2019-10-04 | 8 | Closed | 0 | 0 | 0 | 54000 | 101000 | N |  | 0 | 0 | 0 | 0 | 949 | P4 – Low
E330-RFI-0142 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unexpected ground condition – Bellevue SEM tunnel – 110th Ave NE | During SEM excavation near Sta. 1975+60 at Bellevue SEM tunnel – 110th Ave NE, ground conditions varied from the baseline in the geotechnical baseline report (observed perched groundwater at approx. elevation 174 ft). Contractor requests direction on temporary shoring modification and confirmation of whether this constitutes a differing site condition. See E-490. | Superintendent | 2019-10-09 | 10 | Expedite | Y | Y | N | 3 | DSDC – HJH JV | 1 | 2019-10-21 | 10 | Y | 0 | 1 | 2019-10-21 | 10 | Closed | 4 | 0 | 3 | 166000 | 310000 | Y | E330-CO-039 | 335730 | 201250 | 1.3 | 43.2 | 174 | P2 – High
E330-RFI-0143 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Property owner access/restoration requirement – South portal – 112th Ave SE/Main St | Adjacent property owner has requested additional restoration and access provisions at South portal – 112th Ave SE/Main St beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Field Engineer | 2019-10-18 | 10 | Urgent | Y | Y | Y | 6 | Puget Sound Energy / ST Third-Party Mgmt | 5 | 2019-10-29 | 11 | N | 1 | 1 | 2019-10-29 | 11 | Closed | 6 | 3 | 0 | 752000 | 1404000 | N |  | 0 | 0 | 0 | 3 | 475 | P3 – Medium
E330-RFI-0144 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Puget Sound Energy comment on clearing and grading permit – South portal – 112th Ave SE/Main St | Puget Sound Energy review comments on the clearing and grading permit require changes to the column reinforcement at South portal – 112th Ave SE/Main St. Request direction on scope impacts and whether comments are within the contract requirements. | Project Manager | 2019-11-05 | 10 | Routine | N | Y | Y | 6 | Puget Sound Energy / ST Third-Party Mgmt | 4 | 2019-11-19 | 14 | N | 4 | 2 | 2019-12-05 | 30 | Closed | 21 | 20 | 0 |  |  | N |  | 0 | 0 | 0 | 20 | 361 | P3 – Medium
E330-RFI-0145 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Dimensional discrepancy – East Main Station interface | E-870 shows a 20 ft-2 in. dimension for the duct bank encasement; structural sheet S-358 shows a different value. Request clarification before fabrication/rebar release. | Project Engineer | 2019-11-11 | 10 | Urgent | N | Y | Y | 5 | ST Design Management | 1 | 2019-11-25 | 13 | N | 3 | 1 | 2019-11-25 | 13 | Closed | 7 | 5 | 0 |  |  | N |  | 0 | 0 | 0 | 5 | 433 | P3 – Medium
E330-RFI-0146 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Puget Sound Energy comment on right-of-way use permit – East Main Station interface | Puget Sound Energy review comments on the right-of-way use permit require changes to the pedestrian ramp at East Main Station interface. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2019-11-18 | 10 | Urgent | N | N | N | 0 | WSDOT / ST Third-Party Mgmt | 4 | 2019-12-04 | 16 | N | 6 | 1 | 2019-12-04 | 16 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 950 | P4 – Low
E330-RFI-0147 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Stormwater facility revision – South portal – 112th Ave SE/Main St | Field conditions at South portal – 112th Ave SE/Main St require changes to temporary erosion and sediment control or stormwater facility per C-130. Request direction considering critical-areas conditions and permit requirements. | Project Engineer | 2019-11-25 | 10 | Expedite | N | Y | N | 8 | DSDC – HJH JV | 1 | 2019-12-03 | 8 | Y | 0 | 2 | 2019-12-11 | 16 | Closed | 11 | 0 | 7 |  |  | N |  | 0 | 0 | 0 | 1.6 | 552 | P3 – Medium
E330-RFI-0148 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Drawing/spec discrepancy – NE 6th St tunnel turn | Request clarification of 01 25 00 Substitution Procedures and A-762: dimension/notes appear inconsistent or omitted for the work at NE 6th St tunnel turn. | Field Engineer | 2019-12-09 | 10 | Routine | N | N | N | 4 | DSDC – HJH JV | 1 | 2019-12-16 | 5 | Y | 0 | 1 | 2019-12-16 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 951 | P4 – Low
E330-RFI-0149 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with abandoned utility vault at South portal – 112th Ave SE/Main St | Potholing at Sta. 1752+94 located a abandoned utility vault in conflict with the proposed drilled shaft cap. Utility is not shown on M-594. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Design Manager | 2020-01-21 | 10 | Expedite | Y | Y | Y | 7 | ST Design Management | 1 | 2020-01-24 | 3 | Y | 0 | 2 | 2020-02-11 | 21 | Closed | 13 | 5 | 0 | 322000 | 601000 | N |  | 0 | 0 | 0 | 5 | 434 | P3 – Medium
E330-RFI-0150 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on critical areas permit – NE 6th St tunnel turn | WSDOT review comments on the critical areas permit require changes to the duct bank encasement at NE 6th St tunnel turn. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2020-01-22 | 10 | Routine | Y | Y | N | 1 | WSDOT / ST Third-Party Mgmt | 2 | 2020-01-29 | 7 | Y | 0 | 1 | 2020-01-29 | 7 | Closed | 13 | 0 | 5 | 127000 | 237000 | Y | E330-CO-040 | 209300 | 71100 | 4 | 40.9 | 221 | P2 – High
E330-RFI-0151 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unexpected ground condition – East Main Station interface | During SEM excavation near Sta. 1281+93 at East Main Station interface, ground conditions varied from the baseline in the geotechnical baseline report (observed buried concrete debris and an old foundation). Contractor requests direction on over-excavation limits and replacement fill and confirmation of whether this constitutes a differing site condition. See S-278. | Scheduler | 2020-01-31 | 10 | Routine | Y | Y | N | 4 | DSDC – HJH JV | 2 | 2020-02-07 | 7 | Y | 0 | 1 | 2020-02-07 | 7 | Closed | 10 | 0 | 4 | 183000 | 342000 | Y | E330-CO-041 | 259200 | 142700 | 3 | 42.8 | 183 | P2 – High
E330-RFI-0152 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Bellevue SEM tunnel – 110th Ave NE | E-510 shows a 43 ft-9 in. dimension for the pedestrian ramp; structural sheet S-250 shows a different value. Request clarification before fabrication/rebar release. | Superintendent | 2020-02-10 | 10 | Expedite | Y | N | N | 5 | DSDC – HJH JV | 1 | 2020-02-24 | 14 | N | 4 | 2 | 2020-03-09 | 26 | Closed | 0 | 0 | 0 | 28000 | 52000 | N |  | 0 | 0 | 0 | 0 | 952 | P4 – Low
E330-RFI-0153 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with fiber communications duct bank at Bellevue SEM tunnel – 110th Ave NE | Potholing at Sta. 1396+36 located a fiber communications duct bank in conflict with the proposed bearing pad/embed plate. Utility is not shown on C-205. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Project Engineer | 2020-02-24 | 10 | Expedite | Y | N | Y | 7 | DSDC – HJH JV | 1 | 2020-03-09 | 12 | N | 2 | 1 | 2020-03-09 | 12 | Closed | 0 | 2 | 0 | 104000 | 194000 | N |  | 0 | 0 | 0 | 2 | 514 | P3 – Medium
E330-RFI-0154 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Embedded conduit stub-ups – East Main Station interface | Systems contractor requires 2-in. PVC conduit stub-ups for fiber backbone at East Main Station interface not provided in civil E-740. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Design Manager | 2020-03-13 | 10 | Expedite | Y | Y | N | 5 | DSDC – HJH JV | 2 | 2020-03-23 | 10 | Y | 0 | 1 | 2020-03-23 | 10 | Closed | 2 | 0 | 1 | 1010000 | 1886000 | Y | E330-CO-042 | 1224200 | 1224200 | 1 | 48.9 | 73 | P1 – Critical
E330-RFI-0155 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Missing dimension on E-842 | Request clarification of 00 72 00 General Conditions and E-842: dimension/notes appear inconsistent or omitted for the work at NE 6th St tunnel turn. | Design Manager | 2020-03-16 | 10 | Routine | N | N | N | 7 | DSDC – HJH JV | 3 | 2020-03-19 | 3 | Y | 0 | 1 | 2020-03-19 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 953 | P4 – Low
E330-RFI-0156 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | North shaft near Bellevue City Hall | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with fiber communications duct bank at North shaft near Bellevue City Hall | Potholing at Sta. 1501+11 located a fiber communications duct bank in conflict with the proposed platform edge slab. Utility is not shown on E-309. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2020-03-23 | 10 | Expedite | Y | Y | N | 3 | DSDC – HJH JV | 3 | 2020-04-13 | 19 | N | 9 | 1 | 2020-04-13 | 19 | Closed | 4 | 0 | 5 | 589000 | 1099000 | Y | E330-CO-043 | 497600 | 0 | 0 | 1.1 | 575 | P3 – Medium
E330-RFI-0157 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | Stormwater facility revision – Bellevue Transit Center interface | Field conditions at Bellevue Transit Center interface require changes to temporary erosion and sediment control or stormwater facility per E-446. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2020-04-03 | 10 | Routine | N | N | N | 1 | DSDC – HJH JV | 1 | 2020-04-08 | 5 | Y | 0 | 1 | 2020-04-08 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 954 | P4 – Low
E330-RFI-0158 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | South portal – 112th Ave SE/Main St | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | In-water work window – South portal – 112th Ave SE/Main St | Field conditions at South portal – 112th Ave SE/Main St require changes to temporary erosion and sediment control or stormwater facility per E-696. Request direction considering critical-areas conditions and permit requirements. | Scheduler | 2020-04-06 | 10 | Routine | N | Y | N | 0 | DSDC – HJH JV | 1 | 2020-04-15 | 9 | Y | 0 | 1 | 2020-04-15 | 9 | Closed | 15 | 0 | 7 |  |  | N |  | 0 | 0 | 0 | 1.6 | 553 | P3 – Medium
E330-RFI-0159 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | City of Bellevue comment on street improvement permit – East Main Station interface | City of Bellevue review comments on the street improvement permit require changes to the pedestrian ramp at East Main Station interface. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2020-04-27 | 10 | Routine | N | Y | N | 1 | Puget Sound Energy / ST Third-Party Mgmt | 2 | 2020-05-05 | 8 | Y | 0 | 2 | 2020-05-14 | 17 | Closed | 9 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 660 | P3 – Medium
E330-RFI-0160 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Lane closure window request – Bellevue SEM tunnel – 110th Ave NE | Contractor requests approval of an alternate traffic/staging plan at Bellevue SEM tunnel – 110th Ave NE: extended night closure. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Superintendent | 2020-04-28 | 10 | Routine | N | N | N | 4 | DSDC – HJH JV | 1 | 2020-05-04 | 6 | Y | 0 | 2 | 2020-05-25 | 27 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 955 | P4 – Low
E330-RFI-0161 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Lane closure window request – NE 6th St tunnel turn | Contractor requests approval of an alternate traffic/staging plan at NE 6th St tunnel turn: temporary lane shift. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Superintendent | 2020-05-04 | 10 | Routine | Y | N | N | 1 | DSDC – HJH JV | 2 | 2020-05-11 | 5 | Y | 0 | 1 | 2020-05-11 | 5 | Closed | 0 | 0 | 0 | 162000 | 302000 | N |  | 0 | 0 | 0 | 0 | 956 | P4 – Low
E330-RFI-0162 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Direct fixation fastener spacing at Sta. 1289+09 | Track layout at Sta. 1289+09 (East Main Station interface) differs from the track-structure interface drawing M-875. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Manager | 2020-05-11 | 10 | Expedite | N | N | N | 1 | DSDC – HJH JV | 1 | 2020-05-14 | 3 | Y | 0 | 1 | 2020-05-14 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 957 | P4 – Low
E330-RFI-0163 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unexpected ground condition – Bellevue SEM tunnel – 110th Ave NE | During SEM excavation near Sta. 2287+56 at Bellevue SEM tunnel – 110th Ave NE, ground conditions varied from the baseline in the geotechnical baseline report (observed abandoned timber piles). Contractor requests direction on over-excavation limits and replacement fill and confirmation of whether this constitutes a differing site condition. See A-371. | Superintendent | 2020-05-11 | 10 | Routine | Y | Y | N | 2 | DSDC – HJH JV | 1 | 2020-05-18 | 6 | Y | 0 | 2 | 2020-06-01 | 20 | Closed | 28 | 0 | 16 | 129000 | 241000 | Y | E330-CO-044 | 206700 | 206700 | 21 | 52.7 | 35 | P1 – Critical
E330-RFI-0164 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – drilled shaft cap at Bellevue SEM tunnel – 110th Ave NE | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-426 for smoke control damper at Bellevue SEM tunnel – 110th Ave NE. Request direction on compliant detail. | Design Manager | 2020-05-25 | 10 | Routine | N | Y | Y | 7 | DSDC – HJH JV | 1 | 2020-06-04 | 10 | Y | 0 | 2 | 2020-06-15 | 21 | Closed | 19 | 8 | 0 |  |  | N |  | 0 | 0 | 0 | 8 | 409 | P3 – Medium
E330-RFI-0165 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | Property owner access/restoration requirement – Bellevue Transit Center interface | Adjacent property owner has requested additional restoration and access provisions at Bellevue Transit Center interface beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Project Engineer | 2020-06-17 | 10 | Urgent | N | N | N | 1 | WSDOT / ST Third-Party Mgmt | 3 | 2020-06-23 | 6 | Y | 0 | 1 | 2020-06-23 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 958 | P4 – Low
E330-RFI-0166 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue SEM tunnel – 110th Ave NE | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 8-in. high-pressure gas main at Bellevue SEM tunnel – 110th Ave NE | Potholing at Sta. 1420+39 located a 8-in. high-pressure gas main in conflict with the proposed stair core wall. Utility is not shown on A-749. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Field Engineer | 2020-06-18 | 10 | Routine | Y | Y | N | 0 | DSDC – HJH JV | 1 | 2020-06-25 | 7 | Y | 0 | 1 | 2020-06-25 | 7 | Closed | 19 | 0 | 15 | 286000 | 535000 | Y | E330-CO-045 | 285600 | 184100 | 10 | 48.4 | 86 | P1 – Critical
E330-RFI-0167 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | Bellevue Transit Center interface | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Dimensional discrepancy – Bellevue Transit Center interface | M-751 shows a 56 ft-2 in. dimension for the column reinforcement; structural sheet S-385 shows a different value. Request clarification before fabrication/rebar release. | Field Engineer | 2020-08-10 | 10 | Routine | N | N | N | 0 | DSDC – HJH JV | 1 | 2020-08-21 | 11 | N | 1 | 1 | 2020-08-21 | 11 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 959 | P4 – Low
E330-RFI-0168 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | NE 6th St tunnel turn | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 8-in. high-pressure gas main at NE 6th St tunnel turn | Potholing at Sta. 2095+20 located a 8-in. high-pressure gas main in conflict with the proposed guideway girder diaphragm. Utility is not shown on S-280. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Scheduler | 2020-09-16 | 10 | Expedite | Y | Y | N | 2 | DSDC – HJH JV | 2 | 2020-09-21 | 5 | Y | 0 | 1 | 2020-09-21 | 5 | Closed | 8 | 0 | 2 | 361000 | 674000 | Y | E330-CO-046 | 285900 | 158400 | 3 | 42.7 | 185 | P2 – High
E330-RFI-0169 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unexpected ground condition – East Main Station interface | During SEM excavation near Sta. 1070+61 at East Main Station interface, ground conditions varied from the baseline in the geotechnical baseline report (observed an unmapped abandoned storm line). Contractor requests direction on temporary shoring modification and confirmation of whether this constitutes a differing site condition. See C-189. | Project Engineer | 2020-10-19 | 10 | Urgent | Y | Y | Y | 3 | ST Design Management | 3 | 2020-10-30 | 11 | N | 1 | 2 | 2020-11-05 | 17 | Closed | 5 | 2 | 0 | 355000 | 662000 | Y | E330-CO-047 | 543900 | 382000 | 2 | 47 | 103 | P1 – Critical
E330-RFI-0170 | E330 | East Link Extension | Atkinson Construction (Guy F. Atkinson) | East Main Station interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with PSE distribution duct bank at East Main Station interface | Potholing at Sta. 1983+32 located a PSE distribution duct bank in conflict with the proposed drilled shaft cap. Utility is not shown on A-717. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Engineer | 2020-11-18 | 10 | Routine | Y | N | N | 8 | DSDC – HJH JV | 3 | 2020-11-30 | 11 | N | 1 | 1 | 2020-11-30 | 11 | Closed | 0 | 0 | 0 | 286000 | 534000 | Y | E330-CO-048 | 422100 | 186600 | 0 | 41.8 | 203 | P2 – High
E335-RFI-0001 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – Bellevue Downtown Station | S-363 shows a 53 ft-10 in. dimension for the retaining wall footing; structural sheet S-136 shows a different value. Request clarification before fabrication/rebar release. | Field Engineer | 2017-03-20 | 10 | Routine | N | Y | Y | 2 | ST Design Management | 2 | 2017-03-27 | 5 | Y | 0 | 1 | 2017-03-27 | 5 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 960 | P4 – Low
E335-RFI-0002 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Wetland/stream buffer protection – Bellevue Downtown Station | Field conditions at Bellevue Downtown Station require changes to temporary erosion and sediment control or stormwater facility per E-666. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2017-04-03 | 10 | Routine | N | N | Y | 8 | ST Design Management | 1 | 2017-04-10 | 6 | Y | 0 | 1 | 2017-04-10 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 961 | P4 – Low
E335-RFI-0003 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Art embed coordination – Bellevue Downtown Station | Request to clarify finish/connection detail on E-644 at Bellevue Downtown Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Manager | 2017-04-20 | 10 | Routine | N | N | N | 8 | DSDC – HJH JV | 2 | 2017-04-28 | 8 | Y | 0 | 2 | 2017-05-04 | 14 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 962 | P4 – Low
E335-RFI-0004 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – column reinforcement sequence at 110th Ave NE/NE 6th St | Erection of the column reinforcement as drawn conflicts with adjacent work and access limits at 110th Ave NE/NE 6th St. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Scheduler | 2017-05-02 | 10 | Routine | Y | N | N | 6 | DSDC – HJH JV | 3 | 2017-05-15 | 12 | N | 2 | 1 | 2017-05-15 | 12 | Closed | 0 | 0 | 0 | 50000 | 92000 | Y | E335-CO-001 | 53200 | 46800 | 0 | 37.1 | 289 | P2 – High
E335-RFI-0005 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – station canopy support and drilled shaft cap at NE 12th St guideway | Interference between station canopy support and drilled shaft cap at NE 12th St guideway per A-774. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Engineer | 2017-06-12 | 10 | Routine | Y | Y | N | 6 | ST Design Management | 2 | 2017-06-26 | 12 | N | 2 | 1 | 2017-06-26 | 12 | Closed | 6 | 0 | 4 | 281000 | 525000 | Y | E335-CO-002 | 626800 | 626800 | 3 | 47.9 | 93 | P1 – Critical
E335-RFI-0006 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 8-in. high-pressure gas main at Bellevue Downtown Station | Potholing at Sta. 909+10 located a 8-in. high-pressure gas main in conflict with the proposed stair core wall. Utility is not shown on S-279. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Field Engineer | 2017-09-15 | 10 | Routine | Y | Y | Y | 3 | DSDC – HJH JV | 1 | 2017-09-19 | 4 | Y | 0 | 1 | 2017-09-19 | 4 | Closed | 26 | 10 | 0 | 1172000 | 2188000 | N |  | 0 | 0 | 0 | 10 | 394 | P3 – Medium
E335-RFI-0007 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Wilburton Station | E-869 shows a 30 ft-8 in. dimension for the stair core wall; structural sheet S-413 shows a different value. Request clarification before fabrication/rebar release. | Scheduler | 2017-09-18 | 10 | Routine | N | Y | N | 2 | ST Design Management | 1 | 2017-10-02 | 13 | N | 3 | 1 | 2017-10-02 | 13 | Closed | 3 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 773 | P4 – Low
E335-RFI-0008 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 30-in. storm drain at Bellevue Downtown Station | Potholing at Sta. 1068+43 located a 30-in. storm drain in conflict with the proposed duct bank encasement. Utility is not shown on E-823. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Superintendent | 2017-10-04 | 10 | Routine | N | N | Y | 5 | DSDC – HJH JV | 4 | 2017-10-16 | 12 | N | 2 | 1 | 2017-10-16 | 12 | Closed | 0 | 1 | 0 |  |  | N |  | 0 | 0 | 0 | 1 | 605 | P3 – Medium
E335-RFI-0009 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – bearing pad/embed plate sequence at East Main Station | Erection of the bearing pad/embed plate as drawn conflicts with adjacent work and access limits at East Main Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Project Manager | 2017-10-30 | 10 | Routine | N | Y | N | 4 | DSDC – HJH JV | 2 | 2017-11-10 | 11 | N | 1 | 1 | 2017-11-10 | 11 | Closed | 4 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 706 | P3 – Medium
E335-RFI-0010 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with abandoned utility vault at Spring District/120th Station | Potholing at Sta. 1169+58 located a abandoned utility vault in conflict with the proposed stair core wall. Utility is not shown on A-303. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2017-11-06 | 10 | Routine | Y | Y | N | 4 | DSDC – HJH JV | 2 | 2017-11-13 | 5 | Y | 0 | 1 | 2017-11-13 | 5 | Closed | 7 | 0 | 5 | 117000 | 219000 | Y | E335-CO-003 | 312300 | 178800 | 3 | 43.8 | 163 | P2 – High
E335-RFI-0011 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Track slab/expansion joint interface – Wilburton Station | Track layout at Sta. 949+98 (Wilburton Station) differs from the track-structure interface drawing S-350. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Scheduler | 2017-11-07 | 10 | Routine | Y | N | N | 6 | DSDC – HJH JV | 1 | 2017-11-13 | 4 | Y | 0 | 1 | 2017-11-13 | 4 | Closed | 0 | 0 | 0 | 33000 | 62000 | Y | E335-CO-004 | 14700 | 14700 | 0 | 33.1 | 327 | P2 – High
E335-RFI-0012 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Grounding/bonding and stray-current detail – Wilburton Station | Civil and systems drawings differ on grounding/bonding of bearing pad/embed plate for stray-current control at Wilburton Station. Request governing detail and responsibility for installation. | Scheduler | 2017-11-24 | 10 | Expedite | N | N | N | 6 | DSDC – HJH JV | 2 | 2017-12-01 | 7 | Y | 0 | 2 | 2017-12-18 | 24 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 963 | P4 – Low
E335-RFI-0013 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with fiber communications duct bank at Spring District/120th Station | Potholing at Sta. 955+08 located a fiber communications duct bank in conflict with the proposed guideway girder diaphragm. Utility is not shown on C-513. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Superintendent | 2017-12-19 | 10 | Routine | Y | Y | N | 5 | DSDC – HJH JV | 3 | 2018-01-01 | 13 | N | 3 | 1 | 2018-01-01 | 13 | Closed | 14 | 0 | 4 | 61000 | 113000 | Y | E335-CO-005 | 106700 | 106700 | 10 | 44.1 | 160 | P2 – High
E335-RFI-0014 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on right-of-way use permit – 110th Ave NE/NE 6th St | WSDOT review comments on the right-of-way use permit require changes to the platform edge slab at 110th Ave NE/NE 6th St. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2018-01-29 | 10 | Routine | Y | Y | N | 8 | WSDOT / ST Third-Party Mgmt | 2 | 2018-02-20 | 22 | N | 12 | 2 | 2018-03-01 | 31 | Closed | 31 | 0 | 16 | 312000 | 583000 | Y | E335-CO-006 | 536700 | 455900 | 23 | 56.1 | 24 | P1 – Critical
E335-RFI-0015 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – station canopy support sequence at East Main Station | Erection of the station canopy support as drawn conflicts with adjacent work and access limits at East Main Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Superintendent | 2018-02-05 | 10 | Routine | N | Y | N | 5 | DSDC – HJH JV | 1 | 2018-02-19 | 12 | N | 2 | 1 | 2018-02-19 | 12 | Closed | 5 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 661 | P3 – Medium
E335-RFI-0016 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Canopy/glazing connection – Wilburton Station | Request to clarify finish/connection detail on M-200 at Wilburton Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Scheduler | 2018-02-05 | 10 | Routine | N | N | N | 5 | DSDC – HJH JV | 2 | 2018-02-12 | 6 | Y | 0 | 1 | 2018-02-12 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 964 | P4 – Low
E335-RFI-0017 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – duct bank encasement at Bellevue Downtown Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-528 for standpipe connection at Bellevue Downtown Station. Request direction on compliant detail. | Superintendent | 2018-02-19 | 10 | Routine | Y | N | N | 2 | ST Design Management | 3 | 2018-03-12 | 21 | N | 11 | 1 | 2018-03-12 | 21 | Closed | 0 | 0 | 3 | 169000 | 315000 | N |  | 0 | 0 | 0 | 0.7 | 662 | P3 – Medium
E335-RFI-0018 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Wilburton Station: an unmapped abandoned storm line | During excavation at Wilburton Station (Sta. 1525+09) the contractor encountered an unmapped abandoned storm line, not shown on the GBR or M-196. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Project Manager | 2018-03-05 | 10 | Routine | Y | Y | N | 1 | DSDC – HJH JV | 3 | 2018-03-13 | 8 | Y | 0 | 1 | 2018-03-13 | 8 | Closed | 8 | 0 | 5 | 414000 | 774000 | Y | E335-CO-007 | 399300 | 399300 | 7 | 47.9 | 94 | P1 – Critical
E335-RFI-0019 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with abandoned utility vault at East Main Station | Potholing at Sta. 1202+25 located a abandoned utility vault in conflict with the proposed drilled shaft cap. Utility is not shown on E-869. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Field Engineer | 2018-03-07 | 10 | Routine | Y | Y | N | 0 | DSDC – HJH JV | 1 | 2018-03-21 | 14 | N | 4 | 1 | 2018-03-21 | 14 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 965 | P4 – Low
E335-RFI-0020 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at I-405 light rail bridge: buried concrete debris and an old foundation | During excavation at I-405 light rail bridge (Sta. 1676+03) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or S-586. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Field Engineer | 2018-03-19 | 10 | Routine | Y | N | Y | 7 | DSDC – HJH JV | 1 | 2018-03-23 | 4 | Y | 0 | 1 | 2018-03-23 | 4 | Closed | 0 | 0 | 0 | 49000 | 91000 | Y | E335-CO-008 | 45600 | 0 | 0 | 0 | 966 | P4 – Low
E335-RFI-0021 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on clearing and grading permit – I-405 light rail bridge | WSDOT review comments on the clearing and grading permit require changes to the platform edge slab at I-405 light rail bridge. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2018-03-26 | 10 | Routine | N | N | N | 5 | Puget Sound Energy / ST Third-Party Mgmt | 1 | 2018-04-11 | 16 | N | 6 | 2 | 2018-05-02 | 37 | Closed | 0 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 707 | P3 – Medium
E335-RFI-0022 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – retaining wall footing sequence at East Main Station | Erection of the retaining wall footing as drawn conflicts with adjacent work and access limits at East Main Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2018-03-26 | 10 | Routine | Y | Y | N | 6 | DSDC – HJH JV | 1 | 2018-04-16 | 21 | N | 11 | 1 | 2018-04-16 | 21 | Closed | 2 | 0 | 1 | 1204000 | 2247000 | Y | E335-CO-009 | 1325100 | 1033400 | 2 | 48.6 | 81 | P1 – Critical
E335-RFI-0023 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 24-in. sanitary sewer at Wilburton Station | Potholing at Sta. 2008+51 located a 24-in. sanitary sewer in conflict with the proposed guideway girder diaphragm. Utility is not shown on M-810. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Superintendent | 2018-04-02 | 10 | Routine | N | N | N | 2 | DSDC – HJH JV | 1 | 2018-04-24 | 22 | N | 12 | 1 | 2018-04-24 | 22 | Closed | 0 | 0 | 6 |  |  | N |  | 0 | 0 | 0 | 1.3 | 563 | P3 – Medium
E335-RFI-0024 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – platform edge slab and column reinforcement at East Main Station | Interference between platform edge slab and column reinforcement at East Main Station per S-690. Required clearance of 6 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Field Engineer | 2018-04-02 | 10 | Expedite | N | Y | N | 0 | ST Design Management | 4 | 2018-04-09 | 5 | Y | 0 | 1 | 2018-04-09 | 5 | Closed | 10 | 0 | 8 |  |  | N |  | 0 | 0 | 0 | 1.8 | 540 | P3 – Medium
E335-RFI-0025 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at 110th Ave NE/NE 6th St: buried concrete debris and an old foundation | During excavation at 110th Ave NE/NE 6th St (Sta. 1441+60) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or S-829. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Design Manager | 2018-04-05 | 10 | Routine | Y | N | N | 1 | DSDC – HJH JV | 3 | 2018-04-09 | 3 | Y | 0 | 1 | 2018-04-09 | 3 | Closed | 0 | 0 | 0 | 2531000 | 4724000 | Y | E335-CO-010 | 1941600 | 619600 | 0 | 46 | 123 | P2 – High
E335-RFI-0026 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – drilled shaft cap at Wilburton Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-334 for emergency stair pressurization at Wilburton Station. Request direction on compliant detail. | Superintendent | 2018-04-06 | 10 | Routine | Y | Y | N | 5 | DSDC – HJH JV | 3 | 2018-04-30 | 22 | N | 12 | 1 | 2018-04-30 | 22 | Closed | 5 | 0 | 1 | 69000 | 130000 | N |  | 0 | 0 | 0 | 0.2 | 774 | P4 – Low
E335-RFI-0027 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Art embed coordination – 110th Ave NE/NE 6th St | Request to clarify finish/connection detail on M-700 at 110th Ave NE/NE 6th St. Includes coordination with art program embeds and handrail sleeves as applicable. | Superintendent | 2018-04-13 | 10 | Routine | Y | N | N | 4 | DSDC – HJH JV | 3 | 2018-04-16 | 3 | Y | 0 | 1 | 2018-04-16 | 3 | Closed | 0 | 0 | 0 | 133000 | 248000 | N |  | 0 | 0 | 0 | 0 | 967 | P4 – Low
E335-RFI-0028 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – column reinforcement at Wilburton Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-582 for standpipe connection at Wilburton Station. Request direction on compliant detail. | Scheduler | 2018-05-07 | 10 | Routine | Y | N | N | 6 | DSDC – HJH JV | 3 | 2018-05-22 | 15 | N | 5 | 1 | 2018-05-22 | 15 | Closed | 0 | 0 | 0 | 165000 | 308000 | N |  | 0 | 0 | 0 | 0 | 968 | P4 – Low
E335-RFI-0029 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – platform edge slab and retaining wall footing at East Main Station | Interference between platform edge slab and retaining wall footing at East Main Station per E-751. Required clearance of 4 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Manager | 2018-06-11 | 10 | Routine | N | N | N | 7 | ST Design Management | 2 | 2018-06-21 | 10 | Y | 0 | 1 | 2018-06-21 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 969 | P4 – Low
E335-RFI-0030 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – drilled shaft cap and stair core wall at Spring District/120th Station | Interference between drilled shaft cap and stair core wall at Spring District/120th Station per S-261. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2018-06-12 | 10 | Urgent | N | Y | N | 6 | DSDC – HJH JV | 2 | 2018-06-18 | 5 | Y | 0 | 1 | 2018-06-18 | 5 | Closed | 6 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 622 | P3 – Medium
E335-RFI-0031 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – 110th Ave NE/NE 6th St | A-871 shows a 30 ft-8 in. dimension for the column reinforcement; structural sheet S-585 shows a different value. Request clarification before fabrication/rebar release. | Project Engineer | 2018-06-28 | 10 | Expedite | Y | Y | N | 0 | ST Design Management | 3 | 2018-07-03 | 5 | Y | 0 | 1 | 2018-07-03 | 5 | Closed | 5 | 0 | 2 | 461000 | 861000 | Y | E335-CO-011 | 699680 | 630370 | 0.6 | 46.7 | 113 | P2 – High
E335-RFI-0032 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Direct fixation fastener spacing at Sta. 936+18 | Track layout at Sta. 936+18 (Wilburton Station) differs from the track-structure interface drawing E-629. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Engineer | 2018-07-05 | 10 | Expedite | N | Y | N | 2 | DSDC – HJH JV | 1 | 2018-07-09 | 3 | Y | 0 | 1 | 2018-07-09 | 3 | Closed | 4 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 775 | P4 – Low
E335-RFI-0033 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Clarify spec requirement – NE 12th St guideway | Request clarification of 01 25 00 Substitution Procedures and M-663: dimension/notes appear inconsistent or omitted for the work at NE 12th St guideway. | Design Manager | 2018-07-16 | 10 | Expedite | N | N | N | 7 | DSDC – HJH JV | 1 | 2018-07-19 | 3 | Y | 0 | 1 | 2018-07-19 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 970 | P4 – Low
E335-RFI-0034 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Direct fixation fastener spacing at Sta. 1723+47 | Track layout at Sta. 1723+47 (East Main Station) differs from the track-structure interface drawing C-615. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Design Manager | 2018-08-03 | 10 | Routine | N | N | N | 8 | DSDC – HJH JV | 2 | 2018-08-13 | 10 | Y | 0 | 1 | 2018-08-13 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 971 | P4 – Low
E335-RFI-0035 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Lane closure window request – Bellevue Downtown Station | Contractor requests approval of an alternate traffic/staging plan at Bellevue Downtown Station: revised haul route. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Field Engineer | 2018-08-06 | 10 | Urgent | N | N | Y | 7 | ST Design Management | 2 | 2018-08-08 | 2 | Y | 0 | 1 | 2018-08-08 | 2 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 972 | P4 – Low
E335-RFI-0036 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 24-in. sanitary sewer at Bellevue Downtown Station | Potholing at Sta. 2103+75 located a 24-in. sanitary sewer in conflict with the proposed drilled shaft cap. Utility is not shown on S-297. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Design Manager | 2018-09-03 | 10 | Routine | N | N | N | 7 | DSDC – HJH JV | 2 | 2018-09-10 | 6 | Y | 0 | 2 | 2018-09-25 | 22 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 973 | P4 – Low
E335-RFI-0037 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on right-of-way use permit – I-405 light rail bridge | WSDOT review comments on the right-of-way use permit require changes to the duct bank encasement at I-405 light rail bridge. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2018-09-17 | 10 | Expedite | N | Y | N | 8 | WSDOT / ST Third-Party Mgmt | 5 | 2018-10-01 | 14 | N | 4 | 1 | 2018-10-01 | 14 | Closed | 4 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 708 | P3 – Medium
E335-RFI-0038 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – Spring District/120th Station | S-890 shows a 16 ft-4 in. dimension for the duct bank encasement; structural sheet S-782 shows a different value. Request clarification before fabrication/rebar release. | Field Engineer | 2018-09-25 | 10 | Expedite | Y | N | Y | 8 | ST Design Management | 1 | 2018-10-04 | 9 | Y | 0 | 1 | 2018-10-04 | 9 | Closed | 0 | 3 | 0 | 2419000 | 4516000 | Y | E335-CO-011 | 3855120 | 3473230 | 3.4 | 54.1 | 29 | P1 – Critical
E335-RFI-0039 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Lane closure window request – East Main Station | Contractor requests approval of an alternate traffic/staging plan at East Main Station: temporary lane shift. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Superintendent | 2018-10-22 | 10 | Routine | Y | Y | N | 3 | DSDC – HJH JV | 1 | 2018-10-25 | 3 | Y | 0 | 1 | 2018-10-25 | 3 | Closed | 2 | 0 | 1 | 259000 | 484000 | N |  | 0 | 0 | 0 | 0.2 | 776 | P4 – Low
E335-RFI-0040 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Clarify spec requirement – 110th Ave NE/NE 6th St | Request clarification of 01 33 00 Submittal Procedures and S-184: dimension/notes appear inconsistent or omitted for the work at 110th Ave NE/NE 6th St. | Design Manager | 2018-11-08 | 10 | Routine | N | N | N | 2 | DSDC – HJH JV | 1 | 2018-11-15 | 7 | Y | 0 | 1 | 2018-11-15 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 974 | P4 – Low
E335-RFI-0041 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Station finish detail – NE 12th St guideway | Request to clarify finish/connection detail on C-641 at NE 12th St guideway. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2018-11-21 | 10 | Expedite | N | Y | N | 6 | DSDC – HJH JV | 3 | 2018-11-26 | 5 | Y | 0 | 1 | 2018-11-26 | 5 | Closed | 9 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 709 | P3 – Medium
E335-RFI-0042 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Signal Case location conflict at Sta. 1881+98 | Proposed signal case foundation location at Sta. 1881+98 conflicts with platform edge slab; offset of 5 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Field Engineer | 2018-11-23 | 10 | Routine | N | N | Y | 0 | DSDC – HJH JV | 3 | 2018-12-11 | 18 | N | 8 | 1 | 2018-12-11 | 18 | Closed | 0 | 3 | 0 |  |  | N |  | 0 | 0 | 0 | 3 | 476 | P3 – Medium
E335-RFI-0043 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 24-in. sanitary sewer at Bellevue Downtown Station | Potholing at Sta. 1102+53 located a 24-in. sanitary sewer in conflict with the proposed retaining wall footing. Utility is not shown on E-134. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Engineer | 2018-12-07 | 10 | Urgent | Y | Y | N | 6 | DSDC – HJH JV | 1 | 2018-12-17 | 8 | Y | 0 | 1 | 2018-12-17 | 8 | Closed | 5 | 0 | 2 | 64000 | 119000 | Y | E335-CO-012 | 166800 | 74100 | 1 | 39.4 | 249 | P2 – High
E335-RFI-0044 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – bearing pad/embed plate sequence at East Main Station | Erection of the bearing pad/embed plate as drawn conflicts with adjacent work and access limits at East Main Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2018-12-19 | 10 | Routine | Y | N | N | 7 | DSDC – HJH JV | 1 | 2019-01-07 | 17 | N | 7 | 1 | 2019-01-07 | 17 | Closed | 0 | 0 | 0 | 639000 | 1192000 | N |  | 0 | 0 | 0 | 0 | 975 | P4 – Low
E335-RFI-0045 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | Wetland/stream buffer protection – Spring District/120th Station | Field conditions at Spring District/120th Station require changes to temporary erosion and sediment control or stormwater facility per A-107. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2018-12-24 | 10 | Routine | N | N | N | 0 | DSDC – HJH JV | 1 | 2018-12-31 | 5 | Y | 0 | 1 | 2018-12-31 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 976 | P4 – Low
E335-RFI-0046 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at I-405 light rail bridge: abandoned timber piles | During excavation at I-405 light rail bridge (Sta. 1962+52) the contractor encountered abandoned timber piles, not shown on the GBR or E-226. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Project Manager | 2019-01-07 | 10 | Routine | Y | Y | N | 6 | DSDC – HJH JV | 3 | 2019-01-28 | 19 | N | 9 | 1 | 2019-01-28 | 19 | Closed | 18 | 0 | 4 | 486000 | 908000 | Y | E335-CO-013 | 426800 | 299300 | 12 | 48.3 | 88 | P1 – Critical
E335-RFI-0047 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – Bellevue Downtown Station | E-283 shows a 30 ft-7 in. dimension for the duct bank encasement; structural sheet S-814 shows a different value. Request clarification before fabrication/rebar release. | Project Manager | 2019-01-08 | 10 | Urgent | N | N | Y | 5 | DSDC – HJH JV | 3 | 2019-01-17 | 9 | Y | 0 | 1 | 2019-01-17 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 977 | P4 – Low
E335-RFI-0048 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Grounding/bonding and stray-current detail – I-405 light rail bridge | Civil and systems drawings differ on grounding/bonding of retaining wall footing for stray-current control at I-405 light rail bridge. Request governing detail and responsibility for installation. | Design Manager | 2019-01-21 | 10 | Routine | N | Y | Y | 0 | DSDC – HJH JV | 3 | 2019-02-12 | 22 | N | 12 | 1 | 2019-02-12 | 22 | Closed | 55 | 35 | 0 |  |  | N |  | 0 | 0 | 0 | 30 | 343 | P3 – Medium
E335-RFI-0049 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 24-in. sanitary sewer at Bellevue Downtown Station | Potholing at Sta. 1607+26 located a 24-in. sanitary sewer in conflict with the proposed guideway girder diaphragm. Utility is not shown on E-515. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Superintendent | 2019-01-21 | 10 | Routine | Y | Y | N | 8 | DSDC – HJH JV | 2 | 2019-02-04 | 12 | N | 2 | 1 | 2019-02-04 | 12 | Closed | 8 | 0 | 4 | 1517000 | 2831000 | N |  | 0 | 0 | 0 | 0.9 | 623 | P3 – Medium
E335-RFI-0050 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Canopy/glazing connection – East Main Station | Request to clarify finish/connection detail on S-861 at East Main Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Superintendent | 2019-01-28 | 10 | Routine | N | Y | N | 3 | ST Design Management | 3 | 2019-01-30 | 2 | Y | 0 | 1 | 2019-01-30 | 2 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 777 | P4 – Low
E335-RFI-0051 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – drilled shaft cap and duct bank encasement at Bellevue Downtown Station | Interference between drilled shaft cap and duct bank encasement at Bellevue Downtown Station per E-788. Required clearance of 4 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2019-01-29 | 10 | Urgent | Y | Y | Y | 3 | DSDC – HJH JV | 1 | 2019-02-05 | 7 | Y | 0 | 1 | 2019-02-05 | 7 | Closed | 25 | 8 | 0 | 233000 | 435000 | Y | E335-CO-014 | 259600 | 127300 | 15 | 53.5 | 32 | P1 – Critical
E335-RFI-0052 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – I-405 light rail bridge | C-393 shows a 34 ft-7 in. dimension for the drilled shaft cap; structural sheet S-255 shows a different value. Request clarification before fabrication/rebar release. | Superintendent | 2019-02-07 | 10 | Expedite | N | Y | Y | 0 | DSDC – HJH JV | 1 | 2019-02-13 | 6 | Y | 0 | 1 | 2019-02-13 | 6 | Closed | 7 | 6 | 0 |  |  | Y | E335-CO-015 | 137600 | 0 | 0 | 6 | 421 | P3 – Medium
E335-RFI-0053 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | City of Bellevue comment on street improvement permit – Wilburton Station | City of Bellevue review comments on the street improvement permit require changes to the retaining wall footing at Wilburton Station. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2019-02-11 | 10 | Routine | N | N | Y | 2 | City of Bellevue / ST Third-Party Mgmt | 3 | 2019-02-20 | 9 | Y | 0 | 1 | 2019-02-20 | 9 | Closed | 0 | 5 | 0 |  |  | N |  | 0 | 0 | 0 | 5 | 435 | P3 – Medium
E335-RFI-0054 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Direct fixation fastener spacing at Sta. 2293+82 | Track layout at Sta. 2293+82 (East Main Station) differs from the track-structure interface drawing C-410. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Superintendent | 2019-02-11 | 10 | Routine | N | N | N | 3 | DSDC – HJH JV | 2 | 2019-02-21 | 10 | Y | 0 | 1 | 2019-02-21 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 978 | P4 – Low
E335-RFI-0055 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with abandoned utility vault at East Main Station | Potholing at Sta. 2330+19 located a abandoned utility vault in conflict with the proposed column reinforcement. Utility is not shown on M-718. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Field Engineer | 2019-02-25 | 10 | Urgent | Y | Y | Y | 7 | DSDC – HJH JV | 2 | 2019-03-08 | 11 | N | 1 | 1 | 2019-03-08 | 11 | Closed | 4 | 2 | 0 | 3658000 | 6829000 | Y | E335-CO-016 | 1804700 | 1182700 | 2 | 50.9 | 47 | P1 – Critical
E335-RFI-0056 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Dimensional discrepancy – 110th Ave NE/NE 6th St | E-688 shows a 17 ft-10 in. dimension for the retaining wall footing; structural sheet S-637 shows a different value. Request clarification before fabrication/rebar release. | Superintendent | 2019-03-06 | 10 | Routine | N | N | Y | 5 | DSDC – HJH JV | 2 | 2019-03-18 | 10 | Y | 0 | 1 | 2019-03-18 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 979 | P4 – Low
E335-RFI-0057 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at I-405 light rail bridge: glacially deposited boulders exceeding 36 in. | During excavation at I-405 light rail bridge (Sta. 2034+75) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or E-210. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Scheduler | 2019-03-11 | 10 | Routine | N | Y | N | 7 | DSDC – HJH JV | 3 | 2019-03-14 | 3 | Y | 0 | 1 | 2019-03-14 | 3 | Closed | 24 | 0 | 7 |  |  | N |  | 0 | 0 | 0 | 1.6 | 554 | P3 – Medium
E335-RFI-0058 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Canopy/glazing connection – Spring District/120th Station | Request to clarify finish/connection detail on S-473 at Spring District/120th Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2019-03-18 | 10 | Expedite | N | N | Y | 5 | DSDC – HJH JV | 2 | 2019-03-22 | 4 | Y | 0 | 1 | 2019-03-22 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 980 | P4 – Low
E335-RFI-0059 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Direct fixation fastener spacing at Sta. 1047+52 | Track layout at Sta. 1047+52 (110th Ave NE/NE 6th St) differs from the track-structure interface drawing A-358. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2019-03-22 | 10 | Routine | N | N | N | 3 | DSDC – HJH JV | 1 | 2019-04-01 | 9 | Y | 0 | 1 | 2019-04-01 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 981 | P4 – Low
E335-RFI-0060 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Property owner access/restoration requirement – East Main Station | Adjacent property owner has requested additional restoration and access provisions at East Main Station beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Design Manager | 2019-03-25 | 10 | Routine | Y | N | Y | 8 | City of Bellevue / ST Third-Party Mgmt | 2 | 2019-04-01 | 5 | Y | 0 | 1 | 2019-04-01 | 5 | Closed | 0 | 0 | 0 | 94000 | 176000 | N |  | 0 | 0 | 0 | 0 | 982 | P4 – Low
E335-RFI-0061 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at East Main Station: glacially deposited boulders exceeding 36 in. | During excavation at East Main Station (Sta. 984+08) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or E-223. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Field Engineer | 2019-04-02 | 10 | Routine | Y | Y | N | 1 | DSDC – HJH JV | 1 | 2019-04-08 | 6 | Y | 0 | 1 | 2019-04-08 | 6 | Closed | 4 | 0 | 3 | 335000 | 625000 | Y | E335-CO-017 | 1214700 | 537200 | 1 | 46.5 | 116 | P2 – High
E335-RFI-0062 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – I-405 light rail bridge | S-332 shows a 20 ft-7 in. dimension for the platform edge slab; structural sheet S-711 shows a different value. Request clarification before fabrication/rebar release. | Field Engineer | 2019-04-04 | 10 | Expedite | Y | N | N | 7 | DSDC – HJH JV | 2 | 2019-04-08 | 3 | Y | 0 | 1 | 2019-04-08 | 3 | Closed | 0 | 0 | 0 | 127000 | 237000 | Y | E335-CO-023 | 190380 | 133890 | 0.2 | 40.7 | 223 | P2 – High
E335-RFI-0063 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – recycled-content fly ash blend | Contractor requests approval to substitute recycled-content fly ash blend for Type IL cement mix on work at I-405 light rail bridge, citing procurement lead time. Product data attached. | Field Engineer | 2019-04-15 | 10 | Routine | N | N | Y | 6 | ST Design Management | 1 | 2019-04-18 | 3 | Y | 0 | 1 | 2019-04-18 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 983 | P4 – Low
E335-RFI-0064 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – pedestrian ramp at Spring District/120th Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-648 for egress width at Spring District/120th Station. Request direction on compliant detail. | Project Engineer | 2019-04-15 | 10 | Urgent | Y | N | Y | 2 | DSDC – HJH JV | 1 | 2019-04-18 | 3 | Y | 0 | 1 | 2019-04-18 | 3 | Closed | 0 | 0 | 0 | 60000 | 112000 | Y | E335-CO-018 | 134600 | 89000 | 0 | 39.3 | 252 | P2 – High
E335-RFI-0065 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – East Main Station | Civil and systems drawings differ on grounding/bonding of bearing pad/embed plate for stray-current control at East Main Station. Request governing detail and responsibility for installation. | Project Engineer | 2019-04-15 | 10 | Routine | N | Y | N | 2 | DSDC – HJH JV | 2 | 2019-04-24 | 9 | Y | 0 | 1 | 2019-04-24 | 9 | Closed | 6 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 663 | P3 – Medium
E335-RFI-0066 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – drilled shaft cap sequence at Wilburton Station | Erection of the drilled shaft cap as drawn conflicts with adjacent work and access limits at Wilburton Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Project Manager | 2019-04-15 | 10 | Routine | Y | N | N | 4 | DSDC – HJH JV | 6 | 2019-04-22 | 7 | Y | 0 | 2 | 2019-05-02 | 17 | Closed | 0 | 0 | 0 | 58000 | 109000 | N |  | 0 | 0 | 0 | 0 | 984 | P4 – Low
E335-RFI-0067 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 12-in. ductile iron water main at NE 12th St guideway | Potholing at Sta. 2294+39 located a 12-in. ductile iron water main in conflict with the proposed stair core wall. Utility is not shown on C-851. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Scheduler | 2019-04-23 | 10 | Routine | N | Y | N | 2 | DSDC – HJH JV | 1 | 2019-05-01 | 8 | Y | 0 | 1 | 2019-05-01 | 8 | Closed | 4 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 710 | P3 – Medium
E335-RFI-0068 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Art embed coordination – Spring District/120th Station | Request to clarify finish/connection detail on M-537 at Spring District/120th Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Manager | 2019-04-24 | 10 | Routine | Y | N | N | 2 | ST Design Management | 3 | 2019-04-30 | 6 | Y | 0 | 1 | 2019-04-30 | 6 | Closed | 0 | 0 | 0 | 24000 | 45000 | N |  | 0 | 0 | 0 | 0 | 985 | P4 – Low
E335-RFI-0069 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bellevue Downtown Station: abandoned timber piles | During excavation at Bellevue Downtown Station (Sta. 956+49) the contractor encountered abandoned timber piles, not shown on the GBR or E-623. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Project Engineer | 2019-04-24 | 10 | Urgent | Y | N | N | 5 | DSDC – HJH JV | 1 | 2019-04-30 | 6 | Y | 0 | 2 | 2019-05-21 | 27 | Closed | 0 | 0 | 0 | 140000 | 262000 | Y | E335-CO-022 | 114020 | 100260 | 0 | 39.7 | 245 | P2 – High
E335-RFI-0070 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – galvanized steel handrail | Contractor requests approval to substitute galvanized steel handrail for stainless steel handrail on work at Spring District/120th Station, citing procurement lead time. Product data attached. | Project Engineer | 2019-04-30 | 10 | Routine | N | N | N | 3 | DSDC – HJH JV | 1 | 2019-05-03 | 3 | Y | 0 | 1 | 2019-05-03 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 986 | P4 – Low
E335-RFI-0071 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Bellevue Downtown Station: abandoned timber piles | During excavation at Bellevue Downtown Station (Sta. 1400+84) the contractor encountered abandoned timber piles, not shown on the GBR or S-736. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Superintendent | 2019-05-01 | 10 | Expedite | Y | N | N | 0 | DSDC – HJH JV | 1 | 2019-05-20 | 17 | N | 7 | 1 | 2019-05-20 | 17 | Closed | 0 | 0 | 0 | 44000 | 81000 | Y | E335-CO-019 | 62520 | 18870 | 1.3 | 34.4 | 319 | P2 – High
E335-RFI-0072 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at 110th Ave NE/NE 6th St: loose granular fill below planned bearing elevation | During excavation at 110th Ave NE/NE 6th St (Sta. 2028+96) the contractor encountered loose granular fill below planned bearing elevation, not shown on the GBR or C-491. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Project Engineer | 2019-05-02 | 10 | Routine | Y | Y | Y | 5 | ST Design Management | 3 | 2019-05-10 | 8 | Y | 0 | 2 | 2019-05-20 | 18 | Closed | 11 | 5 | 0 | 52000 | 97000 | Y | E335-CO-019 | 85280 | 25730 | 1.7 | 40.6 | 225 | P2 – High
E335-RFI-0073 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with fiber communications duct bank at NE 12th St guideway | Potholing at Sta. 1268+68 located a fiber communications duct bank in conflict with the proposed stair core wall. Utility is not shown on A-785. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Project Manager | 2019-05-13 | 10 | Expedite | Y | N | Y | 1 | ST Design Management | 1 | 2019-05-16 | 3 | Y | 0 | 1 | 2019-05-16 | 3 | Closed | 0 | 0 | 0 | 18000 | 33000 | Y | E335-CO-020 | 20200 | 11200 | 0 | 32.1 | 335 | P2 – High
E335-RFI-0074 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – drilled shaft cap at I-405 light rail bridge | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-411 for smoke control damper at I-405 light rail bridge. Request direction on compliant detail. | Field Engineer | 2019-05-17 | 10 | Routine | N | Y | N | 0 | DSDC – HJH JV | 2 | 2019-06-03 | 17 | N | 7 | 1 | 2019-06-03 | 17 | Closed | 4 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 576 | P3 – Medium
E335-RFI-0075 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – guideway girder diaphragm sequence at East Main Station | Erection of the guideway girder diaphragm as drawn conflicts with adjacent work and access limits at East Main Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Scheduler | 2019-06-04 | 10 | Routine | Y | N | Y | 8 | DSDC – HJH JV | 1 | 2019-06-10 | 5 | Y | 0 | 1 | 2019-06-10 | 5 | Closed | 0 | 0 | 0 | 229000 | 427000 | Y | E335-CO-023 | 351420 | 247150 | 0.3 | 42.9 | 181 | P2 – High
E335-RFI-0076 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Wetland/stream buffer protection – Bellevue Downtown Station | Field conditions at Bellevue Downtown Station require changes to temporary erosion and sediment control or stormwater facility per E-386. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2019-06-05 | 10 | Urgent | N | N | Y | 5 | DSDC – HJH JV | 2 | 2019-06-10 | 5 | Y | 0 | 1 | 2019-06-10 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 987 | P4 – Low
E335-RFI-0077 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – drilled shaft cap and platform edge slab at East Main Station | Interference between drilled shaft cap and platform edge slab at East Main Station per A-725. Required clearance of 7 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Scheduler | 2019-06-12 | 10 | Routine | Y | N | N | 2 | DSDC – HJH JV | 1 | 2019-07-01 | 19 | N | 9 | 2 | 2019-07-19 | 37 | Closed | 0 | 0 | 0 | 176000 | 329000 | Y | E335-CO-021 | 259900 | 221900 | 0 | 42.4 | 192 | P2 – High
E335-RFI-0078 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Canopy/glazing connection – East Main Station | Request to clarify finish/connection detail on S-752 at East Main Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Scheduler | 2019-06-12 | 10 | Routine | N | N | N | 8 | DSDC – HJH JV | 1 | 2019-06-17 | 3 | Y | 0 | 1 | 2019-06-17 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 988 | P4 – Low
E335-RFI-0079 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – alternate epoxy-coated rebar supplier | Contractor requests approval to substitute alternate epoxy-coated rebar supplier for specified epoxy-coated rebar on work at NE 12th St guideway, citing procurement lead time. Product data attached. | Field Engineer | 2019-06-21 | 10 | Expedite | N | N | N | 8 | DSDC – HJH JV | 3 | 2019-07-03 | 12 | N | 2 | 1 | 2019-07-03 | 12 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 989 | P4 – Low
E335-RFI-0080 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – 110th Ave NE/NE 6th St | Civil and systems drawings differ on grounding/bonding of drilled shaft cap for stray-current control at 110th Ave NE/NE 6th St. Request governing detail and responsibility for installation. | Scheduler | 2019-07-10 | 10 | Routine | N | N | N | 5 | DSDC – HJH JV | 3 | 2019-07-31 | 21 | N | 11 | 1 | 2019-07-31 | 21 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 990 | P4 – Low
E335-RFI-0081 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Lane closure window request – Wilburton Station | Contractor requests approval of an alternate traffic/staging plan at Wilburton Station: extended night closure. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Project Engineer | 2019-07-10 | 10 | Routine | N | N | N | 5 | DSDC – HJH JV | 1 | 2019-07-22 | 12 | N | 2 | 1 | 2019-07-22 | 12 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 991 | P4 – Low
E335-RFI-0082 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – retaining wall footing and drilled shaft cap at I-405 light rail bridge | Interference between retaining wall footing and drilled shaft cap at I-405 light rail bridge per S-492. Required clearance of 4 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Engineer | 2019-07-15 | 10 | Routine | N | N | N | 6 | DSDC – HJH JV | 2 | 2019-07-29 | 12 | N | 2 | 1 | 2019-07-29 | 12 | Closed | 0 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 778 | P4 – Low
E335-RFI-0083 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Wilburton Station: abandoned timber piles | During excavation at Wilburton Station (Sta. 1762+93) the contractor encountered abandoned timber piles, not shown on the GBR or E-218. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Scheduler | 2019-07-18 | 10 | Urgent | Y | N | Y | 5 | DSDC – HJH JV | 5 | 2019-07-22 | 3 | Y | 0 | 1 | 2019-07-22 | 3 | Closed | 0 | 0 | 0 | 572000 | 1069000 | Y | E335-CO-022 | 450580 | 396240 | 0 | 44.4 | 152 | P2 – High
E335-RFI-0084 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at I-405 light rail bridge: loose granular fill below planned bearing elevation | During excavation at I-405 light rail bridge (Sta. 1972+94) the contractor encountered loose granular fill below planned bearing elevation, not shown on the GBR or E-834. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Superintendent | 2019-07-18 | 10 | Urgent | N | N | Y | 4 | DSDC – HJH JV | 1 | 2019-07-22 | 4 | Y | 0 | 1 | 2019-07-22 | 4 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 992 | P4 – Low
E335-RFI-0085 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Grounding/bonding and stray-current detail – Spring District/120th Station | Civil and systems drawings differ on grounding/bonding of station canopy support for stray-current control at Spring District/120th Station. Request governing detail and responsibility for installation. | Scheduler | 2019-07-29 | 10 | Routine | N | N | N | 7 | DSDC – HJH JV | 3 | 2019-08-19 | 19 | N | 9 | 1 | 2019-08-19 | 19 | Closed | 0 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 711 | P3 – Medium
E335-RFI-0086 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – column reinforcement and pedestrian ramp at Wilburton Station | Interference between column reinforcement and pedestrian ramp at Wilburton Station per E-602. Required clearance of 2 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Field Engineer | 2019-07-29 | 10 | Expedite | Y | Y | N | 8 | DSDC – HJH JV | 3 | 2019-08-06 | 8 | Y | 0 | 1 | 2019-08-06 | 8 | Closed | 5 | 0 | 1 | 2839000 | 5300000 | Y | E335-CO-023 | 2921290 | 2054460 | 2.5 | 51.1 | 45 | P1 – Critical
E335-RFI-0087 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at I-405 light rail bridge: an unmapped abandoned storm line | During excavation at I-405 light rail bridge (Sta. 1272+97) the contractor encountered an unmapped abandoned storm line, not shown on the GBR or M-273. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Design Manager | 2019-08-06 | 10 | Routine | N | Y | N | 2 | DSDC – HJH JV | 1 | 2019-08-16 | 10 | Y | 0 | 2 | 2019-08-29 | 23 | Closed | 11 | 0 | 6 |  |  | N |  | 0 | 0 | 0 | 1.3 | 564 | P3 – Medium
E335-RFI-0088 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | Property owner access/restoration requirement – Spring District/120th Station | Adjacent property owner has requested additional restoration and access provisions at Spring District/120th Station beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Field Engineer | 2019-08-19 | 10 | Expedite | Y | N | N | 1 | WSDOT / ST Third-Party Mgmt | 1 | 2019-08-30 | 11 | N | 1 | 1 | 2019-08-30 | 11 | Closed | 0 | 0 | 0 | 352000 | 657000 | N |  | 0 | 0 | 0 | 0 | 993 | P4 – Low
E335-RFI-0089 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | Wetland/stream buffer protection – Bellevue Downtown Station | Field conditions at Bellevue Downtown Station require changes to temporary erosion and sediment control or stormwater facility per C-187. Request direction considering critical-areas conditions and permit requirements. | Scheduler | 2019-08-22 | 10 | Expedite | N | N | Y | 0 | DSDC – HJH JV | 1 | 2019-08-27 | 5 | Y | 0 | 1 | 2019-08-27 | 5 | Closed | 0 | 5 | 0 |  |  | N |  | 0 | 0 | 0 | 5 | 436 | P3 – Medium
E335-RFI-0090 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Special trackwork layout – I-405 light rail bridge | Track layout at Sta. 1933+02 (I-405 light rail bridge) differs from the track-structure interface drawing A-870. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Design Manager | 2019-08-23 | 10 | Routine | N | N | N | 1 | DSDC – HJH JV | 2 | 2019-09-02 | 8 | Y | 0 | 1 | 2019-09-02 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 994 | P4 – Low
E335-RFI-0091 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 30-in. storm drain at East Main Station | Potholing at Sta. 1310+04 located a 30-in. storm drain in conflict with the proposed platform edge slab. Utility is not shown on C-143. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2019-09-02 | 10 | Routine | Y | Y | Y | 5 | DSDC – HJH JV | 2 | 2019-09-09 | 7 | Y | 0 | 1 | 2019-09-09 | 7 | Closed | 53 | 21 | 0 | 120000 | 224000 | Y | E335-CO-024 | 184700 | 131700 | 26 | 70.3 | 6 | P1 – Critical
E335-RFI-0092 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Wilburton Station | Systems contractor requires 4-in. PVC conduit stub-ups for traction power feeder at Wilburton Station not provided in civil C-506. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2019-09-03 | 10 | Routine | Y | Y | N | 7 | DSDC – HJH JV | 5 | 2019-09-16 | 11 | N | 1 | 1 | 2019-09-16 | 11 | Closed | 7 | 0 | 2 | 611000 | 1140000 | N |  | 0 | 0 | 0 | 0.4 | 712 | P3 – Medium
E335-RFI-0093 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – platform edge slab and duct bank encasement at I-405 light rail bridge | Interference between platform edge slab and duct bank encasement at I-405 light rail bridge per S-456. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Engineer | 2019-09-05 | 10 | Urgent | Y | Y | Y | 2 | DSDC – HJH JV | 2 | 2019-09-09 | 3 | Y | 0 | 1 | 2019-09-09 | 3 | Closed | 11 | 10 | 0 | 44000 | 83000 | Y | E335-CO-026 | 36780 | 36780 | 2.4 | 47 | 104 | P1 – Critical
E335-RFI-0094 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 24-in. sanitary sewer at I-405 light rail bridge | Potholing at Sta. 1877+59 located a 24-in. sanitary sewer in conflict with the proposed column reinforcement. Utility is not shown on A-241. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Manager | 2019-09-16 | 10 | Routine | N | N | Y | 3 | DSDC – HJH JV | 3 | 2019-09-20 | 4 | Y | 0 | 2 | 2019-10-03 | 17 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 995 | P4 – Low
E335-RFI-0095 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Canopy/glazing connection – East Main Station | Request to clarify finish/connection detail on C-772 at East Main Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2019-09-26 | 10 | Routine | N | N | N | 3 | DSDC – HJH JV | 1 | 2019-09-30 | 4 | Y | 0 | 1 | 2019-09-30 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 996 | P4 – Low
E335-RFI-0096 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – stair core wall and station canopy support at East Main Station | Interference between stair core wall and station canopy support at East Main Station per C-465. Required clearance of 3 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Manager | 2019-10-07 | 10 | Expedite | N | N | Y | 7 | DSDC – HJH JV | 3 | 2019-10-14 | 7 | Y | 0 | 1 | 2019-10-14 | 7 | Closed | 0 | 1 | 0 |  |  | N |  | 0 | 0 | 0 | 1 | 606 | P3 – Medium
E335-RFI-0097 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – bearing pad/embed plate sequence at Bellevue Downtown Station | Erection of the bearing pad/embed plate as drawn conflicts with adjacent work and access limits at Bellevue Downtown Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Project Engineer | 2019-10-09 | 10 | Urgent | Y | Y | Y | 4 | DSDC – HJH JV | 1 | 2019-10-18 | 9 | Y | 0 | 1 | 2019-10-18 | 9 | Closed | 8 | 4 | 0 | 331000 | 618000 | Y | E335-CO-025 | 579850 | 0 | 0 | 4 | 451 | P3 – Medium
E335-RFI-0098 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – column reinforcement sequence at Spring District/120th Station | Erection of the column reinforcement as drawn conflicts with adjacent work and access limits at Spring District/120th Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Scheduler | 2019-10-17 | 10 | Routine | N | N | Y | 6 | ST Design Management | 4 | 2019-10-25 | 8 | Y | 0 | 1 | 2019-10-25 | 8 | Closed | 0 | 1 | 0 |  |  | N |  | 0 | 0 | 0 | 1 | 607 | P3 – Medium
E335-RFI-0099 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – stair core wall sequence at East Main Station | Erection of the stair core wall as drawn conflicts with adjacent work and access limits at East Main Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Field Engineer | 2019-10-18 | 10 | Routine | Y | N | N | 2 | DSDC – HJH JV | 3 | 2019-10-23 | 5 | Y | 0 | 1 | 2019-10-23 | 5 | Closed | 0 | 0 | 0 | 218000 | 407000 | Y | E335-CO-025 | 389150 | 0 | 0 | 0 | 997 | P4 – Low
E335-RFI-0100 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Night work and noise variance – NE 12th St guideway | Contractor requests approval of an alternate traffic/staging plan at NE 12th St guideway: revised haul route. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Field Engineer | 2019-11-06 | 10 | Expedite | Y | Y | N | 2 | ST Design Management | 2 | 2019-11-11 | 5 | Y | 0 | 2 | 2019-11-29 | 23 | Closed | 6 | 0 | 4 | 62000 | 115000 | N |  | 0 | 0 | 0 | 0.9 | 624 | P3 – Medium
E335-RFI-0101 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Canopy/glazing connection – I-405 light rail bridge | Request to clarify finish/connection detail on M-429 at I-405 light rail bridge. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2019-11-07 | 10 | Routine | Y | N | N | 5 | DSDC – HJH JV | 1 | 2019-11-12 | 5 | Y | 0 | 1 | 2019-11-12 | 5 | Closed | 0 | 0 | 0 | 45000 | 85000 | N |  | 0 | 0 | 0 | 0 | 998 | P4 – Low
E335-RFI-0102 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – duct bank encasement at Bellevue Downtown Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-537 for smoke control damper at Bellevue Downtown Station. Request direction on compliant detail. | Scheduler | 2019-11-11 | 10 | Routine | Y | Y | N | 2 | DSDC – HJH JV | 2 | 2019-12-02 | 21 | N | 11 | 1 | 2019-12-02 | 21 | Closed | 10 | 0 | 4 | 206000 | 384000 | N |  | 0 | 0 | 0 | 0.9 | 625 | P3 – Medium
E335-RFI-0103 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Drawing/spec discrepancy – Wilburton Station | Request clarification of 01 25 00 Substitution Procedures and C-311: dimension/notes appear inconsistent or omitted for the work at Wilburton Station. | Superintendent | 2019-11-11 | 10 | Routine | N | N | N | 1 | ST Design Management | 3 | 2019-11-14 | 3 | Y | 0 | 1 | 2019-11-14 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 999 | P4 – Low
E335-RFI-0104 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – stair core wall and retaining wall footing at Bellevue Downtown Station | Interference between stair core wall and retaining wall footing at Bellevue Downtown Station per E-468. Required clearance of 6 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2019-11-13 | 10 | Routine | N | Y | N | 6 | DSDC – HJH JV | 1 | 2019-11-21 | 8 | Y | 0 | 1 | 2019-11-21 | 8 | Closed | 1 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1000 | P4 – Low
E335-RFI-0105 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Station finish detail – Spring District/120th Station | Request to clarify finish/connection detail on S-344 at Spring District/120th Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Scheduler | 2019-11-15 | 10 | Routine | N | N | N | 1 | DSDC – HJH JV | 2 | 2019-11-20 | 5 | Y | 0 | 1 | 2019-11-20 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1001 | P4 – Low
E335-RFI-0106 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – station canopy support sequence at Spring District/120th Station | Erection of the station canopy support as drawn conflicts with adjacent work and access limits at Spring District/120th Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Field Engineer | 2019-11-19 | 10 | Routine | Y | N | N | 6 | DSDC – HJH JV | 2 | 2019-11-25 | 5 | Y | 0 | 1 | 2019-11-25 | 5 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1002 | P4 – Low
E335-RFI-0107 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Art embed coordination – I-405 light rail bridge | Request to clarify finish/connection detail on M-333 at I-405 light rail bridge. Includes coordination with art program embeds and handrail sleeves as applicable. | Field Engineer | 2019-11-19 | 10 | Expedite | Y | N | N | 7 | DSDC – HJH JV | 1 | 2019-11-22 | 3 | Y | 0 | 1 | 2019-11-22 | 3 | Closed | 0 | 0 | 0 | 85000 | 159000 | N |  | 0 | 0 | 0 | 0 | 1003 | P4 – Low
E335-RFI-0108 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Spring District/120th Station: buried concrete debris and an old foundation | During excavation at Spring District/120th Station (Sta. 1131+13) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or E-732. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Project Engineer | 2019-11-25 | 10 | Urgent | Y | N | Y | 1 | DSDC – HJH JV | 1 | 2019-11-28 | 3 | Y | 0 | 1 | 2019-11-28 | 3 | Closed | 0 | 0 | 0 | 486000 | 907000 | Y | E335-CO-029 | 508550 | 444790 | 0 | 44.8 | 141 | P2 – High
E335-RFI-0109 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Dimensional discrepancy – I-405 light rail bridge | C-233 shows a 32 ft-3 in. dimension for the guideway girder diaphragm; structural sheet S-595 shows a different value. Request clarification before fabrication/rebar release. | Field Engineer | 2019-11-25 | 10 | Routine | Y | Y | Y | 0 | DSDC – HJH JV | 2 | 2019-12-09 | 13 | N | 3 | 1 | 2019-12-09 | 13 | Closed | 3 | 3 | 0 | 124000 | 232000 | Y | E335-CO-026 | 148720 | 148720 | 9.6 | 47.2 | 102 | P1 – Critical
E335-RFI-0110 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Station finish detail – NE 12th St guideway | Request to clarify finish/connection detail on M-569 at NE 12th St guideway. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Manager | 2019-11-26 | 10 | Expedite | N | Y | N | 7 | DSDC – HJH JV | 1 | 2019-12-04 | 8 | Y | 0 | 1 | 2019-12-04 | 8 | Closed | 1 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 779 | P4 – Low
E335-RFI-0111 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with fiber communications duct bank at Spring District/120th Station | Potholing at Sta. 2042+46 located a fiber communications duct bank in conflict with the proposed stair core wall. Utility is not shown on A-226. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2019-11-29 | 10 | Expedite | Y | Y | N | 7 | DSDC – HJH JV | 1 | 2019-12-16 | 15 | N | 5 | 1 | 2019-12-16 | 15 | Closed | 21 | 0 | 7 | 55000 | 103000 | N |  | 0 | 0 | 0 | 1.6 | 555 | P3 – Medium
E335-RFI-0112 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at NE 12th St guideway: perched groundwater | During excavation at NE 12th St guideway (Sta. 2251+61) the contractor encountered perched groundwater at approx. elevation 98 ft, not shown on the GBR or M-679. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Design Manager | 2019-12-18 | 10 | Routine | Y | Y | Y | 2 | DSDC – HJH JV | 2 | 2019-12-23 | 5 | Y | 0 | 1 | 2019-12-23 | 5 | Closed | 10 | 3 | 0 | 156000 | 292000 | N |  | 0 | 0 | 0 | 3 | 477 | P3 – Medium
E335-RFI-0113 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Property owner access/restoration requirement – Wilburton Station | Adjacent property owner has requested additional restoration and access provisions at Wilburton Station beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Project Engineer | 2019-12-23 | 10 | Routine | Y | N | N | 0 | Puget Sound Energy / ST Third-Party Mgmt | 1 | 2020-01-03 | 11 | N | 1 | 2 | 2020-01-21 | 29 | Closed | 0 | 0 | 0 | 317000 | 591000 | Y | E335-CO-027 | 207600 | 149900 | 0 | 41.1 | 218 | P2 – High
E335-RFI-0114 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Dimensional discrepancy – Wilburton Station | E-658 shows a 38 ft-8 in. dimension for the guideway girder diaphragm; structural sheet S-621 shows a different value. Request clarification before fabrication/rebar release. | Design Manager | 2019-12-23 | 10 | Routine | Y | N | Y | 6 | DSDC – HJH JV | 2 | 2020-01-28 | 36 | N | 26 | 1 | 2020-01-28 | 36 | Closed | 0 | 11 | 0 | 202000 | 376000 | Y | E335-CO-028 | 268400 | 114500 | 0 | 51.1 | 46 | P1 – Critical
E335-RFI-0115 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at 110th Ave NE/NE 6th St: petroleum-stained soil with odor | During excavation at 110th Ave NE/NE 6th St (Sta. 1640+95) the contractor encountered petroleum-stained soil with odor, not shown on the GBR or M-839. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Project Engineer | 2020-01-20 | 10 | Routine | Y | N | Y | 0 | DSDC – HJH JV | 3 | 2020-02-03 | 12 | N | 2 | 1 | 2020-02-03 | 12 | Closed | 0 | 0 | 0 | 115000 | 216000 | Y | E335-CO-029 | 124750 | 109110 | 0 | 40 | 236 | P2 – High
E335-RFI-0116 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Station finish detail – NE 12th St guideway | Request to clarify finish/connection detail on M-471 at NE 12th St guideway. Includes coordination with art program embeds and handrail sleeves as applicable. | Scheduler | 2020-01-27 | 10 | Urgent | Y | N | N | 5 | DSDC – HJH JV | 2 | 2020-02-06 | 10 | Y | 0 | 1 | 2020-02-06 | 10 | Closed | 0 | 0 | 0 | 9000 | 18000 | N |  | 0 | 0 | 0 | 0 | 1004 | P4 – Low
E335-RFI-0117 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – alternate LED luminaire | Contractor requests approval to substitute alternate LED luminaire for specified LED luminaire on work at NE 12th St guideway, citing procurement lead time. Product data attached. | Project Engineer | 2020-02-12 | 10 | Urgent | N | N | Y | 3 | DSDC – HJH JV | 3 | 2020-02-17 | 4 | Y | 0 | 1 | 2020-02-17 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1005 | P4 – Low
E335-RFI-0118 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | In-water work window – Wilburton Station | Field conditions at Wilburton Station require changes to temporary erosion and sediment control or stormwater facility per M-591. Request direction considering critical-areas conditions and permit requirements. | Project Engineer | 2020-02-24 | 10 | Expedite | N | N | N | 0 | DSDC – HJH JV | 1 | 2020-03-03 | 8 | Y | 0 | 1 | 2020-03-03 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1006 | P4 – Low
E335-RFI-0119 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – I-405 light rail bridge | Civil and systems drawings differ on grounding/bonding of retaining wall footing for stray-current control at I-405 light rail bridge. Request governing detail and responsibility for installation. | Field Engineer | 2020-02-25 | 10 | Expedite | Y | Y | N | 3 | DSDC – HJH JV | 1 | 2020-03-06 | 10 | Y | 0 | 1 | 2020-03-06 | 10 | Closed | 4 | 0 | 1 | 33000 | 62000 | Y | E335-CO-030 | 45200 | 21200 | 2 | 35.2 | 310 | P2 – High
E335-RFI-0120 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 24-in. sanitary sewer at 110th Ave NE/NE 6th St | Potholing at Sta. 1588+83 located a 24-in. sanitary sewer in conflict with the proposed pedestrian ramp. Utility is not shown on M-256. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Superintendent | 2020-02-27 | 10 | Routine | Y | N | Y | 7 | DSDC – HJH JV | 1 | 2020-03-06 | 8 | Y | 0 | 1 | 2020-03-06 | 8 | Closed | 0 | 0 | 0 | 514000 | 959000 | N |  | 0 | 0 | 0 | 0 | 1007 | P4 – Low
E335-RFI-0121 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – stair core wall at I-405 light rail bridge | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-180 for emergency stair pressurization at I-405 light rail bridge. Request direction on compliant detail. | Superintendent | 2020-03-05 | 10 | Expedite | N | N | N | 1 | ST Design Management | 3 | 2020-03-24 | 19 | N | 9 | 1 | 2020-03-24 | 19 | Closed | 0 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 626 | P3 – Medium
E335-RFI-0122 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – drilled shaft cap at I-405 light rail bridge | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-521 for emergency stair pressurization at I-405 light rail bridge. Request direction on compliant detail. | Superintendent | 2020-03-17 | 10 | Routine | N | N | N | 6 | DSDC – HJH JV | 3 | 2020-04-16 | 30 | N | 20 | 1 | 2020-04-16 | 30 | Closed | 0 | 0 | 11 |  |  | N |  | 0 | 0 | 0 | 2.4 | 498 | P3 – Medium
E335-RFI-0123 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | Property owner access/restoration requirement – I-405 light rail bridge | Adjacent property owner has requested additional restoration and access provisions at I-405 light rail bridge beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Project Engineer | 2020-03-23 | 10 | Routine | Y | N | N | 2 | Puget Sound Energy / ST Third-Party Mgmt | 1 | 2020-03-26 | 3 | Y | 0 | 1 | 2020-03-26 | 3 | Closed | 0 | 0 | 0 | 82000 | 154000 | N |  | 0 | 0 | 0 | 0 | 1008 | P4 – Low
E335-RFI-0124 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Clarify spec requirement – Bellevue Downtown Station | Request clarification of 00 72 00 General Conditions and M-147: dimension/notes appear inconsistent or omitted for the work at Bellevue Downtown Station. | Design Manager | 2020-03-26 | 10 | Urgent | Y | N | N | 0 | ST Design Management | 2 | 2020-03-30 | 3 | Y | 0 | 2 | 2020-04-15 | 20 | Closed | 0 | 0 | 0 | 9000 | 17000 | Y | E335-CO-031 | 16100 | 15300 | 0 | 33.2 | 326 | P2 – High
E335-RFI-0125 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Wilburton Station: soft lacustrine silt below design subgrade | During excavation at Wilburton Station (Sta. 1917+93) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or C-445. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Project Engineer | 2020-04-10 | 10 | Routine | Y | Y | Y | 4 | ST Design Management | 2 | 2020-04-15 | 5 | Y | 0 | 1 | 2020-04-15 | 5 | Closed | 7 | 6 | 0 | 476000 | 888000 | Y | E335-CO-032 | 673100 | 256700 | 3 | 49.9 | 59 | P1 – Critical
E335-RFI-0126 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Drawing/spec discrepancy – Wilburton Station | Request clarification of 01 25 00 Substitution Procedures and C-684: dimension/notes appear inconsistent or omitted for the work at Wilburton Station. | Project Engineer | 2020-04-15 | 10 | Urgent | N | N | N | 7 | ST Design Management | 1 | 2020-04-20 | 4 | Y | 0 | 1 | 2020-04-20 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1009 | P4 – Low
E335-RFI-0127 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – drilled shaft cap at East Main Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-480 for standpipe connection at East Main Station. Request direction on compliant detail. | Scheduler | 2020-04-28 | 10 | Urgent | N | N | Y | 8 | DSDC – HJH JV | 6 | 2020-05-07 | 9 | Y | 0 | 1 | 2020-05-07 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1010 | P4 – Low
E335-RFI-0128 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Dimensional discrepancy – East Main Station | C-640 shows a 18 ft-5 in. dimension for the drilled shaft cap; structural sheet S-454 shows a different value. Request clarification before fabrication/rebar release. | Project Manager | 2020-05-15 | 10 | Routine | N | N | N | 5 | DSDC – HJH JV | 2 | 2020-05-25 | 10 | Y | 0 | 1 | 2020-05-25 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1011 | P4 – Low
E335-RFI-0129 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – drilled shaft cap sequence at 110th Ave NE/NE 6th St | Erection of the drilled shaft cap as drawn conflicts with adjacent work and access limits at 110th Ave NE/NE 6th St. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Field Engineer | 2020-05-21 | 10 | Expedite | N | N | Y | 4 | DSDC – HJH JV | 1 | 2020-05-28 | 7 | Y | 0 | 1 | 2020-05-28 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1012 | P4 – Low
E335-RFI-0130 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Dimensional discrepancy – I-405 light rail bridge | E-437 shows a 56 ft-10 in. dimension for the column reinforcement; structural sheet S-895 shows a different value. Request clarification before fabrication/rebar release. | Field Engineer | 2020-05-26 | 10 | Routine | Y | Y | N | 8 | DSDC – HJH JV | 2 | 2020-06-08 | 13 | N | 3 | 1 | 2020-06-08 | 13 | Closed | 11 | 0 | 6 | 39000 | 72000 | N |  | 0 | 0 | 0 | 1.3 | 565 | P3 – Medium
E335-RFI-0131 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – guideway girder diaphragm at NE 12th St guideway | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-208 for smoke control damper at NE 12th St guideway. Request direction on compliant detail. | Field Engineer | 2020-05-26 | 10 | Routine | N | N | Y | 1 | DSDC – HJH JV | 3 | 2020-06-08 | 11 | N | 1 | 1 | 2020-06-08 | 11 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1013 | P4 – Low
E335-RFI-0132 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | Wetland/stream buffer protection – Bellevue Downtown Station | Field conditions at Bellevue Downtown Station require changes to temporary erosion and sediment control or stormwater facility per C-563. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2020-05-27 | 10 | Routine | N | N | N | 5 | DSDC – HJH JV | 6 | 2020-06-09 | 13 | N | 3 | 1 | 2020-06-09 | 13 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1014 | P4 – Low
E335-RFI-0133 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Spring District/120th Station: soft lacustrine silt below design subgrade | During excavation at Spring District/120th Station (Sta. 1638+34) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or C-748. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Design Manager | 2020-06-05 | 10 | Routine | Y | Y | Y | 4 | ST Design Management | 3 | 2020-06-11 | 6 | Y | 0 | 1 | 2020-06-11 | 6 | Closed | 12 | 5 | 0 | 753000 | 1405000 | N |  | 0 | 0 | 0 | 5 | 437 | P3 – Medium
E335-RFI-0134 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with abandoned utility vault at Bellevue Downtown Station | Potholing at Sta. 1139+31 located a abandoned utility vault in conflict with the proposed guideway girder diaphragm. Utility is not shown on E-381. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Field Engineer | 2020-06-05 | 10 | Urgent | N | Y | N | 5 | DSDC – HJH JV | 1 | 2020-06-09 | 4 | Y | 0 | 1 | 2020-06-09 | 4 | Closed | 6 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 664 | P3 – Medium
E335-RFI-0135 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – guideway girder diaphragm sequence at NE 12th St guideway | Erection of the guideway girder diaphragm as drawn conflicts with adjacent work and access limits at NE 12th St guideway. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Superintendent | 2020-06-08 | 10 | Routine | Y | N | N | 4 | DSDC – HJH JV | 2 | 2020-06-19 | 11 | N | 1 | 1 | 2020-06-19 | 11 | Closed | 0 | 0 | 0 | 149000 | 278000 | N |  | 0 | 0 | 0 | 0 | 1015 | P4 – Low
E335-RFI-0136 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Canopy/glazing connection – Spring District/120th Station | Request to clarify finish/connection detail on C-414 at Spring District/120th Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Superintendent | 2020-06-15 | 10 | Routine | Y | N | N | 7 | DSDC – HJH JV | 1 | 2020-06-23 | 8 | Y | 0 | 2 | 2020-07-13 | 28 | Closed | 0 | 0 | 0 | 116000 | 216000 | N |  | 0 | 0 | 0 | 0 | 1016 | P4 – Low
E335-RFI-0137 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – drilled shaft cap at Spring District/120th Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-783 for smoke control damper at Spring District/120th Station. Request direction on compliant detail. | Superintendent | 2020-06-22 | 10 | Routine | Y | N | Y | 0 | DSDC – HJH JV | 1 | 2020-06-29 | 6 | Y | 0 | 1 | 2020-06-29 | 6 | Closed | 0 | 0 | 0 | 604000 | 1127000 | N |  | 0 | 0 | 0 | 0 | 1017 | P4 – Low
E335-RFI-0138 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | Property owner access/restoration requirement – NE 12th St guideway | Adjacent property owner has requested additional restoration and access provisions at NE 12th St guideway beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Project Manager | 2020-06-22 | 10 | Routine | N | N | Y | 7 | Puget Sound Energy / ST Third-Party Mgmt | 3 | 2020-07-02 | 10 | Y | 0 | 2 | 2020-07-23 | 31 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1018 | P4 – Low
E335-RFI-0139 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Puget Sound Energy comment on street improvement permit – 110th Ave NE/NE 6th St | Puget Sound Energy review comments on the street improvement permit require changes to the duct bank encasement at 110th Ave NE/NE 6th St. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2020-06-22 | 10 | Urgent | Y | Y | Y | 1 | WSDOT / ST Third-Party Mgmt | 2 | 2020-07-02 | 10 | Y | 0 | 1 | 2020-07-02 | 10 | Closed | 12 | 9 | 0 | 52000 | 97000 | Y | E335-CO-033 | 40000 | 29800 | 4 | 45.8 | 127 | P2 – High
E335-RFI-0140 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Fiber Backbone location conflict at Sta. 1577+17 | Proposed fiber backbone foundation location at Sta. 1577+17 conflicts with guideway girder diaphragm; offset of 11 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2020-06-22 | 10 | Urgent | Y | Y | Y | 5 | DSDC – HJH JV | 1 | 2020-06-29 | 5 | Y | 0 | 2 | 2020-07-13 | 19 | Closed | 66 | 28 | 0 | 79000 | 148000 | N |  | 0 | 0 | 0 | 28 | 349 | P3 – Medium
E335-RFI-0141 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | City of Bellevue comment on building permit – Spring District/120th Station | City of Bellevue review comments on the building permit require changes to the duct bank encasement at Spring District/120th Station. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2020-06-23 | 10 | Routine | N | N | N | 7 | Puget Sound Energy / ST Third-Party Mgmt | 2 | 2020-07-07 | 14 | N | 4 | 2 | 2020-07-20 | 27 | Closed | 0 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 780 | P4 – Low
E335-RFI-0142 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Wilburton Station: buried concrete debris and an old foundation | During excavation at Wilburton Station (Sta. 2231+44) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or M-566. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Field Engineer | 2020-06-29 | 10 | Expedite | Y | Y | N | 5 | DSDC – HJH JV | 1 | 2020-07-06 | 5 | Y | 0 | 1 | 2020-07-06 | 5 | Closed | 6 | 0 | 4 | 787000 | 1469000 | Y | E335-CO-034 | 1113500 | 0 | 0 | 0.9 | 627 | P3 – Medium
E335-RFI-0143 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Crane staging in right-of-way – I-405 light rail bridge | Contractor requests approval of an alternate traffic/staging plan at I-405 light rail bridge: extended night closure. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Scheduler | 2020-07-03 | 10 | Routine | N | Y | Y | 5 | DSDC – HJH JV | 3 | 2020-07-13 | 10 | Y | 0 | 1 | 2020-07-13 | 10 | Closed | 26 | 15 | 0 |  |  | N |  | 0 | 0 | 0 | 15 | 371 | P3 – Medium
E335-RFI-0144 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Bellevue Downtown Station: an unmapped abandoned storm line | During excavation at Bellevue Downtown Station (Sta. 1405+10) the contractor encountered an unmapped abandoned storm line, not shown on the GBR or M-579. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Project Manager | 2020-07-06 | 10 | Urgent | Y | N | N | 3 | ST Design Management | 1 | 2020-07-15 | 9 | Y | 0 | 1 | 2020-07-15 | 9 | Closed | 0 | 0 | 0 | 21000 | 40000 | Y | E335-CO-035 | 46800 | 16100 | 0 | 33.4 | 324 | P2 – High
E335-RFI-0145 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 24-in. sanitary sewer at NE 12th St guideway | Potholing at Sta. 1195+72 located a 24-in. sanitary sewer in conflict with the proposed drilled shaft cap. Utility is not shown on M-155. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Engineer | 2020-07-15 | 10 | Urgent | N | Y | Y | 6 | DSDC – HJH JV | 1 | 2020-07-23 | 8 | Y | 0 | 1 | 2020-07-23 | 8 | Closed | 3 | 2 | 0 |  |  | N |  | 0 | 0 | 0 | 2 | 515 | P3 – Medium
E335-RFI-0146 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 24-in. sanitary sewer at NE 12th St guideway | Potholing at Sta. 1006+65 located a 24-in. sanitary sewer in conflict with the proposed retaining wall footing. Utility is not shown on C-812. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Engineer | 2020-07-29 | 10 | Routine | Y | Y | N | 1 | ST Design Management | 2 | 2020-08-10 | 12 | N | 2 | 1 | 2020-08-10 | 12 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1019 | P4 – Low
E335-RFI-0147 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Drawing/spec discrepancy – Bellevue Downtown Station | Request clarification of 01 25 00 Substitution Procedures and M-557: dimension/notes appear inconsistent or omitted for the work at Bellevue Downtown Station. | Project Engineer | 2020-07-30 | 10 | Routine | N | N | N | 7 | ST Design Management | 3 | 2020-08-03 | 3 | Y | 0 | 1 | 2020-08-03 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1020 | P4 – Low
E335-RFI-0148 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – retaining wall footing and station canopy support at NE 12th St guideway | Interference between retaining wall footing and station canopy support at NE 12th St guideway per E-367. Required clearance of 8 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Field Engineer | 2020-08-06 | 10 | Urgent | Y | Y | Y | 3 | DSDC – HJH JV | 1 | 2020-08-21 | 15 | N | 5 | 1 | 2020-08-21 | 15 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1021 | P4 – Low
E335-RFI-0149 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Property owner access/restoration requirement – Wilburton Station | Adjacent property owner has requested additional restoration and access provisions at Wilburton Station beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Superintendent | 2020-08-17 | 10 | Urgent | N | Y | Y | 4 | WSDOT / ST Third-Party Mgmt | 1 | 2020-08-27 | 10 | Y | 0 | 1 | 2020-08-27 | 10 | Closed | 26 | 16 | 0 |  |  | N |  | 0 | 0 | 0 | 16 | 365 | P3 – Medium
E335-RFI-0150 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – platform edge slab and guideway girder diaphragm at East Main Station | Interference between platform edge slab and guideway girder diaphragm at East Main Station per S-256. Required clearance of 4 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Field Engineer | 2020-08-20 | 10 | Routine | Y | Y | N | 6 | DSDC – HJH JV | 2 | 2020-08-31 | 9 | Y | 0 | 1 | 2020-08-31 | 9 | Closed | 6 | 0 | 3 | 157000 | 294000 | N |  | 0 | 0 | 0 | 0.7 | 665 | P3 – Medium
E335-RFI-0151 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at East Main Station: perched groundwater | During excavation at East Main Station (Sta. 1567+60) the contractor encountered perched groundwater at approx. elevation 221 ft, not shown on the GBR or A-128. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Project Manager | 2020-08-31 | 10 | Urgent | Y | N | Y | 7 | DSDC – HJH JV | 3 | 2020-09-04 | 4 | Y | 0 | 1 | 2020-09-04 | 4 | Closed | 0 | 0 | 0 | 2297000 | 4287000 | N |  | 0 | 0 | 0 | 0 | 1022 | P4 – Low
E335-RFI-0152 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Track slab/expansion joint interface – Bellevue Downtown Station | Track layout at Sta. 1813+86 (Bellevue Downtown Station) differs from the track-structure interface drawing E-632. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Engineer | 2020-09-07 | 10 | Routine | N | Y | N | 0 | DSDC – HJH JV | 1 | 2020-09-14 | 6 | Y | 0 | 1 | 2020-09-14 | 6 | Closed | 13 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 628 | P3 – Medium
E335-RFI-0153 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – Spring District/120th Station | S-122 shows a 36 ft-3 in. dimension for the bearing pad/embed plate; structural sheet S-846 shows a different value. Request clarification before fabrication/rebar release. | Design Manager | 2020-09-07 | 10 | Expedite | Y | Y | N | 3 | DSDC – HJH JV | 1 | 2020-09-16 | 9 | Y | 0 | 1 | 2020-09-16 | 9 | Closed | 8 | 0 | 3 | 66000 | 123000 | Y | E335-CO-036 | 60200 | 60200 | 4 | 39.9 | 240 | P2 – High
E335-RFI-0154 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Station finish detail – East Main Station | Request to clarify finish/connection detail on A-434 at East Main Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2020-09-22 | 10 | Routine | N | N | N | 3 | DSDC – HJH JV | 3 | 2020-10-01 | 9 | Y | 0 | 2 | 2020-10-14 | 22 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1023 | P4 – Low
E335-RFI-0155 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Property owner access/restoration requirement – NE 12th St guideway | Adjacent property owner has requested additional restoration and access provisions at NE 12th St guideway beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Field Engineer | 2020-10-05 | 10 | Routine | N | Y | N | 8 | Puget Sound Energy / ST Third-Party Mgmt | 1 | 2020-10-23 | 18 | N | 8 | 1 | 2020-10-23 | 18 | Closed | 5 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 713 | P3 – Medium
E335-RFI-0156 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 8-in. high-pressure gas main at I-405 light rail bridge | Potholing at Sta. 1926+11 located a 8-in. high-pressure gas main in conflict with the proposed stair core wall. Utility is not shown on E-362. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Engineer | 2020-10-14 | 10 | Routine | Y | Y | N | 0 | DSDC – HJH JV | 2 | 2020-10-20 | 6 | Y | 0 | 1 | 2020-10-20 | 6 | Closed | 3 | 0 | 1 | 90000 | 169000 | N |  | 0 | 0 | 0 | 0.2 | 781 | P4 – Low
E335-RFI-0157 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – stair core wall and drilled shaft cap at Bellevue Downtown Station | Interference between stair core wall and drilled shaft cap at Bellevue Downtown Station per E-736. Required clearance of 2 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Engineer | 2020-10-19 | 10 | Expedite | N | N | Y | 7 | DSDC – HJH JV | 2 | 2020-10-27 | 8 | Y | 0 | 1 | 2020-10-27 | 8 | Closed | 0 | 4 | 0 |  |  | N |  | 0 | 0 | 0 | 4 | 452 | P3 – Medium
E335-RFI-0158 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Bellevue Downtown Station | E-676 shows a 45 ft-4 in. dimension for the platform edge slab; structural sheet S-872 shows a different value. Request clarification before fabrication/rebar release. | Field Engineer | 2020-10-19 | 10 | Urgent | Y | N | N | 2 | DSDC – HJH JV | 1 | 2020-10-23 | 4 | Y | 0 | 1 | 2020-10-23 | 4 | Closed | 0 | 0 | 0 | 125000 | 234000 | N |  | 0 | 0 | 0 | 0 | 1024 | P4 – Low
E335-RFI-0159 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – station canopy support sequence at NE 12th St guideway | Erection of the station canopy support as drawn conflicts with adjacent work and access limits at NE 12th St guideway. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2020-10-26 | 10 | Routine | N | N | N | 3 | ST Design Management | 3 | 2020-11-27 | 32 | N | 22 | 1 | 2020-11-27 | 32 | Closed | 0 | 0 | 9 |  |  | N |  | 0 | 0 | 0 | 2 | 516 | P3 – Medium
E335-RFI-0160 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Tunnel Emergency Phone location conflict at Sta. 1837+78 | Proposed tunnel emergency phone foundation location at Sta. 1837+78 conflicts with pedestrian ramp; offset of 4 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Scheduler | 2020-11-02 | 10 | Routine | N | Y | N | 2 | ST Design Management | 2 | 2020-11-09 | 7 | Y | 0 | 2 | 2020-11-19 | 17 | Closed | 8 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 666 | P3 – Medium
E335-RFI-0161 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Bellevue Downtown Station | C-419 shows a 35 ft-7 in. dimension for the pedestrian ramp; structural sheet S-551 shows a different value. Request clarification before fabrication/rebar release. | Superintendent | 2020-11-02 | 10 | Routine | N | N | N | 0 | DSDC – HJH JV | 2 | 2020-11-13 | 11 | N | 1 | 1 | 2020-11-13 | 11 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1025 | P4 – Low
E335-RFI-0162 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Bellevue Downtown Station: abandoned timber piles | During excavation at Bellevue Downtown Station (Sta. 1768+55) the contractor encountered abandoned timber piles, not shown on the GBR or M-450. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Superintendent | 2020-11-02 | 10 | Routine | Y | N | N | 3 | DSDC – HJH JV | 3 | 2020-11-12 | 10 | Y | 0 | 2 | 2020-11-19 | 17 | Closed | 0 | 0 | 0 | 266000 | 496000 | N |  | 0 | 0 | 0 | 0 | 1026 | P4 – Low
E335-RFI-0163 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – drilled shaft cap at I-405 light rail bridge | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-369 for fire alarm device layout at I-405 light rail bridge. Request direction on compliant detail. | Design Manager | 2020-11-06 | 10 | Expedite | Y | Y | Y | 0 | ST Design Management | 2 | 2020-12-02 | 26 | N | 16 | 1 | 2020-12-02 | 26 | Closed | 6 | 9 | 0 | 59000 | 110000 | N |  | 0 | 0 | 0 | 9 | 401 | P3 – Medium
E335-RFI-0164 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – Spring District/120th Station | S-608 shows a 40 ft-7 in. dimension for the station canopy support; structural sheet S-753 shows a different value. Request clarification before fabrication/rebar release. | Field Engineer | 2020-11-09 | 10 | Urgent | N | Y | Y | 0 | DSDC – HJH JV | 1 | 2020-11-16 | 6 | Y | 0 | 1 | 2020-11-16 | 6 | Closed | 30 | 21 | 0 |  |  | N |  | 0 | 0 | 0 | 21 | 358 | P3 – Medium
E335-RFI-0165 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 8-in. high-pressure gas main at NE 12th St guideway | Potholing at Sta. 960+79 located a 8-in. high-pressure gas main in conflict with the proposed retaining wall footing. Utility is not shown on A-441. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Scheduler | 2020-11-10 | 10 | Routine | N | N | N | 0 | DSDC – HJH JV | 3 | 2020-11-16 | 6 | Y | 0 | 1 | 2020-11-16 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1027 | P4 – Low
E335-RFI-0166 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – platform edge slab and station canopy support at NE 12th St guideway | Interference between platform edge slab and station canopy support at NE 12th St guideway per A-592. Required clearance of 7 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2020-11-12 | 10 | Urgent | Y | N | N | 5 | ST Design Management | 2 | 2020-11-25 | 13 | N | 3 | 2 | 2020-12-14 | 32 | Closed | 0 | 0 | 2 | 409000 | 764000 | N |  | 0 | 0 | 0 | 0.4 | 714 | P3 – Medium
E335-RFI-0167 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at I-405 light rail bridge: buried concrete debris and an old foundation | During excavation at I-405 light rail bridge (Sta. 1702+35) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or M-697. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Field Engineer | 2020-11-18 | 10 | Expedite | Y | Y | N | 4 | DSDC – HJH JV | 1 | 2020-12-25 | 37 | N | 27 | 1 | 2020-12-25 | 37 | Closed | 22 | 0 | 9 | 688000 | 1284000 | Y | E335-CO-037 | 1052910 | 705610 | 40.4 | 58.4 | 20 | P1 – Critical
E335-RFI-0168 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at 110th Ave NE/NE 6th St: abandoned timber piles | During excavation at 110th Ave NE/NE 6th St (Sta. 1294+37) the contractor encountered abandoned timber piles, not shown on the GBR or C-473. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Project Manager | 2020-11-30 | 10 | Urgent | Y | Y | Y | 5 | DSDC – HJH JV | 3 | 2020-12-07 | 5 | Y | 0 | 1 | 2020-12-07 | 5 | Closed | 55 | 48 | 0 | 286000 | 535000 | Y | E335-CO-037 | 274690 | 184090 | 10.6 | 75.3 | 3 | P1 – Critical
E335-RFI-0169 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – 110th Ave NE/NE 6th St | Systems contractor requires 3-in. PVC conduit stub-ups for traction power feeder at 110th Ave NE/NE 6th St not provided in civil A-472. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Project Engineer | 2020-12-16 | 10 | Expedite | N | Y | N | 4 | DSDC – HJH JV | 4 | 2020-12-31 | 15 | N | 5 | 1 | 2020-12-31 | 15 | Closed | 9 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 667 | P3 – Medium
E335-RFI-0170 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | City of Bellevue comment on right-of-way use permit – Wilburton Station | City of Bellevue review comments on the right-of-way use permit require changes to the drilled shaft cap at Wilburton Station. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2020-12-24 | 10 | Routine | N | N | N | 0 | City of Bellevue / ST Third-Party Mgmt | 4 | 2021-01-04 | 11 | N | 1 | 1 | 2021-01-04 | 11 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1028 | P4 – Low
E335-RFI-0171 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bellevue Downtown Station: perched groundwater | During excavation at Bellevue Downtown Station (Sta. 1131+65) the contractor encountered perched groundwater at approx. elevation 44 ft, not shown on the GBR or E-215. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Project Manager | 2020-12-31 | 10 | Routine | Y | Y | Y | 1 | DSDC – HJH JV | 3 | 2021-01-12 | 12 | N | 2 | 1 | 2021-01-12 | 12 | Closed | 12 | 10 | 0 | 1986000 | 3708000 | Y | E335-CO-039 | 2554000 | 2015570 | 11.5 | 63.8 | 13 | P1 – Critical
E335-RFI-0172 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Spring District/120th Station: buried concrete debris and an old foundation | During excavation at Spring District/120th Station (Sta. 1388+18) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or A-436. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Scheduler | 2021-01-18 | 10 | Routine | Y | Y | N | 5 | DSDC – HJH JV | 1 | 2021-02-01 | 13 | N | 3 | 1 | 2021-02-01 | 13 | Closed | 15 | 0 | 8 | 173000 | 323000 | Y | E335-CO-039 | 157300 | 124140 | 0.7 | 42.4 | 193 | P2 – High
E335-RFI-0173 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Canopy/glazing connection – Bellevue Downtown Station | Request to clarify finish/connection detail on S-733 at Bellevue Downtown Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2021-01-19 | 10 | Routine | N | N | N | 1 | DSDC – HJH JV | 1 | 2021-01-22 | 3 | Y | 0 | 1 | 2021-01-22 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1029 | P4 – Low
E335-RFI-0174 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – NE 12th St guideway | E-584 shows a 47 ft-7 in. dimension for the stair core wall; structural sheet S-560 shows a different value. Request clarification before fabrication/rebar release. | Field Engineer | 2021-01-21 | 10 | Routine | Y | Y | Y | 1 | DSDC – HJH JV | 2 | 2021-01-25 | 4 | Y | 0 | 2 | 2021-02-08 | 16 | Closed | 31 | 21 | 0 | 36000 | 66000 | Y | E335-CO-040 | 53210 | 53210 | 2.1 | 59.2 | 19 | P1 – Critical
E335-RFI-0175 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – pedestrian ramp at Spring District/120th Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-340 for smoke control damper at Spring District/120th Station. Request direction on compliant detail. | Design Manager | 2021-01-25 | 10 | Urgent | N | N | Y | 8 | DSDC – HJH JV | 3 | 2021-02-01 | 6 | Y | 0 | 1 | 2021-02-01 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1030 | P4 – Low
E335-RFI-0176 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Dimensional discrepancy – Bellevue Downtown Station | E-565 shows a 52 ft-9 in. dimension for the stair core wall; structural sheet S-823 shows a different value. Request clarification before fabrication/rebar release. | Superintendent | 2021-01-29 | 10 | Urgent | Y | Y | Y | 3 | DSDC – HJH JV | 2 | 2021-02-15 | 15 | N | 5 | 1 | 2021-02-15 | 15 | Closed | 17 | 14 | 0 | 22000 | 41000 | Y | E335-CO-038 | 48900 | 24200 | 9 | 51.8 | 41 | P1 – Critical
E335-RFI-0177 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bellevue Downtown Station: glacially deposited boulders exceeding 36 in. | During excavation at Bellevue Downtown Station (Sta. 2058+61) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or C-831. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Superintendent | 2021-02-11 | 10 | Routine | Y | Y | N | 2 | DSDC – HJH JV | 2 | 2021-02-17 | 6 | Y | 0 | 1 | 2021-02-17 | 6 | Closed | 4 | 0 | 3 | 913000 | 1705000 | Y | E335-CO-039 | 1104970 | 872030 | 5 | 49.5 | 67 | P1 – Critical
E335-RFI-0178 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Wilburton Station: abandoned timber piles | During excavation at Wilburton Station (Sta. 2355+09) the contractor encountered abandoned timber piles, not shown on the GBR or E-223. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Design Manager | 2021-03-03 | 10 | Routine | Y | Y | N | 7 | DSDC – HJH JV | 3 | 2021-03-08 | 4 | Y | 0 | 1 | 2021-03-08 | 4 | Closed | 10 | 0 | 7 | 518000 | 967000 | Y | E335-CO-039 | 630730 | 497760 | 2.8 | 47.7 | 96 | P1 – Critical
E335-RFI-0179 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – guideway girder diaphragm and bearing pad/embed plate at NE 12th St guideway | Interference between guideway girder diaphragm and bearing pad/embed plate at NE 12th St guideway per M-220. Required clearance of 6 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2021-03-22 | 10 | Routine | Y | N | N | 7 | DSDC – HJH JV | 1 | 2021-04-01 | 10 | Y | 0 | 2 | 2021-04-14 | 23 | Closed | 0 | 0 | 0 | 347000 | 648000 | Y | E335-CO-040 | 521490 | 521490 | 20.9 | 52.3 | 38 | P1 – Critical
E335-RFI-0180 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – bearing pad/embed plate and pedestrian ramp at Wilburton Station | Interference between bearing pad/embed plate and pedestrian ramp at Wilburton Station per C-705. Required clearance of 4 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2021-04-05 | 10 | Routine | N | Y | N | 0 | DSDC – HJH JV | 1 | 2021-04-09 | 4 | Y | 0 | 1 | 2021-04-09 | 4 | Closed | 1 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1031 | P4 – Low
E335-RFI-0181 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 12-in. ductile iron water main at East Main Station | Potholing at Sta. 1805+53 located a 12-in. ductile iron water main in conflict with the proposed stair core wall. Utility is not shown on S-309. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Field Engineer | 2021-04-19 | 10 | Urgent | N | N | Y | 6 | DSDC – HJH JV | 2 | 2021-04-22 | 3 | Y | 0 | 1 | 2021-04-22 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1032 | P4 – Low
E335-RFI-0182 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Canopy/glazing connection – Bellevue Downtown Station | Request to clarify finish/connection detail on C-698 at Bellevue Downtown Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Manager | 2021-04-19 | 10 | Urgent | N | N | N | 0 | DSDC – HJH JV | 1 | 2021-04-26 | 5 | Y | 0 | 1 | 2021-04-26 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1033 | P4 – Low
E335-RFI-0183 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Lane closure window request – NE 12th St guideway | Contractor requests approval of an alternate traffic/staging plan at NE 12th St guideway: crane pick over active roadway. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Superintendent | 2021-04-27 | 10 | Urgent | N | N | N | 5 | DSDC – HJH JV | 2 | 2021-05-03 | 6 | Y | 0 | 1 | 2021-05-03 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1034 | P4 – Low
E335-RFI-0184 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 8-in. high-pressure gas main at East Main Station | Potholing at Sta. 1200+04 located a 8-in. high-pressure gas main in conflict with the proposed guideway girder diaphragm. Utility is not shown on C-407. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Engineer | 2021-05-25 | 10 | Routine | Y | Y | N | 8 | DSDC – HJH JV | 2 | 2021-06-07 | 13 | N | 3 | 1 | 2021-06-07 | 13 | Closed | 6 | 0 | 3 | 223000 | 416000 | N |  | 0 | 0 | 0 | 0.7 | 668 | P3 – Medium
E335-RFI-0185 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Station finish detail – 110th Ave NE/NE 6th St | Request to clarify finish/connection detail on A-660 at 110th Ave NE/NE 6th St. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2021-06-07 | 10 | Expedite | N | N | N | 1 | DSDC – HJH JV | 2 | 2021-06-14 | 6 | Y | 0 | 1 | 2021-06-14 | 6 | Closed | 0 | 0 | 0 |  |  | Y | E335-CO-041 | 19700 | 9400 | 0 | 31.5 | 337 | P2 – High
E335-RFI-0186 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | Property owner access/restoration requirement – Bellevue Downtown Station | Adjacent property owner has requested additional restoration and access provisions at Bellevue Downtown Station beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Superintendent | 2021-06-08 | 10 | Routine | Y | Y | Y | 3 | WSDOT / ST Third-Party Mgmt | 1 | 2021-06-17 | 9 | Y | 0 | 1 | 2021-06-17 | 9 | Closed | 54 | 18 | 0 | 76000 | 142000 | N |  | 0 | 0 | 0 | 18 | 364 | P3 – Medium
E335-RFI-0187 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Puget Sound Energy comment on street improvement permit – Bellevue Downtown Station | Puget Sound Energy review comments on the street improvement permit require changes to the platform edge slab at Bellevue Downtown Station. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2021-06-11 | 10 | Routine | N | N | Y | 3 | City of Bellevue / ST Third-Party Mgmt | 4 | 2021-06-21 | 9 | Y | 0 | 1 | 2021-06-21 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1035 | P4 – Low
E335-RFI-0188 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with PSE distribution duct bank at NE 12th St guideway | Potholing at Sta. 2101+37 located a PSE distribution duct bank in conflict with the proposed guideway girder diaphragm. Utility is not shown on C-669. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Project Engineer | 2021-06-14 | 10 | Routine | Y | N | N | 5 | DSDC – HJH JV | 2 | 2021-06-21 | 5 | Y | 0 | 1 | 2021-06-21 | 5 | Closed | 0 | 0 | 0 | 175000 | 327000 | Y | E335-CO-042 | 402000 | 302100 | 0 | 43.5 | 168 | P2 – High
E335-RFI-0189 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – platform edge slab sequence at Spring District/120th Station | Erection of the platform edge slab as drawn conflicts with adjacent work and access limits at Spring District/120th Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Project Engineer | 2021-07-16 | 10 | Routine | Y | Y | N | 6 | DSDC – HJH JV | 2 | 2021-07-19 | 3 | Y | 0 | 1 | 2021-07-19 | 3 | Closed | 1 | 0 | 0 | 345000 | 643000 | Y | E335-CO-043 | 297600 | 168100 | 0 | 41.5 | 208 | P2 – High
E335-RFI-0190 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at I-405 light rail bridge: loose granular fill below planned bearing elevation | During excavation at I-405 light rail bridge (Sta. 1131+84) the contractor encountered loose granular fill below planned bearing elevation, not shown on the GBR or E-426. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Superintendent | 2021-08-02 | 10 | Routine | Y | Y | N | 0 | DSDC – HJH JV | 1 | 2021-08-09 | 7 | Y | 0 | 1 | 2021-08-09 | 7 | Closed | 28 | 0 | 19 | 519000 | 969000 | N |  | 0 | 0 | 0 | 4.2 | 448 | P3 – Medium
E335-RFI-0191 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – column reinforcement sequence at Spring District/120th Station | Erection of the column reinforcement as drawn conflicts with adjacent work and access limits at Spring District/120th Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2021-08-05 | 10 | Routine | N | N | N | 7 | DSDC – HJH JV | 4 | 2021-08-30 | 25 | N | 15 | 1 | 2021-08-30 | 25 | Closed | 0 | 0 | 6 |  |  | N |  | 0 | 0 | 0 | 1.3 | 566 | P3 – Medium
E335-RFI-0192 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Scada Cabinet location conflict at Sta. 1525+77 | Proposed SCADA cabinet foundation location at Sta. 1525+77 conflicts with guideway girder diaphragm; offset of 6 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Field Engineer | 2021-08-06 | 10 | Routine | N | N | Y | 5 | DSDC – HJH JV | 4 | 2021-08-23 | 15 | N | 5 | 1 | 2021-08-23 | 15 | Closed | 0 | 1 | 0 |  |  | N |  | 0 | 0 | 0 | 1 | 608 | P3 – Medium
E335-RFI-0193 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – NE 12th St guideway | Systems contractor requires 3-in. PVC conduit stub-ups for rail bonding at NE 12th St guideway not provided in civil C-254. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Scheduler | 2021-08-09 | 10 | Routine | Y | N | N | 0 | DSDC – HJH JV | 2 | 2021-09-03 | 25 | N | 15 | 1 | 2021-09-03 | 25 | Closed | 0 | 0 | 0 | 13000 | 24000 | Y | E335-CO-044 | 30800 | 24800 | 0 | 34.9 | 313 | P2 – High
E335-RFI-0194 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with PSE distribution duct bank at NE 12th St guideway | Potholing at Sta. 2164+00 located a PSE distribution duct bank in conflict with the proposed duct bank encasement. Utility is not shown on S-767. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Engineer | 2021-08-13 | 10 | Routine | N | N | N | 0 | ST Design Management | 2 | 2021-08-20 | 7 | Y | 0 | 1 | 2021-08-20 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1036 | P4 – Low
E335-RFI-0195 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Art embed coordination – East Main Station | Request to clarify finish/connection detail on M-569 at East Main Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Field Engineer | 2021-08-16 | 10 | Routine | N | N | N | 1 | DSDC – HJH JV | 2 | 2021-08-24 | 8 | Y | 0 | 2 | 2021-09-09 | 24 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1037 | P4 – Low
E335-RFI-0196 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 30-in. storm drain at Wilburton Station | Potholing at Sta. 1096+57 located a 30-in. storm drain in conflict with the proposed duct bank encasement. Utility is not shown on M-276. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Design Manager | 2021-08-30 | 10 | Routine | Y | N | Y | 0 | DSDC – HJH JV | 2 | 2021-09-07 | 8 | Y | 0 | 1 | 2021-09-07 | 8 | Closed | 0 | 0 | 0 | 2131000 | 3979000 | Y | E335-CO-045 | 1436120 | 1078880 | 5.9 | 49.8 | 63 | P1 – Critical
E335-RFI-0197 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | City of Bellevue comment on building permit – Bellevue Downtown Station | City of Bellevue review comments on the building permit require changes to the pedestrian ramp at Bellevue Downtown Station. Request direction on scope impacts and whether comments are within the contract requirements. | Project Engineer | 2021-09-03 | 10 | Routine | Y | Y | Y | 4 | City of Bellevue / ST Third-Party Mgmt | 3 | 2021-11-05 | 63 | N | 53 | 1 | 2021-11-05 | 63 | Closed | 7 | 26 | 0 | 55000 | 103000 | N |  | 0 | 0 | 0 | 26 | 350 | P3 – Medium
E335-RFI-0198 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Puget Sound Energy comment on right-of-way use permit – 110th Ave NE/NE 6th St | Puget Sound Energy review comments on the right-of-way use permit require changes to the retaining wall footing at 110th Ave NE/NE 6th St. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2021-09-08 | 10 | Routine | N | N | Y | 7 | Puget Sound Energy / ST Third-Party Mgmt | 4 | 2021-09-16 | 8 | Y | 0 | 1 | 2021-09-16 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1038 | P4 – Low
E335-RFI-0199 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Haul route revision – Spring District/120th Station | Contractor requests approval of an alternate traffic/staging plan at Spring District/120th Station: crane pick over active roadway. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Scheduler | 2021-09-20 | 10 | Routine | N | N | N | 7 | DSDC – HJH JV | 1 | 2021-09-23 | 3 | Y | 0 | 1 | 2021-09-23 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1039 | P4 – Low
E335-RFI-0200 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 30-in. storm drain at NE 12th St guideway | Potholing at Sta. 1255+45 located a 30-in. storm drain in conflict with the proposed stair core wall. Utility is not shown on S-551. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Project Engineer | 2021-09-27 | 10 | Routine | N | Y | Y | 5 | DSDC – HJH JV | 1 | 2021-10-04 | 6 | Y | 0 | 1 | 2021-10-04 | 6 | Closed | 8 | 6 | 0 |  |  | Y | E335-CO-045 | 14280 | 10720 | 0.1 | 38 | 275 | P2 – High
E335-RFI-0201 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – column reinforcement sequence at 110th Ave NE/NE 6th St | Erection of the column reinforcement as drawn conflicts with adjacent work and access limits at 110th Ave NE/NE 6th St. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Scheduler | 2021-09-27 | 10 | Routine | N | Y | Y | 1 | DSDC – HJH JV | 2 | 2021-10-07 | 10 | Y | 0 | 1 | 2021-10-07 | 10 | Closed | 15 | 6 | 0 |  |  | N |  | 0 | 0 | 0 | 6 | 422 | P3 – Medium
E335-RFI-0202 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – I-405 light rail bridge | M-258 shows a 33 ft-5 in. dimension for the column reinforcement; structural sheet S-589 shows a different value. Request clarification before fabrication/rebar release. | Field Engineer | 2021-09-29 | 10 | Routine | N | N | N | 2 | DSDC – HJH JV | 1 | 2021-10-18 | 17 | N | 7 | 1 | 2021-10-18 | 17 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1040 | P4 – Low
E335-RFI-0203 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – bearing pad/embed plate at 110th Ave NE/NE 6th St | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-282 for fire alarm device layout at 110th Ave NE/NE 6th St. Request direction on compliant detail. | Field Engineer | 2021-09-29 | 10 | Routine | N | N | N | 4 | ST Design Management | 2 | 2021-10-04 | 5 | Y | 0 | 2 | 2021-10-18 | 18 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1041 | P4 – Low
E335-RFI-0204 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – platform edge slab and drilled shaft cap at 110th Ave NE/NE 6th St | Interference between platform edge slab and drilled shaft cap at 110th Ave NE/NE 6th St per S-128. Required clearance of 2 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2021-10-13 | 10 | Urgent | Y | N | N | 5 | DSDC – HJH JV | 2 | 2021-10-21 | 8 | Y | 0 | 1 | 2021-10-21 | 8 | Closed | 0 | 0 | 0 | 1553000 | 2900000 | Y | E335-CO-046 | 2017280 | 1397880 | 1.9 | 49.4 | 69 | P1 – Critical
E335-RFI-0205 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Bellevue Downtown Station: glacially deposited boulders exceeding 36 in. | During excavation at Bellevue Downtown Station (Sta. 2215+95) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or E-172. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Project Manager | 2021-10-18 | 10 | Urgent | Y | Y | Y | 4 | ST Design Management | 3 | 2021-10-25 | 6 | Y | 0 | 2 | 2021-11-02 | 15 | Closed | 18 | 11 | 0 | 302000 | 564000 | N |  | 0 | 0 | 0 | 11 | 386 | P3 – Medium
E335-RFI-0206 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Art embed coordination – Spring District/120th Station | Request to clarify finish/connection detail on E-616 at Spring District/120th Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Field Engineer | 2021-10-22 | 10 | Routine | N | N | N | 5 | ST Design Management | 1 | 2021-10-28 | 6 | Y | 0 | 1 | 2021-10-28 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1042 | P4 – Low
E335-RFI-0207 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Art embed coordination – Bellevue Downtown Station | Request to clarify finish/connection detail on M-787 at Bellevue Downtown Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2021-10-26 | 10 | Routine | N | N | N | 2 | DSDC – HJH JV | 3 | 2021-11-04 | 9 | Y | 0 | 2 | 2021-11-24 | 29 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1043 | P4 – Low
E335-RFI-0208 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | Puget Sound Energy comment on critical areas permit – East Main Station | Puget Sound Energy review comments on the critical areas permit require changes to the drilled shaft cap at East Main Station. Request direction on scope impacts and whether comments are within the contract requirements. | Project Engineer | 2021-11-08 | 10 | Routine | N | Y | N | 6 | City of Bellevue / ST Third-Party Mgmt | 2 | 2021-11-23 | 15 | N | 5 | 1 | 2021-11-23 | 15 | Closed | 14 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 577 | P3 – Medium
E335-RFI-0209 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – pedestrian ramp sequence at Wilburton Station | Erection of the pedestrian ramp as drawn conflicts with adjacent work and access limits at Wilburton Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Field Engineer | 2021-11-11 | 10 | Expedite | Y | Y | N | 5 | ST Design Management | 1 | 2021-11-18 | 7 | Y | 0 | 1 | 2021-11-18 | 7 | Closed | 4 | 0 | 1 | 55000 | 103000 | Y | E335-CO-046 | 162520 | 112620 | 0.1 | 40.3 | 229 | P2 – High
E335-RFI-0210 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Station finish detail – Bellevue Downtown Station | Request to clarify finish/connection detail on M-380 at Bellevue Downtown Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Scheduler | 2021-11-12 | 10 | Routine | N | Y | N | 7 | DSDC – HJH JV | 1 | 2021-11-16 | 4 | Y | 0 | 1 | 2021-11-16 | 4 | Closed | 1 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 782 | P4 – Low
E335-RFI-0211 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Wilburton Station | M-565 shows a 10 ft-7 in. dimension for the drilled shaft cap; structural sheet S-830 shows a different value. Request clarification before fabrication/rebar release. | Design Manager | 2021-11-22 | 10 | Routine | N | N | N | 0 | DSDC – HJH JV | 2 | 2021-11-29 | 6 | Y | 0 | 1 | 2021-11-29 | 6 | Closed | 0 | 0 | 0 |  |  | Y | E335-CO-052 | 212300 | 178620 | 8.4 | 44.5 | 150 | P2 – High
E335-RFI-0212 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Art embed coordination – East Main Station | Request to clarify finish/connection detail on A-483 at East Main Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2021-11-25 | 10 | Expedite | N | N | N | 6 | DSDC – HJH JV | 1 | 2021-12-01 | 6 | Y | 0 | 1 | 2021-12-01 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1044 | P4 – Low
E335-RFI-0213 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – column reinforcement sequence at 110th Ave NE/NE 6th St | Erection of the column reinforcement as drawn conflicts with adjacent work and access limits at 110th Ave NE/NE 6th St. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Superintendent | 2021-12-13 | 10 | Urgent | Y | N | N | 2 | ST Design Management | 3 | 2021-12-20 | 5 | Y | 0 | 1 | 2021-12-20 | 5 | Closed | 0 | 0 | 0 | 642000 | 1199000 | N |  | 0 | 0 | 0 | 0 | 1045 | P4 – Low
E335-RFI-0214 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Art embed coordination – East Main Station | Request to clarify finish/connection detail on M-276 at East Main Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Field Engineer | 2021-12-15 | 10 | Routine | Y | N | N | 3 | DSDC – HJH JV | 1 | 2021-12-20 | 5 | Y | 0 | 1 | 2021-12-20 | 5 | Closed | 0 | 0 | 0 | 37000 | 69000 | Y | E335-CO-047 | 49600 | 0 | 0 | 0 | 1046 | P4 – Low
E335-RFI-0215 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – station canopy support sequence at 110th Ave NE/NE 6th St | Erection of the station canopy support as drawn conflicts with adjacent work and access limits at 110th Ave NE/NE 6th St. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2021-12-20 | 10 | Routine | N | Y | Y | 6 | DSDC – HJH JV | 4 | 2021-12-30 | 10 | Y | 0 | 2 | 2022-01-06 | 17 | Closed | 7 | 5 | 0 |  |  | N |  | 0 | 0 | 0 | 5 | 438 | P3 – Medium
E335-RFI-0216 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 24-in. sanitary sewer at Spring District/120th Station | Potholing at Sta. 1359+89 located a 24-in. sanitary sewer in conflict with the proposed bearing pad/embed plate. Utility is not shown on S-138. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Scheduler | 2021-12-29 | 10 | Routine | Y | Y | Y | 7 | DSDC – HJH JV | 2 | 2022-01-05 | 7 | Y | 0 | 1 | 2022-01-05 | 7 | Closed | 34 | 21 | 0 | 519000 | 969000 | Y | E335-CO-048 | 251100 | 105100 | 14 | 65.5 | 9 | P1 – Critical
E335-RFI-0217 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – column reinforcement and bearing pad/embed plate at Spring District/120th Station | Interference between column reinforcement and bearing pad/embed plate at Spring District/120th Station per S-764. Required clearance of 4 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Scheduler | 2022-01-04 | 10 | Expedite | Y | Y | N | 2 | DSDC – HJH JV | 1 | 2022-01-11 | 7 | Y | 0 | 2 | 2022-01-25 | 21 | Closed | 9 | 0 | 5 | 457000 | 852000 | Y | E335-CO-049 | 498700 | 343100 | 4 | 46.4 | 117 | P2 – High
E335-RFI-0218 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – duct bank encasement sequence at Spring District/120th Station | Erection of the duct bank encasement as drawn conflicts with adjacent work and access limits at Spring District/120th Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Scheduler | 2022-01-10 | 10 | Expedite | Y | N | N | 8 | DSDC – HJH JV | 1 | 2022-01-17 | 7 | Y | 0 | 1 | 2022-01-17 | 7 | Closed | 0 | 0 | 0 | 487000 | 909000 | Y | E335-CO-050 | 604600 | 462600 | 0 | 45 | 139 | P2 – High
E335-RFI-0219 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Night work and noise variance – I-405 light rail bridge | Contractor requests approval of an alternate traffic/staging plan at I-405 light rail bridge: crane pick over active roadway. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Superintendent | 2022-01-10 | 10 | Routine | N | Y | Y | 8 | DSDC – HJH JV | 2 | 2022-01-13 | 3 | Y | 0 | 1 | 2022-01-13 | 3 | Closed | 4 | 3 | 0 |  |  | N |  | 0 | 0 | 0 | 3 | 478 | P3 – Medium
E335-RFI-0220 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | City of Bellevue comment on building permit – I-405 light rail bridge | City of Bellevue review comments on the building permit require changes to the bearing pad/embed plate at I-405 light rail bridge. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2022-01-10 | 10 | Routine | N | N | N | 7 | WSDOT / ST Third-Party Mgmt | 2 | 2022-02-09 | 30 | N | 20 | 2 | 2022-02-25 | 46 | Closed | 0 | 0 | 11 |  |  | N |  | 0 | 0 | 0 | 2.4 | 499 | P3 – Medium
E335-RFI-0221 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – I-405 light rail bridge | A-748 shows a 22 ft-3 in. dimension for the platform edge slab; structural sheet S-478 shows a different value. Request clarification before fabrication/rebar release. | Design Manager | 2022-01-12 | 10 | Routine | N | Y | Y | 0 | DSDC – HJH JV | 2 | 2022-01-20 | 8 | Y | 0 | 1 | 2022-01-20 | 8 | Closed | 3 | 2 | 0 |  |  | N |  | 0 | 0 | 0 | 2 | 517 | P3 – Medium
E335-RFI-0222 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Clarify spec requirement – I-405 light rail bridge | Request clarification of 01 33 00 Submittal Procedures and A-369: dimension/notes appear inconsistent or omitted for the work at I-405 light rail bridge. | Field Engineer | 2022-01-13 | 10 | Routine | N | Y | N | 7 | ST Design Management | 1 | 2022-01-18 | 5 | Y | 0 | 1 | 2022-01-18 | 5 | Closed | 3 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 715 | P3 – Medium
E335-RFI-0223 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Embedded conduit stub-ups – I-405 light rail bridge | Systems contractor requires 2-in. PVC conduit stub-ups for OCS pole at I-405 light rail bridge not provided in civil S-228. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Design Manager | 2022-01-31 | 10 | Routine | Y | Y | Y | 7 | ST Design Management | 4 | 2022-02-11 | 11 | N | 1 | 1 | 2022-02-11 | 11 | Closed | 23 | 8 | 0 | 247000 | 462000 | Y | E335-CO-051 | 163700 | 70000 | 12 | 50.4 | 52 | P1 – Critical
E335-RFI-0224 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 30-in. storm drain at Spring District/120th Station | Potholing at Sta. 2298+50 located a 30-in. storm drain in conflict with the proposed station canopy support. Utility is not shown on E-456. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Scheduler | 2022-01-31 | 10 | Routine | N | N | Y | 2 | DSDC – HJH JV | 4 | 2022-02-04 | 4 | Y | 0 | 1 | 2022-02-04 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1047 | P4 – Low
E335-RFI-0225 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Dimensional discrepancy – I-405 light rail bridge | M-884 shows a 34 ft-6 in. dimension for the bearing pad/embed plate; structural sheet S-545 shows a different value. Request clarification before fabrication/rebar release. | Project Engineer | 2022-01-31 | 10 | Routine | N | N | N | 6 | DSDC – HJH JV | 1 | 2022-02-09 | 9 | Y | 0 | 1 | 2022-02-09 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1048 | P4 – Low
E335-RFI-0226 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – stair core wall and column reinforcement at 110th Ave NE/NE 6th St | Interference between stair core wall and column reinforcement at 110th Ave NE/NE 6th St per C-398. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2022-02-07 | 10 | Expedite | Y | Y | N | 7 | DSDC – HJH JV | 4 | 2022-02-18 | 11 | N | 1 | 1 | 2022-02-18 | 11 | Closed | 18 | 0 | 5 | 101000 | 189000 | Y | E335-CO-052 | 117400 | 98780 | 4.6 | 42.3 | 194 | P2 – High
E335-RFI-0227 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 8-in. high-pressure gas main at 110th Ave NE/NE 6th St | Potholing at Sta. 1081+31 located a 8-in. high-pressure gas main in conflict with the proposed column reinforcement. Utility is not shown on C-468. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Design Manager | 2022-02-07 | 10 | Routine | Y | N | N | 4 | DSDC – HJH JV | 2 | 2022-03-24 | 45 | N | 35 | 2 | 2022-04-13 | 65 | Closed | 0 | 0 | 9 | 601000 | 1122000 | Y | E335-CO-053 | 1302200 | 773700 | 0 | 48.7 | 76 | P1 – Critical
E335-RFI-0228 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at NE 12th St guideway: petroleum-stained soil with odor | During excavation at NE 12th St guideway (Sta. 1778+01) the contractor encountered petroleum-stained soil with odor, not shown on the GBR or E-156. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Field Engineer | 2022-02-16 | 10 | Expedite | N | N | Y | 7 | ST Design Management | 1 | 2022-02-21 | 5 | Y | 0 | 1 | 2022-02-21 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1049 | P4 – Low
E335-RFI-0229 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Canopy/glazing connection – Wilburton Station | Request to clarify finish/connection detail on S-777 at Wilburton Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2022-02-21 | 10 | Expedite | N | N | N | 8 | DSDC – HJH JV | 1 | 2022-02-23 | 2 | Y | 0 | 1 | 2022-02-23 | 2 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1050 | P4 – Low
E335-RFI-0230 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – platform edge slab sequence at 110th Ave NE/NE 6th St | Erection of the platform edge slab as drawn conflicts with adjacent work and access limits at 110th Ave NE/NE 6th St. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2022-02-25 | 10 | Expedite | Y | Y | N | 8 | ST Design Management | 1 | 2022-03-14 | 15 | N | 5 | 1 | 2022-03-14 | 15 | Closed | 7 | 0 | 5 | 109000 | 203000 | N |  | 0 | 0 | 0 | 1.1 | 578 | P3 – Medium
E335-RFI-0231 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Station finish detail – East Main Station | Request to clarify finish/connection detail on C-582 at East Main Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Manager | 2022-03-14 | 10 | Routine | N | N | N | 4 | DSDC – HJH JV | 2 | 2022-03-21 | 5 | Y | 0 | 1 | 2022-03-21 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1051 | P4 – Low
E335-RFI-0232 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – Spring District/120th Station | Systems contractor requires 2-in. PVC conduit stub-ups for fiber backbone at Spring District/120th Station not provided in civil A-644. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2022-03-16 | 10 | Routine | Y | Y | N | 6 | ST Design Management | 3 | 2022-03-31 | 15 | N | 5 | 1 | 2022-03-31 | 15 | Closed | 24 | 0 | 18 | 867000 | 1618000 | N |  | 0 | 0 | 0 | 4 | 453 | P3 – Medium
E335-RFI-0233 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – station canopy support and stair core wall at I-405 light rail bridge | Interference between station canopy support and stair core wall at I-405 light rail bridge per S-794. Required clearance of 8 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Scheduler | 2022-03-21 | 10 | Routine | N | N | N | 7 | ST Design Management | 2 | 2022-04-14 | 24 | N | 14 | 2 | 2022-04-25 | 34 | Closed | 0 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 669 | P3 – Medium
E335-RFI-0234 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Crane staging in right-of-way – I-405 light rail bridge | Contractor requests approval of an alternate traffic/staging plan at I-405 light rail bridge: extended night closure. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Superintendent | 2022-04-11 | 10 | Routine | Y | N | N | 1 | ST Design Management | 2 | 2022-04-14 | 3 | Y | 0 | 1 | 2022-04-14 | 3 | Closed | 0 | 0 | 0 | 40000 | 74000 | Y | E335-CO-054 | 77500 | 48000 | 0 | 37.1 | 290 | P2 – High
E335-RFI-0235 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Fiber Backbone location conflict at Sta. 2088+75 | Proposed fiber backbone foundation location at Sta. 2088+75 conflicts with platform edge slab; offset of 8 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Project Engineer | 2022-05-30 | 10 | Urgent | Y | N | N | 4 | ST Design Management | 2 | 2022-06-10 | 11 | N | 1 | 2 | 2022-06-20 | 21 | Closed | 0 | 0 | 0 | 1776000 | 3315000 | N |  | 0 | 0 | 0 | 0 | 1052 | P4 – Low
E335-RFI-0236 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – 110th Ave NE/NE 6th St | A-114 shows a 54 ft-2 in. dimension for the bearing pad/embed plate; structural sheet S-894 shows a different value. Request clarification before fabrication/rebar release. | Scheduler | 2022-05-30 | 10 | Expedite | N | N | N | 2 | ST Design Management | 2 | 2022-06-14 | 15 | N | 5 | 2 | 2022-06-24 | 25 | Closed | 0 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 716 | P3 – Medium
E335-RFI-0237 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Signal Case location conflict at Sta. 2353+35 | Proposed signal case foundation location at Sta. 2353+35 conflicts with retaining wall footing; offset of 7 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Superintendent | 2022-06-13 | 10 | Expedite | Y | Y | N | 3 | DSDC – HJH JV | 1 | 2022-06-20 | 5 | Y | 0 | 2 | 2022-07-11 | 26 | Closed | 7 | 0 | 1 | 314000 | 587000 | N |  | 0 | 0 | 0 | 0.2 | 783 | P4 – Low
E335-RFI-0238 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – retaining wall footing at Bellevue Downtown Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-343 for egress width at Bellevue Downtown Station. Request direction on compliant detail. | Scheduler | 2022-06-14 | 10 | Urgent | N | Y | Y | 6 | ST Design Management | 2 | 2022-06-27 | 12 | N | 2 | 1 | 2022-06-27 | 12 | Closed | 21 | 11 | 0 |  |  | N |  | 0 | 0 | 0 | 11 | 387 | P3 – Medium
E335-RFI-0239 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | NE 12th St guideway | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – retaining wall footing and drilled shaft cap at NE 12th St guideway | Interference between retaining wall footing and drilled shaft cap at NE 12th St guideway per S-204. Required clearance of 6 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Manager | 2022-06-20 | 10 | Urgent | Y | N | N | 4 | DSDC – HJH JV | 1 | 2022-06-23 | 3 | Y | 0 | 2 | 2022-06-30 | 10 | Closed | 0 | 0 | 0 | 66000 | 124000 | Y | E335-CO-055 | 73700 | 0 | 0 | 0 | 1053 | P4 – Low
E335-RFI-0240 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 12-in. ductile iron water main at I-405 light rail bridge | Potholing at Sta. 1437+59 located a 12-in. ductile iron water main in conflict with the proposed stair core wall. Utility is not shown on S-173. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Superintendent | 2022-06-21 | 10 | Urgent | N | Y | N | 4 | DSDC – HJH JV | 1 | 2022-06-30 | 9 | Y | 0 | 1 | 2022-06-30 | 9 | Closed | 30 | 0 | 15 |  |  | N |  | 0 | 0 | 0 | 3.3 | 467 | P3 – Medium
E335-RFI-0241 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – pedestrian ramp sequence at Bellevue Downtown Station | Erection of the pedestrian ramp as drawn conflicts with adjacent work and access limits at Bellevue Downtown Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2022-06-27 | 10 | Routine | N | N | Y | 3 | DSDC – HJH JV | 2 | 2022-07-13 | 16 | N | 6 | 1 | 2022-07-13 | 16 | Closed | 0 | 2 | 0 |  |  | N |  | 0 | 0 | 0 | 2 | 518 | P3 – Medium
E335-RFI-0242 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – platform edge slab sequence at Bellevue Downtown Station | Erection of the platform edge slab as drawn conflicts with adjacent work and access limits at Bellevue Downtown Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Field Engineer | 2022-06-27 | 10 | Urgent | N | Y | Y | 5 | DSDC – HJH JV | 1 | 2022-07-04 | 6 | Y | 0 | 2 | 2022-07-21 | 24 | Closed | 12 | 11 | 0 |  |  | N |  | 0 | 0 | 0 | 11 | 388 | P3 – Medium
E335-RFI-0243 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Canopy/glazing connection – Spring District/120th Station | Request to clarify finish/connection detail on M-201 at Spring District/120th Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2022-06-29 | 10 | Routine | N | Y | N | 0 | DSDC – HJH JV | 1 | 2022-07-04 | 3 | Y | 0 | 1 | 2022-07-04 | 3 | Closed | 2 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 717 | P3 – Medium
E335-RFI-0244 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Property owner access/restoration requirement – 110th Ave NE/NE 6th St | Adjacent property owner has requested additional restoration and access provisions at 110th Ave NE/NE 6th St beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Scheduler | 2022-07-11 | 10 | Urgent | Y | Y | Y | 1 | WSDOT / ST Third-Party Mgmt | 2 | 2022-07-14 | 3 | Y | 0 | 2 | 2022-07-25 | 14 | Closed | 22 | 11 | 0 | 57000 | 107000 | N |  | 0 | 0 | 0 | 11 | 389 | P3 – Medium
E335-RFI-0245 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | Puget Sound Energy comment on street improvement permit – 110th Ave NE/NE 6th St | Puget Sound Energy review comments on the street improvement permit require changes to the station canopy support at 110th Ave NE/NE 6th St. Request direction on scope impacts and whether comments are within the contract requirements. | Project Engineer | 2022-07-11 | 10 | Expedite | N | N | Y | 8 | City of Bellevue / ST Third-Party Mgmt | 1 | 2022-07-25 | 13 | N | 3 | 2 | 2022-08-08 | 26 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1054 | P4 – Low
E335-RFI-0246 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Special trackwork layout – Wilburton Station | Track layout at Sta. 2030+83 (Wilburton Station) differs from the track-structure interface drawing M-271. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2022-07-11 | 10 | Routine | N | N | N | 0 | DSDC – HJH JV | 1 | 2022-07-19 | 8 | Y | 0 | 1 | 2022-07-19 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1055 | P4 – Low
E335-RFI-0247 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Lane closure window request – I-405 light rail bridge | Contractor requests approval of an alternate traffic/staging plan at I-405 light rail bridge: extended night closure. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Superintendent | 2022-09-26 | 10 | Expedite | N | Y | N | 6 | DSDC – HJH JV | 1 | 2022-09-29 | 3 | Y | 0 | 1 | 2022-09-29 | 3 | Closed | 8 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 718 | P3 – Medium
E335-RFI-0248 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at East Main Station: buried concrete debris and an old foundation | During excavation at East Main Station (Sta. 1865+09) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or M-595. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Design Manager | 2022-09-27 | 10 | Routine | Y | N | N | 6 | DSDC – HJH JV | 2 | 2022-10-06 | 9 | Y | 0 | 1 | 2022-10-06 | 9 | Closed | 0 | 0 | 0 | 183000 | 342000 | Y | E335-CO-056 | 135400 | 0 | 0 | 0 | 1056 | P4 – Low
E335-RFI-0249 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – bearing pad/embed plate and platform edge slab at I-405 light rail bridge | Interference between bearing pad/embed plate and platform edge slab at I-405 light rail bridge per M-496. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Scheduler | 2022-10-10 | 10 | Urgent | Y | Y | N | 8 | ST Design Management | 3 | 2022-10-17 | 7 | Y | 0 | 1 | 2022-10-17 | 7 | Closed | 8 | 0 | 5 | 170000 | 317000 | Y | E335-CO-057 | 193000 | 0 | 0 | 1.1 | 579 | P3 – Medium
E335-RFI-0250 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | City of Bellevue comment on critical areas permit – Wilburton Station | City of Bellevue review comments on the critical areas permit require changes to the pedestrian ramp at Wilburton Station. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2022-10-20 | 10 | Expedite | Y | Y | Y | 8 | Puget Sound Energy / ST Third-Party Mgmt | 4 | 2022-11-08 | 19 | N | 9 | 2 | 2022-11-28 | 39 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1057 | P4 – Low
E335-RFI-0251 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – pedestrian ramp at Wilburton Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-785 for smoke control damper at Wilburton Station. Request direction on compliant detail. | Design Manager | 2022-11-03 | 10 | Routine | N | Y | N | 8 | ST Design Management | 1 | 2022-11-17 | 14 | N | 4 | 1 | 2022-11-17 | 14 | Closed | 28 | 0 | 9 |  |  | N |  | 0 | 0 | 0 | 2 | 519 | P3 – Medium
E335-RFI-0252 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Bellevue Downtown Station | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Station finish detail – Bellevue Downtown Station | Request to clarify finish/connection detail on M-204 at Bellevue Downtown Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2022-11-08 | 10 | Expedite | N | N | N | 0 | DSDC – HJH JV | 1 | 2022-11-09 | 1 | Y | 0 | 1 | 2022-11-09 | 1 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1058 | P4 – Low
E335-RFI-0253 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – recycled-content fly ash blend | Contractor requests approval to substitute recycled-content fly ash blend for Type IL cement mix on work at East Main Station, citing procurement lead time. Product data attached. | Scheduler | 2022-11-14 | 10 | Expedite | N | N | N | 3 | DSDC – HJH JV | 2 | 2022-11-23 | 9 | Y | 0 | 1 | 2022-11-23 | 9 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1059 | P4 – Low
E335-RFI-0254 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Wetland/stream buffer protection – East Main Station | Field conditions at East Main Station require changes to temporary erosion and sediment control or stormwater facility per S-473. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2023-01-03 | 10 | Routine | Y | N | N | 6 | DSDC – HJH JV | 1 | 2023-01-13 | 10 | Y | 0 | 1 | 2023-01-13 | 10 | Closed | 0 | 0 | 0 | 326000 | 609000 | Y | E335-CO-058 | 607600 | 495900 | 0 | 45.2 | 135 | P2 – High
E335-RFI-0255 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Wilburton Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – Wilburton Station | Civil and systems drawings differ on grounding/bonding of bearing pad/embed plate for stray-current control at Wilburton Station. Request governing detail and responsibility for installation. | Superintendent | 2023-01-30 | 10 | Routine | N | Y | N | 0 | DSDC – HJH JV | 3 | 2023-02-07 | 8 | Y | 0 | 1 | 2023-02-07 | 8 | Closed | 9 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 719 | P3 – Medium
E335-RFI-0256 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | I-405 light rail bridge | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Rail Bonding location conflict at Sta. 2191+24 | Proposed rail bonding foundation location at Sta. 2191+24 conflicts with retaining wall footing; offset of 4 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Field Engineer | 2023-02-06 | 10 | Routine | N | Y | N | 2 | DSDC – HJH JV | 3 | 2023-02-23 | 17 | N | 7 | 2 | 2023-03-13 | 35 | Closed | 5 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 670 | P3 – Medium
E335-RFI-0257 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | East Main Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with fiber communications duct bank at East Main Station | Potholing at Sta. 1240+87 located a fiber communications duct bank in conflict with the proposed retaining wall footing. Utility is not shown on E-188. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Manager | 2023-02-06 | 10 | Routine | Y | Y | Y | 0 | DSDC – HJH JV | 1 | 2023-02-13 | 6 | Y | 0 | 1 | 2023-02-13 | 6 | Closed | 12 | 5 | 0 | 768000 | 1434000 | N |  | 0 | 0 | 0 | 5 | 439 | P3 – Medium
E335-RFI-0258 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Drawing/spec discrepancy – 110th Ave NE/NE 6th St | Request clarification of 00 72 00 General Conditions and S-157: dimension/notes appear inconsistent or omitted for the work at 110th Ave NE/NE 6th St. | Project Engineer | 2023-02-13 | 10 | Routine | N | N | N | 7 | ST Design Management | 2 | 2023-02-16 | 3 | Y | 0 | 1 | 2023-02-16 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1060 | P4 – Low
E335-RFI-0259 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | 110th Ave NE/NE 6th St | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – platform edge slab and drilled shaft cap at 110th Ave NE/NE 6th St | Interference between platform edge slab and drilled shaft cap at 110th Ave NE/NE 6th St per A-805. Required clearance of 8 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Scheduler | 2023-03-07 | 10 | Urgent | Y | N | N | 3 | DSDC – HJH JV | 2 | 2023-03-13 | 6 | Y | 0 | 1 | 2023-03-13 | 6 | Closed | 0 | 0 | 0 | 316000 | 590000 | Y | E335-CO-059 | 450400 | 331900 | 0 | 43.8 | 164 | P2 – High
E335-RFI-0260 | E335 | East Link Extension | Stacy and Witbeck/Atkinson, JV | Spring District/120th Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | Wetland/stream buffer protection – Spring District/120th Station | Field conditions at Spring District/120th Station require changes to temporary erosion and sediment control or stormwater facility per A-329. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2023-03-20 | 10 | Routine | Y | N | Y | 6 | DSDC – HJH JV | 1 | 2023-04-03 | 13 | N | 3 | 1 | 2023-04-03 | 13 | Closed | 0 | 0 | 0 | 56000 | 104000 | N |  | 0 | 0 | 0 | 0 | 1061 | P4 – Low
E340-RFI-0001 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – guideway girder diaphragm and retaining wall footing at 130th Station | Interference between guideway girder diaphragm and retaining wall footing at 130th Station per E-609. Required clearance of 7 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2017-08-09 | 10 | Routine | N | Y | Y | 5 | DSDC – HJH JV | 1 | 2017-08-14 | 5 | Y | 0 | 1 | 2017-08-14 | 5 | Closed | 25 | 8 | 0 |  |  | N |  | 0 | 0 | 0 | 8 | 410 | P3 – Medium
E340-RFI-0002 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Grounding/bonding and stray-current detail – Bel-Red Rd/NE 16th corridor | Civil and systems drawings differ on grounding/bonding of station canopy support for stray-current control at Bel-Red Rd/NE 16th corridor. Request governing detail and responsibility for installation. | Field Engineer | 2017-09-04 | 10 | Routine | N | N | N | 2 | DSDC – HJH JV | 1 | 2017-09-19 | 15 | N | 5 | 1 | 2017-09-19 | 15 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1062 | P4 – Low
E340-RFI-0003 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Bel-Red Rd/NE 16th corridor: loose granular fill below planned bearing elevation | During excavation at Bel-Red Rd/NE 16th corridor (Sta. 1600+09) the contractor encountered loose granular fill below planned bearing elevation, not shown on the GBR or M-859. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Design Manager | 2017-09-06 | 10 | Routine | N | Y | N | 7 | DSDC – HJH JV | 1 | 2017-09-19 | 13 | N | 3 | 1 | 2017-09-19 | 13 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1063 | P4 – Low
E340-RFI-0004 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – drilled shaft cap at 124th Ave NE crossing | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-859 for standpipe connection at 124th Ave NE crossing. Request direction on compliant detail. | Superintendent | 2017-11-27 | 10 | Expedite | Y | N | Y | 8 | DSDC – HJH JV | 4 | 2017-12-13 | 16 | N | 6 | 1 | 2017-12-13 | 16 | Closed | 0 | 5 | 0 | 19000 | 36000 | Y | E340-CO-001 | 30500 | 30500 | 0 | 40.6 | 226 | P2 – High
E340-RFI-0005 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – duct bank encasement sequence at 124th Ave NE crossing | Erection of the duct bank encasement as drawn conflicts with adjacent work and access limits at 124th Ave NE crossing. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Project Manager | 2017-12-13 | 10 | Routine | Y | N | N | 7 | ST Design Management | 3 | 2017-12-15 | 2 | Y | 0 | 1 | 2017-12-15 | 2 | Closed | 0 | 0 | 0 | 112000 | 210000 | Y | E340-CO-002 | 110100 | 72000 | 0 | 38.5 | 262 | P2 – High
E340-RFI-0006 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – platform edge slab and drilled shaft cap at 130th Station | Interference between platform edge slab and drilled shaft cap at 130th Station per C-154. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2018-01-16 | 10 | Expedite | N | N | N | 0 | ST Design Management | 1 | 2018-01-24 | 8 | Y | 0 | 2 | 2018-02-12 | 27 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1064 | P4 – Low
E340-RFI-0007 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red at-grade guideway | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – recycled-content fly ash blend | Contractor requests approval to substitute recycled-content fly ash blend for Type IL cement mix on work at Bel-Red at-grade guideway, citing procurement lead time. Product data attached. | Superintendent | 2018-02-08 | 10 | Routine | N | N | N | 0 | DSDC – HJH JV | 2 | 2018-02-12 | 2 | Y | 0 | 1 | 2018-02-12 | 2 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1065 | P4 – Low
E340-RFI-0008 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Dimensional discrepancy – 130th Station | C-669 shows a 50 ft-3 in. dimension for the bearing pad/embed plate; structural sheet S-265 shows a different value. Request clarification before fabrication/rebar release. | Project Manager | 2018-02-15 | 10 | Routine | Y | Y | N | 7 | DSDC – HJH JV | 1 | 2018-02-22 | 7 | Y | 0 | 1 | 2018-02-22 | 7 | Closed | 14 | 0 | 5 | 59000 | 110000 | Y | E340-CO-003 | 104000 | 104000 | 11 | 44.6 | 146 | P2 – High
E340-RFI-0009 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Special trackwork layout – 124th Ave NE crossing | Track layout at Sta. 2071+41 (124th Ave NE crossing) differs from the track-structure interface drawing S-681. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2018-02-26 | 10 | Routine | N | N | N | 6 | DSDC – HJH JV | 2 | 2018-03-05 | 7 | Y | 0 | 1 | 2018-03-05 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1066 | P4 – Low
E340-RFI-0010 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 8-in. high-pressure gas main at 130th Station | Potholing at Sta. 953+04 located a 8-in. high-pressure gas main in conflict with the proposed guideway girder diaphragm. Utility is not shown on A-819. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Engineer | 2018-03-28 | 10 | Urgent | Y | Y | N | 0 | DSDC – HJH JV | 2 | 2018-04-02 | 3 | Y | 0 | 1 | 2018-04-02 | 3 | Closed | 4 | 0 | 2 | 319000 | 595000 | Y | E340-CO-004 | 434900 | 103500 | 1 | 40.6 | 227 | P2 – High
E340-RFI-0011 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Lane closure window request – Bel-Red stormwater facility | Contractor requests approval of an alternate traffic/staging plan at Bel-Red stormwater facility: extended night closure. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Scheduler | 2018-03-29 | 10 | Routine | Y | N | N | 5 | DSDC – HJH JV | 2 | 2018-04-02 | 3 | Y | 0 | 2 | 2018-04-19 | 21 | Closed | 0 | 0 | 0 | 30000 | 57000 | Y | E340-CO-005 | 38000 | 25100 | 0 | 34.9 | 314 | P2 – High
E340-RFI-0012 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with fiber communications duct bank at Bel-Red stormwater facility | Potholing at Sta. 1651+09 located a fiber communications duct bank in conflict with the proposed column reinforcement. Utility is not shown on C-617. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Project Engineer | 2018-04-02 | 10 | Urgent | N | Y | Y | 3 | ST Design Management | 3 | 2018-04-05 | 3 | Y | 0 | 1 | 2018-04-05 | 3 | Closed | 68 | 56 | 0 |  |  | N |  | 0 | 0 | 0 | 30 | 344 | P3 – Medium
E340-RFI-0013 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Station finish detail – 130th Station | Request to clarify finish/connection detail on E-445 at 130th Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Field Engineer | 2018-04-10 | 10 | Routine | N | N | N | 7 | ST Design Management | 2 | 2018-04-18 | 8 | Y | 0 | 1 | 2018-04-18 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1067 | P4 – Low
E340-RFI-0014 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | TESC modification – Bel-Red Rd/NE 16th corridor | Field conditions at Bel-Red Rd/NE 16th corridor require changes to temporary erosion and sediment control or stormwater facility per M-283. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2018-04-12 | 10 | Routine | N | Y | N | 7 | DSDC – HJH JV | 1 | 2018-04-30 | 18 | N | 8 | 1 | 2018-04-30 | 18 | Closed | 6 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 629 | P3 – Medium
E340-RFI-0015 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | TESC modification – Bel-Red stormwater facility | Field conditions at Bel-Red stormwater facility require changes to temporary erosion and sediment control or stormwater facility per C-238. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2018-04-27 | 10 | Routine | N | N | N | 1 | DSDC – HJH JV | 2 | 2018-05-14 | 15 | N | 5 | 1 | 2018-05-14 | 15 | Closed | 0 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 784 | P4 – Low
E340-RFI-0016 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red at-grade guideway | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Bel-Red at-grade guideway: petroleum-stained soil with odor | During excavation at Bel-Red at-grade guideway (Sta. 1263+76) the contractor encountered petroleum-stained soil with odor, not shown on the GBR or S-183. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Project Engineer | 2018-05-10 | 10 | Expedite | Y | N | N | 4 | DSDC – HJH JV | 2 | 2018-05-14 | 4 | Y | 0 | 1 | 2018-05-14 | 4 | Closed | 0 | 0 | 0 | 91000 | 169000 | Y | E340-CO-006 | 180400 | 90100 | 0 | 39.3 | 253 | P2 – High
E340-RFI-0017 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – station canopy support sequence at 124th Ave NE crossing | Erection of the station canopy support as drawn conflicts with adjacent work and access limits at 124th Ave NE crossing. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Project Engineer | 2018-05-28 | 10 | Expedite | Y | N | N | 0 | DSDC – HJH JV | 2 | 2018-06-06 | 9 | Y | 0 | 2 | 2018-06-18 | 19 | Closed | 0 | 0 | 0 | 223000 | 416000 | Y | E340-CO-007 | 221400 | 108700 | 0 | 40 | 237 | P2 – High
E340-RFI-0018 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – guideway girder diaphragm and pedestrian ramp at Bel-Red Rd/NE 16th corridor | Interference between guideway girder diaphragm and pedestrian ramp at Bel-Red Rd/NE 16th corridor per M-619. Required clearance of 3 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2018-06-21 | 10 | Routine | Y | N | N | 1 | ST Design Management | 3 | 2018-06-25 | 4 | Y | 0 | 1 | 2018-06-25 | 4 | Closed | 0 | 0 | 0 | 89000 | 166000 | N |  | 0 | 0 | 0 | 0 | 1068 | P4 – Low
E340-RFI-0019 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 12-in. ductile iron water main at 130th Station | Potholing at Sta. 1192+67 located a 12-in. ductile iron water main in conflict with the proposed duct bank encasement. Utility is not shown on E-830. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Design Manager | 2018-07-23 | 10 | Expedite | N | Y | Y | 4 | DSDC – HJH JV | 1 | 2018-07-27 | 4 | Y | 0 | 1 | 2018-07-27 | 4 | Closed | 12 | 7 | 0 |  |  | N |  | 0 | 0 | 0 | 7 | 417 | P3 – Medium
E340-RFI-0020 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with fiber communications duct bank at Bel-Red stormwater facility | Potholing at Sta. 1324+92 located a fiber communications duct bank in conflict with the proposed station canopy support. Utility is not shown on E-380. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Field Engineer | 2018-08-16 | 10 | Routine | N | Y | N | 0 | DSDC – HJH JV | 1 | 2018-08-21 | 5 | Y | 0 | 1 | 2018-08-21 | 5 | Closed | 8 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 630 | P3 – Medium
E340-RFI-0021 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on street improvement permit – 124th Ave NE crossing | WSDOT review comments on the street improvement permit require changes to the bearing pad/embed plate at 124th Ave NE crossing. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2018-09-03 | 10 | Expedite | Y | Y | Y | 1 | WSDOT / ST Third-Party Mgmt | 3 | 2018-09-18 | 15 | N | 5 | 1 | 2018-09-18 | 15 | Closed | 11 | 6 | 0 | 9000 | 17000 | Y | E340-CO-009 | 12100 | 4800 | 2 | 35.9 | 302 | P2 – High
E340-RFI-0022 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Bel-Red Rd/NE 16th corridor: soft lacustrine silt below design subgrade | During excavation at Bel-Red Rd/NE 16th corridor (Sta. 1357+68) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or S-310. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Field Engineer | 2018-09-05 | 10 | Routine | Y | N | N | 6 | ST Design Management | 2 | 2018-09-10 | 3 | Y | 0 | 2 | 2018-09-24 | 19 | Closed | 0 | 0 | 0 | 340000 | 634000 | Y | E340-CO-008 | 637900 | 381900 | 0 | 44.3 | 155 | P2 – High
E340-RFI-0023 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 12-in. ductile iron water main at Bel-Red Rd/NE 16th corridor | Potholing at Sta. 1826+11 located a 12-in. ductile iron water main in conflict with the proposed column reinforcement. Utility is not shown on C-168. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Project Engineer | 2018-09-10 | 10 | Routine | Y | Y | N | 2 | DSDC – HJH JV | 2 | 2018-10-02 | 22 | N | 12 | 2 | 2018-10-16 | 36 | Closed | 3 | 0 | 2 | 25000 | 47000 | Y | E340-CO-010 | 23600 | 15800 | 2 | 34.4 | 320 | P2 – High
E340-RFI-0024 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at 130th Station: buried concrete debris and an old foundation | During excavation at 130th Station (Sta. 2209+52) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or A-120. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Project Manager | 2018-09-10 | 10 | Routine | N | N | N | 8 | DSDC – HJH JV | 6 | 2018-09-27 | 17 | N | 7 | 1 | 2018-09-27 | 17 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1069 | P4 – Low
E340-RFI-0025 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Direct fixation fastener spacing at Sta. 2191+11 | Track layout at Sta. 2191+11 (124th Ave NE crossing) differs from the track-structure interface drawing A-601. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2018-09-17 | 10 | Urgent | N | N | N | 5 | ST Design Management | 2 | 2018-09-20 | 3 | Y | 0 | 1 | 2018-09-20 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1070 | P4 – Low
E340-RFI-0026 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 30-in. storm drain at Bel-Red stormwater facility | Potholing at Sta. 2116+76 located a 30-in. storm drain in conflict with the proposed guideway girder diaphragm. Utility is not shown on E-212. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Field Engineer | 2018-10-02 | 10 | Routine | N | N | N | 1 | DSDC – HJH JV | 2 | 2018-10-22 | 20 | N | 10 | 1 | 2018-10-22 | 20 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1071 | P4 – Low
E340-RFI-0027 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 30-in. storm drain at 124th Ave NE crossing | Potholing at Sta. 1833+77 located a 30-in. storm drain in conflict with the proposed station canopy support. Utility is not shown on S-180. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2018-10-08 | 10 | Routine | Y | N | Y | 4 | ST Design Management | 1 | 2018-10-16 | 8 | Y | 0 | 1 | 2018-10-16 | 8 | Closed | 0 | 0 | 0 | 66000 | 124000 | Y | E340-CO-011 | 54700 | 49400 | 0 | 37.2 | 284 | P2 – High
E340-RFI-0028 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Property owner access/restoration requirement – 130th Station | Adjacent property owner has requested additional restoration and access provisions at 130th Station beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Project Manager | 2018-10-15 | 10 | Urgent | Y | Y | N | 5 | WSDOT / ST Third-Party Mgmt | 1 | 2018-10-22 | 6 | Y | 0 | 1 | 2018-10-22 | 6 | Closed | 11 | 0 | 3 | 784000 | 1464000 | Y | E340-CO-012 | 643700 | 499700 | 7 | 48.2 | 90 | P1 – Critical
E340-RFI-0029 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Night work and noise variance – 124th Ave NE crossing | Contractor requests approval of an alternate traffic/staging plan at 124th Ave NE crossing: temporary lane shift. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Superintendent | 2018-11-07 | 10 | Routine | Y | N | N | 4 | DSDC – HJH JV | 1 | 2018-11-14 | 7 | Y | 0 | 2 | 2018-11-26 | 18 | Closed | 0 | 0 | 0 | 69000 | 129000 | N |  | 0 | 0 | 0 | 0 | 1072 | P4 – Low
E340-RFI-0030 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Bel-Red Rd/NE 16th corridor: buried concrete debris and an old foundation | During excavation at Bel-Red Rd/NE 16th corridor (Sta. 1405+31) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or S-580. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Scheduler | 2018-11-29 | 10 | Routine | Y | N | Y | 7 | ST Design Management | 2 | 2018-12-07 | 8 | Y | 0 | 1 | 2018-12-07 | 8 | Closed | 0 | 0 | 0 | 125000 | 233000 | Y | E340-CO-016 | 163200 | 98110 | 1 | 39.9 | 241 | P2 – High
E340-RFI-0031 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | City of Bellevue comment on building permit – Bel-Red Rd/NE 16th corridor | City of Bellevue review comments on the building permit require changes to the bearing pad/embed plate at Bel-Red Rd/NE 16th corridor. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2018-12-12 | 10 | Routine | N | Y | Y | 0 | City of Bellevue / ST Third-Party Mgmt | 1 | 2018-12-24 | 10 | Y | 0 | 2 | 2019-01-09 | 28 | Closed | 27 | 16 | 0 |  |  | N |  | 0 | 0 | 0 | 16 | 366 | P3 – Medium
E340-RFI-0032 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at 130th Station, citing procurement lead time. Product data attached. | Project Engineer | 2018-12-31 | 10 | Routine | N | N | N | 6 | DSDC – HJH JV | 1 | 2019-01-08 | 8 | Y | 0 | 2 | 2019-01-16 | 16 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1073 | P4 – Low
E340-RFI-0033 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red at-grade guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Signal Case location conflict at Sta. 1812+94 | Proposed signal case foundation location at Sta. 1812+94 conflicts with guideway girder diaphragm; offset of 6 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2019-01-09 | 10 | Routine | N | N | N | 2 | ST Design Management | 4 | 2019-01-31 | 22 | N | 12 | 1 | 2019-01-31 | 22 | Closed | 0 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 671 | P3 – Medium
E340-RFI-0034 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – 124th Ave NE crossing | Civil and systems drawings differ on grounding/bonding of duct bank encasement for stray-current control at 124th Ave NE crossing. Request governing detail and responsibility for installation. | Design Manager | 2019-01-14 | 10 | Urgent | N | Y | Y | 6 | DSDC – HJH JV | 1 | 2019-01-22 | 8 | Y | 0 | 1 | 2019-01-22 | 8 | Closed | 8 | 5 | 0 |  |  | N |  | 0 | 0 | 0 | 5 | 440 | P3 – Medium
E340-RFI-0035 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red at-grade guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | WSDOT comment on right-of-way use permit – Bel-Red at-grade guideway | WSDOT review comments on the right-of-way use permit require changes to the duct bank encasement at Bel-Red at-grade guideway. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2019-01-17 | 10 | Routine | N | N | Y | 4 | Puget Sound Energy / ST Third-Party Mgmt | 3 | 2019-02-01 | 15 | N | 5 | 1 | 2019-02-01 | 15 | Closed | 0 | 1 | 0 |  |  | N |  | 0 | 0 | 0 | 1 | 609 | P3 – Medium
E340-RFI-0036 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 12-in. ductile iron water main at Bel-Red Rd/NE 16th corridor | Potholing at Sta. 1500+77 located a 12-in. ductile iron water main in conflict with the proposed bearing pad/embed plate. Utility is not shown on M-579. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Field Engineer | 2019-01-25 | 10 | Routine | N | Y | Y | 1 | DSDC – HJH JV | 2 | 2019-02-11 | 15 | N | 5 | 1 | 2019-02-11 | 15 | Closed | 13 | 7 | 0 |  |  | Y | E340-CO-014 | 25540 | 14280 | 0.3 | 40.1 | 233 | P2 – High
E340-RFI-0037 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | Puget Sound Energy comment on critical areas permit – Bel-Red stormwater facility | Puget Sound Energy review comments on the critical areas permit require changes to the pedestrian ramp at Bel-Red stormwater facility. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2019-02-15 | 10 | Routine | Y | N | N | 0 | WSDOT / ST Third-Party Mgmt | 1 | 2019-02-20 | 5 | Y | 0 | 1 | 2019-02-20 | 5 | Closed | 0 | 0 | 0 | 31000 | 58000 | Y | E340-CO-013 | 74500 | 74500 | 0 | 38.7 | 259 | P2 – High
E340-RFI-0038 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at 130th Station: glacially deposited boulders exceeding 36 in. | During excavation at 130th Station (Sta. 1099+08) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or M-780. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Project Engineer | 2019-02-26 | 10 | Routine | Y | Y | Y | 5 | DSDC – HJH JV | 1 | 2019-03-04 | 5 | Y | 0 | 1 | 2019-03-04 | 5 | Closed | 30 | 19 | 0 | 1415000 | 2641000 | Y | E340-CO-016 | 763780 | 459140 | 4.8 | 65.5 | 10 | P1 – Critical
E340-RFI-0039 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 8-in. high-pressure gas main at Bel-Red stormwater facility | Potholing at Sta. 1078+60 located a 8-in. high-pressure gas main in conflict with the proposed pedestrian ramp. Utility is not shown on C-750. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2019-03-12 | 10 | Urgent | Y | N | Y | 3 | DSDC – HJH JV | 3 | 2019-03-15 | 3 | Y | 0 | 1 | 2019-03-15 | 3 | Closed | 0 | 0 | 0 | 176000 | 328000 | Y | E340-CO-014 | 355760 | 198820 | 4.7 | 43.6 | 167 | P2 – High
E340-RFI-0040 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Canopy/glazing connection – 124th Ave NE crossing | Request to clarify finish/connection detail on C-799 at 124th Ave NE crossing. Includes coordination with art program embeds and handrail sleeves as applicable. | Scheduler | 2019-03-13 | 10 | Routine | N | N | N | 6 | DSDC – HJH JV | 2 | 2019-03-22 | 9 | Y | 0 | 1 | 2019-03-22 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1074 | P4 – Low
E340-RFI-0041 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red at-grade guideway | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Station finish detail – Bel-Red at-grade guideway | Request to clarify finish/connection detail on S-417 at Bel-Red at-grade guideway. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2019-03-18 | 10 | Routine | N | N | N | 6 | DSDC – HJH JV | 1 | 2019-03-25 | 6 | Y | 0 | 1 | 2019-03-25 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1075 | P4 – Low
E340-RFI-0042 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Bel-Red stormwater facility | E-422 shows a 38 ft-5 in. dimension for the duct bank encasement; structural sheet S-445 shows a different value. Request clarification before fabrication/rebar release. | Project Engineer | 2019-04-01 | 10 | Urgent | Y | Y | N | 2 | DSDC – HJH JV | 2 | 2019-04-11 | 10 | Y | 0 | 1 | 2019-04-11 | 10 | Closed | 7 | 0 | 5 | 33000 | 61000 | Y | E340-CO-015 | 48800 | 31500 | 5 | 38.5 | 263 | P2 – High
E340-RFI-0043 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Tunnel Emergency Phone location conflict at Sta. 1394+46 | Proposed tunnel emergency phone foundation location at Sta. 1394+46 conflicts with stair core wall; offset of 3 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2019-04-09 | 10 | Expedite | N | Y | N | 7 | DSDC – HJH JV | 2 | 2019-04-15 | 5 | Y | 0 | 1 | 2019-04-15 | 5 | Closed | 9 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 631 | P3 – Medium
E340-RFI-0044 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Direct fixation fastener spacing at Sta. 1801+50 | Track layout at Sta. 1801+50 (Bel-Red Rd/NE 16th corridor) differs from the track-structure interface drawing A-759. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Superintendent | 2019-04-15 | 10 | Routine | N | N | N | 7 | DSDC – HJH JV | 2 | 2019-04-25 | 10 | Y | 0 | 1 | 2019-04-25 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1076 | P4 – Low
E340-RFI-0045 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – retaining wall footing at Bel-Red stormwater facility | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-500 for smoke control damper at Bel-Red stormwater facility. Request direction on compliant detail. | Project Engineer | 2019-05-21 | 10 | Routine | N | N | N | 2 | DSDC – HJH JV | 2 | 2019-05-28 | 7 | Y | 0 | 2 | 2019-06-11 | 21 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1077 | P4 – Low
E340-RFI-0046 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red at-grade guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 30-in. storm drain at Bel-Red at-grade guideway | Potholing at Sta. 1434+05 located a 30-in. storm drain in conflict with the proposed guideway girder diaphragm. Utility is not shown on A-253. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Manager | 2019-05-23 | 10 | Urgent | Y | Y | Y | 5 | DSDC – HJH JV | 2 | 2019-05-31 | 8 | Y | 0 | 1 | 2019-05-31 | 8 | Closed | 24 | 16 | 0 | 657000 | 1227000 | N |  | 0 | 0 | 0 | 16 | 367 | P3 – Medium
E340-RFI-0047 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at 130th Station: loose granular fill below planned bearing elevation | During excavation at 130th Station (Sta. 1532+90) the contractor encountered loose granular fill below planned bearing elevation, not shown on the GBR or S-380. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Field Engineer | 2019-05-24 | 10 | Routine | Y | Y | Y | 8 | DSDC – HJH JV | 2 | 2019-05-30 | 6 | Y | 0 | 1 | 2019-05-30 | 6 | Closed | 4 | 3 | 0 | 1635000 | 3051000 | Y | E340-CO-016 | 1321720 | 794550 | 8.2 | 52.6 | 36 | P1 – Critical
E340-RFI-0048 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red at-grade guideway | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bel-Red at-grade guideway: perched groundwater | During excavation at Bel-Red at-grade guideway (Sta. 1279+24) the contractor encountered perched groundwater at approx. elevation 45 ft, not shown on the GBR or A-526. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Field Engineer | 2019-06-10 | 10 | Routine | N | N | N | 8 | DSDC – HJH JV | 2 | 2019-06-18 | 8 | Y | 0 | 2 | 2019-07-01 | 19 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1078 | P4 – Low
E340-RFI-0049 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Drawing/spec discrepancy – Bel-Red Rd/NE 16th corridor | Request clarification of 01 33 00 Submittal Procedures and M-197: dimension/notes appear inconsistent or omitted for the work at Bel-Red Rd/NE 16th corridor. | Project Manager | 2019-07-25 | 10 | Urgent | Y | Y | N | 1 | DSDC – HJH JV | 1 | 2019-07-29 | 3 | Y | 0 | 1 | 2019-07-29 | 3 | Closed | 2 | 0 | 1 | 26000 | 48000 | N |  | 0 | 0 | 0 | 0.2 | 785 | P4 – Low
E340-RFI-0050 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 12-in. ductile iron water main at Bel-Red Rd/NE 16th corridor | Potholing at Sta. 1002+69 located a 12-in. ductile iron water main in conflict with the proposed station canopy support. Utility is not shown on A-554. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Project Manager | 2019-07-25 | 10 | Routine | N | N | Y | 0 | DSDC – HJH JV | 4 | 2019-07-31 | 6 | Y | 0 | 1 | 2019-07-31 | 6 | Closed | 0 | 2 | 0 |  |  | N |  | 0 | 0 | 0 | 2 | 520 | P3 – Medium
E340-RFI-0051 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – 124th Ave NE crossing | A-477 shows a 11 ft-5 in. dimension for the column reinforcement; structural sheet S-643 shows a different value. Request clarification before fabrication/rebar release. | Project Engineer | 2019-07-26 | 10 | Routine | Y | N | N | 2 | DSDC – HJH JV | 1 | 2019-08-06 | 11 | N | 1 | 2 | 2019-08-12 | 17 | Closed | 0 | 0 | 0 | 25000 | 46000 | Y | E340-CO-018 | 36660 | 25030 | 0 | 34.9 | 315 | P2 – High
E340-RFI-0052 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | City of Bellevue comment on street improvement permit – Bel-Red stormwater facility | City of Bellevue review comments on the street improvement permit require changes to the column reinforcement at Bel-Red stormwater facility. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2019-08-29 | 10 | Routine | N | Y | Y | 6 | WSDOT / ST Third-Party Mgmt | 2 | 2019-09-03 | 5 | Y | 0 | 1 | 2019-09-03 | 5 | Closed | 13 | 6 | 0 |  |  | N |  | 0 | 0 | 0 | 6 | 423 | P3 – Medium
E340-RFI-0053 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 24-in. sanitary sewer at 130th Station | Potholing at Sta. 1517+82 located a 24-in. sanitary sewer in conflict with the proposed duct bank encasement. Utility is not shown on C-560. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Scheduler | 2019-09-19 | 10 | Routine | Y | Y | N | 6 | DSDC – HJH JV | 2 | 2019-09-23 | 4 | Y | 0 | 1 | 2019-09-23 | 4 | Closed | 8 | 0 | 2 | 190000 | 355000 | N |  | 0 | 0 | 0 | 0.4 | 720 | P3 – Medium
E340-RFI-0054 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red at-grade guideway | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Haul route revision – Bel-Red at-grade guideway | Contractor requests approval of an alternate traffic/staging plan at Bel-Red at-grade guideway: extended night closure. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Superintendent | 2019-10-03 | 10 | Routine | Y | Y | N | 5 | ST Design Management | 2 | 2019-10-07 | 4 | Y | 0 | 1 | 2019-10-07 | 4 | Closed | 6 | 0 | 1 | 120000 | 224000 | Y | E340-CO-017 | 67300 | 54600 | 2 | 38.5 | 264 | P2 – High
E340-RFI-0055 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – 124th Ave NE crossing | E-238 shows a 55 ft-4 in. dimension for the pedestrian ramp; structural sheet S-767 shows a different value. Request clarification before fabrication/rebar release. | Scheduler | 2019-10-07 | 10 | Routine | Y | Y | N | 2 | DSDC – HJH JV | 1 | 2019-10-25 | 18 | N | 8 | 1 | 2019-10-25 | 18 | Closed | 4 | 0 | 3 | 3627000 | 6770000 | Y | E340-CO-018 | 1913740 | 1306770 | 2 | 49.9 | 60 | P1 – Critical
E340-RFI-0056 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Lane closure window request – 124th Ave NE crossing | Contractor requests approval of an alternate traffic/staging plan at 124th Ave NE crossing: revised haul route. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Design Manager | 2019-10-08 | 10 | Expedite | N | Y | N | 1 | DSDC – HJH JV | 2 | 2019-10-10 | 2 | Y | 0 | 1 | 2019-10-10 | 2 | Closed | 3 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 721 | P3 – Medium
E340-RFI-0057 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Haul route revision – 124th Ave NE crossing | Contractor requests approval of an alternate traffic/staging plan at 124th Ave NE crossing: extended night closure. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Design Manager | 2019-10-18 | 10 | Routine | Y | N | Y | 7 | ST Design Management | 1 | 2019-10-21 | 3 | Y | 0 | 2 | 2019-10-30 | 12 | Closed | 0 | 0 | 0 | 210000 | 393000 | N |  | 0 | 0 | 0 | 0 | 1079 | P4 – Low
E340-RFI-0058 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Night work and noise variance – Bel-Red Rd/NE 16th corridor | Contractor requests approval of an alternate traffic/staging plan at Bel-Red Rd/NE 16th corridor: revised haul route. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Superintendent | 2019-10-28 | 10 | Routine | N | N | N | 6 | DSDC – HJH JV | 2 | 2019-11-04 | 6 | Y | 0 | 1 | 2019-11-04 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1080 | P4 – Low
E340-RFI-0059 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Grounding/bonding and stray-current detail – 130th Station | Civil and systems drawings differ on grounding/bonding of platform edge slab for stray-current control at 130th Station. Request governing detail and responsibility for installation. | Field Engineer | 2019-10-29 | 10 | Expedite | N | Y | N | 1 | ST Design Management | 5 | 2019-12-02 | 33 | N | 23 | 1 | 2019-12-02 | 33 | Closed | 6 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 672 | P3 – Medium
E340-RFI-0060 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bel-Red stormwater facility: buried concrete debris and an old foundation | During excavation at Bel-Red stormwater facility (Sta. 2396+43) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or C-385. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Scheduler | 2019-11-14 | 10 | Expedite | Y | Y | N | 2 | DSDC – HJH JV | 2 | 2019-11-25 | 10 | Y | 0 | 1 | 2019-11-25 | 10 | Closed | 6 | 0 | 3 | 262000 | 488000 | Y | E340-CO-019 | 172700 | 42400 | 1 | 37.7 | 281 | P2 – High
E340-RFI-0061 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 30-in. storm drain at 130th Station | Potholing at Sta. 1596+06 located a 30-in. storm drain in conflict with the proposed column reinforcement. Utility is not shown on E-181. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Scheduler | 2019-11-18 | 10 | Routine | N | Y | Y | 8 | DSDC – HJH JV | 1 | 2019-11-27 | 9 | Y | 0 | 2 | 2019-12-11 | 23 | Closed | 7 | 3 | 0 |  |  | N |  | 0 | 0 | 0 | 3 | 479 | P3 – Medium
E340-RFI-0062 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – retaining wall footing at 124th Ave NE crossing | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-484 for standpipe connection at 124th Ave NE crossing. Request direction on compliant detail. | Superintendent | 2019-12-03 | 10 | Expedite | Y | Y | Y | 2 | DSDC – HJH JV | 5 | 2020-01-14 | 42 | N | 32 | 1 | 2020-01-14 | 42 | Closed | 24 | 12 | 0 | 489000 | 913000 | N |  | 0 | 0 | 0 | 12 | 378 | P3 – Medium
E340-RFI-0063 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Haul route revision – Bel-Red Rd/NE 16th corridor | Contractor requests approval of an alternate traffic/staging plan at Bel-Red Rd/NE 16th corridor: temporary lane shift. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Field Engineer | 2019-12-10 | 10 | Urgent | N | N | Y | 8 | DSDC – HJH JV | 1 | 2019-12-16 | 4 | Y | 0 | 1 | 2019-12-16 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1081 | P4 – Low
E340-RFI-0064 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with PSE distribution duct bank at Bel-Red Rd/NE 16th corridor | Potholing at Sta. 1215+42 located a PSE distribution duct bank in conflict with the proposed guideway girder diaphragm. Utility is not shown on C-106. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Engineer | 2019-12-30 | 10 | Routine | Y | Y | N | 1 | DSDC – HJH JV | 2 | 2020-01-06 | 7 | Y | 0 | 1 | 2020-01-06 | 7 | Closed | 19 | 0 | 6 | 239000 | 447000 | Y | E340-CO-020 | 351600 | 290900 | 12 | 48.7 | 77 | P1 – Critical
E340-RFI-0065 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Haul route revision – 130th Station | Contractor requests approval of an alternate traffic/staging plan at 130th Station: crane pick over active roadway. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Scheduler | 2020-01-10 | 10 | Routine | N | N | N | 2 | DSDC – HJH JV | 3 | 2020-01-13 | 2 | Y | 0 | 1 | 2020-01-13 | 2 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1082 | P4 – Low
E340-RFI-0066 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Bel-Red Rd/NE 16th corridor: soft lacustrine silt below design subgrade | During excavation at Bel-Red Rd/NE 16th corridor (Sta. 1690+06) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or A-492. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Superintendent | 2020-01-13 | 10 | Routine | N | Y | N | 2 | DSDC – HJH JV | 1 | 2020-01-20 | 5 | Y | 0 | 1 | 2020-01-20 | 5 | Closed | 8 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 580 | P3 – Medium
E340-RFI-0067 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Direct fixation fastener spacing at Sta. 929+95 | Track layout at Sta. 929+95 (Bel-Red Rd/NE 16th corridor) differs from the track-structure interface drawing C-721. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Engineer | 2020-01-20 | 10 | Routine | Y | N | N | 2 | DSDC – HJH JV | 1 | 2020-01-31 | 11 | N | 1 | 1 | 2020-01-31 | 11 | Closed | 0 | 0 | 0 | 147000 | 274000 | N |  | 0 | 0 | 0 | 0 | 1083 | P4 – Low
E340-RFI-0068 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Canopy/glazing connection – Bel-Red Rd/NE 16th corridor | Request to clarify finish/connection detail on S-866 at Bel-Red Rd/NE 16th corridor. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2020-01-20 | 10 | Routine | N | N | N | 0 | DSDC – HJH JV | 2 | 2020-01-28 | 8 | Y | 0 | 1 | 2020-01-28 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1084 | P4 – Low
E340-RFI-0069 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red at-grade guideway | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Bel-Red at-grade guideway: glacially deposited boulders exceeding 36 in. | During excavation at Bel-Red at-grade guideway (Sta. 1827+84) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or A-319. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Superintendent | 2020-02-19 | 10 | Expedite | N | N | N | 2 | DSDC – HJH JV | 1 | 2020-02-26 | 7 | Y | 0 | 1 | 2020-02-26 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1085 | P4 – Low
E340-RFI-0070 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red at-grade guideway | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Track slab/expansion joint interface – Bel-Red at-grade guideway | Track layout at Sta. 1190+20 (Bel-Red at-grade guideway) differs from the track-structure interface drawing E-262. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Manager | 2020-02-21 | 10 | Expedite | Y | N | N | 8 | ST Design Management | 1 | 2020-03-03 | 11 | N | 1 | 1 | 2020-03-03 | 11 | Closed | 0 | 0 | 1 | 37000 | 70000 | N |  | 0 | 0 | 0 | 0.2 | 786 | P4 – Low
E340-RFI-0071 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Bel-Red stormwater facility: soft lacustrine silt below design subgrade | During excavation at Bel-Red stormwater facility (Sta. 1065+92) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or C-749. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Superintendent | 2020-02-24 | 10 | Urgent | Y | N | Y | 6 | DSDC – HJH JV | 2 | 2020-02-28 | 4 | Y | 0 | 1 | 2020-02-28 | 4 | Closed | 0 | 0 | 0 | 227000 | 423000 | Y | E340-CO-021 | 212100 | 0 | 0 | 0 | 1086 | P4 – Low
E340-RFI-0072 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – drilled shaft cap and platform edge slab at Bel-Red Rd/NE 16th corridor | Interference between drilled shaft cap and platform edge slab at Bel-Red Rd/NE 16th corridor per C-347. Required clearance of 2 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2020-02-24 | 10 | Routine | N | N | N | 7 | DSDC – HJH JV | 1 | 2020-03-11 | 16 | N | 6 | 2 | 2020-03-31 | 36 | Closed | 0 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 632 | P3 – Medium
E340-RFI-0073 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 30-in. storm drain at 124th Ave NE crossing | Potholing at Sta. 1277+11 located a 30-in. storm drain in conflict with the proposed column reinforcement. Utility is not shown on C-246. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Field Engineer | 2020-03-06 | 10 | Routine | N | Y | N | 1 | DSDC – HJH JV | 4 | 2020-03-23 | 15 | N | 5 | 1 | 2020-03-23 | 15 | Closed | 1 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 722 | P3 – Medium
E340-RFI-0074 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | SPC | Spec / Drawing Clarification | General | 01 25 00 Substitution Procedures | Missing dimension on C-367 | Request clarification of 00 72 00 General Conditions and C-367: dimension/notes appear inconsistent or omitted for the work at Bel-Red Rd/NE 16th corridor. | Project Engineer | 2020-04-02 | 10 | Routine | Y | Y | N | 6 | ST Design Management | 2 | 2020-04-08 | 6 | Y | 0 | 1 | 2020-04-08 | 6 | Closed | 1 | 0 | 0 | 27000 | 50000 | N |  | 0 | 0 | 0 | 0 | 1087 | P4 – Low
E340-RFI-0075 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – alternate epoxy-coated rebar supplier | Contractor requests approval to substitute alternate epoxy-coated rebar supplier for specified epoxy-coated rebar on work at 130th Station, citing procurement lead time. Product data attached. | Project Manager | 2020-04-06 | 10 | Routine | N | N | N | 6 | ST Design Management | 4 | 2020-04-20 | 13 | N | 3 | 1 | 2020-04-20 | 13 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1088 | P4 – Low
E340-RFI-0076 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | In-water work window – Bel-Red stormwater facility | Field conditions at Bel-Red stormwater facility require changes to temporary erosion and sediment control or stormwater facility per M-667. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2020-04-09 | 10 | Routine | N | N | N | 2 | DSDC – HJH JV | 3 | 2020-04-23 | 14 | N | 4 | 1 | 2020-04-23 | 14 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1089 | P4 – Low
E340-RFI-0077 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Ocs Pole location conflict at Sta. 1334+78 | Proposed OCS pole foundation location at Sta. 1334+78 conflicts with duct bank encasement; offset of 6 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2020-05-11 | 10 | Expedite | N | N | Y | 7 | DSDC – HJH JV | 2 | 2020-05-14 | 3 | Y | 0 | 2 | 2020-06-02 | 22 | Closed | 0 | 0 | 0 |  |  | Y | E340-CO-022 | 45600 | 14300 | 0 | 33 | 328 | P2 – High
E340-RFI-0078 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Puget Sound Energy comment on right-of-way use permit – Bel-Red stormwater facility | Puget Sound Energy review comments on the right-of-way use permit require changes to the retaining wall footing at Bel-Red stormwater facility. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2020-05-11 | 10 | Routine | Y | Y | N | 8 | WSDOT / ST Third-Party Mgmt | 1 | 2020-06-05 | 25 | N | 15 | 1 | 2020-06-05 | 25 | Closed | 14 | 0 | 5 | 313000 | 584000 | N |  | 0 | 0 | 0 | 1.1 | 581 | P3 – Medium
E340-RFI-0079 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Lane closure window request – Bel-Red Rd/NE 16th corridor | Contractor requests approval of an alternate traffic/staging plan at Bel-Red Rd/NE 16th corridor: extended night closure. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Design Manager | 2020-07-10 | 10 | Routine | Y | Y | N | 6 | DSDC – HJH JV | 1 | 2020-07-13 | 3 | Y | 0 | 1 | 2020-07-13 | 3 | Closed | 8 | 0 | 5 | 564000 | 1052000 | N |  | 0 | 0 | 0 | 1.1 | 582 | P3 – Medium
E340-RFI-0080 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Special trackwork layout – Bel-Red Rd/NE 16th corridor | Track layout at Sta. 1662+96 (Bel-Red Rd/NE 16th corridor) differs from the track-structure interface drawing C-794. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Superintendent | 2020-07-10 | 10 | Urgent | Y | N | Y | 7 | ST Design Management | 4 | 2020-07-20 | 9 | Y | 0 | 1 | 2020-07-20 | 9 | Closed | 0 | 0 | 0 | 216000 | 403000 | Y | E340-CO-023 | 191300 | 0 | 0 | 0 | 1090 | P4 – Low
E340-RFI-0081 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with fiber communications duct bank at 124th Ave NE crossing | Potholing at Sta. 1590+73 located a fiber communications duct bank in conflict with the proposed retaining wall footing. Utility is not shown on E-416. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2020-07-16 | 10 | Routine | Y | Y | N | 5 | DSDC – HJH JV | 2 | 2020-07-29 | 13 | N | 3 | 1 | 2020-07-29 | 13 | Closed | 3 | 0 | 2 | 256000 | 478000 | Y | E340-CO-024 | 255100 | 142900 | 1 | 41.7 | 205 | P2 – High
E340-RFI-0082 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bel-Red Rd/NE 16th corridor: perched groundwater | During excavation at Bel-Red Rd/NE 16th corridor (Sta. 1216+71) the contractor encountered perched groundwater at approx. elevation 228 ft, not shown on the GBR or S-820. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Project Engineer | 2020-09-11 | 10 | Urgent | Y | N | Y | 5 | DSDC – HJH JV | 3 | 2020-09-21 | 10 | Y | 0 | 1 | 2020-09-21 | 10 | Closed | 0 | 0 | 0 | 636000 | 1188000 | Y | E340-CO-025 | 651600 | 524200 | 0 | 45.4 | 131 | P2 – High
E340-RFI-0083 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Bel-Red stormwater facility | S-481 shows a 41 ft-6 in. dimension for the stair core wall; structural sheet S-285 shows a different value. Request clarification before fabrication/rebar release. | Project Manager | 2020-09-23 | 10 | Urgent | N | Y | N | 5 | DSDC – HJH JV | 2 | 2020-09-29 | 6 | Y | 0 | 1 | 2020-09-29 | 6 | Closed | 4 | 0 | 2 |  |  | Y | E340-CO-026 | 68400 | 57000 | 1 | 38.5 | 265 | P2 – High
E340-RFI-0084 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | City of Bellevue comment on clearing and grading permit – 130th Station | City of Bellevue review comments on the clearing and grading permit require changes to the stair core wall at 130th Station. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2020-10-22 | 10 | Urgent | N | N | N | 0 | Puget Sound Energy / ST Third-Party Mgmt | 1 | 2020-10-27 | 5 | Y | 0 | 1 | 2020-10-27 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1091 | P4 – Low
E340-RFI-0085 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red Rd/NE 16th corridor | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – platform edge slab and column reinforcement at Bel-Red Rd/NE 16th corridor | Interference between platform edge slab and column reinforcement at Bel-Red Rd/NE 16th corridor per A-814. Required clearance of 7 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2020-10-26 | 10 | Urgent | N | N | Y | 5 | DSDC – HJH JV | 1 | 2020-11-02 | 7 | Y | 0 | 1 | 2020-11-02 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1092 | P4 – Low
E340-RFI-0086 | E340 | East Link Extension | Max J. Kuney Company | 124th Ave NE crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 12-in. ductile iron water main at 124th Ave NE crossing | Potholing at Sta. 1179+29 located a 12-in. ductile iron water main in conflict with the proposed platform edge slab. Utility is not shown on C-884. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Project Manager | 2020-11-02 | 10 | Routine | Y | Y | N | 5 | DSDC – HJH JV | 3 | 2020-11-05 | 3 | Y | 0 | 2 | 2020-11-25 | 23 | Closed | 9 | 0 | 7 | 63000 | 118000 | Y | E340-CO-027 | 73400 | 73400 | 7 | 42.5 | 188 | P2 – High
E340-RFI-0087 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red at-grade guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 24-in. sanitary sewer at Bel-Red at-grade guideway | Potholing at Sta. 1202+35 located a 24-in. sanitary sewer in conflict with the proposed column reinforcement. Utility is not shown on E-235. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Superintendent | 2020-11-09 | 10 | Expedite | Y | N | N | 4 | ST Design Management | 1 | 2020-11-16 | 7 | Y | 0 | 1 | 2020-11-16 | 7 | Closed | 0 | 0 | 0 | 30000 | 55000 | Y | E340-CO-028 | 33800 | 12200 | 0 | 32.4 | 333 | P2 – High
E340-RFI-0088 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Canopy/glazing connection – 130th Station | Request to clarify finish/connection detail on C-810 at 130th Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Manager | 2020-11-30 | 10 | Routine | N | N | N | 6 | DSDC – HJH JV | 2 | 2020-12-07 | 5 | Y | 0 | 1 | 2020-12-07 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1093 | P4 – Low
E340-RFI-0089 | E340 | East Link Extension | Max J. Kuney Company | Bel-Red stormwater facility | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | WSDOT comment on street improvement permit – Bel-Red stormwater facility | WSDOT review comments on the street improvement permit require changes to the retaining wall footing at Bel-Red stormwater facility. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2020-12-22 | 10 | Expedite | N | N | Y | 7 | Puget Sound Energy / ST Third-Party Mgmt | 3 | 2021-01-05 | 14 | N | 4 | 1 | 2021-01-05 | 14 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1094 | P4 – Low
E340-RFI-0090 | E340 | East Link Extension | Max J. Kuney Company | 130th Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 24-in. sanitary sewer at 130th Station | Potholing at Sta. 1404+29 located a 24-in. sanitary sewer in conflict with the proposed retaining wall footing. Utility is not shown on M-117. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Field Engineer | 2021-06-16 | 10 | Routine | N | N | N | 7 | DSDC – HJH JV | 2 | 2021-06-22 | 6 | Y | 0 | 1 | 2021-06-22 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1095 | P4 – Low
E360-RFI-0001 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – retaining wall footing at 152nd Ave NE crossing | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-826 for egress width at 152nd Ave NE crossing. Request direction on compliant detail. | Superintendent | 2016-10-06 | 10 | Routine | Y | Y | N | 5 | Design-Builder EOR / ST Design Review | 2 | 2016-10-10 | 4 | Y | 0 | 1 | 2016-10-10 | 4 | Closed | 3 | 0 | 2 | 231000 | 432000 | N |  | 0 | 0 | 0 | 0.4 | 723 | P3 – Medium
E360-RFI-0002 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Overlake Village Station | S-625 shows a 38 ft-5 in. dimension for the column reinforcement; structural sheet S-508 shows a different value. Request clarification before fabrication/rebar release. | Scheduler | 2016-11-08 | 10 | Routine | N | Y | N | 7 | Design-Builder EOR / ST Design Review | 1 | 2016-11-14 | 4 | Y | 0 | 2 | 2016-11-30 | 22 | Closed | 2 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 724 | P3 – Medium
E360-RFI-0003 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – Redmond Technology Station | Civil and systems drawings differ on grounding/bonding of bearing pad/embed plate for stray-current control at Redmond Technology Station. Request governing detail and responsibility for installation. | Design Manager | 2016-12-26 | 10 | Urgent | N | N | N | 7 | Design-Builder EOR / ST Design Review | 2 | 2017-01-10 | 15 | N | 5 | 1 | 2017-01-10 | 15 | Closed | 0 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 725 | P3 – Medium
E360-RFI-0004 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Stormwater facility revision – Overlake Village Station | Field conditions at Overlake Village Station require changes to temporary erosion and sediment control or stormwater facility per A-325. Request direction considering critical-areas conditions and permit requirements. | Scheduler | 2017-01-12 | 10 | Urgent | N | N | N | 5 | Design-Builder EOR / ST Design Review | 1 | 2017-01-23 | 9 | Y | 0 | 1 | 2017-01-23 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1096 | P4 – Low
E360-RFI-0005 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | WSDOT comment on clearing and grading permit – Overlake Village Station | WSDOT review comments on the clearing and grading permit require changes to the column reinforcement at Overlake Village Station. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2017-01-24 | 10 | Routine | N | Y | N | 4 | City of Bellevue / ST Third-Party Mgmt | 2 | 2017-02-13 | 18 | N | 8 | 1 | 2017-02-13 | 18 | Closed | 18 | 0 | 4 |  |  | Y | E360-CO-001 | 25700 | 20800 | 12 | 39.2 | 256 | P2 – High
E360-RFI-0006 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – galvanized steel handrail | Contractor requests approval to substitute galvanized steel handrail for stainless steel handrail on work at Redmond Technology Station, citing procurement lead time. Product data attached. | Project Engineer | 2017-02-02 | 10 | Routine | N | N | N | 1 | Design-Builder EOR / ST Design Review | 1 | 2017-02-10 | 8 | Y | 0 | 1 | 2017-02-10 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1097 | P4 – Low
E360-RFI-0007 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – NE 40th St | C-338 shows a 25 ft-5 in. dimension for the stair core wall; structural sheet S-523 shows a different value. Request clarification before fabrication/rebar release. | Project Manager | 2017-02-08 | 10 | Routine | N | Y | N | 3 | Design-Builder EOR / ST Design Review | 2 | 2017-02-13 | 4 | Y | 0 | 1 | 2017-02-13 | 4 | Closed | 5 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 673 | P3 – Medium
E360-RFI-0008 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Rail Bonding location conflict at Sta. 927+87 | Proposed rail bonding foundation location at Sta. 927+87 conflicts with bearing pad/embed plate; offset of 4 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2017-03-13 | 10 | Routine | Y | Y | N | 5 | Design-Builder EOR / ST Design Review | 3 | 2017-03-20 | 7 | Y | 0 | 1 | 2017-03-20 | 7 | Closed | 5 | 0 | 2 | 1775000 | 3313000 | Y | E360-CO-002 | 2029700 | 1062900 | 1 | 48.6 | 82 | P1 – Critical
E360-RFI-0009 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Overlake Village Station | A-277 shows a 11 ft-3 in. dimension for the bearing pad/embed plate; structural sheet S-284 shows a different value. Request clarification before fabrication/rebar release. | Field Engineer | 2017-04-07 | 10 | Urgent | N | N | Y | 2 | Design-Builder EOR / ST Design Review | 1 | 2017-04-13 | 6 | Y | 0 | 1 | 2017-04-13 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1098 | P4 – Low
E360-RFI-0010 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | TESC modification – NE 40th St | Field conditions at NE 40th St require changes to temporary erosion and sediment control or stormwater facility per A-355. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2017-04-17 | 10 | Expedite | Y | N | N | 8 | Design-Builder EOR / ST Design Review | 2 | 2017-04-24 | 7 | Y | 0 | 1 | 2017-04-24 | 7 | Closed | 0 | 0 | 0 | 362000 | 675000 | N |  | 0 | 0 | 0 | 0 | 1099 | P4 – Low
E360-RFI-0011 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Property owner access/restoration requirement – SR 520 right-of-way aerial guideway | Adjacent property owner has requested additional restoration and access provisions at SR 520 right-of-way aerial guideway beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Design Manager | 2017-05-04 | 10 | Expedite | N | Y | N | 7 | City of Bellevue / ST Third-Party Mgmt | 2 | 2017-05-29 | 25 | N | 15 | 1 | 2017-05-29 | 25 | Closed | 16 | 0 | 13 |  |  | Y | E360-CO-003 | 70700 | 63100 | 10 | 44.3 | 156 | P2 – High
E360-RFI-0012 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | City of Bellevue comment on critical areas permit – Redmond Technology Station | City of Bellevue review comments on the critical areas permit require changes to the column reinforcement at Redmond Technology Station. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2017-06-05 | 10 | Routine | Y | Y | N | 6 | City of Bellevue / ST Third-Party Mgmt | 4 | 2017-06-16 | 11 | N | 1 | 1 | 2017-06-16 | 11 | Closed | 3 | 0 | 2 | 212000 | 396000 | Y | E360-CO-004 | 185100 | 0 | 0 | 0.4 | 726 | P3 – Medium
E360-RFI-0013 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Missing dimension on M-116 | Request clarification of 01 33 00 Submittal Procedures and M-116: dimension/notes appear inconsistent or omitted for the work at SR 520 pedestrian bridges. | Project Engineer | 2017-06-14 | 10 | Routine | Y | N | N | 1 | Design-Builder EOR / ST Design Review | 3 | 2017-06-19 | 4 | Y | 0 | 2 | 2017-07-05 | 21 | Closed | 0 | 0 | 0 | 35000 | 65000 | Y | E360-CO-005 | 33900 | 33900 | 0 | 35.9 | 303 | P2 – High
E360-RFI-0014 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with abandoned utility vault at Redmond Technology Station | Potholing at Sta. 1550+66 located a abandoned utility vault in conflict with the proposed guideway girder diaphragm. Utility is not shown on S-451. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Manager | 2017-07-05 | 10 | Expedite | Y | N | N | 1 | Design-Builder EOR / ST Design Review | 1 | 2017-07-20 | 15 | N | 5 | 1 | 2017-07-20 | 15 | Closed | 0 | 0 | 3 | 57000 | 106000 | Y | E360-CO-006 | 129600 | 75900 | 0 | 39.4 | 250 | P2 – High
E360-RFI-0015 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at SR 520 right-of-way aerial guideway: abandoned timber piles | During excavation at SR 520 right-of-way aerial guideway (Sta. 2180+75) the contractor encountered abandoned timber piles, not shown on the GBR or E-130. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Field Engineer | 2017-07-19 | 10 | Routine | Y | Y | N | 8 | Design-Builder EOR / ST Design Review | 2 | 2017-07-31 | 10 | Y | 0 | 1 | 2017-07-31 | 10 | Closed | 9 | 0 | 5 | 97000 | 181000 | Y | E360-CO-007 | 182300 | 182300 | 9 | 45.9 | 125 | P2 – High
E360-RFI-0016 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | WSDOT comment on critical areas permit – Redmond Technology Station | WSDOT review comments on the critical areas permit require changes to the drilled shaft cap at Redmond Technology Station. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2017-07-21 | 10 | Expedite | N | N | N | 0 | Puget Sound Energy / ST Third-Party Mgmt | 2 | 2017-08-07 | 17 | N | 7 | 2 | 2017-08-21 | 29 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1100 | P4 – Low
E360-RFI-0017 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with fiber communications duct bank at 152nd Ave NE crossing | Potholing at Sta. 2121+15 located a fiber communications duct bank in conflict with the proposed pedestrian ramp. Utility is not shown on C-850. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Scheduler | 2017-07-27 | 10 | Routine | N | Y | Y | 4 | Design-Builder EOR / ST Design Review | 1 | 2017-07-31 | 4 | Y | 0 | 1 | 2017-07-31 | 4 | Closed | 24 | 21 | 0 |  |  | Y | E360-CO-008 | 115300 | 57100 | 13 | 63.1 | 15 | P1 – Critical
E360-RFI-0018 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Canopy/glazing connection – 152nd Ave NE crossing | Request to clarify finish/connection detail on S-198 at 152nd Ave NE crossing. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Manager | 2017-07-28 | 10 | Urgent | N | N | N | 7 | Design-Builder EOR / ST Design Review | 2 | 2017-07-31 | 3 | Y | 0 | 1 | 2017-07-31 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1101 | P4 – Low
E360-RFI-0019 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Embedded conduit stub-ups – Redmond Technology Station | Systems contractor requires 5-in. PVC conduit stub-ups for fiber backbone at Redmond Technology Station not provided in civil C-244. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2017-08-01 | 10 | Routine | N | N | N | 1 | Design-Builder EOR / ST Design Review | 2 | 2017-08-21 | 19 | N | 9 | 1 | 2017-08-21 | 19 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1102 | P4 – Low
E360-RFI-0020 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – guideway girder diaphragm sequence at 152nd Ave NE crossing | Erection of the guideway girder diaphragm as drawn conflicts with adjacent work and access limits at 152nd Ave NE crossing. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Field Engineer | 2017-08-08 | 10 | Routine | N | Y | N | 1 | Design-Builder EOR / ST Design Review | 2 | 2017-08-16 | 8 | Y | 0 | 1 | 2017-08-16 | 8 | Closed | 5 | 0 | 2 |  |  | Y | E360-CO-009 | 240900 | 156600 | 2 | 42.3 | 195 | P2 – High
E360-RFI-0021 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Overlake Village Station: buried concrete debris and an old foundation | During excavation at Overlake Village Station (Sta. 1742+57) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or C-817. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Design Manager | 2017-08-11 | 10 | Urgent | N | Y | Y | 4 | Design-Builder EOR / ST Design Review | 4 | 2017-08-16 | 5 | Y | 0 | 1 | 2017-08-16 | 5 | Closed | 5 | 5 | 0 |  |  | N |  | 0 | 0 | 0 | 5 | 441 | P3 – Medium
E360-RFI-0022 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 30-in. storm drain at Overlake Village Station | Potholing at Sta. 1439+45 located a 30-in. storm drain in conflict with the proposed drilled shaft cap. Utility is not shown on E-757. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Field Engineer | 2017-09-20 | 10 | Routine | Y | N | Y | 3 | Design-Builder EOR / ST Design Review | 2 | 2017-09-26 | 6 | Y | 0 | 1 | 2017-09-26 | 6 | Closed | 0 | 0 | 0 | 72000 | 135000 | Y | E360-CO-010 | 72400 | 32500 | 0 | 35.8 | 306 | P2 – High
E360-RFI-0023 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – SR 520 pedestrian bridges | Systems contractor requires 2-in. PVC conduit stub-ups for SCADA cabinet at SR 520 pedestrian bridges not provided in civil A-164. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2017-09-20 | 10 | Expedite | Y | Y | Y | 3 | Design-Builder EOR / ST Design Review | 2 | 2017-10-06 | 16 | N | 6 | 1 | 2017-10-06 | 16 | Closed | 59 | 23 | 0 | 26000 | 49000 | Y | E360-CO-011 | 29400 | 22000 | 24 | 65.5 | 11 | P1 – Critical
E360-RFI-0024 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – Redmond Technology Station | Civil and systems drawings differ on grounding/bonding of retaining wall footing for stray-current control at Redmond Technology Station. Request governing detail and responsibility for installation. | Design Manager | 2017-10-02 | 10 | Routine | N | Y | N | 1 | Design-Builder EOR / ST Design Review | 3 | 2017-10-23 | 20 | N | 10 | 1 | 2017-10-23 | 20 | Closed | 2 | 0 | 7 |  |  | N |  | 0 | 0 | 0 | 1.6 | 556 | P3 – Medium
E360-RFI-0025 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – stair core wall at SR 520 pedestrian bridges | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-346 for emergency stair pressurization at SR 520 pedestrian bridges. Request direction on compliant detail. | Design Manager | 2017-10-13 | 10 | Routine | Y | N | N | 2 | Design-Builder EOR / ST Design Review | 3 | 2017-10-23 | 8 | Y | 0 | 1 | 2017-10-23 | 8 | Closed | 0 | 0 | 0 | 1025000 | 1913000 | Y | E360-CO-012 | 946300 | 0 | 0 | 0 | 1103 | P4 – Low
E360-RFI-0026 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on building permit – Overlake Village Station | WSDOT review comments on the building permit require changes to the duct bank encasement at Overlake Village Station. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2017-11-13 | 10 | Routine | Y | N | Y | 7 | City of Bellevue / ST Third-Party Mgmt | 3 | 2017-11-24 | 11 | N | 1 | 1 | 2017-11-24 | 11 | Closed | 0 | 0 | 0 | 203000 | 379000 | N |  | 0 | 0 | 0 | 0 | 1104 | P4 – Low
E360-RFI-0027 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Drawing/spec discrepancy – Overlake Village Station | Request clarification of 00 72 00 General Conditions and C-473: dimension/notes appear inconsistent or omitted for the work at Overlake Village Station. | Field Engineer | 2017-11-20 | 10 | Urgent | N | N | N | 8 | Design-Builder EOR / ST Design Review | 1 | 2017-11-27 | 5 | Y | 0 | 1 | 2017-11-27 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1105 | P4 – Low
E360-RFI-0028 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on street improvement permit – NE 40th St | WSDOT review comments on the street improvement permit require changes to the station canopy support at NE 40th St. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2017-12-11 | 10 | Routine | Y | Y | N | 8 | WSDOT / ST Third-Party Mgmt | 2 | 2017-12-15 | 4 | Y | 0 | 1 | 2017-12-15 | 4 | Closed | 5 | 0 | 2 | 1066000 | 1990000 | N |  | 0 | 0 | 0 | 0.4 | 727 | P3 – Medium
E360-RFI-0029 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Grounding/bonding and stray-current detail – Redmond Technology Station | Civil and systems drawings differ on grounding/bonding of stair core wall for stray-current control at Redmond Technology Station. Request governing detail and responsibility for installation. | Design Manager | 2017-12-28 | 10 | Routine | N | N | N | 3 | Design-Builder EOR / ST Design Review | 1 | 2018-01-03 | 6 | Y | 0 | 1 | 2018-01-03 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1106 | P4 – Low
E360-RFI-0030 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with abandoned utility vault at SR 520 pedestrian bridges | Potholing at Sta. 1674+00 located a abandoned utility vault in conflict with the proposed stair core wall. Utility is not shown on E-520. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Superintendent | 2018-01-09 | 10 | Routine | Y | Y | N | 2 | Design-Builder EOR / ST Design Review | 1 | 2018-01-15 | 5 | Y | 0 | 1 | 2018-01-15 | 5 | Closed | 9 | 0 | 5 | 169000 | 315000 | N |  | 0 | 0 | 0 | 1.1 | 583 | P3 – Medium
E360-RFI-0031 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Lane closure window request – SR 520 pedestrian bridges | Contractor requests approval of an alternate traffic/staging plan at SR 520 pedestrian bridges: crane pick over active roadway. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Superintendent | 2018-01-12 | 10 | Urgent | N | N | Y | 3 | Design-Builder EOR / ST Design Review | 2 | 2018-01-15 | 3 | Y | 0 | 2 | 2018-01-22 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1107 | P4 – Low
E360-RFI-0032 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with abandoned utility vault at SR 520 pedestrian bridges | Potholing at Sta. 1153+75 located a abandoned utility vault in conflict with the proposed station canopy support. Utility is not shown on M-634. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Manager | 2018-01-17 | 10 | Expedite | N | Y | N | 4 | Design-Builder EOR / ST Design Review | 1 | 2018-01-24 | 7 | Y | 0 | 1 | 2018-01-24 | 7 | Closed | 3 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 728 | P3 – Medium
E360-RFI-0033 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake garage | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – pedestrian ramp and stair core wall at Overlake garage | Interference between pedestrian ramp and stair core wall at Overlake garage per S-567. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Field Engineer | 2018-02-05 | 10 | Urgent | Y | N | Y | 6 | Design-Builder EOR / ST Design Review | 1 | 2018-02-12 | 6 | Y | 0 | 1 | 2018-02-12 | 6 | Closed | 0 | 0 | 0 | 2608000 | 4868000 | Y | E360-CO-013 | 3336300 | 2288300 | 0 | 50 | 57 | P1 – Critical
E360-RFI-0034 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Missing dimension on E-895 | Request clarification of 01 33 00 Submittal Procedures and E-895: dimension/notes appear inconsistent or omitted for the work at Redmond Technology Station. | Project Manager | 2018-02-23 | 10 | Routine | N | N | N | 6 | Design-Builder EOR / ST Design Review | 5 | 2018-02-28 | 5 | Y | 0 | 1 | 2018-02-28 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1108 | P4 – Low
E360-RFI-0035 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on street improvement permit – 152nd Ave NE crossing | WSDOT review comments on the street improvement permit require changes to the station canopy support at 152nd Ave NE crossing. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2018-03-06 | 10 | Urgent | Y | Y | N | 3 | WSDOT / ST Third-Party Mgmt | 4 | 2018-03-12 | 4 | Y | 0 | 1 | 2018-03-12 | 4 | Closed | 7 | 0 | 2 | 733000 | 1369000 | N |  | 0 | 0 | 0 | 0.4 | 729 | P3 – Medium
E360-RFI-0036 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Art embed coordination – SR 520 right-of-way aerial guideway | Request to clarify finish/connection detail on A-626 at SR 520 right-of-way aerial guideway. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2018-03-07 | 10 | Routine | N | N | N | 6 | Design-Builder EOR / ST Design Review | 2 | 2018-03-12 | 3 | Y | 0 | 1 | 2018-03-12 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1109 | P4 – Low
E360-RFI-0037 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Missing dimension on A-634 | Request clarification of 01 25 00 Substitution Procedures and A-634: dimension/notes appear inconsistent or omitted for the work at SR 520 right-of-way aerial guideway. | Project Engineer | 2018-03-08 | 10 | Routine | N | N | N | 1 | Design-Builder EOR / ST Design Review | 3 | 2018-03-12 | 4 | Y | 0 | 1 | 2018-03-12 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1110 | P4 – Low
E360-RFI-0038 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Overlake Village Station: an unmapped abandoned storm line | During excavation at Overlake Village Station (Sta. 1599+20) the contractor encountered an unmapped abandoned storm line, not shown on the GBR or S-258. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Scheduler | 2018-03-12 | 10 | Urgent | Y | Y | Y | 2 | Design-Builder EOR / ST Design Review | 4 | 2018-03-13 | 1 | Y | 0 | 1 | 2018-03-13 | 1 | Closed | 22 | 19 | 0 | 2961000 | 5527000 | Y | E360-CO-014 | 5182700 | 0 | 0 | 19 | 363 | P3 – Medium
E360-RFI-0039 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Property owner access/restoration requirement – Redmond Technology Station | Adjacent property owner has requested additional restoration and access provisions at Redmond Technology Station beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Design Manager | 2018-03-13 | 10 | Routine | N | N | Y | 7 | WSDOT / ST Third-Party Mgmt | 1 | 2018-03-27 | 14 | N | 4 | 2 | 2018-04-12 | 30 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1111 | P4 – Low
E360-RFI-0040 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 24-in. sanitary sewer at Redmond Technology Station | Potholing at Sta. 1325+52 located a 24-in. sanitary sewer in conflict with the proposed bearing pad/embed plate. Utility is not shown on S-105. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Scheduler | 2018-04-09 | 10 | Urgent | N | Y | Y | 3 | Design-Builder EOR / ST Design Review | 1 | 2018-04-11 | 2 | Y | 0 | 1 | 2018-04-11 | 2 | Closed | 20 | 8 | 0 |  |  | N |  | 0 | 0 | 0 | 8 | 411 | P3 – Medium
E360-RFI-0041 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | WSDOT comment on right-of-way use permit – 152nd Ave NE crossing | WSDOT review comments on the right-of-way use permit require changes to the guideway girder diaphragm at 152nd Ave NE crossing. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2018-04-11 | 10 | Routine | N | N | N | 3 | Puget Sound Energy / ST Third-Party Mgmt | 1 | 2018-04-18 | 7 | Y | 0 | 1 | 2018-04-18 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1112 | P4 – Low
E360-RFI-0042 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake garage | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Overlake garage | Systems contractor requires 3-in. PVC conduit stub-ups for rail bonding at Overlake garage not provided in civil C-811. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2018-04-23 | 10 | Routine | N | N | Y | 1 | Design-Builder EOR / ST Design Review | 1 | 2018-05-02 | 9 | Y | 0 | 1 | 2018-05-02 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1113 | P4 – Low
E360-RFI-0043 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 12-in. ductile iron water main at 152nd Ave NE crossing | Potholing at Sta. 1467+95 located a 12-in. ductile iron water main in conflict with the proposed guideway girder diaphragm. Utility is not shown on A-336. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Design Manager | 2018-05-21 | 10 | Routine | Y | N | Y | 6 | Design-Builder EOR / ST Design Review | 1 | 2018-05-30 | 9 | Y | 0 | 1 | 2018-05-30 | 9 | Closed | 0 | 2 | 0 | 157000 | 294000 | Y | E360-CO-015 | 237200 | 237200 | 0 | 44.7 | 144 | P2 – High
E360-RFI-0044 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | WSDOT comment on critical areas permit – SR 520 right-of-way aerial guideway | WSDOT review comments on the critical areas permit require changes to the bearing pad/embed plate at SR 520 right-of-way aerial guideway. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2018-06-11 | 10 | Expedite | Y | Y | N | 4 | City of Bellevue / ST Third-Party Mgmt | 3 | 2018-06-20 | 9 | Y | 0 | 2 | 2018-07-02 | 21 | Closed | 12 | 0 | 7 | 827000 | 1544000 | N |  | 0 | 0 | 0 | 1.6 | 557 | P3 – Medium
E360-RFI-0045 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – platform edge slab and bearing pad/embed plate at NE 40th St | Interference between platform edge slab and bearing pad/embed plate at NE 40th St per M-569. Required clearance of 6 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Scheduler | 2018-06-18 | 10 | Routine | Y | Y | N | 3 | Design-Builder EOR / ST Design Review | 1 | 2018-06-25 | 7 | Y | 0 | 1 | 2018-06-25 | 7 | Closed | 2 | 0 | 1 | 116000 | 217000 | N |  | 0 | 0 | 0 | 0.2 | 787 | P4 – Low
E360-RFI-0046 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with PSE distribution duct bank at NE 40th St | Potholing at Sta. 1066+64 located a PSE distribution duct bank in conflict with the proposed station canopy support. Utility is not shown on S-872. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Scheduler | 2018-06-21 | 10 | Routine | N | N | N | 6 | Design-Builder EOR / ST Design Review | 3 | 2018-07-03 | 12 | N | 2 | 2 | 2018-07-18 | 27 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1114 | P4 – Low
E360-RFI-0047 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – stair core wall and station canopy support at Redmond Technology Station | Interference between stair core wall and station canopy support at Redmond Technology Station per E-237. Required clearance of 7 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2018-07-02 | 10 | Routine | N | N | N | 6 | Design-Builder EOR / ST Design Review | 2 | 2018-07-13 | 11 | N | 1 | 2 | 2018-07-26 | 24 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1115 | P4 – Low
E360-RFI-0048 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at SR 520 right-of-way aerial guideway, citing procurement lead time. Product data attached. | Field Engineer | 2018-07-25 | 10 | Urgent | Y | N | N | 5 | Design-Builder EOR / ST Design Review | 1 | 2018-07-30 | 5 | Y | 0 | 1 | 2018-07-30 | 5 | Closed | 0 | 0 | 0 | 244000 | 455000 | N |  | 0 | 0 | 0 | 0 | 1116 | P4 – Low
E360-RFI-0049 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on critical areas permit – Redmond Technology Station | WSDOT review comments on the critical areas permit require changes to the duct bank encasement at Redmond Technology Station. Request direction on scope impacts and whether comments are within the contract requirements. | Project Engineer | 2018-08-10 | 10 | Routine | Y | Y | N | 8 | Puget Sound Energy / ST Third-Party Mgmt | 1 | 2018-08-20 | 8 | Y | 0 | 2 | 2018-09-07 | 28 | Closed | 1 | 0 | 1 | 17000 | 32000 | N |  | 0 | 0 | 0 | 0.2 | 788 | P4 – Low
E360-RFI-0050 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake garage | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Stormwater facility revision – Overlake garage | Field conditions at Overlake garage require changes to temporary erosion and sediment control or stormwater facility per E-128. Request direction considering critical-areas conditions and permit requirements. | Field Engineer | 2018-08-24 | 10 | Urgent | N | Y | Y | 1 | Design-Builder EOR / ST Design Review | 2 | 2018-09-03 | 8 | Y | 0 | 1 | 2018-09-03 | 8 | Closed | 31 | 12 | 0 |  |  | N |  | 0 | 0 | 0 | 12 | 379 | P3 – Medium
E360-RFI-0051 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at NE 40th St: soft lacustrine silt below design subgrade | During excavation at NE 40th St (Sta. 1130+12) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or A-613. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Scheduler | 2018-08-27 | 10 | Routine | Y | Y | Y | 4 | Design-Builder EOR / ST Design Review | 1 | 2018-09-03 | 6 | Y | 0 | 1 | 2018-09-03 | 6 | Closed | 8 | 5 | 0 | 2559000 | 4776000 | Y | E360-CO-016 | 2131300 | 488900 | 2 | 50.8 | 50 | P1 – Critical
E360-RFI-0052 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | WSDOT comment on building permit – SR 520 pedestrian bridges | WSDOT review comments on the building permit require changes to the platform edge slab at SR 520 pedestrian bridges. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2018-09-11 | 10 | Routine | Y | N | N | 0 | WSDOT / ST Third-Party Mgmt | 4 | 2018-09-27 | 16 | N | 6 | 1 | 2018-09-27 | 16 | Closed | 0 | 0 | 0 | 434000 | 810000 | Y | E360-CO-017 | 327910 | 158600 | 1.1 | 41.6 | 207 | P2 – High
E360-RFI-0053 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – NE 40th St | M-839 shows a 25 ft-4 in. dimension for the pedestrian ramp; structural sheet S-892 shows a different value. Request clarification before fabrication/rebar release. | Design Manager | 2018-09-18 | 10 | Routine | Y | N | Y | 4 | Design-Builder EOR / ST Design Review | 1 | 2018-10-01 | 11 | N | 1 | 1 | 2018-10-01 | 11 | Closed | 0 | 0 | 0 | 898000 | 1677000 | N |  | 0 | 0 | 0 | 0 | 1117 | P4 – Low
E360-RFI-0054 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Haul route revision – SR 520 pedestrian bridges | Contractor requests approval of an alternate traffic/staging plan at SR 520 pedestrian bridges: revised haul route. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Project Engineer | 2018-09-27 | 10 | Urgent | N | Y | Y | 7 | Design-Builder EOR / ST Design Review | 2 | 2018-10-03 | 6 | Y | 0 | 1 | 2018-10-03 | 6 | Closed | 35 | 16 | 0 |  |  | N |  | 0 | 0 | 0 | 16 | 368 | P3 – Medium
E360-RFI-0055 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake garage | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Property owner access/restoration requirement – Overlake garage | Adjacent property owner has requested additional restoration and access provisions at Overlake garage beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Scheduler | 2018-10-11 | 10 | Routine | Y | Y | Y | 4 | WSDOT / ST Third-Party Mgmt | 3 | 2018-10-22 | 11 | N | 1 | 1 | 2018-10-22 | 11 | Closed | 4 | 1 | 0 | 219000 | 409000 | Y | E360-CO-017 | 257190 | 124400 | 0.9 | 41.7 | 206 | P2 – High
E360-RFI-0056 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake garage | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Signal Case location conflict at Sta. 2384+87 | Proposed signal case foundation location at Sta. 2384+87 conflicts with station canopy support; offset of 13 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Project Manager | 2018-10-11 | 10 | Routine | N | Y | N | 8 | Design-Builder EOR / ST Design Review | 1 | 2018-10-24 | 13 | N | 3 | 1 | 2018-10-24 | 13 | Closed | 6 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 674 | P3 – Medium
E360-RFI-0057 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Overlake Village Station: an unmapped abandoned storm line | During excavation at Overlake Village Station (Sta. 1550+63) the contractor encountered an unmapped abandoned storm line, not shown on the GBR or M-558. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Superintendent | 2018-11-06 | 10 | Expedite | Y | Y | Y | 0 | Design-Builder EOR / ST Design Review | 2 | 2018-11-13 | 7 | Y | 0 | 1 | 2018-11-13 | 7 | Closed | 5 | 3 | 0 | 447000 | 835000 | Y | E360-CO-018 | 748600 | 346100 | 1 | 47.3 | 100 | P1 – Critical
E360-RFI-0058 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Grounding/bonding and stray-current detail – SR 520 right-of-way aerial guideway | Civil and systems drawings differ on grounding/bonding of column reinforcement for stray-current control at SR 520 right-of-way aerial guideway. Request governing detail and responsibility for installation. | Field Engineer | 2018-11-07 | 10 | Expedite | Y | N | N | 6 | Design-Builder EOR / ST Design Review | 2 | 2018-11-21 | 14 | N | 4 | 1 | 2018-11-21 | 14 | Closed | 0 | 0 | 1 | 260000 | 485000 | Y | E360-CO-019 | 479900 | 332100 | 0 | 44 | 161 | P2 – High
E360-RFI-0059 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – guideway girder diaphragm at NE 40th St | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-131 for standpipe connection at NE 40th St. Request direction on compliant detail. | Design Manager | 2018-11-13 | 10 | Urgent | N | N | Y | 7 | Design-Builder EOR / ST Design Review | 4 | 2018-12-07 | 24 | N | 14 | 1 | 2018-12-07 | 24 | Closed | 0 | 3 | 0 |  |  | N |  | 0 | 0 | 0 | 3 | 480 | P3 – Medium
E360-RFI-0060 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake garage | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Art embed coordination – Overlake garage | Request to clarify finish/connection detail on C-795 at Overlake garage. Includes coordination with art program embeds and handrail sleeves as applicable. | Scheduler | 2018-11-26 | 10 | Routine | N | Y | N | 2 | Design-Builder EOR / ST Design Review | 2 | 2018-12-04 | 8 | Y | 0 | 1 | 2018-12-04 | 8 | Closed | 3 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 730 | P3 – Medium
E360-RFI-0061 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Canopy/glazing connection – SR 520 right-of-way aerial guideway | Request to clarify finish/connection detail on M-602 at SR 520 right-of-way aerial guideway. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2018-11-30 | 10 | Routine | N | N | N | 3 | Design-Builder EOR / ST Design Review | 4 | 2018-12-07 | 7 | Y | 0 | 1 | 2018-12-07 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1118 | P4 – Low
E360-RFI-0062 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | In-water work window – Redmond Technology Station | Field conditions at Redmond Technology Station require changes to temporary erosion and sediment control or stormwater facility per C-827. Request direction considering critical-areas conditions and permit requirements. | Project Manager | 2018-12-19 | 10 | Routine | N | N | N | 6 | Design-Builder EOR / ST Design Review | 4 | 2019-01-14 | 26 | N | 16 | 1 | 2019-01-14 | 26 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1119 | P4 – Low
E360-RFI-0063 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 12-in. ductile iron water main at Overlake Village Station | Potholing at Sta. 1198+23 located a 12-in. ductile iron water main in conflict with the proposed pedestrian ramp. Utility is not shown on A-207. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Scheduler | 2018-12-31 | 10 | Routine | N | Y | Y | 3 | Design-Builder EOR / ST Design Review | 3 | 2019-01-09 | 9 | Y | 0 | 1 | 2019-01-09 | 9 | Closed | 2 | 2 | 0 |  |  | N |  | 0 | 0 | 0 | 2 | 521 | P3 – Medium
E360-RFI-0064 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Scada Cabinet location conflict at Sta. 984+18 | Proposed SCADA cabinet foundation location at Sta. 984+18 conflicts with guideway girder diaphragm; offset of 2 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Superintendent | 2019-01-07 | 10 | Routine | N | Y | N | 8 | Design-Builder EOR / ST Design Review | 2 | 2019-01-14 | 7 | Y | 0 | 1 | 2019-01-14 | 7 | Closed | 24 | 0 | 14 |  |  | N |  | 0 | 0 | 0 | 3.1 | 469 | P3 – Medium
E360-RFI-0065 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | WSDOT comment on building permit – 152nd Ave NE crossing | WSDOT review comments on the building permit require changes to the bearing pad/embed plate at 152nd Ave NE crossing. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2019-01-14 | 10 | Routine | Y | N | N | 4 | Puget Sound Energy / ST Third-Party Mgmt | 2 | 2019-01-18 | 4 | Y | 0 | 1 | 2019-01-18 | 4 | Closed | 0 | 0 | 0 | 730000 | 1363000 | N |  | 0 | 0 | 0 | 0 | 1120 | P4 – Low
E360-RFI-0066 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Tunnel Emergency Phone location conflict at Sta. 2015+39 | Proposed tunnel emergency phone foundation location at Sta. 2015+39 conflicts with guideway girder diaphragm; offset of 3 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Superintendent | 2019-01-18 | 10 | Urgent | Y | Y | Y | 3 | Design-Builder EOR / ST Design Review | 1 | 2019-01-24 | 6 | Y | 0 | 1 | 2019-01-24 | 6 | Closed | 14 | 5 | 0 | 874000 | 1632000 | N |  | 0 | 0 | 0 | 5 | 442 | P3 – Medium
E360-RFI-0067 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Special trackwork layout – SR 520 right-of-way aerial guideway | Track layout at Sta. 2298+02 (SR 520 right-of-way aerial guideway) differs from the track-structure interface drawing A-160. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Engineer | 2019-01-22 | 10 | Expedite | N | N | N | 7 | Design-Builder EOR / ST Design Review | 2 | 2019-02-04 | 13 | N | 3 | 1 | 2019-02-04 | 13 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1121 | P4 – Low
E360-RFI-0068 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | In-water work window – NE 40th St | Field conditions at NE 40th St require changes to temporary erosion and sediment control or stormwater facility per M-860. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2019-01-28 | 10 | Urgent | N | Y | N | 5 | Design-Builder EOR / ST Design Review | 1 | 2019-02-04 | 7 | Y | 0 | 1 | 2019-02-04 | 7 | Closed | 13 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 584 | P3 – Medium
E360-RFI-0069 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | TESC modification – Redmond Technology Station | Field conditions at Redmond Technology Station require changes to temporary erosion and sediment control or stormwater facility per E-709. Request direction considering critical-areas conditions and permit requirements. | Project Manager | 2019-02-05 | 10 | Urgent | Y | N | Y | 4 | Design-Builder EOR / ST Design Review | 3 | 2019-02-25 | 20 | N | 10 | 1 | 2019-02-25 | 20 | Closed | 0 | 2 | 0 | 2429000 | 4534000 | N |  | 0 | 0 | 0 | 2 | 522 | P3 – Medium
E360-RFI-0070 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Station finish detail – SR 520 right-of-way aerial guideway | Request to clarify finish/connection detail on M-236 at SR 520 right-of-way aerial guideway. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2019-02-21 | 10 | Routine | N | Y | N | 7 | Design-Builder EOR / ST Design Review | 1 | 2019-02-25 | 3 | Y | 0 | 2 | 2019-03-14 | 21 | Closed | 4 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 675 | P3 – Medium
E360-RFI-0071 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on right-of-way use permit – SR 520 right-of-way aerial guideway | WSDOT review comments on the right-of-way use permit require changes to the column reinforcement at SR 520 right-of-way aerial guideway. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2019-02-25 | 10 | Routine | Y | N | N | 4 | City of Bellevue / ST Third-Party Mgmt | 1 | 2019-03-14 | 17 | N | 7 | 1 | 2019-03-14 | 17 | Closed | 0 | 0 | 0 | 111000 | 207000 | N |  | 0 | 0 | 0 | 0 | 1122 | P4 – Low
E360-RFI-0072 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Stormwater facility revision – SR 520 pedestrian bridges | Field conditions at SR 520 pedestrian bridges require changes to temporary erosion and sediment control or stormwater facility per C-520. Request direction considering critical-areas conditions and permit requirements. | Scheduler | 2019-02-28 | 10 | Routine | N | Y | N | 0 | Design-Builder EOR / ST Design Review | 4 | 2019-03-15 | 15 | N | 5 | 1 | 2019-03-15 | 15 | Closed | 15 | 0 | 7 |  |  | N |  | 0 | 0 | 0 | 1.6 | 558 | P3 – Medium
E360-RFI-0073 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Drawing/spec discrepancy – Overlake Village Station | Request clarification of 00 72 00 General Conditions and A-105: dimension/notes appear inconsistent or omitted for the work at Overlake Village Station. | Project Manager | 2019-03-04 | 10 | Routine | Y | N | N | 3 | Design-Builder EOR / ST Design Review | 1 | 2019-03-07 | 3 | Y | 0 | 2 | 2019-03-28 | 24 | Closed | 0 | 0 | 0 | 6000 | 12000 | N |  | 0 | 0 | 0 | 0 | 1123 | P4 – Low
E360-RFI-0074 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 12-in. ductile iron water main at Overlake Village Station | Potholing at Sta. 1573+25 located a 12-in. ductile iron water main in conflict with the proposed duct bank encasement. Utility is not shown on M-320. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2019-03-05 | 10 | Urgent | N | N | N | 8 | Design-Builder EOR / ST Design Review | 2 | 2019-03-11 | 4 | Y | 0 | 1 | 2019-03-11 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1124 | P4 – Low
E360-RFI-0075 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – platform edge slab sequence at SR 520 right-of-way aerial guideway | Erection of the platform edge slab as drawn conflicts with adjacent work and access limits at SR 520 right-of-way aerial guideway. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Superintendent | 2019-03-05 | 10 | Urgent | Y | Y | Y | 0 | Design-Builder EOR / ST Design Review | 1 | 2019-03-15 | 10 | Y | 0 | 1 | 2019-03-15 | 10 | Closed | 6 | 3 | 0 | 2223000 | 4149000 | Y | E360-CO-020 | 3229000 | 1199600 | 1 | 51.6 | 42 | P1 – Critical
E360-RFI-0076 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 24-in. sanitary sewer at Redmond Technology Station | Potholing at Sta. 1274+42 located a 24-in. sanitary sewer in conflict with the proposed stair core wall. Utility is not shown on M-651. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Engineer | 2019-03-08 | 10 | Urgent | Y | Y | N | 6 | Design-Builder EOR / ST Design Review | 2 | 2019-03-18 | 8 | Y | 0 | 1 | 2019-03-18 | 8 | Closed | 8 | 0 | 5 | 746000 | 1392000 | Y | E360-CO-023 | 998660 | 0 | 0 | 1.1 | 585 | P3 – Medium
E360-RFI-0077 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – pedestrian ramp and station canopy support at Redmond Technology Station | Interference between pedestrian ramp and station canopy support at Redmond Technology Station per C-652. Required clearance of 7 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2019-03-20 | 10 | Routine | Y | Y | Y | 1 | Design-Builder EOR / ST Design Review | 1 | 2019-04-03 | 14 | N | 4 | 2 | 2019-04-24 | 35 | Closed | 13 | 12 | 0 | 78000 | 146000 | Y | E360-CO-021 | 132500 | 77100 | 6 | 52.8 | 34 | P1 – Critical
E360-RFI-0078 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Puget Sound Energy comment on right-of-way use permit – Overlake Village Station | Puget Sound Energy review comments on the right-of-way use permit require changes to the stair core wall at Overlake Village Station. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2019-03-28 | 10 | Expedite | Y | Y | Y | 3 | WSDOT / ST Third-Party Mgmt | 3 | 2019-04-08 | 10 | Y | 0 | 2 | 2019-04-22 | 24 | Closed | 11 | 4 | 0 | 410000 | 766000 | N |  | 0 | 0 | 0 | 4 | 454 | P3 – Medium
E360-RFI-0079 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Missing dimension on M-474 | Request clarification of 01 33 00 Submittal Procedures and M-474: dimension/notes appear inconsistent or omitted for the work at 152nd Ave NE crossing. | Project Engineer | 2019-04-08 | 10 | Routine | N | N | N | 6 | Design-Builder EOR / ST Design Review | 2 | 2019-04-12 | 4 | Y | 0 | 2 | 2019-04-22 | 14 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1125 | P4 – Low
E360-RFI-0080 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – galvanized steel handrail | Contractor requests approval to substitute galvanized steel handrail for stainless steel handrail on work at NE 40th St, citing procurement lead time. Product data attached. | Design Manager | 2019-04-15 | 10 | Routine | N | N | N | 5 | Design-Builder EOR / ST Design Review | 2 | 2019-04-23 | 8 | Y | 0 | 1 | 2019-04-23 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1126 | P4 – Low
E360-RFI-0081 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Track slab/expansion joint interface – Overlake Village Station | Track layout at Sta. 1994+77 (Overlake Village Station) differs from the track-structure interface drawing A-506. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2019-04-29 | 10 | Routine | N | N | Y | 5 | Design-Builder EOR / ST Design Review | 2 | 2019-05-06 | 7 | Y | 0 | 1 | 2019-05-06 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1127 | P4 – Low
E360-RFI-0082 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with fiber communications duct bank at SR 520 pedestrian bridges | Potholing at Sta. 1070+33 located a fiber communications duct bank in conflict with the proposed retaining wall footing. Utility is not shown on M-222. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Scheduler | 2019-05-02 | 10 | Routine | Y | N | Y | 5 | Design-Builder EOR / ST Design Review | 1 | 2019-05-10 | 8 | Y | 0 | 1 | 2019-05-10 | 8 | Closed | 0 | 5 | 0 | 318000 | 594000 | Y | E360-CO-022 | 287200 | 220200 | 0 | 47.4 | 99 | P1 – Critical
E360-RFI-0083 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Crane staging in right-of-way – Redmond Technology Station | Contractor requests approval of an alternate traffic/staging plan at Redmond Technology Station: revised haul route. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Project Engineer | 2019-05-06 | 10 | Routine | N | N | N | 5 | Design-Builder EOR / ST Design Review | 1 | 2019-05-08 | 2 | Y | 0 | 1 | 2019-05-08 | 2 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1128 | P4 – Low
E360-RFI-0084 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – duct bank encasement and retaining wall footing at SR 520 right-of-way aerial guideway | Interference between duct bank encasement and retaining wall footing at SR 520 right-of-way aerial guideway per M-230. Required clearance of 8 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2019-05-31 | 10 | Expedite | Y | N | N | 4 | Design-Builder EOR / ST Design Review | 3 | 2019-06-12 | 12 | N | 2 | 1 | 2019-06-12 | 12 | Closed | 0 | 0 | 0 | 289000 | 539000 | Y | E360-CO-024 | 287800 | 287800 | 0 | 43.3 | 173 | P2 – High
E360-RFI-0085 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 30-in. storm drain at NE 40th St | Potholing at Sta. 1121+00 located a 30-in. storm drain in conflict with the proposed station canopy support. Utility is not shown on E-299. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Engineer | 2019-05-31 | 10 | Routine | N | N | N | 4 | Design-Builder EOR / ST Design Review | 4 | 2019-06-10 | 9 | Y | 0 | 1 | 2019-06-10 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1129 | P4 – Low
E360-RFI-0086 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Lane closure window request – SR 520 right-of-way aerial guideway | Contractor requests approval of an alternate traffic/staging plan at SR 520 right-of-way aerial guideway: extended night closure. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Superintendent | 2019-06-03 | 10 | Routine | N | Y | N | 5 | Design-Builder EOR / ST Design Review | 1 | 2019-06-10 | 7 | Y | 0 | 1 | 2019-06-10 | 7 | Closed | 3 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 731 | P3 – Medium
E360-RFI-0087 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with abandoned utility vault at SR 520 pedestrian bridges | Potholing at Sta. 1384+24 located a abandoned utility vault in conflict with the proposed pedestrian ramp. Utility is not shown on S-768. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Scheduler | 2019-06-05 | 10 | Expedite | Y | Y | N | 1 | Design-Builder EOR / ST Design Review | 2 | 2019-06-11 | 6 | Y | 0 | 1 | 2019-06-11 | 6 | Closed | 6 | 0 | 2 | 1392000 | 2598000 | Y | E360-CO-023 | 2275440 | 0 | 0 | 0.4 | 732 | P3 – Medium
E360-RFI-0088 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake garage | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Property owner access/restoration requirement – Overlake garage | Adjacent property owner has requested additional restoration and access provisions at Overlake garage beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Design Manager | 2019-06-07 | 10 | Expedite | N | N | N | 1 | WSDOT / ST Third-Party Mgmt | 2 | 2019-06-19 | 12 | N | 2 | 1 | 2019-06-19 | 12 | Closed | 0 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 789 | P4 – Low
E360-RFI-0089 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake garage | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Overlake garage | S-300 shows a 43 ft-10 in. dimension for the bearing pad/embed plate; structural sheet S-404 shows a different value. Request clarification before fabrication/rebar release. | Project Manager | 2019-06-13 | 10 | Urgent | N | N | N | 3 | Design-Builder EOR / ST Design Review | 1 | 2019-06-27 | 14 | N | 4 | 1 | 2019-06-27 | 14 | Closed | 0 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 790 | P4 – Low
E360-RFI-0090 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Overlake Village Station: buried concrete debris and an old foundation | During excavation at Overlake Village Station (Sta. 902+86) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or A-562. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Design Manager | 2019-06-24 | 10 | Routine | N | Y | Y | 7 | Design-Builder EOR / ST Design Review | 1 | 2019-07-10 | 16 | N | 6 | 1 | 2019-07-10 | 16 | Closed | 5 | 4 | 0 |  |  | N |  | 0 | 0 | 0 | 4 | 455 | P3 – Medium
E360-RFI-0091 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | Stormwater facility revision – NE 40th St | Field conditions at NE 40th St require changes to temporary erosion and sediment control or stormwater facility per A-741. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2019-06-26 | 10 | Expedite | N | N | N | 2 | Design-Builder EOR / ST Design Review | 2 | 2019-07-08 | 10 | Y | 0 | 1 | 2019-07-08 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1130 | P4 – Low
E360-RFI-0092 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Property owner access/restoration requirement – NE 40th St | Adjacent property owner has requested additional restoration and access provisions at NE 40th St beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Project Engineer | 2019-07-11 | 10 | Routine | N | N | Y | 2 | Puget Sound Energy / ST Third-Party Mgmt | 2 | 2019-07-29 | 16 | N | 6 | 1 | 2019-07-29 | 16 | Closed | 0 | 2 | 0 |  |  | N |  | 0 | 0 | 0 | 2 | 523 | P3 – Medium
E360-RFI-0093 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Special trackwork layout – 152nd Ave NE crossing | Track layout at Sta. 1873+11 (152nd Ave NE crossing) differs from the track-structure interface drawing E-317. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Design Manager | 2019-07-15 | 10 | Routine | N | Y | N | 1 | Design-Builder EOR / ST Design Review | 2 | 2019-07-24 | 9 | Y | 0 | 1 | 2019-07-24 | 9 | Closed | 5 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 633 | P3 – Medium
E360-RFI-0094 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake garage | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – station canopy support at Overlake garage | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-498 for egress width at Overlake garage. Request direction on compliant detail. | Field Engineer | 2019-07-16 | 10 | Routine | N | Y | N | 7 | Design-Builder EOR / ST Design Review | 3 | 2019-07-25 | 9 | Y | 0 | 1 | 2019-07-25 | 9 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 791 | P4 – Low
E360-RFI-0095 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Redmond Technology Station | Systems contractor requires 3-in. PVC conduit stub-ups for OCS pole at Redmond Technology Station not provided in civil A-245. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Project Engineer | 2019-07-26 | 10 | Routine | N | Y | N | 6 | Design-Builder EOR / ST Design Review | 3 | 2019-08-05 | 9 | Y | 0 | 1 | 2019-08-05 | 9 | Closed | 11 | 0 | 6 |  |  | N |  | 0 | 0 | 0 | 1.3 | 567 | P3 – Medium
E360-RFI-0096 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Redmond Technology Station: an unmapped abandoned storm line | During excavation at Redmond Technology Station (Sta. 1238+23) the contractor encountered an unmapped abandoned storm line, not shown on the GBR or M-345. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Project Engineer | 2019-07-29 | 10 | Urgent | N | Y | Y | 8 | Design-Builder EOR / ST Design Review | 4 | 2019-08-02 | 4 | Y | 0 | 1 | 2019-08-02 | 4 | Closed | 26 | 22 | 0 |  |  | N |  | 0 | 0 | 0 | 22 | 356 | P3 – Medium
E360-RFI-0097 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – alternate epoxy-coated rebar supplier | Contractor requests approval to substitute alternate epoxy-coated rebar supplier for specified epoxy-coated rebar on work at SR 520 pedestrian bridges, citing procurement lead time. Product data attached. | Scheduler | 2019-08-13 | 10 | Routine | N | Y | Y | 4 | Design-Builder EOR / ST Design Review | 1 | 2019-08-22 | 9 | Y | 0 | 1 | 2019-08-22 | 9 | Closed | 13 | 10 | 0 |  |  | N |  | 0 | 0 | 0 | 10 | 395 | P3 – Medium
E360-RFI-0098 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Stormwater facility revision – Overlake Village Station | Field conditions at Overlake Village Station require changes to temporary erosion and sediment control or stormwater facility per E-591. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2019-08-27 | 10 | Urgent | N | Y | N | 6 | Design-Builder EOR / ST Design Review | 1 | 2019-09-09 | 11 | N | 1 | 1 | 2019-09-09 | 11 | Closed | 19 | 0 | 13 |  |  | N |  | 0 | 0 | 0 | 2.9 | 490 | P3 – Medium
E360-RFI-0099 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Canopy/glazing connection – Overlake Village Station | Request to clarify finish/connection detail on C-329 at Overlake Village Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2019-08-29 | 10 | Expedite | N | N | Y | 4 | Design-Builder EOR / ST Design Review | 1 | 2019-09-06 | 8 | Y | 0 | 1 | 2019-09-06 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1131 | P4 – Low
E360-RFI-0100 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – retaining wall footing sequence at Overlake Village Station | Erection of the retaining wall footing as drawn conflicts with adjacent work and access limits at Overlake Village Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Scheduler | 2019-10-09 | 10 | Routine | Y | Y | Y | 0 | Design-Builder EOR / ST Design Review | 3 | 2019-10-18 | 9 | Y | 0 | 1 | 2019-10-18 | 9 | Closed | 6 | 3 | 0 | 840000 | 1568000 | N |  | 0 | 0 | 0 | 3 | 481 | P3 – Medium
E360-RFI-0101 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Station finish detail – 152nd Ave NE crossing | Request to clarify finish/connection detail on A-270 at 152nd Ave NE crossing. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2019-10-14 | 10 | Urgent | Y | N | N | 8 | Design-Builder EOR / ST Design Review | 2 | 2019-10-21 | 6 | Y | 0 | 1 | 2019-10-21 | 6 | Closed | 0 | 0 | 0 | 501000 | 936000 | N |  | 0 | 0 | 0 | 0 | 1132 | P4 – Low
E360-RFI-0102 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Stormwater facility revision – NE 40th St | Field conditions at NE 40th St require changes to temporary erosion and sediment control or stormwater facility per A-801. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2019-10-16 | 10 | Expedite | Y | N | N | 5 | Design-Builder EOR / ST Design Review | 2 | 2019-10-31 | 15 | N | 5 | 1 | 2019-10-31 | 15 | Closed | 0 | 0 | 1 | 417000 | 779000 | N |  | 0 | 0 | 0 | 0.2 | 792 | P4 – Low
E360-RFI-0103 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Track slab/expansion joint interface – SR 520 right-of-way aerial guideway | Track layout at Sta. 1981+66 (SR 520 right-of-way aerial guideway) differs from the track-structure interface drawing A-401. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Scheduler | 2019-10-28 | 10 | Urgent | Y | Y | Y | 2 | Design-Builder EOR / ST Design Review | 4 | 2019-11-04 | 6 | Y | 0 | 2 | 2019-11-25 | 27 | Closed | 3 | 1 | 0 | 38000 | 72000 | N |  | 0 | 0 | 0 | 1 | 610 | P3 – Medium
E360-RFI-0104 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – duct bank encasement sequence at Redmond Technology Station | Erection of the duct bank encasement as drawn conflicts with adjacent work and access limits at Redmond Technology Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Superintendent | 2019-10-31 | 10 | Urgent | N | Y | Y | 1 | Design-Builder EOR / ST Design Review | 1 | 2019-11-04 | 4 | Y | 0 | 1 | 2019-11-04 | 4 | Closed | 8 | 7 | 0 |  |  | N |  | 0 | 0 | 0 | 7 | 418 | P3 – Medium
E360-RFI-0105 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at NE 40th St: an unmapped abandoned storm line | During excavation at NE 40th St (Sta. 1903+55) the contractor encountered an unmapped abandoned storm line, not shown on the GBR or C-728. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Superintendent | 2019-11-04 | 10 | Routine | Y | Y | N | 8 | Design-Builder EOR / ST Design Review | 1 | 2019-11-18 | 13 | N | 3 | 1 | 2019-11-18 | 13 | Closed | 12 | 0 | 9 | 412000 | 769000 | Y | E360-CO-025 | 328700 | 206000 | 5 | 45.8 | 128 | P2 – High
E360-RFI-0106 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – column reinforcement at SR 520 right-of-way aerial guideway | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-746 for fire alarm device layout at SR 520 right-of-way aerial guideway. Request direction on compliant detail. | Project Engineer | 2019-11-04 | 10 | Routine | N | Y | Y | 6 | Design-Builder EOR / ST Design Review | 3 | 2019-11-11 | 5 | Y | 0 | 1 | 2019-11-11 | 5 | Closed | 10 | 6 | 0 |  |  | N |  | 0 | 0 | 0 | 6 | 424 | P3 – Medium
E360-RFI-0107 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with fiber communications duct bank at SR 520 pedestrian bridges | Potholing at Sta. 2015+59 located a fiber communications duct bank in conflict with the proposed retaining wall footing. Utility is not shown on S-724. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Engineer | 2019-11-27 | 10 | Routine | Y | Y | Y | 7 | Design-Builder EOR / ST Design Review | 1 | 2019-12-12 | 15 | N | 5 | 1 | 2019-12-12 | 15 | Closed | 9 | 8 | 0 | 150000 | 280000 | Y | E360-CO-028 | 310380 | 200450 | 1.9 | 50.7 | 51 | P1 – Critical
E360-RFI-0108 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at 152nd Ave NE crossing: an unmapped abandoned storm line | During excavation at 152nd Ave NE crossing (Sta. 1779+39) the contractor encountered an unmapped abandoned storm line, not shown on the GBR or M-718. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Superintendent | 2019-11-29 | 10 | Urgent | Y | N | Y | 0 | Design-Builder EOR / ST Design Review | 2 | 2019-12-06 | 7 | Y | 0 | 2 | 2019-12-19 | 20 | Closed | 0 | 0 | 0 | 197000 | 368000 | Y | E360-CO-026 | 193700 | 54900 | 0 | 37.6 | 283 | P2 – High
E360-RFI-0109 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – recycled-content fly ash blend | Contractor requests approval to substitute recycled-content fly ash blend for Type IL cement mix on work at SR 520 pedestrian bridges, citing procurement lead time. Product data attached. | Project Engineer | 2019-11-29 | 10 | Expedite | N | N | N | 6 | Design-Builder EOR / ST Design Review | 1 | 2019-12-05 | 6 | Y | 0 | 2 | 2019-12-19 | 20 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1133 | P4 – Low
E360-RFI-0110 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with abandoned utility vault at Redmond Technology Station | Potholing at Sta. 1232+71 located a abandoned utility vault in conflict with the proposed pedestrian ramp. Utility is not shown on C-331. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Scheduler | 2019-12-02 | 10 | Routine | Y | Y | Y | 0 | Design-Builder EOR / ST Design Review | 2 | 2019-12-09 | 6 | Y | 0 | 1 | 2019-12-09 | 6 | Closed | 4 | 2 | 0 | 2515000 | 4694000 | Y | E360-CO-027 | 1827200 | 0 | 0 | 2 | 524 | P3 – Medium
E360-RFI-0111 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – 152nd Ave NE crossing | E-775 shows a 28 ft-5 in. dimension for the pedestrian ramp; structural sheet S-374 shows a different value. Request clarification before fabrication/rebar release. | Project Manager | 2019-12-05 | 10 | Urgent | N | N | N | 2 | Design-Builder EOR / ST Design Review | 1 | 2019-12-10 | 5 | Y | 0 | 1 | 2019-12-10 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1134 | P4 – Low
E360-RFI-0112 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Art embed coordination – Overlake Village Station | Request to clarify finish/connection detail on S-549 at Overlake Village Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Scheduler | 2020-01-06 | 10 | Routine | Y | N | N | 5 | Design-Builder EOR / ST Design Review | 1 | 2020-01-15 | 9 | Y | 0 | 1 | 2020-01-15 | 9 | Closed | 0 | 0 | 0 | 60000 | 112000 | N |  | 0 | 0 | 0 | 0 | 1135 | P4 – Low
E360-RFI-0113 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Lane closure window request – 152nd Ave NE crossing | Contractor requests approval of an alternate traffic/staging plan at 152nd Ave NE crossing: extended night closure. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Scheduler | 2020-01-20 | 10 | Routine | Y | N | Y | 1 | Design-Builder EOR / ST Design Review | 1 | 2020-01-24 | 4 | Y | 0 | 1 | 2020-01-24 | 4 | Closed | 0 | 0 | 0 | 111000 | 207000 | N |  | 0 | 0 | 0 | 0 | 1136 | P4 – Low
E360-RFI-0114 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with fiber communications duct bank at 152nd Ave NE crossing | Potholing at Sta. 1511+03 located a fiber communications duct bank in conflict with the proposed drilled shaft cap. Utility is not shown on E-340. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Superintendent | 2020-02-20 | 10 | Routine | Y | N | Y | 2 | Design-Builder EOR / ST Design Review | 1 | 2020-02-26 | 6 | Y | 0 | 1 | 2020-02-26 | 6 | Closed | 0 | 0 | 0 | 296000 | 553000 | Y | E360-CO-028 | 342920 | 221450 | 2.1 | 43.1 | 176 | P2 – High
E360-RFI-0115 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Haul route revision – Overlake Village Station | Contractor requests approval of an alternate traffic/staging plan at Overlake Village Station: crane pick over active roadway. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Superintendent | 2020-02-20 | 10 | Expedite | Y | Y | N | 7 | Design-Builder EOR / ST Design Review | 1 | 2020-02-26 | 6 | Y | 0 | 1 | 2020-02-26 | 6 | Closed | 2 | 0 | 2 | 28000 | 53000 | N |  | 0 | 0 | 0 | 0.4 | 733 | P3 – Medium
E360-RFI-0116 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at SR 520 right-of-way aerial guideway: perched groundwater | During excavation at SR 520 right-of-way aerial guideway (Sta. 1357+29) the contractor encountered perched groundwater at approx. elevation 129 ft, not shown on the GBR or A-779. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Design Manager | 2020-02-24 | 10 | Urgent | Y | Y | Y | 8 | Design-Builder EOR / ST Design Review | 1 | 2020-02-28 | 4 | Y | 0 | 1 | 2020-02-28 | 4 | Closed | 34 | 16 | 0 | 751000 | 1402000 | Y | E360-CO-029 | 341100 | 193200 | 20 | 64.6 | 12 | P1 – Critical
E360-RFI-0117 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at SR 520 right-of-way aerial guideway: petroleum-stained soil with odor | During excavation at SR 520 right-of-way aerial guideway (Sta. 1390+31) the contractor encountered petroleum-stained soil with odor, not shown on the GBR or S-815. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Design Manager | 2020-03-11 | 10 | Routine | Y | N | Y | 2 | Design-Builder EOR / ST Design Review | 2 | 2020-03-17 | 6 | Y | 0 | 1 | 2020-03-17 | 6 | Closed | 0 | 0 | 0 | 357000 | 667000 | Y | E360-CO-030 | 503200 | 391900 | 0 | 44.4 | 153 | P2 – High
E360-RFI-0118 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake garage | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Overlake garage: soft lacustrine silt below design subgrade | During excavation at Overlake garage (Sta. 1553+86) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or E-808. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Scheduler | 2020-03-16 | 10 | Routine | Y | Y | N | 6 | Design-Builder EOR / ST Design Review | 3 | 2020-03-24 | 8 | Y | 0 | 1 | 2020-03-24 | 8 | Closed | 10 | 0 | 6 | 6284000 | 11730000 | Y | E360-CO-031 | 4826600 | 2032900 | 2 | 52 | 40 | P1 – Critical
E360-RFI-0119 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | WSDOT comment on building permit – 152nd Ave NE crossing | WSDOT review comments on the building permit require changes to the drilled shaft cap at 152nd Ave NE crossing. Request direction on scope impacts and whether comments are within the contract requirements. | Project Engineer | 2020-03-20 | 10 | Routine | N | N | N | 4 | City of Bellevue / ST Third-Party Mgmt | 3 | 2020-05-04 | 45 | N | 35 | 1 | 2020-05-04 | 45 | Closed | 0 | 0 | 12 |  |  | N |  | 0 | 0 | 0 | 2.7 | 493 | P3 – Medium
E360-RFI-0120 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – retaining wall footing and pedestrian ramp at Overlake Village Station | Interference between retaining wall footing and pedestrian ramp at Overlake Village Station per M-835. Required clearance of 8 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Field Engineer | 2020-04-07 | 10 | Expedite | Y | Y | N | 7 | Design-Builder EOR / ST Design Review | 2 | 2020-04-15 | 8 | Y | 0 | 1 | 2020-04-15 | 8 | Closed | 4 | 0 | 2 | 2160000 | 4032000 | Y | E360-CO-032 | 2569600 | 0 | 0 | 0.4 | 734 | P3 – Medium
E360-RFI-0121 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – alternate epoxy-coated rebar supplier | Contractor requests approval to substitute alternate epoxy-coated rebar supplier for specified epoxy-coated rebar on work at SR 520 pedestrian bridges, citing procurement lead time. Product data attached. | Project Engineer | 2020-04-09 | 10 | Urgent | N | Y | N | 8 | Design-Builder EOR / ST Design Review | 1 | 2020-04-13 | 2 | Y | 0 | 1 | 2020-04-13 | 2 | Closed | 3 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 793 | P4 – Low
E360-RFI-0122 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Art embed coordination – Overlake Village Station | Request to clarify finish/connection detail on S-601 at Overlake Village Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2020-05-19 | 10 | Routine | N | N | N | 8 | Design-Builder EOR / ST Design Review | 3 | 2020-05-25 | 5 | Y | 0 | 2 | 2020-06-12 | 24 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1137 | P4 – Low
E360-RFI-0123 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – drilled shaft cap and bearing pad/embed plate at SR 520 right-of-way aerial guideway | Interference between drilled shaft cap and bearing pad/embed plate at SR 520 right-of-way aerial guideway per C-810. Required clearance of 4 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2020-05-25 | 10 | Expedite | N | N | N | 1 | Design-Builder EOR / ST Design Review | 2 | 2020-05-29 | 4 | Y | 0 | 2 | 2020-06-18 | 24 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1138 | P4 – Low
E360-RFI-0124 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Wetland/stream buffer protection – SR 520 pedestrian bridges | Field conditions at SR 520 pedestrian bridges require changes to temporary erosion and sediment control or stormwater facility per E-384. Request direction considering critical-areas conditions and permit requirements. | Project Manager | 2020-06-15 | 10 | Routine | Y | Y | N | 1 | Design-Builder EOR / ST Design Review | 1 | 2020-06-23 | 8 | Y | 0 | 1 | 2020-06-23 | 8 | Closed | 24 | 0 | 18 | 2805000 | 5236000 | Y | E360-CO-033 | 1823900 | 0 | 0 | 4 | 456 | P3 – Medium
E360-RFI-0125 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – drilled shaft cap and platform edge slab at NE 40th St | Interference between drilled shaft cap and platform edge slab at NE 40th St per E-806. Required clearance of 4 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Engineer | 2020-06-19 | 10 | Routine | Y | Y | Y | 3 | Design-Builder EOR / ST Design Review | 2 | 2020-06-23 | 4 | Y | 0 | 1 | 2020-06-23 | 4 | Closed | 4 | 3 | 0 | 139000 | 259000 | Y | E360-CO-034 | 182400 | 111000 | 1 | 43.4 | 171 | P2 – High
E360-RFI-0126 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Redmond Technology Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Redmond Technology Station: abandoned timber piles | During excavation at Redmond Technology Station (Sta. 1032+61) the contractor encountered abandoned timber piles, not shown on the GBR or A-499. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Design Manager | 2020-08-06 | 10 | Expedite | N | Y | N | 6 | Design-Builder EOR / ST Design Review | 3 | 2020-08-19 | 13 | N | 3 | 1 | 2020-08-19 | 13 | Closed | 18 | 0 | 12 |  |  | N |  | 0 | 0 | 0 | 2.7 | 494 | P3 – Medium
E360-RFI-0127 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake garage | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | City of Bellevue comment on street improvement permit – Overlake garage | City of Bellevue review comments on the street improvement permit require changes to the pedestrian ramp at Overlake garage. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2020-08-24 | 10 | Routine | N | Y | N | 8 | City of Bellevue / ST Third-Party Mgmt | 5 | 2020-09-10 | 17 | N | 7 | 2 | 2020-10-01 | 38 | Closed | 12 | 0 | 9 |  |  | N |  | 0 | 0 | 0 | 2 | 525 | P3 – Medium
E360-RFI-0128 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Direct fixation fastener spacing at Sta. 992+57 | Track layout at Sta. 992+57 (152nd Ave NE crossing) differs from the track-structure interface drawing E-273. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Design Manager | 2020-09-07 | 10 | Expedite | N | N | Y | 2 | Design-Builder EOR / ST Design Review | 3 | 2020-09-14 | 6 | Y | 0 | 1 | 2020-09-14 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1139 | P4 – Low
E360-RFI-0129 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – alternate epoxy-coated rebar supplier | Contractor requests approval to substitute alternate epoxy-coated rebar supplier for specified epoxy-coated rebar on work at NE 40th St, citing procurement lead time. Product data attached. | Project Engineer | 2020-09-10 | 10 | Routine | Y | Y | N | 8 | Design-Builder EOR / ST Design Review | 4 | 2020-09-15 | 5 | Y | 0 | 1 | 2020-09-15 | 5 | Closed | 2 | 0 | 1 | 50000 | 93000 | Y | E360-CO-035 | 59100 | 59100 | 1 | 38.4 | 266 | P2 – High
E360-RFI-0130 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | NE 40th St | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – guideway girder diaphragm and platform edge slab at NE 40th St | Interference between guideway girder diaphragm and platform edge slab at NE 40th St per E-738. Required clearance of 4 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Engineer | 2020-09-10 | 10 | Expedite | Y | N | N | 2 | Design-Builder EOR / ST Design Review | 2 | 2020-09-22 | 12 | N | 2 | 1 | 2020-09-22 | 12 | Closed | 0 | 0 | 1 | 408000 | 761000 | N |  | 0 | 0 | 0 | 0.2 | 794 | P4 – Low
E360-RFI-0131 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – duct bank encasement at 152nd Ave NE crossing | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-328 for fire alarm device layout at 152nd Ave NE crossing. Request direction on compliant detail. | Scheduler | 2020-09-24 | 10 | Expedite | N | N | Y | 3 | Design-Builder EOR / ST Design Review | 1 | 2020-10-07 | 13 | N | 3 | 1 | 2020-10-07 | 13 | Closed | 0 | 1 | 0 |  |  | N |  | 0 | 0 | 0 | 1 | 611 | P3 – Medium
E360-RFI-0132 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake Village Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – guideway girder diaphragm at Overlake Village Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-594 for egress width at Overlake Village Station. Request direction on compliant detail. | Project Engineer | 2020-09-25 | 10 | Routine | N | N | N | 0 | Design-Builder EOR / ST Design Review | 4 | 2020-10-01 | 6 | Y | 0 | 1 | 2020-10-01 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1140 | P4 – Low
E360-RFI-0133 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – retaining wall footing at SR 520 right-of-way aerial guideway | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-199 for smoke control damper at SR 520 right-of-way aerial guideway. Request direction on compliant detail. | Design Manager | 2020-10-13 | 10 | Routine | N | N | N | 7 | Design-Builder EOR / ST Design Review | 3 | 2020-10-19 | 6 | Y | 0 | 1 | 2020-10-19 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1141 | P4 – Low
E360-RFI-0134 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 pedestrian bridges | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with PSE distribution duct bank at SR 520 pedestrian bridges | Potholing at Sta. 1476+53 located a PSE distribution duct bank in conflict with the proposed stair core wall. Utility is not shown on S-306. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Scheduler | 2020-10-23 | 10 | Routine | Y | Y | N | 5 | Design-Builder EOR / ST Design Review | 3 | 2020-11-02 | 10 | Y | 0 | 1 | 2020-11-02 | 10 | Closed | 8 | 0 | 3 | 648000 | 1211000 | Y | E360-CO-036 | 1487900 | 940000 | 5 | 49.7 | 65 | P1 – Critical
E360-RFI-0135 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – SR 520 right-of-way aerial guideway | C-133 shows a 52 ft-0 in. dimension for the station canopy support; structural sheet S-813 shows a different value. Request clarification before fabrication/rebar release. | Project Manager | 2020-12-21 | 10 | Routine | Y | N | N | 7 | Design-Builder EOR / ST Design Review | 1 | 2020-12-29 | 8 | Y | 0 | 1 | 2020-12-29 | 8 | Closed | 0 | 0 | 0 | 1006000 | 1877000 | Y | E360-CO-037 | 1014400 | 744900 | 0 | 46.6 | 115 | P2 – High
E360-RFI-0136 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | Overlake garage | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Overlake garage: glacially deposited boulders exceeding 36 in. | During excavation at Overlake garage (Sta. 1094+59) the contractor encountered glacially deposited boulders exceeding 36 in., not shown on the GBR or E-684. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Superintendent | 2020-12-28 | 10 | Urgent | Y | Y | Y | 2 | Design-Builder EOR / ST Design Review | 4 | 2021-01-06 | 9 | Y | 0 | 1 | 2021-01-06 | 9 | Closed | 30 | 26 | 0 | 229000 | 427000 | Y | E360-CO-038 | 374400 | 169200 | 12 | 71.5 | 5 | P1 – Critical
E360-RFI-0137 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Drawing/spec discrepancy – SR 520 right-of-way aerial guideway | Request clarification of 00 72 00 General Conditions and E-350: dimension/notes appear inconsistent or omitted for the work at SR 520 right-of-way aerial guideway. | Project Manager | 2021-02-08 | 10 | Urgent | N | N | N | 4 | Design-Builder EOR / ST Design Review | 1 | 2021-02-11 | 3 | Y | 0 | 2 | 2021-03-04 | 24 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1142 | P4 – Low
E360-RFI-0138 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | TESC modification – 152nd Ave NE crossing | Field conditions at 152nd Ave NE crossing require changes to temporary erosion and sediment control or stormwater facility per C-164. Request direction considering critical-areas conditions and permit requirements. | Project Engineer | 2021-03-01 | 10 | Routine | Y | N | N | 6 | Design-Builder EOR / ST Design Review | 2 | 2021-03-10 | 9 | Y | 0 | 1 | 2021-03-10 | 9 | Closed | 0 | 0 | 0 | 1608000 | 3002000 | Y | E360-CO-040 | 950600 | 494100 | 0 | 45.2 | 136 | P2 – High
E360-RFI-0139 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | SR 520 right-of-way aerial guideway | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at SR 520 right-of-way aerial guideway: soft lacustrine silt below design subgrade | During excavation at SR 520 right-of-way aerial guideway (Sta. 1355+53) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or A-653. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Project Engineer | 2021-03-02 | 10 | Routine | Y | N | N | 1 | Design-Builder EOR / ST Design Review | 2 | 2021-03-08 | 4 | Y | 0 | 1 | 2021-03-08 | 4 | Closed | 0 | 0 | 0 | 2064000 | 3853000 | Y | E360-CO-039 | 2301800 | 1360400 | 0 | 48.7 | 78 | P1 – Critical
E360-RFI-0140 | E360 | East Link Extension | Kiewit-Hoffman East Link Constructors | 152nd Ave NE crossing | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at 152nd Ave NE crossing, citing procurement lead time. Product data attached. | Superintendent | 2021-04-02 | 10 | Urgent | Y | N | N | 4 | Design-Builder EOR / ST Design Review | 1 | 2021-04-08 | 6 | Y | 0 | 1 | 2021-04-08 | 6 | Closed | 0 | 0 | 0 | 129000 | 241000 | N |  | 0 | 0 | 0 | 0 | 1143 | P4 – Low
E750-RFI-0001 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – alternate LED luminaire | Contractor requests approval to substitute alternate LED luminaire for specified LED luminaire on work at Train control – Overlake Village, citing procurement lead time. Product data attached. | Project Manager | 2018-03-19 | 14 | Expedite | N | N | N | 1 | DSDC – LTK Engineering | 2 | 2018-04-02 | 13 | Y | 0 | 1 | 2018-04-02 | 13 | Closed | 0 | 0 | 0 |  |  | Y | E750-CO-001 | 14900 | 6200 | 0 | 30.1 | 341 | P2 – High
E750-RFI-0002 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on building permit – Train control – Overlake Village | WSDOT review comments on the building permit require changes to the column reinforcement at Train control – Overlake Village. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2018-04-19 | 14 | Urgent | Y | Y | N | 6 | DSDC – LTK Engineering | 4 | 2018-05-10 | 21 | N | 7 | 1 | 2018-05-10 | 21 | Closed | 16 | 0 | 10 | 85000 | 158000 | N |  | 0 | 0 | 0 | 2.2 | 506 | P3 – Medium
E750-RFI-0003 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – bearing pad/embed plate at OCS – Bel-Red/Overlake guideway | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-157 for standpipe connection at OCS – Bel-Red/Overlake guideway. Request direction on compliant detail. | Project Manager | 2018-04-27 | 14 | Routine | Y | N | N | 3 | DSDC – LTK Engineering | 6 | 2018-05-14 | 16 | N | 2 | 1 | 2018-05-14 | 16 | Closed | 0 | 0 | 0 | 203000 | 380000 | N |  | 0 | 0 | 0 | 0 | 1144 | P4 – Low
E750-RFI-0004 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Night work and noise variance – Bellevue tunnel systems | Contractor requests approval of an alternate traffic/staging plan at Bellevue tunnel systems: crane pick over active roadway. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Field Engineer | 2018-07-09 | 14 | Routine | N | N | N | 1 | DSDC – LTK Engineering | 1 | 2018-07-16 | 6 | Y | 0 | 1 | 2018-07-16 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1145 | P4 – Low
E750-RFI-0005 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Rail Bonding location conflict at Sta. 1080+65 | Proposed rail bonding foundation location at Sta. 1080+65 conflicts with retaining wall footing; offset of 7 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2018-08-01 | 14 | Expedite | Y | Y | N | 7 | DSDC – LTK Engineering | 1 | 2018-08-14 | 13 | Y | 0 | 1 | 2018-08-14 | 13 | Closed | 10 | 0 | 7 | 128000 | 239000 | Y | E750-CO-003 | 137900 | 104800 | 6 | 43.4 | 172 | P2 – High
E750-RFI-0006 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – retaining wall footing at OCS – I-90/Mercer Island to South Bellevue | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-514 for emergency stair pressurization at OCS – I-90/Mercer Island to South Bellevue. Request direction on compliant detail. | Superintendent | 2018-08-06 | 14 | Routine | Y | N | N | 7 | DSDC – LTK Engineering | 4 | 2018-08-13 | 5 | Y | 0 | 1 | 2018-08-13 | 5 | Closed | 0 | 0 | 0 | 1907000 | 3559000 | Y | E750-CO-002 | 1842700 | 0 | 0 | 0 | 1146 | P4 – Low
E750-RFI-0007 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Tunnel Emergency Phone location conflict at Sta. 1896+27 | Proposed tunnel emergency phone foundation location at Sta. 1896+27 conflicts with station canopy support; offset of 9 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Project Engineer | 2018-08-07 | 14 | Expedite | N | N | N | 4 | DSDC – LTK Engineering | 4 | 2018-09-10 | 33 | N | 19 | 1 | 2018-09-10 | 33 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1147 | P4 – Low
E750-RFI-0008 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Traction power substation – Bellevue | Systems contractor requires 4-in. PVC conduit stub-ups for rail bonding at Traction power substation – Bellevue not provided in civil A-296. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2018-08-17 | 14 | Expedite | N | Y | N | 0 | DSDC – LTK Engineering | 1 | 2018-09-07 | 21 | N | 7 | 2 | 2018-09-26 | 40 | Closed | 5 | 0 | 6 |  |  | Y | E750-CO-004 | 51000 | 40800 | 2 | 38.6 | 260 | P2 – High
E750-RFI-0009 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – OCS – I-90/Mercer Island to South Bellevue | Civil and systems drawings differ on grounding/bonding of retaining wall footing for stray-current control at OCS – I-90/Mercer Island to South Bellevue. Request governing detail and responsibility for installation. | Project Engineer | 2018-08-29 | 14 | Urgent | Y | Y | Y | 4 | DSDC – LTK Engineering | 2 | 2018-09-10 | 12 | Y | 0 | 2 | 2018-09-24 | 25 | Closed | 34 | 21 | 0 | 4019000 | 7502000 | N |  | 0 | 0 | 0 | 21 | 359 | P3 – Medium
E750-RFI-0010 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – bearing pad/embed plate at OCS – I-90/Mercer Island to South Bellevue | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-448 for smoke control damper at OCS – I-90/Mercer Island to South Bellevue. Request direction on compliant detail. | Scheduler | 2018-09-11 | 14 | Expedite | N | N | N | 2 | DSDC – LTK Engineering | 3 | 2018-09-18 | 7 | Y | 0 | 1 | 2018-09-18 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1148 | P4 – Low
E750-RFI-0011 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at Communications room – Bellevue Downtown Station, citing procurement lead time. Product data attached. | Design Manager | 2018-09-19 | 14 | Routine | N | Y | N | 8 | DSDC – LTK Engineering | 1 | 2018-09-27 | 8 | Y | 0 | 1 | 2018-09-27 | 8 | Closed | 6 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 634 | P3 – Medium
E750-RFI-0012 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – pedestrian ramp and column reinforcement at OCS – I-90/Mercer Island to South Bellevue | Interference between pedestrian ramp and column reinforcement at OCS – I-90/Mercer Island to South Bellevue per E-804. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2018-09-27 | 14 | Urgent | N | N | N | 5 | DSDC – LTK Engineering | 2 | 2018-10-05 | 8 | Y | 0 | 1 | 2018-10-05 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1149 | P4 – Low
E750-RFI-0013 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Ocs Pole location conflict at Sta. 2100+43 | Proposed OCS pole foundation location at Sta. 2100+43 conflicts with retaining wall footing; offset of 4 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Field Engineer | 2018-10-25 | 14 | Routine | N | N | N | 2 | DSDC – LTK Engineering | 5 | 2018-11-09 | 15 | N | 1 | 1 | 2018-11-09 | 15 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1150 | P4 – Low
E750-RFI-0014 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | SPC | Spec / Drawing Clarification | General | 01 25 00 Substitution Procedures | Drawing/spec discrepancy – Systems ductbank – Bel-Red | Request clarification of 01 25 00 Substitution Procedures and E-547: dimension/notes appear inconsistent or omitted for the work at Systems ductbank – Bel-Red. | Project Engineer | 2018-11-21 | 14 | Routine | N | N | N | 7 | DSDC – LTK Engineering | 1 | 2018-11-26 | 4 | Y | 0 | 2 | 2018-12-07 | 16 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1151 | P4 – Low
E750-RFI-0015 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – guideway girder diaphragm and platform edge slab at Bellevue tunnel systems | Interference between guideway girder diaphragm and platform edge slab at Bellevue tunnel systems per S-747. Required clearance of 8 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2019-01-08 | 14 | Routine | N | Y | N | 6 | DSDC – LTK Engineering | 1 | 2019-01-18 | 10 | Y | 0 | 1 | 2019-01-18 | 10 | Closed | 5 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 676 | P3 – Medium
E750-RFI-0016 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – alternate LED luminaire | Contractor requests approval to substitute alternate LED luminaire for specified LED luminaire on work at Bellevue tunnel systems, citing procurement lead time. Product data attached. | Project Manager | 2019-01-15 | 14 | Routine | N | N | N | 4 | DSDC – LTK Engineering | 2 | 2019-01-21 | 5 | Y | 0 | 1 | 2019-01-21 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1152 | P4 – Low
E750-RFI-0017 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – alternate LED luminaire | Contractor requests approval to substitute alternate LED luminaire for specified LED luminaire on work at Bellevue tunnel systems, citing procurement lead time. Product data attached. | Field Engineer | 2019-01-17 | 14 | Routine | N | Y | Y | 0 | DSDC – LTK Engineering | 2 | 2019-01-21 | 3 | Y | 0 | 1 | 2019-01-21 | 3 | Closed | 5 | 4 | 0 |  |  | N |  | 0 | 0 | 0 | 4 | 457 | P3 – Medium
E750-RFI-0018 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – bearing pad/embed plate at Bellevue tunnel systems | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-584 for fire alarm device layout at Bellevue tunnel systems. Request direction on compliant detail. | Field Engineer | 2019-02-21 | 14 | Urgent | N | N | N | 7 | DSDC – LTK Engineering | 1 | 2019-02-27 | 6 | Y | 0 | 1 | 2019-02-27 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1153 | P4 – Low
E750-RFI-0019 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – column reinforcement at Bellevue tunnel systems | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-826 for smoke control damper at Bellevue tunnel systems. Request direction on compliant detail. | Field Engineer | 2019-02-28 | 14 | Expedite | N | N | N | 4 | DSDC – LTK Engineering | 2 | 2019-03-07 | 7 | Y | 0 | 1 | 2019-03-07 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1154 | P4 – Low
E750-RFI-0020 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – OCS – Bel-Red/Overlake guideway | Civil and systems drawings differ on grounding/bonding of drilled shaft cap for stray-current control at OCS – Bel-Red/Overlake guideway. Request governing detail and responsibility for installation. | Scheduler | 2019-03-01 | 14 | Routine | Y | Y | N | 7 | DSDC – LTK Engineering | 4 | 2019-03-11 | 8 | Y | 0 | 2 | 2019-03-15 | 14 | Closed | 45 | 0 | 13 | 466000 | 869000 | Y | E750-CO-005 | 434320 | 340290 | 44.4 | 56.8 | 23 | P1 – Critical
E750-RFI-0021 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Puget Sound Energy comment on building permit – Traction power substation – Bellevue | Puget Sound Energy review comments on the building permit require changes to the stair core wall at Traction power substation – Bellevue. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2019-03-04 | 14 | Urgent | N | N | Y | 2 | DSDC – LTK Engineering | 1 | 2019-03-13 | 9 | Y | 0 | 1 | 2019-03-13 | 9 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1155 | P4 – Low
E750-RFI-0022 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 30-in. storm drain at Bellevue tunnel systems | Potholing at Sta. 1570+78 located a 30-in. storm drain in conflict with the proposed drilled shaft cap. Utility is not shown on S-240. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Scheduler | 2019-03-11 | 14 | Urgent | N | N | Y | 6 | DSDC – LTK Engineering | 3 | 2019-03-25 | 13 | Y | 0 | 1 | 2019-03-25 | 13 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1156 | P4 – Low
E750-RFI-0023 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Traction power substation – Bellevue | Systems contractor requires 2-in. PVC conduit stub-ups for OCS pole at Traction power substation – Bellevue not provided in civil M-477. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Project Engineer | 2019-03-13 | 14 | Routine | Y | Y | N | 7 | DSDC – LTK Engineering | 1 | 2019-04-08 | 26 | N | 12 | 2 | 2019-04-24 | 42 | Closed | 68 | 0 | 26 | 680000 | 1269000 | Y | E750-CO-005 | 582280 | 456210 | 59.6 | 60.7 | 16 | P1 – Critical
E750-RFI-0024 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – duct bank encasement at OCS – Bel-Red/Overlake guideway | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-177 for fire alarm device layout at OCS – Bel-Red/Overlake guideway. Request direction on compliant detail. | Field Engineer | 2019-03-19 | 14 | Routine | N | N | Y | 1 | DSDC – LTK Engineering | 4 | 2019-04-25 | 37 | N | 23 | 2 | 2019-05-09 | 51 | Closed | 0 | 9 | 0 |  |  | Y | E750-CO-006 | 82700 | 72800 | 0 | 47.6 | 98 | P1 – Critical
E750-RFI-0025 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Ocs Pole location conflict at Sta. 2153+90 | Proposed OCS pole foundation location at Sta. 2153+90 conflicts with station canopy support; offset of 13 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Project Engineer | 2019-03-20 | 14 | Expedite | N | N | Y | 2 | DSDC – LTK Engineering | 2 | 2019-04-01 | 11 | Y | 0 | 1 | 2019-04-01 | 11 | Closed | 0 | 3 | 0 |  |  | N |  | 0 | 0 | 0 | 3 | 482 | P3 – Medium
E750-RFI-0026 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | WSDOT comment on critical areas permit – Bellevue tunnel systems | WSDOT review comments on the critical areas permit require changes to the bearing pad/embed plate at Bellevue tunnel systems. Request direction on scope impacts and whether comments are within the contract requirements. | Project Engineer | 2019-04-01 | 14 | Urgent | N | N | N | 4 | DSDC – LTK Engineering | 2 | 2019-04-08 | 6 | Y | 0 | 1 | 2019-04-08 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1157 | P4 – Low
E750-RFI-0027 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Haul route revision – Communications room – Bellevue Downtown Station | Contractor requests approval of an alternate traffic/staging plan at Communications room – Bellevue Downtown Station: extended night closure. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Superintendent | 2019-04-22 | 14 | Routine | Y | N | N | 4 | DSDC – LTK Engineering | 2 | 2019-04-25 | 3 | Y | 0 | 1 | 2019-04-25 | 3 | Closed | 0 | 0 | 0 | 25000 | 47000 | N |  | 0 | 0 | 0 | 0 | 1158 | P4 – Low
E750-RFI-0028 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Grounding/bonding and stray-current detail – Systems ductbank – Bel-Red | Civil and systems drawings differ on grounding/bonding of bearing pad/embed plate for stray-current control at Systems ductbank – Bel-Red. Request governing detail and responsibility for installation. | Superintendent | 2019-05-09 | 14 | Routine | Y | Y | N | 7 | DSDC – LTK Engineering | 2 | 2019-05-21 | 12 | Y | 0 | 1 | 2019-05-21 | 12 | Closed | 17 | 0 | 10 | 68000 | 126000 | Y | E750-CO-009 | 103680 | 103680 | 12.3 | 46.1 | 121 | P2 – High
E750-RFI-0029 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Direct fixation fastener spacing at Sta. 2178+30 | Track layout at Sta. 2178+30 (OCS – Bel-Red/Overlake guideway) differs from the track-structure interface drawing E-770. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Superintendent | 2019-05-13 | 14 | Expedite | Y | N | N | 7 | DSDC – LTK Engineering | 1 | 2019-05-22 | 9 | Y | 0 | 1 | 2019-05-22 | 9 | Closed | 0 | 0 | 0 | 260000 | 485000 | N |  | 0 | 0 | 0 | 0 | 1159 | P4 – Low
E750-RFI-0030 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Embedded conduit stub-ups – Communications room – Bellevue Downtown Station | Systems contractor requires 3-in. PVC conduit stub-ups for SCADA cabinet at Communications room – Bellevue Downtown Station not provided in civil C-684. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Project Engineer | 2019-05-13 | 14 | Routine | Y | N | N | 0 | DSDC – LTK Engineering | 2 | 2019-05-31 | 18 | N | 4 | 1 | 2019-05-31 | 18 | Closed | 0 | 0 | 2 | 167000 | 311000 | Y | E750-CO-009 | 177240 | 177240 | 21 | 49.1 | 72 | P1 – Critical
E750-RFI-0031 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Special trackwork layout – OCS – Bel-Red/Overlake guideway | Track layout at Sta. 1034+40 (OCS – Bel-Red/Overlake guideway) differs from the track-structure interface drawing C-385. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Superintendent | 2019-05-13 | 14 | Routine | N | N | N | 6 | DSDC – LTK Engineering | 1 | 2019-05-20 | 5 | Y | 0 | 2 | 2019-05-31 | 18 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1160 | P4 – Low
E750-RFI-0032 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Tunnel Emergency Phone location conflict at Sta. 1360+42 | Proposed tunnel emergency phone foundation location at Sta. 1360+42 conflicts with platform edge slab; offset of 10 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Project Engineer | 2019-06-03 | 14 | Routine | Y | Y | N | 6 | DSDC – LTK Engineering | 2 | 2019-06-17 | 12 | Y | 0 | 1 | 2019-06-17 | 12 | Closed | 26 | 0 | 8 | 795000 | 1483000 | N |  | 0 | 0 | 0 | 1.8 | 541 | P3 – Medium
E750-RFI-0033 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Ocs Pole location conflict at Sta. 1525+02 | Proposed OCS pole foundation location at Sta. 1525+02 conflicts with drilled shaft cap; offset of 13 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Field Engineer | 2019-06-03 | 14 | Expedite | N | Y | N | 5 | DSDC – LTK Engineering | 2 | 2019-06-11 | 8 | Y | 0 | 1 | 2019-06-11 | 8 | Closed | 16 | 0 | 7 |  |  | Y | E750-CO-009 | 245380 | 245380 | 29 | 54 | 30 | P1 – Critical
E750-RFI-0034 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Signal Case location conflict at Sta. 2370+03 | Proposed signal case foundation location at Sta. 2370+03 conflicts with pedestrian ramp; offset of 7 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Superintendent | 2019-06-24 | 14 | Expedite | Y | N | N | 1 | DSDC – LTK Engineering | 5 | 2019-07-08 | 13 | Y | 0 | 1 | 2019-07-08 | 13 | Closed | 0 | 0 | 0 | 1405000 | 2622000 | N |  | 0 | 0 | 0 | 0 | 1161 | P4 – Low
E750-RFI-0035 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – Train control – Overlake Village | Civil and systems drawings differ on grounding/bonding of duct bank encasement for stray-current control at Train control – Overlake Village. Request governing detail and responsibility for installation. | Design Manager | 2019-07-01 | 14 | Routine | N | Y | N | 1 | DSDC – LTK Engineering | 3 | 2019-07-15 | 12 | Y | 0 | 1 | 2019-07-15 | 12 | Closed | 13 | 0 | 8 |  |  | N |  | 0 | 0 | 0 | 1.8 | 542 | P3 – Medium
E750-RFI-0036 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Direct fixation fastener spacing at Sta. 1208+75 | Track layout at Sta. 1208+75 (Systems ductbank – Bel-Red) differs from the track-structure interface drawing A-373. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Engineer | 2019-07-04 | 14 | Routine | Y | Y | N | 7 | DSDC – LTK Engineering | 3 | 2019-07-15 | 9 | Y | 0 | 2 | 2019-07-29 | 25 | Closed | 3 | 0 | 2 | 211000 | 393000 | Y | E750-CO-007 | 239500 | 188300 | 2 | 43 | 177 | P2 – High
E750-RFI-0037 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | WSDOT comment on street improvement permit – OCS – Bel-Red/Overlake guideway | WSDOT review comments on the street improvement permit require changes to the drilled shaft cap at OCS – Bel-Red/Overlake guideway. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2019-07-23 | 14 | Routine | Y | N | N | 2 | DSDC – LTK Engineering | 5 | 2019-08-05 | 13 | Y | 0 | 1 | 2019-08-05 | 13 | Closed | 0 | 0 | 0 | 2534000 | 4730000 | Y | E750-CO-008 | 1678000 | 661300 | 0 | 46.2 | 119 | P2 – High
E750-RFI-0038 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Systems ductbank – Bel-Red | Systems contractor requires 5-in. PVC conduit stub-ups for rail bonding at Systems ductbank – Bel-Red not provided in civil C-814. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2019-07-30 | 14 | Urgent | Y | N | N | 1 | DSDC – LTK Engineering | 4 | 2019-08-19 | 19 | N | 5 | 2 | 2019-09-06 | 38 | Closed | 0 | 0 | 0 | 482000 | 900000 | N |  | 0 | 0 | 0 | 0 | 1162 | P4 – Low
E750-RFI-0039 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Missing dimension on E-606 | Request clarification of 01 25 00 Substitution Procedures and E-606: dimension/notes appear inconsistent or omitted for the work at Train control – Overlake Village. | Scheduler | 2019-08-02 | 14 | Routine | N | N | N | 3 | DSDC – LTK Engineering | 2 | 2019-08-12 | 8 | Y | 0 | 2 | 2019-08-19 | 17 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1163 | P4 – Low
E750-RFI-0040 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Property owner access/restoration requirement – Communications room – Bellevue Downtown Station | Adjacent property owner has requested additional restoration and access provisions at Communications room – Bellevue Downtown Station beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Scheduler | 2019-08-02 | 14 | Routine | Y | N | N | 2 | DSDC – LTK Engineering | 4 | 2019-08-26 | 22 | N | 8 | 1 | 2019-08-26 | 22 | Closed | 0 | 0 | 0 | 67000 | 125000 | N |  | 0 | 0 | 0 | 0 | 1164 | P4 – Low
E750-RFI-0041 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – Bellevue tunnel systems | Civil and systems drawings differ on grounding/bonding of bearing pad/embed plate for stray-current control at Bellevue tunnel systems. Request governing detail and responsibility for installation. | Project Manager | 2019-08-29 | 14 | Routine | N | Y | N | 7 | DSDC – LTK Engineering | 4 | 2019-09-10 | 12 | Y | 0 | 1 | 2019-09-10 | 12 | Closed | 29 | 0 | 18 |  |  | N |  | 0 | 0 | 0 | 4 | 458 | P3 – Medium
E750-RFI-0042 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Embedded conduit stub-ups – Train control – Overlake Village | Systems contractor requires 4-in. PVC conduit stub-ups for OCS pole at Train control – Overlake Village not provided in civil E-142. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2019-08-30 | 14 | Urgent | Y | Y | Y | 2 | DSDC – LTK Engineering | 4 | 2019-09-09 | 10 | Y | 0 | 1 | 2019-09-09 | 10 | Closed | 96 | 54 | 0 | 34000 | 63000 | Y | E750-CO-009 | 31800 | 31800 | 3.8 | 67 | 7 | P1 – Critical
E750-RFI-0043 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Haul route revision – Traction power substation – Bellevue | Contractor requests approval of an alternate traffic/staging plan at Traction power substation – Bellevue: temporary lane shift. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Scheduler | 2019-09-03 | 14 | Urgent | N | N | Y | 6 | DSDC – LTK Engineering | 2 | 2019-09-09 | 4 | Y | 0 | 2 | 2019-09-23 | 20 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1165 | P4 – Low
E750-RFI-0044 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – station canopy support at Communications room – Bellevue Downtown Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-698 for standpipe connection at Communications room – Bellevue Downtown Station. Request direction on compliant detail. | Project Manager | 2019-09-23 | 14 | Routine | N | Y | N | 8 | DSDC – LTK Engineering | 4 | 2019-10-01 | 8 | Y | 0 | 1 | 2019-10-01 | 8 | Closed | 7 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 635 | P3 – Medium
E750-RFI-0045 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Direct fixation fastener spacing at Sta. 1719+73 | Track layout at Sta. 1719+73 (Bellevue tunnel systems) differs from the track-structure interface drawing A-786. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Manager | 2019-09-23 | 14 | Routine | N | N | N | 0 | DSDC – LTK Engineering | 2 | 2019-10-01 | 8 | Y | 0 | 1 | 2019-10-01 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1166 | P4 – Low
E750-RFI-0046 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Clarify spec requirement – Bellevue tunnel systems | Request clarification of 01 25 00 Substitution Procedures and E-485: dimension/notes appear inconsistent or omitted for the work at Bellevue tunnel systems. | Scheduler | 2019-09-24 | 14 | Routine | N | N | N | 2 | DSDC – LTK Engineering | 3 | 2019-09-30 | 5 | Y | 0 | 1 | 2019-09-30 | 5 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1167 | P4 – Low
E750-RFI-0047 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – pedestrian ramp sequence at OCS – Bel-Red/Overlake guideway | Erection of the pedestrian ramp as drawn conflicts with adjacent work and access limits at OCS – Bel-Red/Overlake guideway. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Superintendent | 2019-10-08 | 14 | Expedite | Y | Y | Y | 7 | DSDC – LTK Engineering | 3 | 2019-10-11 | 3 | Y | 0 | 1 | 2019-10-11 | 3 | Closed | 8 | 5 | 0 | 730000 | 1363000 | N |  | 0 | 0 | 0 | 5 | 443 | P3 – Medium
E750-RFI-0048 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – OCS – Bel-Red/Overlake guideway | Civil and systems drawings differ on grounding/bonding of platform edge slab for stray-current control at OCS – Bel-Red/Overlake guideway. Request governing detail and responsibility for installation. | Field Engineer | 2019-10-09 | 14 | Routine | Y | Y | Y | 0 | DSDC – LTK Engineering | 3 | 2019-10-22 | 13 | Y | 0 | 1 | 2019-10-22 | 13 | Closed | 8 | 4 | 0 | 125000 | 233000 | N |  | 0 | 0 | 0 | 4 | 459 | P3 – Medium
E750-RFI-0049 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – stair core wall at Bellevue tunnel systems | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-500 for standpipe connection at Bellevue tunnel systems. Request direction on compliant detail. | Project Manager | 2019-10-14 | 14 | Urgent | N | Y | Y | 3 | DSDC – LTK Engineering | 1 | 2019-10-24 | 10 | Y | 0 | 1 | 2019-10-24 | 10 | Closed | 17 | 15 | 0 |  |  | N |  | 0 | 0 | 0 | 15 | 372 | P3 – Medium
E750-RFI-0050 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Embedded conduit stub-ups – Systems ductbank – Bel-Red | Systems contractor requires 4-in. PVC conduit stub-ups for OCS pole at Systems ductbank – Bel-Red not provided in civil E-300. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Design Manager | 2019-10-15 | 14 | Urgent | N | Y | Y | 5 | DSDC – LTK Engineering | 1 | 2019-10-28 | 13 | Y | 0 | 2 | 2019-11-18 | 33 | Closed | 16 | 9 | 0 |  |  | N |  | 0 | 0 | 0 | 9 | 402 | P3 – Medium
E750-RFI-0051 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Clarify spec requirement – Train control – Overlake Village | Request clarification of 00 72 00 General Conditions and E-230: dimension/notes appear inconsistent or omitted for the work at Train control – Overlake Village. | Project Engineer | 2019-10-30 | 14 | Routine | N | N | N | 3 | DSDC – LTK Engineering | 3 | 2019-11-04 | 4 | Y | 0 | 1 | 2019-11-04 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1168 | P4 – Low
E750-RFI-0052 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | City of Bellevue comment on critical areas permit – Train control – Overlake Village | City of Bellevue review comments on the critical areas permit require changes to the drilled shaft cap at Train control – Overlake Village. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2019-11-01 | 14 | Expedite | Y | Y | Y | 0 | DSDC – LTK Engineering | 2 | 2019-11-21 | 20 | N | 6 | 2 | 2019-11-28 | 27 | Closed | 11 | 6 | 0 | 140000 | 261000 | Y | E750-CO-010 | 120900 | 62400 | 3 | 45.1 | 138 | P2 – High
E750-RFI-0053 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Special trackwork layout – OCS – I-90/Mercer Island to South Bellevue | Track layout at Sta. 1899+33 (OCS – I-90/Mercer Island to South Bellevue) differs from the track-structure interface drawing C-556. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2019-11-04 | 14 | Routine | N | N | N | 3 | DSDC – LTK Engineering | 1 | 2019-11-11 | 5 | Y | 0 | 1 | 2019-11-11 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1169 | P4 – Low
E750-RFI-0054 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Haul route revision – Bellevue tunnel systems | Contractor requests approval of an alternate traffic/staging plan at Bellevue tunnel systems: temporary lane shift. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Superintendent | 2019-11-11 | 14 | Urgent | N | Y | N | 6 | DSDC – LTK Engineering | 2 | 2019-11-15 | 4 | Y | 0 | 1 | 2019-11-15 | 4 | Closed | 5 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 677 | P3 – Medium
E750-RFI-0055 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – OCS – I-90/Mercer Island to South Bellevue | E-797 shows a 31 ft-10 in. dimension for the duct bank encasement; structural sheet S-655 shows a different value. Request clarification before fabrication/rebar release. | Project Manager | 2019-12-09 | 14 | Expedite | Y | Y | N | 5 | DSDC – LTK Engineering | 2 | 2019-12-16 | 5 | Y | 0 | 1 | 2019-12-16 | 5 | Closed | 6 | 0 | 2 | 2521000 | 4706000 | N |  | 0 | 0 | 0 | 0.4 | 735 | P3 – Medium
E750-RFI-0056 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Clarify spec requirement – Traction power substation – Bellevue | Request clarification of 01 33 00 Submittal Procedures and C-445: dimension/notes appear inconsistent or omitted for the work at Traction power substation – Bellevue. | Superintendent | 2019-12-25 | 14 | Routine | N | N | N | 6 | DSDC – LTK Engineering | 2 | 2020-01-01 | 7 | Y | 0 | 1 | 2020-01-01 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1170 | P4 – Low
E750-RFI-0057 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Track slab/expansion joint interface – OCS – Bel-Red/Overlake guideway | Track layout at Sta. 1916+22 (OCS – Bel-Red/Overlake guideway) differs from the track-structure interface drawing M-451. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2020-01-02 | 14 | Routine | N | N | N | 1 | DSDC – LTK Engineering | 2 | 2020-01-13 | 11 | Y | 0 | 1 | 2020-01-13 | 11 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1171 | P4 – Low
E750-RFI-0058 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – stair core wall at Train control – Overlake Village | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-159 for egress width at Train control – Overlake Village. Request direction on compliant detail. | Design Manager | 2020-01-06 | 14 | Urgent | N | N | N | 6 | DSDC – LTK Engineering | 2 | 2020-01-13 | 6 | Y | 0 | 1 | 2020-01-13 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1172 | P4 – Low
E750-RFI-0059 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – bearing pad/embed plate at Communications room – Bellevue Downtown Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-613 for standpipe connection at Communications room – Bellevue Downtown Station. Request direction on compliant detail. | Project Engineer | 2020-01-08 | 14 | Routine | N | N | N | 2 | DSDC – LTK Engineering | 3 | 2020-01-22 | 14 | Y | 0 | 2 | 2020-02-03 | 26 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1173 | P4 – Low
E750-RFI-0060 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Missing dimension on C-395 | Request clarification of 01 33 00 Submittal Procedures and C-395: dimension/notes appear inconsistent or omitted for the work at Communications room – Bellevue Downtown Station. | Design Manager | 2020-01-10 | 14 | Routine | N | N | N | 4 | DSDC – LTK Engineering | 2 | 2020-01-20 | 10 | Y | 0 | 1 | 2020-01-20 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1174 | P4 – Low
E750-RFI-0061 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – Systems ductbank – Bel-Red | Civil and systems drawings differ on grounding/bonding of retaining wall footing for stray-current control at Systems ductbank – Bel-Red. Request governing detail and responsibility for installation. | Project Manager | 2020-01-16 | 14 | Urgent | N | N | Y | 8 | DSDC – LTK Engineering | 3 | 2020-02-12 | 27 | N | 13 | 2 | 2020-02-24 | 38 | Closed | 0 | 11 | 0 |  |  | N |  | 0 | 0 | 0 | 11 | 390 | P3 – Medium
E750-RFI-0062 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 24-in. sanitary sewer at OCS – I-90/Mercer Island to South Bellevue | Potholing at Sta. 2064+27 located a 24-in. sanitary sewer in conflict with the proposed bearing pad/embed plate. Utility is not shown on E-867. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Scheduler | 2020-01-28 | 14 | Routine | N | Y | N | 1 | DSDC – LTK Engineering | 1 | 2020-02-03 | 4 | Y | 0 | 1 | 2020-02-03 | 4 | Closed | 4 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 678 | P3 – Medium
E750-RFI-0063 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Ocs Pole location conflict at Sta. 1194+84 | Proposed OCS pole foundation location at Sta. 1194+84 conflicts with drilled shaft cap; offset of 13 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Scheduler | 2020-02-05 | 14 | Routine | Y | Y | N | 5 | DSDC – LTK Engineering | 2 | 2020-02-26 | 21 | N | 7 | 1 | 2020-02-26 | 21 | Closed | 13 | 0 | 9 | 525000 | 980000 | Y | E750-CO-011 | 1091600 | 577200 | 5 | 49.4 | 70 | P1 – Critical
E750-RFI-0064 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – drilled shaft cap at OCS – I-90/Mercer Island to South Bellevue | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-894 for fire alarm device layout at OCS – I-90/Mercer Island to South Bellevue. Request direction on compliant detail. | Superintendent | 2020-02-14 | 14 | Routine | Y | Y | N | 2 | DSDC – LTK Engineering | 1 | 2020-02-26 | 12 | Y | 0 | 1 | 2020-02-26 | 12 | Closed | 1 | 0 | 0 | 260000 | 485000 | N |  | 0 | 0 | 0 | 0 | 1175 | P4 – Low
E750-RFI-0065 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Ocs Pole location conflict at Sta. 2171+40 | Proposed OCS pole foundation location at Sta. 2171+40 conflicts with station canopy support; offset of 10 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Project Engineer | 2020-02-18 | 14 | Routine | Y | Y | N | 4 | DSDC – LTK Engineering | 3 | 2020-03-12 | 23 | N | 9 | 1 | 2020-03-12 | 23 | Closed | 21 | 0 | 18 | 550000 | 1027000 | N |  | 0 | 0 | 0 | 4 | 460 | P3 – Medium
E750-RFI-0066 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – column reinforcement sequence at Bellevue tunnel systems | Erection of the column reinforcement as drawn conflicts with adjacent work and access limits at Bellevue tunnel systems. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Project Manager | 2020-02-20 | 14 | Routine | N | Y | Y | 5 | DSDC – LTK Engineering | 1 | 2020-02-28 | 8 | Y | 0 | 2 | 2020-03-16 | 23 | Closed | 7 | 6 | 0 |  |  | N |  | 0 | 0 | 0 | 6 | 425 | P3 – Medium
E750-RFI-0067 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – OCS – Bel-Red/Overlake guideway | Systems contractor requires 2-in. PVC conduit stub-ups for SCADA cabinet at OCS – Bel-Red/Overlake guideway not provided in civil E-315. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Design Manager | 2020-02-21 | 14 | Routine | Y | Y | N | 4 | DSDC – LTK Engineering | 3 | 2020-03-16 | 23 | N | 9 | 1 | 2020-03-16 | 23 | Closed | 6 | 0 | 6 | 81000 | 152000 | N |  | 0 | 0 | 0 | 1.3 | 568 | P3 – Medium
E750-RFI-0068 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Grounding/bonding and stray-current detail – OCS – I-90/Mercer Island to South Bellevue | Civil and systems drawings differ on grounding/bonding of station canopy support for stray-current control at OCS – I-90/Mercer Island to South Bellevue. Request governing detail and responsibility for installation. | Project Engineer | 2020-03-02 | 14 | Expedite | N | Y | N | 7 | DSDC – LTK Engineering | 1 | 2020-03-10 | 8 | Y | 0 | 1 | 2020-03-10 | 8 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1176 | P4 – Low
E750-RFI-0069 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Missing dimension on E-197 | Request clarification of 01 33 00 Submittal Procedures and E-197: dimension/notes appear inconsistent or omitted for the work at Bellevue tunnel systems. | Scheduler | 2020-03-06 | 14 | Routine | N | N | N | 1 | DSDC – LTK Engineering | 1 | 2020-03-09 | 3 | Y | 0 | 1 | 2020-03-09 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1177 | P4 – Low
E750-RFI-0070 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – platform edge slab at Bellevue tunnel systems | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-650 for smoke control damper at Bellevue tunnel systems. Request direction on compliant detail. | Field Engineer | 2020-03-16 | 14 | Routine | N | N | N | 7 | DSDC – LTK Engineering | 3 | 2020-04-01 | 16 | N | 2 | 1 | 2020-04-01 | 16 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1178 | P4 – Low
E750-RFI-0071 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – pedestrian ramp at Traction power substation – Bellevue | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-348 for emergency stair pressurization at Traction power substation – Bellevue. Request direction on compliant detail. | Field Engineer | 2020-04-02 | 14 | Routine | Y | Y | N | 6 | DSDC – LTK Engineering | 2 | 2020-04-13 | 10 | Y | 0 | 1 | 2020-04-13 | 10 | Closed | 4 | 0 | 1 | 1976000 | 3688000 | Y | E750-CO-012 | 2081600 | 1822500 | 3 | 50.9 | 48 | P1 – Critical
E750-RFI-0072 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – recycled-content fly ash blend | Contractor requests approval to substitute recycled-content fly ash blend for Type IL cement mix on work at OCS – Bel-Red/Overlake guideway, citing procurement lead time. Product data attached. | Design Manager | 2020-04-24 | 14 | Urgent | N | N | Y | 4 | DSDC – LTK Engineering | 1 | 2020-04-27 | 3 | Y | 0 | 1 | 2020-04-27 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1179 | P4 – Low
E750-RFI-0073 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – column reinforcement and stair core wall at Systems ductbank – Bel-Red | Interference between column reinforcement and stair core wall at Systems ductbank – Bel-Red per S-593. Required clearance of 2 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2020-05-11 | 14 | Routine | Y | N | N | 5 | DSDC – LTK Engineering | 3 | 2020-05-19 | 8 | Y | 0 | 2 | 2020-06-08 | 27 | Closed | 0 | 0 | 0 | 60000 | 111000 | N |  | 0 | 0 | 0 | 0 | 1180 | P4 – Low
E750-RFI-0074 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Embedded conduit stub-ups – Traction power substation – Bellevue | Systems contractor requires 4-in. PVC conduit stub-ups for rail bonding at Traction power substation – Bellevue not provided in civil A-606. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Scheduler | 2020-05-11 | 14 | Routine | N | N | N | 3 | DSDC – LTK Engineering | 4 | 2020-06-10 | 30 | N | 16 | 2 | 2020-07-01 | 51 | Closed | 0 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 586 | P3 – Medium
E750-RFI-0075 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – guideway girder diaphragm at Bellevue tunnel systems | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-709 for fire alarm device layout at Bellevue tunnel systems. Request direction on compliant detail. | Superintendent | 2020-05-14 | 14 | Urgent | Y | N | N | 8 | DSDC – LTK Engineering | 1 | 2020-05-22 | 8 | Y | 0 | 1 | 2020-05-22 | 8 | Closed | 0 | 0 | 0 | 328000 | 612000 | Y | E750-CO-013 | 248100 | 248100 | 0 | 42.8 | 184 | P2 – High
E750-RFI-0076 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Embedded conduit stub-ups – Train control – Overlake Village | Systems contractor requires 2-in. PVC conduit stub-ups for rail bonding at Train control – Overlake Village not provided in civil C-351. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2020-05-18 | 14 | Urgent | Y | Y | Y | 2 | DSDC – LTK Engineering | 3 | 2020-05-28 | 10 | Y | 0 | 1 | 2020-05-28 | 10 | Closed | 12 | 9 | 0 | 121000 | 226000 | N |  | 0 | 0 | 0 | 9 | 403 | P3 – Medium
E750-RFI-0077 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – alternate LED luminaire | Contractor requests approval to substitute alternate LED luminaire for specified LED luminaire on work at Systems ductbank – Bel-Red, citing procurement lead time. Product data attached. | Scheduler | 2020-05-20 | 14 | Expedite | N | N | N | 3 | DSDC – LTK Engineering | 2 | 2020-05-26 | 6 | Y | 0 | 1 | 2020-05-26 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1181 | P4 – Low
E750-RFI-0078 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – OCS – I-90/Mercer Island to South Bellevue | Civil and systems drawings differ on grounding/bonding of drilled shaft cap for stray-current control at OCS – I-90/Mercer Island to South Bellevue. Request governing detail and responsibility for installation. | Project Manager | 2020-05-29 | 14 | Routine | N | N | Y | 3 | DSDC – LTK Engineering | 3 | 2020-06-17 | 19 | N | 5 | 2 | 2020-06-29 | 29 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1182 | P4 – Low
E750-RFI-0079 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Tunnel Emergency Phone location conflict at Sta. 2186+63 | Proposed tunnel emergency phone foundation location at Sta. 2186+63 conflicts with duct bank encasement; offset of 13 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Superintendent | 2020-06-12 | 14 | Expedite | N | N | N | 0 | DSDC – LTK Engineering | 2 | 2020-06-30 | 18 | N | 4 | 1 | 2020-06-30 | 18 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1183 | P4 – Low
E750-RFI-0080 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Special trackwork layout – Traction power substation – Bellevue | Track layout at Sta. 1526+16 (Traction power substation – Bellevue) differs from the track-structure interface drawing E-311. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Superintendent | 2020-06-25 | 14 | Urgent | N | N | N | 5 | DSDC – LTK Engineering | 1 | 2020-06-30 | 5 | Y | 0 | 1 | 2020-06-30 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1184 | P4 – Low
E750-RFI-0081 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at Bellevue tunnel systems, citing procurement lead time. Product data attached. | Design Manager | 2020-06-26 | 14 | Expedite | N | N | N | 1 | DSDC – LTK Engineering | 2 | 2020-07-07 | 11 | Y | 0 | 1 | 2020-07-07 | 11 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1185 | P4 – Low
E750-RFI-0082 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Art embed coordination – OCS – Bel-Red/Overlake guideway | Request to clarify finish/connection detail on E-770 at OCS – Bel-Red/Overlake guideway. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2020-07-13 | 14 | Routine | N | N | N | 5 | DSDC – LTK Engineering | 1 | 2020-07-24 | 11 | Y | 0 | 2 | 2020-08-06 | 24 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1186 | P4 – Low
E750-RFI-0083 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Lane closure window request – Systems ductbank – Bel-Red | Contractor requests approval of an alternate traffic/staging plan at Systems ductbank – Bel-Red: revised haul route. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Design Manager | 2020-07-17 | 14 | Routine | Y | N | Y | 6 | DSDC – LTK Engineering | 2 | 2020-07-22 | 5 | Y | 0 | 1 | 2020-07-22 | 5 | Closed | 0 | 0 | 0 | 59000 | 110000 | Y | E750-CO-014 | 68400 | 24000 | 0 | 34.8 | 316 | P2 – High
E750-RFI-0084 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – bearing pad/embed plate and retaining wall footing at Train control – Overlake Village | Interference between bearing pad/embed plate and retaining wall footing at Train control – Overlake Village per C-848. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Engineer | 2020-07-21 | 14 | Urgent | N | Y | Y | 5 | DSDC – LTK Engineering | 3 | 2020-07-30 | 9 | Y | 0 | 1 | 2020-07-30 | 9 | Closed | 5 | 2 | 0 |  |  | N |  | 0 | 0 | 0 | 2 | 526 | P3 – Medium
E750-RFI-0085 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – galvanized steel handrail | Contractor requests approval to substitute galvanized steel handrail for stainless steel handrail on work at Traction power substation – Bellevue, citing procurement lead time. Product data attached. | Scheduler | 2020-07-21 | 14 | Expedite | N | N | N | 5 | DSDC – LTK Engineering | 2 | 2020-07-30 | 9 | Y | 0 | 1 | 2020-07-30 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1187 | P4 – Low
E750-RFI-0086 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Grounding/bonding and stray-current detail – Systems ductbank – Bel-Red | Civil and systems drawings differ on grounding/bonding of duct bank encasement for stray-current control at Systems ductbank – Bel-Red. Request governing detail and responsibility for installation. | Project Engineer | 2020-08-03 | 14 | Urgent | N | N | N | 7 | DSDC – LTK Engineering | 2 | 2020-08-14 | 11 | Y | 0 | 1 | 2020-08-14 | 11 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1188 | P4 – Low
E750-RFI-0087 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – alternate LED luminaire | Contractor requests approval to substitute alternate LED luminaire for specified LED luminaire on work at Bellevue tunnel systems, citing procurement lead time. Product data attached. | Field Engineer | 2020-08-06 | 14 | Routine | N | N | N | 6 | DSDC – LTK Engineering | 2 | 2020-08-10 | 4 | Y | 0 | 1 | 2020-08-10 | 4 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1189 | P4 – Low
E750-RFI-0088 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – pedestrian ramp sequence at Bellevue tunnel systems | Erection of the pedestrian ramp as drawn conflicts with adjacent work and access limits at Bellevue tunnel systems. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2020-08-07 | 14 | Urgent | N | Y | Y | 0 | DSDC – LTK Engineering | 2 | 2020-08-20 | 13 | Y | 0 | 1 | 2020-08-20 | 13 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1190 | P4 – Low
E750-RFI-0089 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – alternate LED luminaire | Contractor requests approval to substitute alternate LED luminaire for specified LED luminaire on work at Systems ductbank – Bel-Red, citing procurement lead time. Product data attached. | Design Manager | 2020-08-17 | 14 | Routine | N | N | N | 6 | DSDC – LTK Engineering | 2 | 2020-09-09 | 23 | N | 9 | 1 | 2020-09-09 | 23 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1191 | P4 – Low
E750-RFI-0090 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – Train control – Overlake Village | Civil and systems drawings differ on grounding/bonding of stair core wall for stray-current control at Train control – Overlake Village. Request governing detail and responsibility for installation. | Project Engineer | 2020-08-21 | 14 | Routine | N | Y | Y | 0 | DSDC – LTK Engineering | 2 | 2020-09-02 | 12 | Y | 0 | 2 | 2020-09-23 | 33 | Closed | 31 | 20 | 0 |  |  | N |  | 0 | 0 | 0 | 20 | 362 | P3 – Medium
E750-RFI-0091 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – Systems ductbank – Bel-Red | Systems contractor requires 2-in. PVC conduit stub-ups for tunnel emergency phone at Systems ductbank – Bel-Red not provided in civil A-620. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2020-08-27 | 14 | Routine | N | N | N | 0 | DSDC – LTK Engineering | 2 | 2020-09-18 | 22 | N | 8 | 1 | 2020-09-18 | 22 | Closed | 0 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 736 | P3 – Medium
E750-RFI-0092 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – Bellevue tunnel systems | Civil and systems drawings differ on grounding/bonding of duct bank encasement for stray-current control at Bellevue tunnel systems. Request governing detail and responsibility for installation. | Design Manager | 2020-08-31 | 14 | Expedite | N | N | N | 8 | DSDC – LTK Engineering | 3 | 2020-09-08 | 8 | Y | 0 | 1 | 2020-09-08 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1192 | P4 – Low
E750-RFI-0093 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at Communications room – Bellevue Downtown Station, citing procurement lead time. Product data attached. | Scheduler | 2020-09-03 | 14 | Routine | N | Y | N | 6 | DSDC – LTK Engineering | 1 | 2020-09-14 | 9 | Y | 0 | 1 | 2020-09-14 | 9 | Closed | 18 | 0 | 13 |  |  | N |  | 0 | 0 | 0 | 2.9 | 491 | P3 – Medium
E750-RFI-0094 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – Bellevue tunnel systems | Civil and systems drawings differ on grounding/bonding of column reinforcement for stray-current control at Bellevue tunnel systems. Request governing detail and responsibility for installation. | Project Engineer | 2020-09-10 | 14 | Routine | N | Y | N | 3 | DSDC – LTK Engineering | 4 | 2020-09-21 | 10 | Y | 0 | 2 | 2020-10-09 | 29 | Closed | 31 | 0 | 23 |  |  | N |  | 0 | 0 | 0 | 5.1 | 430 | P3 – Medium
E750-RFI-0095 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – OCS – I-90/Mercer Island to South Bellevue | Systems contractor requires 4-in. PVC conduit stub-ups for traction power feeder at OCS – I-90/Mercer Island to South Bellevue not provided in civil C-503. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Design Manager | 2020-09-14 | 14 | Routine | N | Y | Y | 4 | DSDC – LTK Engineering | 3 | 2020-10-16 | 32 | N | 18 | 1 | 2020-10-16 | 32 | Closed | 31 | 16 | 0 |  |  | N |  | 0 | 0 | 0 | 16 | 369 | P3 – Medium
E750-RFI-0096 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – guideway girder diaphragm sequence at Traction power substation – Bellevue | Erection of the guideway girder diaphragm as drawn conflicts with adjacent work and access limits at Traction power substation – Bellevue. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Superintendent | 2020-09-17 | 14 | Expedite | N | Y | Y | 0 | DSDC – LTK Engineering | 2 | 2020-09-22 | 5 | Y | 0 | 2 | 2020-10-05 | 17 | Closed | 4 | 3 | 0 |  |  | Y | E750-CO-015 | 125700 | 83800 | 2 | 42.7 | 186 | P2 – High
E750-RFI-0097 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Night work and noise variance – OCS – Bel-Red/Overlake guideway | Contractor requests approval of an alternate traffic/staging plan at OCS – Bel-Red/Overlake guideway: revised haul route. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Superintendent | 2020-09-17 | 14 | Expedite | N | N | Y | 8 | DSDC – LTK Engineering | 1 | 2020-09-21 | 4 | Y | 0 | 1 | 2020-09-21 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1193 | P4 – Low
E750-RFI-0098 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – column reinforcement at OCS – Bel-Red/Overlake guideway | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-419 for smoke control damper at OCS – Bel-Red/Overlake guideway. Request direction on compliant detail. | Field Engineer | 2020-09-21 | 14 | Routine | N | Y | N | 2 | DSDC – LTK Engineering | 2 | 2020-10-05 | 14 | Y | 0 | 2 | 2020-10-15 | 24 | Closed | 3 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 737 | P3 – Medium
E750-RFI-0099 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Track slab/expansion joint interface – OCS – Bel-Red/Overlake guideway | Track layout at Sta. 1249+61 (OCS – Bel-Red/Overlake guideway) differs from the track-structure interface drawing C-631. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2020-09-23 | 14 | Expedite | N | N | Y | 1 | DSDC – LTK Engineering | 3 | 2020-10-08 | 15 | N | 1 | 1 | 2020-10-08 | 15 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1194 | P4 – Low
E750-RFI-0100 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Embedded conduit stub-ups – OCS – Bel-Red/Overlake guideway | Systems contractor requires 5-in. PVC conduit stub-ups for rail bonding at OCS – Bel-Red/Overlake guideway not provided in civil C-760. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2020-10-12 | 14 | Urgent | N | Y | Y | 1 | DSDC – LTK Engineering | 4 | 2020-10-22 | 10 | Y | 0 | 1 | 2020-10-22 | 10 | Closed | 16 | 12 | 0 |  |  | N |  | 0 | 0 | 0 | 12 | 380 | P3 – Medium
E750-RFI-0101 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at OCS – Bel-Red/Overlake guideway, citing procurement lead time. Product data attached. | Project Engineer | 2020-10-15 | 14 | Routine | N | N | N | 7 | DSDC – LTK Engineering | 2 | 2020-10-21 | 6 | Y | 0 | 1 | 2020-10-21 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1195 | P4 – Low
E750-RFI-0102 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Grounding/bonding and stray-current detail – OCS – I-90/Mercer Island to South Bellevue | Civil and systems drawings differ on grounding/bonding of bearing pad/embed plate for stray-current control at OCS – I-90/Mercer Island to South Bellevue. Request governing detail and responsibility for installation. | Design Manager | 2020-10-21 | 14 | Routine | N | Y | N | 6 | DSDC – LTK Engineering | 1 | 2020-11-17 | 27 | N | 13 | 1 | 2020-11-17 | 27 | Closed | 24 | 0 | 7 |  |  | N |  | 0 | 0 | 0 | 1.6 | 559 | P3 – Medium
E750-RFI-0103 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – alternate epoxy-coated rebar supplier | Contractor requests approval to substitute alternate epoxy-coated rebar supplier for specified epoxy-coated rebar on work at Traction power substation – Bellevue, citing procurement lead time. Product data attached. | Field Engineer | 2020-10-21 | 14 | Routine | N | N | Y | 4 | DSDC – LTK Engineering | 1 | 2020-10-28 | 7 | Y | 0 | 1 | 2020-10-28 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1196 | P4 – Low
E750-RFI-0104 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 30-in. storm drain at Bellevue tunnel systems | Potholing at Sta. 2151+41 located a 30-in. storm drain in conflict with the proposed platform edge slab. Utility is not shown on S-722. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Design Manager | 2020-10-22 | 14 | Routine | N | Y | Y | 8 | DSDC – LTK Engineering | 2 | 2020-11-09 | 18 | N | 4 | 1 | 2020-11-09 | 18 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1197 | P4 – Low
E750-RFI-0105 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – platform edge slab at Train control – Overlake Village | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-128 for fire alarm device layout at Train control – Overlake Village. Request direction on compliant detail. | Design Manager | 2020-11-05 | 14 | Routine | N | N | N | 1 | DSDC – LTK Engineering | 2 | 2020-11-13 | 8 | Y | 0 | 1 | 2020-11-13 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1198 | P4 – Low
E750-RFI-0106 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – OCS – I-90/Mercer Island to South Bellevue | Systems contractor requires 3-in. PVC conduit stub-ups for SCADA cabinet at OCS – I-90/Mercer Island to South Bellevue not provided in civil E-182. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2020-11-16 | 14 | Urgent | Y | N | Y | 0 | DSDC – LTK Engineering | 1 | 2020-11-24 | 8 | Y | 0 | 2 | 2020-12-07 | 20 | Closed | 0 | 0 | 0 | 2301000 | 4295000 | Y | E750-CO-016 | 2110600 | 0 | 0 | 0 | 1199 | P4 – Low
E750-RFI-0107 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – retaining wall footing at OCS – Bel-Red/Overlake guideway | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-356 for emergency stair pressurization at OCS – Bel-Red/Overlake guideway. Request direction on compliant detail. | Field Engineer | 2020-11-23 | 14 | Routine | N | N | N | 4 | DSDC – LTK Engineering | 4 | 2020-11-30 | 5 | Y | 0 | 1 | 2020-11-30 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1200 | P4 – Low
E750-RFI-0108 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – drilled shaft cap sequence at Systems ductbank – Bel-Red | Erection of the drilled shaft cap as drawn conflicts with adjacent work and access limits at Systems ductbank – Bel-Red. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2020-11-30 | 14 | Routine | Y | N | N | 6 | DSDC – LTK Engineering | 3 | 2020-12-14 | 12 | Y | 0 | 1 | 2020-12-14 | 12 | Closed | 0 | 0 | 0 | 579000 | 1080000 | Y | E750-CO-018 | 795300 | 410900 | 0 | 44.5 | 151 | P2 – High
E750-RFI-0109 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Embedded conduit stub-ups – OCS – I-90/Mercer Island to South Bellevue | Systems contractor requires 2-in. PVC conduit stub-ups for signal case at OCS – I-90/Mercer Island to South Bellevue not provided in civil M-798. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2020-11-30 | 14 | Routine | N | N | Y | 0 | DSDC – LTK Engineering | 2 | 2020-12-28 | 26 | N | 12 | 2 | 2021-01-15 | 46 | Closed | 0 | 3 | 0 |  |  | N |  | 0 | 0 | 0 | 3 | 483 | P3 – Medium
E750-RFI-0110 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – retaining wall footing at Systems ductbank – Bel-Red | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-668 for egress width at Systems ductbank – Bel-Red. Request direction on compliant detail. | Design Manager | 2020-12-04 | 14 | Urgent | N | N | Y | 4 | DSDC – LTK Engineering | 1 | 2020-12-15 | 11 | Y | 0 | 2 | 2021-01-04 | 31 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1201 | P4 – Low
E750-RFI-0111 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | WSDOT comment on building permit – Communications room – Bellevue Downtown Station | WSDOT review comments on the building permit require changes to the platform edge slab at Communications room – Bellevue Downtown Station. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2020-12-07 | 14 | Urgent | Y | Y | Y | 3 | DSDC – LTK Engineering | 2 | 2020-12-14 | 7 | Y | 0 | 1 | 2020-12-14 | 7 | Closed | 30 | 19 | 0 | 122000 | 229000 | Y | E750-CO-017 | 164300 | 108200 | 24 | 66.9 | 8 | P1 – Critical
E750-RFI-0112 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – duct bank encasement at Communications room – Bellevue Downtown Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-445 for smoke control damper at Communications room – Bellevue Downtown Station. Request direction on compliant detail. | Field Engineer | 2021-01-08 | 14 | Routine | N | N | N | 1 | DSDC – LTK Engineering | 1 | 2021-01-25 | 15 | N | 1 | 1 | 2021-01-25 | 15 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1202 | P4 – Low
E750-RFI-0113 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Night work and noise variance – Systems ductbank – Bel-Red | Contractor requests approval of an alternate traffic/staging plan at Systems ductbank – Bel-Red: revised haul route. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Project Engineer | 2021-02-01 | 14 | Urgent | N | Y | Y | 1 | DSDC – LTK Engineering | 2 | 2021-02-04 | 3 | Y | 0 | 1 | 2021-02-04 | 3 | Closed | 31 | 25 | 0 |  |  | N |  | 0 | 0 | 0 | 25 | 351 | P3 – Medium
E750-RFI-0114 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 12-in. ductile iron water main at Bellevue tunnel systems | Potholing at Sta. 1257+60 located a 12-in. ductile iron water main in conflict with the proposed drilled shaft cap. Utility is not shown on S-574. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Manager | 2021-02-04 | 14 | Expedite | Y | Y | N | 8 | DSDC – LTK Engineering | 1 | 2021-02-18 | 14 | Y | 0 | 1 | 2021-02-18 | 14 | Closed | 25 | 0 | 8 | 574000 | 1072000 | Y | E750-CO-019 | 519300 | 367300 | 8 | 48.6 | 83 | P1 – Critical
E750-RFI-0115 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – recycled-content fly ash blend | Contractor requests approval to substitute recycled-content fly ash blend for Type IL cement mix on work at OCS – I-90/Mercer Island to South Bellevue, citing procurement lead time. Product data attached. | Project Engineer | 2021-02-08 | 14 | Routine | N | Y | N | 5 | DSDC – LTK Engineering | 2 | 2021-02-17 | 9 | Y | 0 | 1 | 2021-02-17 | 9 | Closed | 10 | 0 | 8 |  |  | N |  | 0 | 0 | 0 | 1.8 | 543 | P3 – Medium
E750-RFI-0116 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – Traction power substation – Bellevue | Systems contractor requires 2-in. PVC conduit stub-ups for fiber backbone at Traction power substation – Bellevue not provided in civil A-314. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2021-02-15 | 14 | Routine | N | Y | N | 6 | DSDC – LTK Engineering | 3 | 2021-02-26 | 11 | Y | 0 | 1 | 2021-02-26 | 11 | Closed | 27 | 0 | 14 |  |  | N |  | 0 | 0 | 0 | 3.1 | 470 | P3 – Medium
E750-RFI-0117 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 8-in. high-pressure gas main at OCS – Bel-Red/Overlake guideway | Potholing at Sta. 2217+06 located a 8-in. high-pressure gas main in conflict with the proposed stair core wall. Utility is not shown on E-706. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Design Manager | 2021-02-16 | 14 | Routine | Y | N | N | 5 | DSDC – LTK Engineering | 2 | 2021-03-01 | 13 | Y | 0 | 1 | 2021-03-01 | 13 | Closed | 0 | 0 | 0 | 203000 | 378000 | Y | E750-CO-020 | 200400 | 112600 | 0 | 40.1 | 234 | P2 – High
E750-RFI-0118 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Dimensional discrepancy – OCS – I-90/Mercer Island to South Bellevue | E-636 shows a 30 ft-9 in. dimension for the platform edge slab; structural sheet S-564 shows a different value. Request clarification before fabrication/rebar release. | Project Manager | 2021-02-16 | 14 | Routine | Y | Y | N | 2 | DSDC – LTK Engineering | 1 | 2021-03-10 | 22 | N | 8 | 1 | 2021-03-10 | 22 | Closed | 4 | 0 | 1 | 448000 | 836000 | Y | E750-CO-021 | 507900 | 401100 | 2 | 45.4 | 132 | P2 – High
E750-RFI-0119 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Train control – Overlake Village | M-101 shows a 20 ft-6 in. dimension for the duct bank encasement; structural sheet S-381 shows a different value. Request clarification before fabrication/rebar release. | Project Manager | 2021-02-25 | 14 | Routine | Y | Y | N | 3 | DSDC – LTK Engineering | 1 | 2021-03-08 | 10 | Y | 0 | 1 | 2021-03-08 | 10 | Closed | 4 | 0 | 1 | 562000 | 1050000 | N |  | 0 | 0 | 0 | 0.2 | 795 | P4 – Low
E750-RFI-0120 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Direct fixation fastener spacing at Sta. 2274+26 | Track layout at Sta. 2274+26 (Bellevue tunnel systems) differs from the track-structure interface drawing C-214. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Scheduler | 2021-02-25 | 14 | Routine | Y | Y | Y | 0 | DSDC – LTK Engineering | 2 | 2021-03-09 | 12 | Y | 0 | 1 | 2021-03-09 | 12 | Closed | 4 | 2 | 0 | 26000 | 49000 | N |  | 0 | 0 | 0 | 2 | 527 | P3 – Medium
E750-RFI-0121 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Track slab/expansion joint interface – OCS – I-90/Mercer Island to South Bellevue | Track layout at Sta. 2002+94 (OCS – I-90/Mercer Island to South Bellevue) differs from the track-structure interface drawing S-736. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2021-03-04 | 14 | Routine | Y | Y | N | 5 | DSDC – LTK Engineering | 2 | 2021-03-23 | 19 | N | 5 | 1 | 2021-03-23 | 19 | Closed | 8 | 0 | 6 | 140000 | 262000 | N |  | 0 | 0 | 0 | 1.3 | 569 | P3 – Medium
E750-RFI-0122 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Direct fixation fastener spacing at Sta. 1029+71 | Track layout at Sta. 1029+71 (Train control – Overlake Village) differs from the track-structure interface drawing M-895. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Superintendent | 2021-03-05 | 14 | Routine | N | Y | N | 2 | DSDC – LTK Engineering | 3 | 2021-03-22 | 16 | N | 2 | 1 | 2021-03-22 | 16 | Closed | 5 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 796 | P4 – Low
E750-RFI-0123 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Scada Cabinet location conflict at Sta. 1505+16 | Proposed SCADA cabinet foundation location at Sta. 1505+16 conflicts with station canopy support; offset of 13 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Project Manager | 2021-03-05 | 14 | Routine | N | Y | Y | 6 | DSDC – LTK Engineering | 2 | 2021-03-22 | 16 | N | 2 | 1 | 2021-03-22 | 16 | Closed | 24 | 11 | 0 |  |  | N |  | 0 | 0 | 0 | 11 | 391 | P3 – Medium
E750-RFI-0124 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – Bellevue tunnel systems | C-498 shows a 49 ft-10 in. dimension for the stair core wall; structural sheet S-810 shows a different value. Request clarification before fabrication/rebar release. | Design Manager | 2021-03-25 | 14 | Routine | Y | N | Y | 7 | DSDC – LTK Engineering | 2 | 2021-04-05 | 11 | Y | 0 | 2 | 2021-04-23 | 29 | Closed | 0 | 3 | 0 | 939000 | 1754000 | N |  | 0 | 0 | 0 | 3 | 484 | P3 – Medium
E750-RFI-0125 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Communications room – Bellevue Downtown Station | Systems contractor requires 3-in. PVC conduit stub-ups for fiber backbone at Communications room – Bellevue Downtown Station not provided in civil A-887. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2021-03-31 | 14 | Expedite | N | N | Y | 6 | DSDC – LTK Engineering | 3 | 2021-04-20 | 20 | N | 6 | 1 | 2021-04-20 | 20 | Closed | 0 | 2 | 0 |  |  | N |  | 0 | 0 | 0 | 2 | 528 | P3 – Medium
E750-RFI-0126 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Missing dimension on E-465 | Request clarification of 00 72 00 General Conditions and E-465: dimension/notes appear inconsistent or omitted for the work at Traction power substation – Bellevue. | Superintendent | 2021-04-21 | 14 | Routine | N | N | N | 8 | DSDC – LTK Engineering | 2 | 2021-04-26 | 3 | Y | 0 | 2 | 2021-05-11 | 20 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1203 | P4 – Low
E750-RFI-0127 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Lane closure window request – OCS – Bel-Red/Overlake guideway | Contractor requests approval of an alternate traffic/staging plan at OCS – Bel-Red/Overlake guideway: crane pick over active roadway. Existing work restrictions limit production; requests ST/Puget Sound Energy concurrence. | Field Engineer | 2021-04-26 | 14 | Urgent | N | Y | Y | 6 | DSDC – LTK Engineering | 2 | 2021-04-29 | 3 | Y | 0 | 2 | 2021-05-06 | 10 | Closed | 7 | 4 | 0 |  |  | N |  | 0 | 0 | 0 | 4 | 461 | P3 – Medium
E750-RFI-0128 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Crane staging in right-of-way – Systems ductbank – Bel-Red | Contractor requests approval of an alternate traffic/staging plan at Systems ductbank – Bel-Red: extended night closure. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Scheduler | 2021-04-26 | 14 | Routine | Y | N | N | 1 | DSDC – LTK Engineering | 1 | 2021-05-05 | 9 | Y | 0 | 1 | 2021-05-05 | 9 | Closed | 0 | 0 | 0 | 863000 | 1610000 | Y | E750-CO-022 | 957100 | 900700 | 0 | 47.3 | 101 | P1 – Critical
E750-RFI-0129 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – platform edge slab and drilled shaft cap at Systems ductbank – Bel-Red | Interference between platform edge slab and drilled shaft cap at Systems ductbank – Bel-Red per S-210. Required clearance of 8 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Manager | 2021-04-30 | 14 | Urgent | Y | Y | N | 5 | DSDC – LTK Engineering | 1 | 2021-05-10 | 10 | Y | 0 | 1 | 2021-05-10 | 10 | Closed | 13 | 0 | 10 | 1898000 | 3542000 | Y | E750-CO-023 | 1351100 | 1032400 | 10 | 53.3 | 33 | P1 – Critical
E750-RFI-0130 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | City of Bellevue comment on clearing and grading permit – Traction power substation – Bellevue | City of Bellevue review comments on the clearing and grading permit require changes to the retaining wall footing at Traction power substation – Bellevue. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2021-05-17 | 14 | Urgent | Y | Y | N | 6 | DSDC – LTK Engineering | 4 | 2021-05-24 | 7 | Y | 0 | 1 | 2021-05-24 | 7 | Closed | 17 | 0 | 8 | 404000 | 755000 | N |  | 0 | 0 | 0 | 1.8 | 544 | P3 – Medium
E750-RFI-0131 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Grounding/bonding and stray-current detail – Traction power substation – Bellevue | Civil and systems drawings differ on grounding/bonding of bearing pad/embed plate for stray-current control at Traction power substation – Bellevue. Request governing detail and responsibility for installation. | Project Manager | 2021-05-28 | 14 | Routine | N | Y | N | 3 | DSDC – LTK Engineering | 2 | 2021-06-08 | 11 | Y | 0 | 1 | 2021-06-08 | 11 | Closed | 4 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 797 | P4 – Low
E750-RFI-0132 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – bearing pad/embed plate at Systems ductbank – Bel-Red | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-465 for egress width at Systems ductbank – Bel-Red. Request direction on compliant detail. | Design Manager | 2021-06-07 | 14 | Urgent | Y | N | Y | 6 | DSDC – LTK Engineering | 2 | 2021-06-21 | 12 | Y | 0 | 1 | 2021-06-21 | 12 | Closed | 0 | 0 | 0 | 174000 | 324000 | N |  | 0 | 0 | 0 | 0 | 1204 | P4 – Low
E750-RFI-0133 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – guideway girder diaphragm sequence at Train control – Overlake Village | Erection of the guideway girder diaphragm as drawn conflicts with adjacent work and access limits at Train control – Overlake Village. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Field Engineer | 2021-06-09 | 14 | Urgent | Y | Y | N | 5 | DSDC – LTK Engineering | 1 | 2021-06-14 | 5 | Y | 0 | 1 | 2021-06-14 | 5 | Closed | 4 | 0 | 1 | 1306000 | 2438000 | N |  | 0 | 0 | 0 | 0.2 | 798 | P4 – Low
E750-RFI-0134 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with abandoned utility vault at Bellevue tunnel systems | Potholing at Sta. 1142+25 located a abandoned utility vault in conflict with the proposed platform edge slab. Utility is not shown on S-388. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Superintendent | 2021-06-14 | 14 | Routine | Y | Y | N | 8 | DSDC – LTK Engineering | 1 | 2021-06-28 | 13 | Y | 0 | 1 | 2021-06-28 | 13 | Closed | 20 | 0 | 5 | 430000 | 803000 | N |  | 0 | 0 | 0 | 1.1 | 587 | P3 – Medium
E750-RFI-0135 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Missing dimension on C-543 | Request clarification of 01 33 00 Submittal Procedures and C-543: dimension/notes appear inconsistent or omitted for the work at Communications room – Bellevue Downtown Station. | Superintendent | 2021-06-14 | 14 | Expedite | N | N | N | 3 | DSDC – LTK Engineering | 2 | 2021-06-21 | 7 | Y | 0 | 1 | 2021-06-21 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1205 | P4 – Low
E750-RFI-0136 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Wetland/stream buffer protection – Traction power substation – Bellevue | Field conditions at Traction power substation – Bellevue require changes to temporary erosion and sediment control or stormwater facility per M-287. Request direction considering critical-areas conditions and permit requirements. | Project Engineer | 2021-06-21 | 14 | Routine | Y | N | N | 4 | DSDC – LTK Engineering | 3 | 2021-07-09 | 18 | N | 4 | 1 | 2021-07-09 | 18 | Closed | 0 | 0 | 1 | 105000 | 197000 | N |  | 0 | 0 | 0 | 0.2 | 799 | P4 – Low
E750-RFI-0137 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – galvanized steel handrail | Contractor requests approval to substitute galvanized steel handrail for stainless steel handrail on work at Communications room – Bellevue Downtown Station, citing procurement lead time. Product data attached. | Project Manager | 2021-06-22 | 14 | Expedite | N | N | N | 6 | DSDC – LTK Engineering | 4 | 2021-07-05 | 11 | Y | 0 | 1 | 2021-07-05 | 11 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1206 | P4 – Low
E750-RFI-0138 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Grounding/bonding and stray-current detail – Traction power substation – Bellevue | Civil and systems drawings differ on grounding/bonding of drilled shaft cap for stray-current control at Traction power substation – Bellevue. Request governing detail and responsibility for installation. | Project Engineer | 2021-07-06 | 14 | Urgent | Y | Y | N | 6 | DSDC – LTK Engineering | 3 | 2021-07-20 | 14 | Y | 0 | 1 | 2021-07-20 | 14 | Closed | 14 | 0 | 5 | 731000 | 1365000 | Y | E750-CO-027 | 1033130 | 412150 | 1.6 | 46.2 | 120 | P2 – High
E750-RFI-0139 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – pedestrian ramp and guideway girder diaphragm at OCS – Bel-Red/Overlake guideway | Interference between pedestrian ramp and guideway girder diaphragm at OCS – Bel-Red/Overlake guideway per S-784. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2021-07-06 | 14 | Routine | N | N | N | 2 | DSDC – LTK Engineering | 2 | 2021-07-15 | 9 | Y | 0 | 1 | 2021-07-15 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1207 | P4 – Low
E750-RFI-0140 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – OCS – Bel-Red/Overlake guideway | Systems contractor requires 3-in. PVC conduit stub-ups for OCS pole at OCS – Bel-Red/Overlake guideway not provided in civil C-121. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2021-07-15 | 14 | Routine | Y | Y | N | 5 | DSDC – LTK Engineering | 2 | 2021-08-02 | 18 | N | 4 | 1 | 2021-08-02 | 18 | Closed | 26 | 0 | 6 | 1295000 | 2417000 | Y | E750-CO-025 | 1236400 | 1236400 | 24 | 57.7 | 22 | P1 – Critical
E750-RFI-0141 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – retaining wall footing at Systems ductbank – Bel-Red | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-773 for fire alarm device layout at Systems ductbank – Bel-Red. Request direction on compliant detail. | Design Manager | 2021-07-19 | 14 | Routine | Y | Y | N | 8 | DSDC – LTK Engineering | 7 | 2021-08-10 | 22 | N | 8 | 1 | 2021-08-10 | 22 | Closed | 17 | 0 | 10 | 350000 | 653000 | N |  | 0 | 0 | 0 | 2.2 | 507 | P3 – Medium
E750-RFI-0142 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Train control – Overlake Village: soft lacustrine silt below design subgrade | During excavation at Train control – Overlake Village (Sta. 1954+36) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or A-812. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Superintendent | 2021-07-19 | 14 | Urgent | Y | Y | Y | 6 | DSDC – LTK Engineering | 2 | 2021-07-29 | 10 | Y | 0 | 1 | 2021-07-29 | 10 | Closed | 20 | 14 | 0 | 652000 | 1218000 | Y | E750-CO-024 | 809600 | 622600 | 11 | 63.6 | 14 | P1 – Critical
E750-RFI-0143 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – alternate epoxy-coated rebar supplier | Contractor requests approval to substitute alternate epoxy-coated rebar supplier for specified epoxy-coated rebar on work at OCS – Bel-Red/Overlake guideway, citing procurement lead time. Product data attached. | Project Manager | 2021-07-26 | 14 | Expedite | Y | N | N | 3 | DSDC – LTK Engineering | 1 | 2021-08-02 | 5 | Y | 0 | 1 | 2021-08-02 | 5 | Closed | 0 | 0 | 0 | 104000 | 194000 | N |  | 0 | 0 | 0 | 0 | 1208 | P4 – Low
E750-RFI-0144 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | SPC | Spec / Drawing Clarification | General | 01 25 00 Substitution Procedures | Missing dimension on S-628 | Request clarification of 01 33 00 Submittal Procedures and S-628: dimension/notes appear inconsistent or omitted for the work at OCS – I-90/Mercer Island to South Bellevue. | Field Engineer | 2021-07-26 | 14 | Routine | N | N | N | 5 | DSDC – LTK Engineering | 2 | 2021-07-30 | 4 | Y | 0 | 2 | 2021-08-09 | 13 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1209 | P4 – Low
E750-RFI-0145 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – alternate LED luminaire | Contractor requests approval to substitute alternate LED luminaire for specified LED luminaire on work at Systems ductbank – Bel-Red, citing procurement lead time. Product data attached. | Design Manager | 2021-07-30 | 14 | Routine | N | Y | N | 0 | DSDC – LTK Engineering | 3 | 2021-08-06 | 7 | Y | 0 | 1 | 2021-08-06 | 7 | Closed | 3 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 738 | P3 – Medium
E750-RFI-0146 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Fiber Backbone location conflict at Sta. 2044+92 | Proposed fiber backbone foundation location at Sta. 2044+92 conflicts with stair core wall; offset of 2 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Scheduler | 2021-08-06 | 14 | Routine | Y | N | N | 6 | DSDC – LTK Engineering | 2 | 2021-08-23 | 15 | N | 1 | 1 | 2021-08-23 | 15 | Closed | 0 | 0 | 0 | 841000 | 1571000 | N |  | 0 | 0 | 0 | 0 | 1210 | P4 – Low
E750-RFI-0147 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – Traction power substation – Bellevue | Civil and systems drawings differ on grounding/bonding of guideway girder diaphragm for stray-current control at Traction power substation – Bellevue. Request governing detail and responsibility for installation. | Field Engineer | 2021-08-16 | 14 | Routine | Y | N | Y | 1 | DSDC – LTK Engineering | 4 | 2021-09-20 | 34 | N | 20 | 1 | 2021-09-20 | 34 | Closed | 0 | 0 | 0 | 2291000 | 4277000 | Y | E750-CO-027 | 1611170 | 642750 | 2.4 | 46.9 | 107 | P1 – Critical
E750-RFI-0148 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | Puget Sound Energy comment on street improvement permit – Bellevue tunnel systems | Puget Sound Energy review comments on the street improvement permit require changes to the platform edge slab at Bellevue tunnel systems. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2021-08-17 | 14 | Urgent | N | N | Y | 4 | DSDC – LTK Engineering | 3 | 2021-08-30 | 11 | Y | 0 | 1 | 2021-08-30 | 11 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1211 | P4 – Low
E750-RFI-0149 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – Communications room – Bellevue Downtown Station | Civil and systems drawings differ on grounding/bonding of stair core wall for stray-current control at Communications room – Bellevue Downtown Station. Request governing detail and responsibility for installation. | Project Engineer | 2021-08-23 | 14 | Routine | N | N | Y | 6 | DSDC – LTK Engineering | 1 | 2021-09-10 | 18 | N | 4 | 1 | 2021-09-10 | 18 | Closed | 0 | 1 | 0 |  |  | N |  | 0 | 0 | 0 | 1 | 612 | P3 – Medium
E750-RFI-0150 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Embedded conduit stub-ups – Systems ductbank – Bel-Red | Systems contractor requires 5-in. PVC conduit stub-ups for SCADA cabinet at Systems ductbank – Bel-Red not provided in civil A-428. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2021-08-23 | 14 | Routine | N | N | Y | 6 | DSDC – LTK Engineering | 3 | 2021-09-13 | 19 | N | 5 | 1 | 2021-09-13 | 19 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1212 | P4 – Low
E750-RFI-0151 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Scada Cabinet location conflict at Sta. 1871+07 | Proposed SCADA cabinet foundation location at Sta. 1871+07 conflicts with drilled shaft cap; offset of 9 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2021-08-24 | 14 | Routine | Y | Y | Y | 3 | DSDC – LTK Engineering | 1 | 2021-09-06 | 12 | Y | 0 | 1 | 2021-09-06 | 12 | Closed | 19 | 8 | 0 | 672000 | 1255000 | N |  | 0 | 0 | 0 | 8 | 412 | P3 – Medium
E750-RFI-0152 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Embedded conduit stub-ups – Communications room – Bellevue Downtown Station | Systems contractor requires 3-in. PVC conduit stub-ups for SCADA cabinet at Communications room – Bellevue Downtown Station not provided in civil A-618. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Design Manager | 2021-08-26 | 14 | Routine | Y | N | N | 7 | DSDC – LTK Engineering | 2 | 2021-09-10 | 15 | N | 1 | 1 | 2021-09-10 | 15 | Closed | 0 | 0 | 0 | 525000 | 980000 | Y | E750-CO-026 | 952900 | 0 | 0 | 0 | 1213 | P4 – Low
E750-RFI-0153 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Track slab/expansion joint interface – Systems ductbank – Bel-Red | Track layout at Sta. 2372+04 (Systems ductbank – Bel-Red) differs from the track-structure interface drawing C-823. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Superintendent | 2021-09-15 | 14 | Urgent | N | N | Y | 4 | DSDC – LTK Engineering | 1 | 2021-09-22 | 7 | Y | 0 | 1 | 2021-09-22 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1214 | P4 – Low
E750-RFI-0154 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Rail Bonding location conflict at Sta. 1032+38 | Proposed rail bonding foundation location at Sta. 1032+38 conflicts with drilled shaft cap; offset of 5 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Field Engineer | 2021-09-20 | 14 | Routine | Y | N | Y | 5 | DSDC – LTK Engineering | 1 | 2021-09-28 | 8 | Y | 0 | 1 | 2021-09-28 | 8 | Closed | 0 | 0 | 0 | 152000 | 283000 | N |  | 0 | 0 | 0 | 0 | 1215 | P4 – Low
E750-RFI-0155 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Special trackwork layout – OCS – Bel-Red/Overlake guideway | Track layout at Sta. 2194+54 (OCS – Bel-Red/Overlake guideway) differs from the track-structure interface drawing A-529. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Engineer | 2021-09-29 | 14 | Expedite | N | N | N | 5 | DSDC – LTK Engineering | 1 | 2021-10-05 | 6 | Y | 0 | 1 | 2021-10-05 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1216 | P4 – Low
E750-RFI-0156 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – platform edge slab at OCS – I-90/Mercer Island to South Bellevue | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-146 for standpipe connection at OCS – I-90/Mercer Island to South Bellevue. Request direction on compliant detail. | Design Manager | 2021-09-30 | 14 | Urgent | N | N | Y | 8 | DSDC – LTK Engineering | 1 | 2021-10-06 | 6 | Y | 0 | 1 | 2021-10-06 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1217 | P4 – Low
E750-RFI-0157 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – OCS – I-90/Mercer Island to South Bellevue | Systems contractor requires 2-in. PVC conduit stub-ups for SCADA cabinet at OCS – I-90/Mercer Island to South Bellevue not provided in civil A-437. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Project Engineer | 2021-10-07 | 14 | Urgent | Y | N | Y | 2 | DSDC – LTK Engineering | 3 | 2021-10-15 | 8 | Y | 0 | 1 | 2021-10-15 | 8 | Closed | 0 | 0 | 0 | 357000 | 667000 | N |  | 0 | 0 | 0 | 0 | 1218 | P4 – Low
E750-RFI-0158 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Special trackwork layout – OCS – I-90/Mercer Island to South Bellevue | Track layout at Sta. 1663+60 (OCS – I-90/Mercer Island to South Bellevue) differs from the track-structure interface drawing A-604. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Scheduler | 2021-10-11 | 14 | Routine | Y | N | Y | 1 | DSDC – LTK Engineering | 1 | 2021-10-18 | 6 | Y | 0 | 1 | 2021-10-18 | 6 | Closed | 0 | 0 | 0 | 121000 | 226000 | Y | E750-CO-028 | 205300 | 205300 | 0 | 42.2 | 196 | P2 – High
E750-RFI-0159 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Signal Case location conflict at Sta. 2245+29 | Proposed signal case foundation location at Sta. 2245+29 conflicts with duct bank encasement; offset of 12 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Field Engineer | 2021-10-15 | 14 | Routine | N | N | N | 8 | DSDC – LTK Engineering | 2 | 2021-12-06 | 52 | N | 38 | 2 | 2021-12-27 | 71 | Closed | 0 | 0 | 12 |  |  | N |  | 0 | 0 | 0 | 2.7 | 495 | P3 – Medium
E750-RFI-0160 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Bellevue tunnel systems | Systems contractor requires 2-in. PVC conduit stub-ups for OCS pole at Bellevue tunnel systems not provided in civil S-679. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2021-10-22 | 14 | Routine | N | Y | Y | 6 | DSDC – LTK Engineering | 2 | 2021-12-14 | 53 | N | 39 | 1 | 2021-12-14 | 53 | Closed | 35 | 42 | 0 |  |  | N |  | 0 | 0 | 0 | 30 | 345 | P3 – Medium
E750-RFI-0161 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – retaining wall footing at Traction power substation – Bellevue | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and E-697 for emergency stair pressurization at Traction power substation – Bellevue. Request direction on compliant detail. | Design Manager | 2021-11-01 | 14 | Expedite | N | Y | N | 3 | DSDC – LTK Engineering | 1 | 2021-11-08 | 6 | Y | 0 | 1 | 2021-11-08 | 6 | Closed | 4 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 739 | P3 – Medium
E750-RFI-0162 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – Bellevue tunnel systems | Civil and systems drawings differ on grounding/bonding of pedestrian ramp for stray-current control at Bellevue tunnel systems. Request governing detail and responsibility for installation. | Superintendent | 2021-11-02 | 14 | Routine | N | Y | Y | 6 | DSDC – LTK Engineering | 4 | 2021-11-15 | 11 | Y | 0 | 1 | 2021-11-15 | 11 | Closed | 32 | 21 | 0 |  |  | N |  | 0 | 0 | 0 | 21 | 360 | P3 – Medium
E750-RFI-0163 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Tunnel Emergency Phone location conflict at Sta. 2091+52 | Proposed tunnel emergency phone foundation location at Sta. 2091+52 conflicts with duct bank encasement; offset of 4 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Field Engineer | 2021-11-22 | 14 | Urgent | N | Y | Y | 4 | DSDC – LTK Engineering | 2 | 2021-11-29 | 7 | Y | 0 | 1 | 2021-11-29 | 7 | Closed | 34 | 24 | 0 |  |  | N |  | 0 | 0 | 0 | 24 | 352 | P3 – Medium
E750-RFI-0164 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – bearing pad/embed plate at Bellevue tunnel systems | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-649 for smoke control damper at Bellevue tunnel systems. Request direction on compliant detail. | Project Engineer | 2021-11-24 | 14 | Routine | N | N | N | 0 | DSDC – LTK Engineering | 2 | 2021-12-07 | 13 | Y | 0 | 1 | 2021-12-07 | 13 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1219 | P4 – Low
E750-RFI-0165 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 12-in. ductile iron water main at Bellevue tunnel systems | Potholing at Sta. 1588+19 located a 12-in. ductile iron water main in conflict with the proposed drilled shaft cap. Utility is not shown on C-306. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Project Manager | 2021-12-06 | 14 | Routine | Y | Y | N | 3 | DSDC – LTK Engineering | 1 | 2021-12-20 | 12 | Y | 0 | 1 | 2021-12-20 | 12 | Closed | 13 | 0 | 9 | 1077000 | 2011000 | Y | E750-CO-029 | 1390310 | 1065130 | 4.5 | 51.3 | 43 | P1 – Critical
E750-RFI-0166 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Missing dimension on C-168 | Request clarification of 01 33 00 Submittal Procedures and C-168: dimension/notes appear inconsistent or omitted for the work at Communications room – Bellevue Downtown Station. | Superintendent | 2021-12-08 | 14 | Routine | N | N | N | 3 | DSDC – LTK Engineering | 1 | 2021-12-13 | 3 | Y | 0 | 1 | 2021-12-13 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1220 | P4 – Low
E750-RFI-0167 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Embedded conduit stub-ups – Traction power substation – Bellevue | Systems contractor requires 2-in. PVC conduit stub-ups for tunnel emergency phone at Traction power substation – Bellevue not provided in civil M-625. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Design Manager | 2021-12-23 | 14 | Expedite | N | N | Y | 5 | DSDC – LTK Engineering | 5 | 2022-01-21 | 29 | N | 15 | 1 | 2022-01-21 | 29 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1221 | P4 – Low
E750-RFI-0168 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with fiber communications duct bank at Bellevue tunnel systems | Potholing at Sta. 2142+57 located a fiber communications duct bank in conflict with the proposed guideway girder diaphragm. Utility is not shown on A-437. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Field Engineer | 2022-01-10 | 14 | Expedite | Y | Y | N | 3 | DSDC – LTK Engineering | 4 | 2022-01-24 | 12 | Y | 0 | 1 | 2022-01-24 | 12 | Closed | 6 | 0 | 3 | 4323000 | 8069000 | Y | E750-CO-029 | 3259690 | 2497270 | 10.5 | 54.2 | 28 | P1 – Critical
E750-RFI-0169 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Track slab/expansion joint interface – Traction power substation – Bellevue | Track layout at Sta. 1354+95 (Traction power substation – Bellevue) differs from the track-structure interface drawing A-323. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Manager | 2022-01-21 | 14 | Routine | N | Y | N | 6 | DSDC – LTK Engineering | 1 | 2022-01-28 | 7 | Y | 0 | 1 | 2022-01-28 | 7 | Closed | 4 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 679 | P3 – Medium
E750-RFI-0170 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – Traction power substation – Bellevue | Civil and systems drawings differ on grounding/bonding of platform edge slab for stray-current control at Traction power substation – Bellevue. Request governing detail and responsibility for installation. | Field Engineer | 2022-01-24 | 14 | Urgent | N | Y | Y | 6 | DSDC – LTK Engineering | 3 | 2022-02-22 | 29 | N | 15 | 1 | 2022-02-22 | 29 | Closed | 21 | 24 | 0 |  |  | N |  | 0 | 0 | 0 | 24 | 353 | P3 – Medium
E750-RFI-0171 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – drilled shaft cap sequence at Train control – Overlake Village | Erection of the drilled shaft cap as drawn conflicts with adjacent work and access limits at Train control – Overlake Village. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Scheduler | 2022-01-24 | 14 | Urgent | Y | N | Y | 7 | DSDC – LTK Engineering | 1 | 2022-02-01 | 8 | Y | 0 | 2 | 2022-02-17 | 24 | Closed | 0 | 0 | 0 | 309000 | 576000 | Y | E750-CO-030 | 695100 | 317800 | 0 | 43.7 | 165 | P2 – High
E750-RFI-0172 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Direct fixation fastener spacing at Sta. 1724+10 | Track layout at Sta. 1724+10 (Bellevue tunnel systems) differs from the track-structure interface drawing A-306. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Design Manager | 2022-01-28 | 14 | Routine | N | N | N | 2 | DSDC – LTK Engineering | 1 | 2022-02-11 | 14 | Y | 0 | 1 | 2022-02-11 | 14 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1222 | P4 – Low
E750-RFI-0173 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Direct fixation fastener spacing at Sta. 1535+96 | Track layout at Sta. 1535+96 (Communications room – Bellevue Downtown Station) differs from the track-structure interface drawing A-817. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Scheduler | 2022-02-04 | 14 | Routine | Y | Y | N | 0 | DSDC – LTK Engineering | 1 | 2022-02-21 | 15 | N | 1 | 1 | 2022-02-21 | 15 | Closed | 2 | 0 | 1 | 446000 | 833000 | N |  | 0 | 0 | 0 | 0.2 | 800 | P4 – Low
E750-RFI-0174 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Embedded conduit stub-ups – Train control – Overlake Village | Systems contractor requires 5-in. PVC conduit stub-ups for OCS pole at Train control – Overlake Village not provided in civil C-632. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2022-02-28 | 14 | Routine | Y | N | Y | 7 | DSDC – LTK Engineering | 3 | 2022-03-21 | 19 | N | 5 | 1 | 2022-03-21 | 19 | Closed | 0 | 1 | 0 | 2085000 | 3892000 | Y | E750-CO-031 | 2475400 | 1457300 | 0 | 49.9 | 61 | P1 – Critical
E750-RFI-0175 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – galvanized steel handrail | Contractor requests approval to substitute galvanized steel handrail for stainless steel handrail on work at Communications room – Bellevue Downtown Station, citing procurement lead time. Product data attached. | Project Manager | 2022-02-28 | 14 | Routine | Y | N | N | 4 | DSDC – LTK Engineering | 3 | 2022-03-14 | 13 | Y | 0 | 1 | 2022-03-14 | 13 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1223 | P4 – Low
E750-RFI-0176 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Grounding/bonding and stray-current detail – Systems ductbank – Bel-Red | Civil and systems drawings differ on grounding/bonding of retaining wall footing for stray-current control at Systems ductbank – Bel-Red. Request governing detail and responsibility for installation. | Field Engineer | 2022-03-14 | 14 | Routine | Y | Y | Y | 5 | DSDC – LTK Engineering | 2 | 2022-03-28 | 13 | Y | 0 | 1 | 2022-03-28 | 13 | Closed | 35 | 23 | 0 | 363000 | 677000 | Y | E750-CO-032 | 700900 | 593700 | 24 | 76.8 | 2 | P1 – Critical
E750-RFI-0177 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – galvanized steel handrail | Contractor requests approval to substitute galvanized steel handrail for stainless steel handrail on work at OCS – I-90/Mercer Island to South Bellevue, citing procurement lead time. Product data attached. | Design Manager | 2022-03-17 | 14 | Routine | N | N | N | 8 | DSDC – LTK Engineering | 2 | 2022-03-28 | 11 | Y | 0 | 1 | 2022-03-28 | 11 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1224 | P4 – Low
E750-RFI-0178 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Property owner access/restoration requirement – OCS – Bel-Red/Overlake guideway | Adjacent property owner has requested additional restoration and access provisions at OCS – Bel-Red/Overlake guideway beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Scheduler | 2022-04-07 | 14 | Urgent | N | N | Y | 6 | DSDC – LTK Engineering | 3 | 2022-04-14 | 7 | Y | 0 | 1 | 2022-04-14 | 7 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1225 | P4 – Low
E750-RFI-0179 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – platform edge slab at Systems ductbank – Bel-Red | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-891 for smoke control damper at Systems ductbank – Bel-Red. Request direction on compliant detail. | Scheduler | 2022-04-19 | 14 | Routine | Y | N | N | 0 | DSDC – LTK Engineering | 3 | 2022-04-29 | 10 | Y | 0 | 1 | 2022-04-29 | 10 | Closed | 0 | 0 | 0 | 1322000 | 2468000 | Y | E750-CO-033 | 2090600 | 1025800 | 0 | 47.7 | 97 | P1 – Critical
E750-RFI-0180 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Direct fixation fastener spacing at Sta. 1572+34 | Track layout at Sta. 1572+34 (OCS – I-90/Mercer Island to South Bellevue) differs from the track-structure interface drawing M-690. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Scheduler | 2022-04-25 | 14 | Urgent | N | Y | Y | 3 | DSDC – LTK Engineering | 1 | 2022-05-02 | 6 | Y | 0 | 1 | 2022-05-02 | 6 | Closed | 2 | 2 | 0 |  |  | N |  | 0 | 0 | 0 | 2 | 529 | P3 – Medium
E750-RFI-0181 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – OCS – Bel-Red/Overlake guideway | Civil and systems drawings differ on grounding/bonding of drilled shaft cap for stray-current control at OCS – Bel-Red/Overlake guideway. Request governing detail and responsibility for installation. | Field Engineer | 2022-05-12 | 14 | Routine | Y | N | Y | 5 | DSDC – LTK Engineering | 2 | 2022-05-19 | 7 | Y | 0 | 1 | 2022-05-19 | 7 | Closed | 0 | 0 | 0 | 86000 | 160000 | Y | E750-CO-034 | 144100 | 60100 | 0 | 37.9 | 277 | P2 – High
E750-RFI-0182 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Dimensional discrepancy – Systems ductbank – Bel-Red | S-355 shows a 30 ft-2 in. dimension for the guideway girder diaphragm; structural sheet S-495 shows a different value. Request clarification before fabrication/rebar release. | Scheduler | 2022-05-24 | 14 | Routine | N | N | N | 6 | DSDC – LTK Engineering | 1 | 2022-06-01 | 8 | Y | 0 | 1 | 2022-06-01 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1226 | P4 – Low
E750-RFI-0183 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | City of Bellevue comment on clearing and grading permit – OCS – Bel-Red/Overlake guideway | City of Bellevue review comments on the clearing and grading permit require changes to the bearing pad/embed plate at OCS – Bel-Red/Overlake guideway. Request direction on scope impacts and whether comments are within the contract requirements. | Project Manager | 2022-06-10 | 14 | Routine | N | N | Y | 4 | DSDC – LTK Engineering | 2 | 2022-06-27 | 15 | N | 1 | 1 | 2022-06-27 | 15 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1227 | P4 – Low
E750-RFI-0184 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Haul route revision – OCS – Bel-Red/Overlake guideway | Contractor requests approval of an alternate traffic/staging plan at OCS – Bel-Red/Overlake guideway: temporary lane shift. Existing work restrictions limit production; requests ST/City of Bellevue concurrence. | Design Manager | 2022-06-20 | 14 | Expedite | N | N | N | 8 | DSDC – LTK Engineering | 2 | 2022-07-01 | 11 | Y | 0 | 1 | 2022-07-01 | 11 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1228 | P4 – Low
E750-RFI-0185 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at Bellevue tunnel systems, citing procurement lead time. Product data attached. | Project Engineer | 2022-07-11 | 14 | Urgent | N | N | N | 1 | DSDC – LTK Engineering | 2 | 2022-08-03 | 23 | N | 9 | 1 | 2022-08-03 | 23 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1229 | P4 – Low
E750-RFI-0186 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – OCS – Bel-Red/Overlake guideway | E-244 shows a 10 ft-6 in. dimension for the column reinforcement; structural sheet S-535 shows a different value. Request clarification before fabrication/rebar release. | Design Manager | 2022-08-02 | 14 | Routine | Y | Y | N | 4 | DSDC – LTK Engineering | 2 | 2022-08-22 | 19 | N | 5 | 2 | 2022-08-29 | 26 | Closed | 18 | 0 | 8 | 1211000 | 2261000 | Y | E750-CO-036 | 1578200 | 1066100 | 8 | 52.3 | 39 | P1 – Critical
E750-RFI-0187 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Drawing/spec discrepancy – Traction power substation – Bellevue | Request clarification of 01 25 00 Substitution Procedures and M-784: dimension/notes appear inconsistent or omitted for the work at Traction power substation – Bellevue. | Design Manager | 2022-08-04 | 14 | Routine | Y | N | N | 1 | DSDC – LTK Engineering | 2 | 2022-08-12 | 8 | Y | 0 | 1 | 2022-08-12 | 8 | Closed | 0 | 0 | 0 | 91000 | 170000 | N |  | 0 | 0 | 0 | 0 | 1230 | P4 – Low
E750-RFI-0188 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – OCS – Bel-Red/Overlake guideway | Civil and systems drawings differ on grounding/bonding of duct bank encasement for stray-current control at OCS – Bel-Red/Overlake guideway. Request governing detail and responsibility for installation. | Project Engineer | 2022-08-08 | 14 | Routine | N | Y | Y | 3 | DSDC – LTK Engineering | 3 | 2022-08-18 | 10 | Y | 0 | 2 | 2022-08-31 | 23 | Closed | 17 | 11 | 0 |  |  | Y | E750-CO-035 | 238400 | 143800 | 8 | 54.6 | 26 | P1 – Critical
E750-RFI-0189 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Communications room – Bellevue Downtown Station | Systems contractor requires 4-in. PVC conduit stub-ups for signal case at Communications room – Bellevue Downtown Station not provided in civil C-796. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Scheduler | 2022-09-05 | 14 | Routine | Y | Y | Y | 0 | DSDC – LTK Engineering | 2 | 2022-09-12 | 5 | Y | 0 | 1 | 2022-09-12 | 5 | Closed | 18 | 9 | 0 | 146000 | 273000 | N |  | 0 | 0 | 0 | 9 | 404 | P3 – Medium
E750-RFI-0190 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Tunnel Emergency Phone location conflict at Sta. 1912+07 | Proposed tunnel emergency phone foundation location at Sta. 1912+07 conflicts with bearing pad/embed plate; offset of 9 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Field Engineer | 2022-09-12 | 14 | Routine | Y | Y | Y | 0 | DSDC – LTK Engineering | 3 | 2022-09-23 | 11 | Y | 0 | 1 | 2022-09-23 | 11 | Closed | 7 | 6 | 0 | 139000 | 259000 | N |  | 0 | 0 | 0 | 6 | 426 | P3 – Medium
E750-RFI-0191 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – pedestrian ramp at Systems ductbank – Bel-Red | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-156 for emergency stair pressurization at Systems ductbank – Bel-Red. Request direction on compliant detail. | Field Engineer | 2022-09-26 | 14 | Urgent | N | Y | N | 8 | DSDC – LTK Engineering | 3 | 2022-10-07 | 11 | Y | 0 | 1 | 2022-10-07 | 11 | Closed | 6 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 636 | P3 – Medium
E750-RFI-0192 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – recycled-content fly ash blend | Contractor requests approval to substitute recycled-content fly ash blend for Type IL cement mix on work at Bellevue tunnel systems, citing procurement lead time. Product data attached. | Field Engineer | 2022-10-14 | 14 | Routine | N | Y | N | 2 | DSDC – LTK Engineering | 1 | 2022-10-17 | 3 | Y | 0 | 2 | 2022-10-31 | 17 | Closed | 3 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 801 | P4 – Low
E750-RFI-0193 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Direct fixation fastener spacing at Sta. 955+79 | Track layout at Sta. 955+79 (Train control – Overlake Village) differs from the track-structure interface drawing A-762. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Design Manager | 2022-10-18 | 14 | Urgent | N | N | Y | 7 | DSDC – LTK Engineering | 3 | 2022-10-20 | 2 | Y | 0 | 1 | 2022-10-20 | 2 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1231 | P4 – Low
E750-RFI-0194 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – OCS – I-90/Mercer Island to South Bellevue | Systems contractor requires 3-in. PVC conduit stub-ups for OCS pole at OCS – I-90/Mercer Island to South Bellevue not provided in civil M-809. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2022-10-19 | 14 | Routine | Y | Y | N | 1 | DSDC – LTK Engineering | 2 | 2022-10-28 | 9 | Y | 0 | 1 | 2022-10-28 | 9 | Closed | 9 | 0 | 5 | 4049000 | 7558000 | N |  | 0 | 0 | 0 | 1.1 | 588 | P3 – Medium
E750-RFI-0195 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Systems ductbank – Bel-Red | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | WSDOT comment on critical areas permit – Systems ductbank – Bel-Red | WSDOT review comments on the critical areas permit require changes to the bearing pad/embed plate at Systems ductbank – Bel-Red. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2022-11-07 | 14 | Routine | N | Y | Y | 2 | DSDC – LTK Engineering | 3 | 2022-11-21 | 12 | Y | 0 | 1 | 2022-11-21 | 12 | Closed | 27 | 11 | 0 |  |  | N |  | 0 | 0 | 0 | 11 | 392 | P3 – Medium
E750-RFI-0196 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | WSDOT comment on critical areas permit – OCS – Bel-Red/Overlake guideway | WSDOT review comments on the critical areas permit require changes to the drilled shaft cap at OCS – Bel-Red/Overlake guideway. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2022-11-18 | 14 | Routine | Y | Y | N | 8 | DSDC – LTK Engineering | 2 | 2022-12-14 | 26 | N | 12 | 1 | 2022-12-14 | 26 | Closed | 3 | 0 | 1 | 262000 | 490000 | N |  | 0 | 0 | 0 | 0.2 | 802 | P4 – Low
E750-RFI-0197 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Tunnel Emergency Phone location conflict at Sta. 1861+96 | Proposed tunnel emergency phone foundation location at Sta. 1861+96 conflicts with guideway girder diaphragm; offset of 5 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Superintendent | 2023-01-16 | 14 | Urgent | Y | N | Y | 4 | DSDC – LTK Engineering | 2 | 2023-01-30 | 14 | Y | 0 | 1 | 2023-01-30 | 14 | Closed | 0 | 0 | 0 | 2159000 | 4031000 | Y | E750-CO-037 | 2431400 | 2010500 | 0 | 50 | 58 | P1 – Critical
E750-RFI-0198 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – platform edge slab at Bellevue tunnel systems | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-697 for emergency stair pressurization at Bellevue tunnel systems. Request direction on compliant detail. | Project Manager | 2023-01-25 | 14 | Expedite | N | N | Y | 7 | DSDC – LTK Engineering | 1 | 2023-02-06 | 10 | Y | 0 | 1 | 2023-02-06 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1232 | P4 – Low
E750-RFI-0199 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Special trackwork layout – OCS – Bel-Red/Overlake guideway | Track layout at Sta. 1671+97 (OCS – Bel-Red/Overlake guideway) differs from the track-structure interface drawing C-813. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Scheduler | 2023-01-27 | 14 | Routine | N | N | N | 1 | DSDC – LTK Engineering | 1 | 2023-02-03 | 7 | Y | 0 | 1 | 2023-02-03 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1233 | P4 – Low
E750-RFI-0200 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 30-in. storm drain at Traction power substation – Bellevue | Potholing at Sta. 1837+71 located a 30-in. storm drain in conflict with the proposed column reinforcement. Utility is not shown on E-446. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Bellevue. | Design Manager | 2023-02-13 | 14 | Routine | Y | Y | Y | 1 | DSDC – LTK Engineering | 2 | 2023-02-21 | 8 | Y | 0 | 1 | 2023-02-21 | 8 | Closed | 11 | 6 | 0 | 16485000 | 30772000 | N |  | 0 | 0 | 0 | 6 | 427 | P3 – Medium
E750-RFI-0201 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – duct bank encasement at OCS – Bel-Red/Overlake guideway | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-588 for standpipe connection at OCS – Bel-Red/Overlake guideway. Request direction on compliant detail. | Design Manager | 2023-02-20 | 14 | Urgent | Y | N | Y | 7 | DSDC – LTK Engineering | 3 | 2023-03-03 | 11 | Y | 0 | 1 | 2023-03-03 | 11 | Closed | 0 | 0 | 0 | 102000 | 190000 | N |  | 0 | 0 | 0 | 0 | 1234 | P4 – Low
E750-RFI-0202 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Track slab/expansion joint interface – Train control – Overlake Village | Track layout at Sta. 1921+78 (Train control – Overlake Village) differs from the track-structure interface drawing E-442. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Scheduler | 2023-02-23 | 14 | Routine | N | N | Y | 2 | DSDC – LTK Engineering | 1 | 2023-03-06 | 10 | Y | 0 | 1 | 2023-03-06 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1235 | P4 – Low
E750-RFI-0203 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – column reinforcement at OCS – I-90/Mercer Island to South Bellevue | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-561 for smoke control damper at OCS – I-90/Mercer Island to South Bellevue. Request direction on compliant detail. | Project Engineer | 2023-03-06 | 14 | Routine | N | Y | N | 5 | DSDC – LTK Engineering | 2 | 2023-03-15 | 9 | Y | 0 | 1 | 2023-03-15 | 9 | Closed | 1 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 803 | P4 – Low
E750-RFI-0204 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Traction power substation – Bellevue: soft lacustrine silt below design subgrade | During excavation at Traction power substation – Bellevue (Sta. 1550+90) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or A-639. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Scheduler | 2023-03-09 | 14 | Urgent | Y | N | N | 2 | DSDC – LTK Engineering | 2 | 2023-03-20 | 9 | Y | 0 | 1 | 2023-03-20 | 9 | Closed | 0 | 0 | 0 | 1927000 | 3597000 | Y | E750-CO-038 | 2809000 | 1273600 | 0 | 48.4 | 87 | P1 – Critical
E750-RFI-0205 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with abandoned utility vault at Train control – Overlake Village | Potholing at Sta. 1500+03 located a abandoned utility vault in conflict with the proposed drilled shaft cap. Utility is not shown on C-658. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Superintendent | 2023-03-20 | 14 | Urgent | Y | N | Y | 2 | DSDC – LTK Engineering | 2 | 2023-03-28 | 8 | Y | 0 | 1 | 2023-03-28 | 8 | Closed | 0 | 0 | 0 | 6461000 | 12061000 | Y | E750-CO-039 | 3873100 | 1680900 | 0 | 49.4 | 71 | P1 – Critical
E750-RFI-0206 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – Bel-Red/Overlake guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Property owner access/restoration requirement – OCS – Bel-Red/Overlake guideway | Adjacent property owner has requested additional restoration and access provisions at OCS – Bel-Red/Overlake guideway beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Design Manager | 2023-05-03 | 14 | Routine | Y | Y | N | 4 | DSDC – LTK Engineering | 3 | 2023-05-22 | 18 | N | 4 | 1 | 2023-05-22 | 18 | Closed | 10 | 0 | 5 | 211000 | 395000 | N |  | 0 | 0 | 0 | 1.1 | 589 | P3 – Medium
E750-RFI-0207 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | WSDOT comment on building permit – Train control – Overlake Village | WSDOT review comments on the building permit require changes to the pedestrian ramp at Train control – Overlake Village. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2023-05-12 | 14 | Expedite | N | N | Y | 6 | DSDC – LTK Engineering | 3 | 2023-05-29 | 15 | N | 1 | 1 | 2023-05-29 | 15 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1236 | P4 – Low
E750-RFI-0208 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – alternate epoxy-coated rebar supplier | Contractor requests approval to substitute alternate epoxy-coated rebar supplier for specified epoxy-coated rebar on work at OCS – I-90/Mercer Island to South Bellevue, citing procurement lead time. Product data attached. | Design Manager | 2023-05-15 | 14 | Routine | N | Y | N | 2 | DSDC – LTK Engineering | 1 | 2023-05-29 | 13 | Y | 0 | 2 | 2023-06-15 | 31 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 804 | P4 – Low
E750-RFI-0209 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Communications room – Bellevue Downtown Station | C-608 shows a 37 ft-6 in. dimension for the stair core wall; structural sheet S-688 shows a different value. Request clarification before fabrication/rebar release. | Project Engineer | 2023-05-29 | 14 | Urgent | Y | N | N | 0 | DSDC – LTK Engineering | 2 | 2023-06-08 | 10 | Y | 0 | 2 | 2023-06-14 | 16 | Closed | 0 | 0 | 0 | 2153000 | 4019000 | Y | E750-CO-040 | 3230100 | 1839900 | 0 | 49.7 | 66 | P1 – Critical
E750-RFI-0210 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Ocs Pole location conflict at Sta. 2117+09 | Proposed OCS pole foundation location at Sta. 2117+09 conflicts with pedestrian ramp; offset of 5 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Superintendent | 2023-06-06 | 14 | Expedite | N | Y | N | 0 | DSDC – LTK Engineering | 2 | 2023-06-13 | 7 | Y | 0 | 1 | 2023-06-13 | 7 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 805 | P4 – Low
E750-RFI-0211 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – station canopy support at Communications room – Bellevue Downtown Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-866 for emergency stair pressurization at Communications room – Bellevue Downtown Station. Request direction on compliant detail. | Scheduler | 2023-06-23 | 14 | Routine | Y | Y | N | 8 | DSDC – LTK Engineering | 2 | 2023-07-10 | 16 | N | 2 | 1 | 2023-07-10 | 16 | Closed | 26 | 0 | 10 | 670000 | 1251000 | N |  | 0 | 0 | 0 | 2.2 | 508 | P3 – Medium
E750-RFI-0212 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Direct fixation fastener spacing at Sta. 1852+56 | Track layout at Sta. 1852+56 (Communications room – Bellevue Downtown Station) differs from the track-structure interface drawing S-889. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Engineer | 2023-06-26 | 14 | Routine | N | N | N | 5 | DSDC – LTK Engineering | 2 | 2023-07-03 | 6 | Y | 0 | 1 | 2023-07-03 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1237 | P4 – Low
E750-RFI-0213 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 8-in. high-pressure gas main at OCS – I-90/Mercer Island to South Bellevue | Potholing at Sta. 2042+49 located a 8-in. high-pressure gas main in conflict with the proposed drilled shaft cap. Utility is not shown on E-583. Contractor requests direction on relocation, redesign, or protection in place, and coordination with Puget Sound Energy. | Field Engineer | 2023-08-17 | 14 | Routine | N | Y | N | 1 | DSDC – LTK Engineering | 2 | 2023-08-31 | 14 | Y | 0 | 1 | 2023-08-31 | 14 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 806 | P4 – Low
E750-RFI-0214 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | OCS – I-90/Mercer Island to South Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – OCS – I-90/Mercer Island to South Bellevue | Civil and systems drawings differ on grounding/bonding of bearing pad/embed plate for stray-current control at OCS – I-90/Mercer Island to South Bellevue. Request governing detail and responsibility for installation. | Scheduler | 2023-08-23 | 14 | Routine | N | N | N | 2 | DSDC – LTK Engineering | 3 | 2023-09-11 | 17 | N | 3 | 1 | 2023-09-11 | 17 | Closed | 0 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 807 | P4 – Low
E750-RFI-0215 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Traction Power Feeder location conflict at Sta. 2390+77 | Proposed traction power feeder foundation location at Sta. 2390+77 conflicts with retaining wall footing; offset of 10 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2023-08-25 | 14 | Urgent | N | Y | Y | 6 | DSDC – LTK Engineering | 4 | 2023-09-18 | 23 | N | 9 | 1 | 2023-09-18 | 23 | Closed | 7 | 5 | 0 |  |  | N |  | 0 | 0 | 0 | 5 | 444 | P3 – Medium
E750-RFI-0216 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Track slab/expansion joint interface – Train control – Overlake Village | Track layout at Sta. 1905+88 (Train control – Overlake Village) differs from the track-structure interface drawing M-127. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2023-08-29 | 14 | Routine | N | N | Y | 3 | DSDC – LTK Engineering | 3 | 2023-09-05 | 7 | Y | 0 | 1 | 2023-09-05 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1238 | P4 – Low
E750-RFI-0217 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Communications room – Bellevue Downtown Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – stair core wall sequence at Communications room – Bellevue Downtown Station | Erection of the stair core wall as drawn conflicts with adjacent work and access limits at Communications room – Bellevue Downtown Station. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Design Manager | 2023-10-11 | 14 | Expedite | Y | N | N | 7 | DSDC – LTK Engineering | 2 | 2023-10-23 | 11 | Y | 0 | 1 | 2023-10-23 | 11 | Closed | 0 | 0 | 0 | 546000 | 1019000 | Y | E750-CO-041 | 782100 | 782100 | 0 | 46.8 | 110 | P2 – High
E750-RFI-0218 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Train control – Overlake Village | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – platform edge slab at Train control – Overlake Village | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-774 for emergency stair pressurization at Train control – Overlake Village. Request direction on compliant detail. | Project Manager | 2023-11-01 | 14 | Routine | Y | N | N | 8 | DSDC – LTK Engineering | 3 | 2023-11-13 | 12 | Y | 0 | 1 | 2023-11-13 | 12 | Closed | 0 | 0 | 0 | 1541000 | 2877000 | Y | E750-CO-042 | 1475300 | 1286800 | 0 | 48.5 | 85 | P1 – Critical
E750-RFI-0219 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Bellevue tunnel systems | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Track slab/expansion joint interface – Bellevue tunnel systems | Track layout at Sta. 1671+80 (Bellevue tunnel systems) differs from the track-structure interface drawing A-170. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2024-02-14 | 14 | Urgent | N | N | N | 7 | DSDC – LTK Engineering | 3 | 2024-03-01 | 16 | N | 2 | 1 | 2024-03-01 | 16 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1239 | P4 – Low
E750-RFI-0220 | E750 | East Link Extension | E750 Systems contractor (not named in sources) | Traction power substation – Bellevue | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Embedded conduit stub-ups – Traction power substation – Bellevue | Systems contractor requires 3-in. PVC conduit stub-ups for signal case at Traction power substation – Bellevue not provided in civil E-824. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Design Manager | 2024-03-26 | 14 | Routine | N | N | Y | 6 | DSDC – LTK Engineering | 2 | 2024-04-08 | 12 | Y | 0 | 1 | 2024-04-08 | 12 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1240 | P4 – Low
DRLE-RFI-0001 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Ocs Pole location conflict at Sta. 2391+82 | Proposed OCS pole foundation location at Sta. 2391+82 conflicts with bearing pad/embed plate; offset of 3 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Superintendent | 2019-10-07 | 7 | Urgent | Y | N | N | 8 | Design-Build EOR / ST Design Review | 3 | 2019-10-25 | 18 | N | 11 | 1 | 2019-10-25 | 18 | Closed | 0 | 0 | 0 | 148000 | 277000 | N |  | 0 | 0 | 0 | 0 | 1241 | P4 – Low
DRLE-RFI-0002 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – column reinforcement and bearing pad/embed plate at Downtown Redmond Station | Interference between column reinforcement and bearing pad/embed plate at Downtown Redmond Station per S-426. Required clearance of 3 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Scheduler | 2019-12-03 | 7 | Expedite | N | N | N | 7 | Design-Build EOR / ST Design Review | 1 | 2019-12-12 | 9 | N | 2 | 2 | 2019-12-30 | 25 | Closed | 0 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 808 | P4 – Low
DRLE-RFI-0003 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with fiber communications duct bank at Marymoor Village parking garage | Potholing at Sta. 1224+65 located a fiber communications duct bank in conflict with the proposed duct bank encasement. Utility is not shown on M-461. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Project Engineer | 2019-12-30 | 7 | Routine | Y | N | N | 6 | Design-Build EOR / ST Design Review | 1 | 2020-01-03 | 4 | Y | 0 | 1 | 2020-01-03 | 4 | Closed | 0 | 0 | 0 | 1218000 | 2273000 | Y | DRLE-CO-001 | 762000 | 0 | 0 | 0 | 1242 | P4 – Low
DRLE-RFI-0004 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Marymoor Village Station: abandoned timber piles | During excavation at Marymoor Village Station (Sta. 1125+21) the contractor encountered abandoned timber piles, not shown on the GBR or C-827. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Superintendent | 2020-01-08 | 7 | Routine | N | N | N | 4 | Design-Build EOR / ST Design Review | 3 | 2020-01-13 | 4 | Y | 0 | 2 | 2020-01-27 | 18 | Closed | 0 | 0 | 0 |  |  | Y | DRLE-CO-002 | 52600 | 26000 | 0 | 35 | 311 | P2 – High
DRLE-RFI-0005 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – alternate LED luminaire | Contractor requests approval to substitute alternate LED luminaire for specified LED luminaire on work at Redmond Way (SR 202) crossing, citing procurement lead time. Product data attached. | Field Engineer | 2020-01-22 | 7 | Routine | N | N | N | 8 | Design-Build EOR / ST Design Review | 1 | 2020-01-28 | 6 | Y | 0 | 1 | 2020-01-28 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1243 | P4 – Low
DRLE-RFI-0006 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with abandoned utility vault at Leary Way crossing | Potholing at Sta. 1598+10 located a abandoned utility vault in conflict with the proposed drilled shaft cap. Utility is not shown on E-278. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Project Engineer | 2020-02-06 | 7 | Expedite | N | N | N | 8 | Design-Build EOR / ST Design Review | 3 | 2020-02-14 | 8 | N | 1 | 1 | 2020-02-14 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1244 | P4 – Low
DRLE-RFI-0007 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | City of Redmond comment on right-of-way use permit – SE Redmond aerial guideway | City of Redmond review comments on the right-of-way use permit require changes to the stair core wall at SE Redmond aerial guideway. Request direction on scope impacts and whether comments are within the contract requirements. | Project Manager | 2020-02-25 | 7 | Routine | N | Y | N | 1 | City of Redmond / ST Third-Party Mgmt | 4 | 2020-03-11 | 15 | N | 8 | 1 | 2020-03-11 | 15 | Closed | 8 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 637 | P3 – Medium
DRLE-RFI-0008 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Marymoor Village parking garage: buried concrete debris and an old foundation | During excavation at Marymoor Village parking garage (Sta. 2178+96) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or E-298. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Project Engineer | 2020-02-28 | 7 | Routine | N | Y | N | 2 | Design-Build EOR / ST Design Review | 1 | 2020-03-09 | 8 | N | 1 | 1 | 2020-03-09 | 8 | Closed | 5 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 809 | P4 – Low
DRLE-RFI-0009 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 30-in. storm drain at Leary Way crossing | Potholing at Sta. 1469+16 located a 30-in. storm drain in conflict with the proposed duct bank encasement. Utility is not shown on E-821. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Superintendent | 2020-03-16 | 7 | Urgent | Y | Y | N | 6 | Design-Build EOR / ST Design Review | 2 | 2020-03-23 | 6 | Y | 0 | 1 | 2020-03-23 | 6 | Closed | 8 | 0 | 2 | 36000 | 67000 | Y | DRLE-CO-005 | 58530 | 58530 | 0.3 | 38.4 | 267 | P2 – High
DRLE-RFI-0010 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 24-in. sanitary sewer at Downtown Redmond Station | Potholing at Sta. 1409+81 located a 24-in. sanitary sewer in conflict with the proposed column reinforcement. Utility is not shown on E-575. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Scheduler | 2020-03-18 | 7 | Routine | Y | Y | N | 3 | Design-Build EOR / ST Design Review | 2 | 2020-03-24 | 6 | Y | 0 | 1 | 2020-03-24 | 6 | Closed | 5 | 0 | 3 | 95000 | 177000 | Y | DRLE-CO-003 | 150100 | 96200 | 3 | 41.2 | 216 | P2 – High
DRLE-RFI-0011 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | Property owner access/restoration requirement – Leary Way crossing | Adjacent property owner has requested additional restoration and access provisions at Leary Way crossing beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Project Manager | 2020-03-31 | 7 | Expedite | Y | Y | N | 5 | City of Redmond / ST Third-Party Mgmt | 2 | 2020-04-06 | 5 | Y | 0 | 1 | 2020-04-06 | 5 | Closed | 9 | 0 | 4 | 518000 | 968000 | Y | DRLE-CO-004 | 550100 | 393300 | 5 | 47 | 105 | P1 – Critical
DRLE-RFI-0012 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 30-in. storm drain at Downtown Redmond Station | Potholing at Sta. 2220+84 located a 30-in. storm drain in conflict with the proposed drilled shaft cap. Utility is not shown on S-149. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Project Engineer | 2020-04-21 | 7 | Expedite | Y | Y | Y | 1 | Design-Build EOR / ST Design Review | 2 | 2020-04-27 | 5 | Y | 0 | 1 | 2020-04-27 | 5 | Closed | 10 | 4 | 0 | 2107000 | 3933000 | Y | DRLE-CO-005 | 2231970 | 2231970 | 12.7 | 58.2 | 21 | P1 – Critical
DRLE-RFI-0013 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 8-in. high-pressure gas main at Marymoor Village parking garage | Potholing at Sta. 2140+95 located a 8-in. high-pressure gas main in conflict with the proposed retaining wall footing. Utility is not shown on M-344. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Field Engineer | 2020-04-28 | 7 | Routine | Y | Y | N | 7 | Design-Build EOR / ST Design Review | 2 | 2020-04-30 | 2 | Y | 0 | 1 | 2020-04-30 | 2 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1245 | P4 – Low
DRLE-RFI-0014 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Downtown Redmond Station | C-891 shows a 56 ft-10 in. dimension for the retaining wall footing; structural sheet S-580 shows a different value. Request clarification before fabrication/rebar release. | Field Engineer | 2020-05-05 | 7 | Urgent | Y | N | N | 2 | Design-Build EOR / ST Design Review | 1 | 2020-05-11 | 5 | Y | 0 | 2 | 2020-05-18 | 12 | Closed | 0 | 0 | 0 | 15000 | 28000 | Y | DRLE-CO-006 | 10300 | 5400 | 0 | 29.6 | 346 | P3 – Medium
DRLE-RFI-0015 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Lane closure window request – Marymoor Village parking garage | Contractor requests approval of an alternate traffic/staging plan at Marymoor Village parking garage: crane pick over active roadway. Existing work restrictions limit production; requests ST/King County Parks concurrence. | Field Engineer | 2020-05-13 | 7 | Expedite | N | N | N | 3 | Design-Build EOR / ST Design Review | 3 | 2020-05-18 | 5 | Y | 0 | 1 | 2020-05-18 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1246 | P4 – Low
DRLE-RFI-0016 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | King County Parks comment on right-of-way use permit – Marymoor Village parking garage | King County Parks review comments on the right-of-way use permit require changes to the pedestrian ramp at Marymoor Village parking garage. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2020-05-15 | 7 | Expedite | N | Y | N | 5 | King County Parks / ST Third-Party Mgmt | 2 | 2020-06-01 | 15 | N | 8 | 2 | 2020-06-08 | 22 | Closed | 3 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 590 | P3 – Medium
DRLE-RFI-0017 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Night work and noise variance – Redmond Way (SR 202) crossing | Contractor requests approval of an alternate traffic/staging plan at Redmond Way (SR 202) crossing: crane pick over active roadway. Existing work restrictions limit production; requests ST/King County Parks concurrence. | Field Engineer | 2020-06-08 | 7 | Routine | N | N | N | 0 | Design-Build EOR / ST Design Review | 1 | 2020-06-12 | 4 | Y | 0 | 1 | 2020-06-12 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1247 | P4 – Low
DRLE-RFI-0018 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Crane staging in right-of-way – Leary Way crossing | Contractor requests approval of an alternate traffic/staging plan at Leary Way crossing: extended night closure. Existing work restrictions limit production; requests ST/City of Redmond concurrence. | Project Engineer | 2020-06-15 | 7 | Routine | N | N | Y | 5 | Design-Build EOR / ST Design Review | 1 | 2020-06-17 | 2 | Y | 0 | 1 | 2020-06-17 | 2 | Closed | 0 | 2 | 0 |  |  | N |  | 0 | 0 | 0 | 2 | 530 | P3 – Medium
DRLE-RFI-0019 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | SPC | Spec / Drawing Clarification | General | 01 25 00 Substitution Procedures | Drawing/spec discrepancy – Marymoor Park interface | Request clarification of 01 33 00 Submittal Procedures and C-768: dimension/notes appear inconsistent or omitted for the work at Marymoor Park interface. | Scheduler | 2020-07-14 | 7 | Routine | N | N | N | 0 | Design-Build EOR / ST Design Review | 2 | 2020-07-20 | 4 | Y | 0 | 1 | 2020-07-20 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1248 | P4 – Low
DRLE-RFI-0020 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | TESC modification – SE Redmond aerial guideway | Field conditions at SE Redmond aerial guideway require changes to temporary erosion and sediment control or stormwater facility per E-838. Request direction considering critical-areas conditions and permit requirements. | Field Engineer | 2020-07-22 | 7 | Urgent | Y | N | N | 8 | Design-Build EOR / ST Design Review | 4 | 2020-07-27 | 4 | Y | 0 | 1 | 2020-07-27 | 4 | Closed | 0 | 0 | 0 | 98000 | 183000 | N |  | 0 | 0 | 0 | 0 | 1249 | P4 – Low
DRLE-RFI-0021 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | City of Redmond comment on clearing and grading permit – SE Redmond aerial guideway | City of Redmond review comments on the clearing and grading permit require changes to the duct bank encasement at SE Redmond aerial guideway. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2020-07-27 | 7 | Expedite | N | N | Y | 1 | City of Redmond / ST Third-Party Mgmt | 1 | 2020-08-05 | 9 | N | 2 | 1 | 2020-08-05 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1250 | P4 – Low
DRLE-RFI-0022 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Tunnel Emergency Phone location conflict at Sta. 1322+71 | Proposed tunnel emergency phone foundation location at Sta. 1322+71 conflicts with drilled shaft cap; offset of 9 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Scheduler | 2020-07-27 | 7 | Routine | N | N | Y | 8 | Design-Build EOR / ST Design Review | 2 | 2020-08-05 | 9 | N | 2 | 1 | 2020-08-05 | 9 | Closed | 0 | 1 | 0 |  |  | N |  | 0 | 0 | 0 | 1 | 613 | P3 – Medium
DRLE-RFI-0023 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Night work and noise variance – Marymoor Village Station | Contractor requests approval of an alternate traffic/staging plan at Marymoor Village Station: crane pick over active roadway. Existing work restrictions limit production; requests ST/City of Redmond concurrence. | Superintendent | 2020-08-04 | 7 | Routine | Y | N | N | 7 | Design-Build EOR / ST Design Review | 2 | 2020-08-10 | 5 | Y | 0 | 1 | 2020-08-10 | 5 | Closed | 0 | 0 | 0 | 205000 | 383000 | N |  | 0 | 0 | 0 | 0 | 1251 | P4 – Low
DRLE-RFI-0024 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – Bear Creek crossing | Systems contractor requires 4-in. PVC conduit stub-ups for tunnel emergency phone at Bear Creek crossing not provided in civil E-454. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2020-08-10 | 7 | Routine | Y | Y | Y | 3 | Design-Build EOR / ST Design Review | 1 | 2020-08-17 | 6 | Y | 0 | 1 | 2020-08-17 | 6 | Closed | 13 | 5 | 0 | 416000 | 776000 | Y | DRLE-CO-008 | 284700 | 0 | 0 | 5 | 445 | P3 – Medium
DRLE-RFI-0025 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – duct bank encasement sequence at Bear Creek crossing | Erection of the duct bank encasement as drawn conflicts with adjacent work and access limits at Bear Creek crossing. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Superintendent | 2020-08-12 | 7 | Urgent | Y | Y | N | 8 | Design-Build EOR / ST Design Review | 1 | 2020-08-17 | 3 | Y | 0 | 1 | 2020-08-17 | 3 | Closed | 3 | 0 | 2 | 74000 | 138000 | Y | DRLE-CO-007 | 186400 | 148800 | 2 | 42.2 | 197 | P2 – High
DRLE-RFI-0026 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | Stormwater facility revision – Marymoor Village parking garage | Field conditions at Marymoor Village parking garage require changes to temporary erosion and sediment control or stormwater facility per M-515. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2020-08-13 | 7 | Expedite | N | N | N | 6 | Design-Build EOR / ST Design Review | 3 | 2020-09-09 | 27 | N | 20 | 1 | 2020-09-09 | 27 | Closed | 0 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 638 | P3 – Medium
DRLE-RFI-0027 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | Stormwater facility revision – Bear Creek crossing | Field conditions at Bear Creek crossing require changes to temporary erosion and sediment control or stormwater facility per S-164. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2020-08-24 | 7 | Routine | Y | Y | N | 2 | Design-Build EOR / ST Design Review | 1 | 2020-09-03 | 10 | N | 3 | 1 | 2020-09-03 | 10 | Closed | 3 | 0 | 2 | 800000 | 1492000 | N |  | 0 | 0 | 0 | 0.4 | 740 | P3 – Medium
DRLE-RFI-0028 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with abandoned utility vault at Marymoor Village Station | Potholing at Sta. 1134+83 located a abandoned utility vault in conflict with the proposed platform edge slab. Utility is not shown on C-533. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Design Manager | 2020-08-25 | 7 | Routine | N | N | N | 0 | Design-Build EOR / ST Design Review | 3 | 2020-09-09 | 15 | N | 8 | 1 | 2020-09-09 | 15 | Closed | 0 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 680 | P3 – Medium
DRLE-RFI-0029 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Embedded conduit stub-ups – Redmond Way (SR 202) crossing | Systems contractor requires 3-in. PVC conduit stub-ups for fiber backbone at Redmond Way (SR 202) crossing not provided in civil M-792. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Design Manager | 2020-09-07 | 7 | Expedite | N | N | N | 3 | Design-Build EOR / ST Design Review | 2 | 2020-09-14 | 6 | Y | 0 | 2 | 2020-09-22 | 15 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1252 | P4 – Low
DRLE-RFI-0030 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – platform edge slab at Marymoor Park interface | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-457 for fire alarm device layout at Marymoor Park interface. Request direction on compliant detail. | Design Manager | 2020-09-10 | 7 | Routine | N | Y | N | 2 | Design-Build EOR / ST Design Review | 2 | 2020-09-18 | 8 | N | 1 | 1 | 2020-09-18 | 8 | Closed | 12 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 591 | P3 – Medium
DRLE-RFI-0031 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on building permit – Marymoor Park interface | WSDOT review comments on the building permit require changes to the stair core wall at Marymoor Park interface. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2020-09-11 | 7 | Expedite | N | N | Y | 5 | City of Redmond / ST Third-Party Mgmt | 1 | 2020-09-17 | 6 | Y | 0 | 1 | 2020-09-17 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1253 | P4 – Low
DRLE-RFI-0032 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – guideway girder diaphragm at Marymoor Park interface | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-675 for egress width at Marymoor Park interface. Request direction on compliant detail. | Project Engineer | 2020-09-16 | 7 | Routine | Y | Y | N | 5 | Design-Build EOR / ST Design Review | 3 | 2020-09-28 | 12 | N | 5 | 1 | 2020-09-28 | 12 | Closed | 5 | 0 | 1 | 131000 | 244000 | N |  | 0 | 0 | 0 | 0.2 | 810 | P4 – Low
DRLE-RFI-0033 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Marymoor Park interface | E-254 shows a 51 ft-7 in. dimension for the column reinforcement; structural sheet S-799 shows a different value. Request clarification before fabrication/rebar release. | Scheduler | 2020-09-18 | 7 | Routine | Y | Y | N | 7 | Design-Build EOR / ST Design Review | 1 | 2020-09-25 | 7 | Y | 0 | 1 | 2020-09-25 | 7 | Closed | 1 | 0 | 1 | 242000 | 452000 | Y | DRLE-CO-009 | 396500 | 211800 | 0 | 42.5 | 189 | P2 – High
DRLE-RFI-0034 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with abandoned utility vault at SE Redmond aerial guideway | Potholing at Sta. 2379+27 located a abandoned utility vault in conflict with the proposed pedestrian ramp. Utility is not shown on C-602. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Manager | 2020-10-08 | 7 | Routine | Y | N | N | 2 | Design-Build EOR / ST Design Review | 2 | 2020-10-15 | 7 | Y | 0 | 1 | 2020-10-15 | 7 | Closed | 0 | 0 | 0 | 60000 | 112000 | Y | DRLE-CO-010 | 62400 | 40500 | 0 | 36.6 | 297 | P2 – High
DRLE-RFI-0035 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – Leary Way crossing | Civil and systems drawings differ on grounding/bonding of guideway girder diaphragm for stray-current control at Leary Way crossing. Request governing detail and responsibility for installation. | Design Manager | 2020-10-09 | 7 | Expedite | Y | N | N | 7 | Design-Build EOR / ST Design Review | 2 | 2020-10-13 | 4 | Y | 0 | 2 | 2020-10-19 | 10 | Closed | 0 | 0 | 0 | 32000 | 60000 | N |  | 0 | 0 | 0 | 0 | 1254 | P4 – Low
DRLE-RFI-0036 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at SE Redmond aerial guideway: petroleum-stained soil with odor | During excavation at SE Redmond aerial guideway (Sta. 1509+73) the contractor encountered petroleum-stained soil with odor, not shown on the GBR or E-670. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Design Manager | 2020-10-20 | 7 | Routine | Y | Y | N | 5 | Design-Build EOR / ST Design Review | 2 | 2020-10-27 | 7 | Y | 0 | 1 | 2020-10-27 | 7 | Closed | 3 | 0 | 1 | 376000 | 702000 | Y | DRLE-CO-011 | 777600 | 600500 | 1 | 46.4 | 118 | P2 – High
DRLE-RFI-0037 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at SE Redmond aerial guideway, citing procurement lead time. Product data attached. | Project Manager | 2020-10-26 | 7 | Expedite | N | N | N | 2 | Design-Build EOR / ST Design Review | 1 | 2020-10-30 | 4 | Y | 0 | 1 | 2020-10-30 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1255 | P4 – Low
DRLE-RFI-0038 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Drawing/spec discrepancy – Sammamish River bridge | Request clarification of 00 72 00 General Conditions and C-612: dimension/notes appear inconsistent or omitted for the work at Sammamish River bridge. | Design Manager | 2020-11-02 | 7 | Routine | N | N | N | 5 | Design-Build EOR / ST Design Review | 2 | 2020-11-03 | 1 | Y | 0 | 1 | 2020-11-03 | 1 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1256 | P4 – Low
DRLE-RFI-0039 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Art embed coordination – Redmond Way (SR 202) crossing | Request to clarify finish/connection detail on S-660 at Redmond Way (SR 202) crossing. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2020-11-24 | 7 | Routine | N | N | N | 0 | Design-Build EOR / ST Design Review | 3 | 2020-11-30 | 4 | Y | 0 | 1 | 2020-11-30 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1257 | P4 – Low
DRLE-RFI-0040 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Stormwater facility revision – Redmond Way (SR 202) crossing | Field conditions at Redmond Way (SR 202) crossing require changes to temporary erosion and sediment control or stormwater facility per A-741. Request direction considering critical-areas conditions and permit requirements. | Scheduler | 2020-11-30 | 7 | Expedite | N | N | N | 0 | Design-Build EOR / ST Design Review | 3 | 2020-12-07 | 6 | Y | 0 | 1 | 2020-12-07 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1258 | P4 – Low
DRLE-RFI-0041 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 24-in. sanitary sewer at Bear Creek crossing | Potholing at Sta. 1122+18 located a 24-in. sanitary sewer in conflict with the proposed duct bank encasement. Utility is not shown on C-290. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Superintendent | 2020-12-28 | 7 | Routine | N | Y | N | 4 | Design-Build EOR / ST Design Review | 1 | 2020-12-30 | 2 | Y | 0 | 1 | 2020-12-30 | 2 | Closed | 10 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 741 | P3 – Medium
DRLE-RFI-0042 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with PSE distribution duct bank at SE Redmond aerial guideway | Potholing at Sta. 2044+19 located a PSE distribution duct bank in conflict with the proposed station canopy support. Utility is not shown on S-209. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Project Engineer | 2021-01-04 | 7 | Routine | N | Y | Y | 2 | Design-Build EOR / ST Design Review | 1 | 2021-01-07 | 3 | Y | 0 | 1 | 2021-01-07 | 3 | Closed | 6 | 4 | 0 |  |  | Y | DRLE-CO-012 | 121500 | 49500 | 2 | 41.9 | 202 | P2 – High
DRLE-RFI-0043 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Stormwater facility revision – Downtown Redmond Station | Field conditions at Downtown Redmond Station require changes to temporary erosion and sediment control or stormwater facility per E-876. Request direction considering critical-areas conditions and permit requirements. | Field Engineer | 2021-01-13 | 7 | Urgent | N | N | N | 0 | Design-Build EOR / ST Design Review | 3 | 2021-01-25 | 10 | N | 3 | 2 | 2021-02-02 | 20 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1259 | P4 – Low
DRLE-RFI-0044 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Art embed coordination – Downtown Redmond Station | Request to clarify finish/connection detail on E-256 at Downtown Redmond Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Superintendent | 2021-01-15 | 7 | Expedite | N | N | N | 0 | Design-Build EOR / ST Design Review | 1 | 2021-01-18 | 3 | Y | 0 | 1 | 2021-01-18 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1260 | P4 – Low
DRLE-RFI-0045 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 8-in. high-pressure gas main at Redmond Way (SR 202) crossing | Potholing at Sta. 2037+33 located a 8-in. high-pressure gas main in conflict with the proposed retaining wall footing. Utility is not shown on E-790. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Project Engineer | 2021-01-19 | 7 | Expedite | N | Y | N | 6 | Design-Build EOR / ST Design Review | 2 | 2021-01-21 | 2 | Y | 0 | 2 | 2021-02-09 | 21 | Closed | 12 | 0 | 8 |  |  | N |  | 0 | 0 | 0 | 1.8 | 545 | P3 – Medium
DRLE-RFI-0046 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | King County Parks comment on street improvement permit – Downtown Redmond Station | King County Parks review comments on the street improvement permit require changes to the retaining wall footing at Downtown Redmond Station. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2021-01-22 | 7 | Routine | N | Y | N | 2 | WSDOT / ST Third-Party Mgmt | 2 | 2021-02-03 | 12 | N | 5 | 1 | 2021-02-03 | 12 | Closed | 5 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 639 | P3 – Medium
DRLE-RFI-0047 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | SPC | Spec / Drawing Clarification | General | 01 25 00 Substitution Procedures | Missing dimension on S-575 | Request clarification of 00 72 00 General Conditions and S-575: dimension/notes appear inconsistent or omitted for the work at Marymoor Village parking garage. | Scheduler | 2021-02-08 | 7 | Routine | N | N | N | 4 | Design-Build EOR / ST Design Review | 1 | 2021-02-11 | 3 | Y | 0 | 1 | 2021-02-11 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1261 | P4 – Low
DRLE-RFI-0048 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Property owner access/restoration requirement – Bear Creek crossing | Adjacent property owner has requested additional restoration and access provisions at Bear Creek crossing beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Field Engineer | 2021-02-08 | 7 | Routine | N | Y | Y | 2 | City of Redmond / ST Third-Party Mgmt | 3 | 2021-02-19 | 11 | N | 4 | 1 | 2021-02-19 | 11 | Closed | 5 | 4 | 0 |  |  | N |  | 0 | 0 | 0 | 4 | 462 | P3 – Medium
DRLE-RFI-0049 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Special trackwork layout – Redmond Way (SR 202) crossing | Track layout at Sta. 2036+64 (Redmond Way (SR 202) crossing) differs from the track-structure interface drawing S-321. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Engineer | 2021-02-11 | 7 | Expedite | Y | N | Y | 8 | Design-Build EOR / ST Design Review | 2 | 2021-02-15 | 4 | Y | 0 | 1 | 2021-02-15 | 4 | Closed | 0 | 0 | 0 | 956000 | 1785000 | N |  | 0 | 0 | 0 | 0 | 1262 | P4 – Low
DRLE-RFI-0050 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | City of Redmond comment on clearing and grading permit – Sammamish River bridge | City of Redmond review comments on the clearing and grading permit require changes to the stair core wall at Sammamish River bridge. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2021-02-25 | 7 | Routine | N | Y | Y | 1 | King County Parks / ST Third-Party Mgmt | 4 | 2021-03-08 | 9 | N | 2 | 1 | 2021-03-08 | 9 | Closed | 13 | 12 | 0 |  |  | N |  | 0 | 0 | 0 | 12 | 381 | P3 – Medium
DRLE-RFI-0051 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Crane staging in right-of-way – Marymoor Village parking garage | Contractor requests approval of an alternate traffic/staging plan at Marymoor Village parking garage: crane pick over active roadway. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Scheduler | 2021-03-31 | 7 | Expedite | N | N | Y | 2 | Design-Build EOR / ST Design Review | 1 | 2021-04-08 | 8 | N | 1 | 2 | 2021-04-19 | 19 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1263 | P4 – Low
DRLE-RFI-0052 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Scada Cabinet location conflict at Sta. 1123+14 | Proposed SCADA cabinet foundation location at Sta. 1123+14 conflicts with platform edge slab; offset of 6 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Scheduler | 2021-04-05 | 7 | Urgent | N | N | Y | 6 | Design-Build EOR / ST Design Review | 1 | 2021-04-13 | 8 | N | 1 | 1 | 2021-04-13 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1264 | P4 – Low
DRLE-RFI-0053 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Wetland/stream buffer protection – SE Redmond aerial guideway | Field conditions at SE Redmond aerial guideway require changes to temporary erosion and sediment control or stormwater facility per S-845. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2021-04-15 | 7 | Routine | Y | Y | N | 8 | Design-Build EOR / ST Design Review | 1 | 2021-04-21 | 6 | Y | 0 | 2 | 2021-05-04 | 19 | Closed | 2 | 0 | 1 | 213000 | 398000 | N |  | 0 | 0 | 0 | 0.2 | 811 | P4 – Low
DRLE-RFI-0054 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Station finish detail – Leary Way crossing | Request to clarify finish/connection detail on E-374 at Leary Way crossing. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2021-04-16 | 7 | Routine | Y | N | N | 8 | Design-Build EOR / ST Design Review | 1 | 2021-04-21 | 5 | Y | 0 | 1 | 2021-04-21 | 5 | Closed | 0 | 0 | 0 | 26000 | 49000 | N |  | 0 | 0 | 0 | 0 | 1265 | P4 – Low
DRLE-RFI-0055 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | Stormwater facility revision – Leary Way crossing | Field conditions at Leary Way crossing require changes to temporary erosion and sediment control or stormwater facility per C-349. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2021-04-19 | 7 | Urgent | Y | Y | Y | 6 | Design-Build EOR / ST Design Review | 1 | 2021-04-23 | 4 | Y | 0 | 1 | 2021-04-23 | 4 | Closed | 4 | 1 | 0 | 56000 | 104000 | N |  | 0 | 0 | 0 | 1 | 614 | P3 – Medium
DRLE-RFI-0056 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Grounding/bonding and stray-current detail – Sammamish River bridge | Civil and systems drawings differ on grounding/bonding of pedestrian ramp for stray-current control at Sammamish River bridge. Request governing detail and responsibility for installation. | Project Manager | 2021-04-19 | 7 | Urgent | Y | Y | Y | 3 | Design-Build EOR / ST Design Review | 2 | 2021-04-26 | 6 | Y | 0 | 1 | 2021-04-26 | 6 | Closed | 3 | 2 | 0 | 335000 | 626000 | Y | DRLE-CO-014 | 751900 | 284790 | 0.8 | 45.5 | 130 | P2 – High
DRLE-RFI-0057 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – alternate LED luminaire | Contractor requests approval to substitute alternate LED luminaire for specified LED luminaire on work at Bear Creek crossing, citing procurement lead time. Product data attached. | Project Engineer | 2021-04-19 | 7 | Expedite | N | Y | N | 6 | Design-Build EOR / ST Design Review | 1 | 2021-04-23 | 4 | Y | 0 | 1 | 2021-04-23 | 4 | Closed | 6 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 681 | P3 – Medium
DRLE-RFI-0058 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Wetland/stream buffer protection – Marymoor Village Station | Field conditions at Marymoor Village Station require changes to temporary erosion and sediment control or stormwater facility per A-442. Request direction considering critical-areas conditions and permit requirements. | Scheduler | 2021-04-20 | 7 | Routine | N | N | N | 7 | Design-Build EOR / ST Design Review | 3 | 2021-04-26 | 4 | Y | 0 | 1 | 2021-04-26 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1266 | P4 – Low
DRLE-RFI-0059 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Haul route revision – Downtown Redmond Station | Contractor requests approval of an alternate traffic/staging plan at Downtown Redmond Station: crane pick over active roadway. Existing work restrictions limit production; requests ST/King County Parks concurrence. | Design Manager | 2021-04-26 | 7 | Expedite | N | N | N | 3 | Design-Build EOR / ST Design Review | 3 | 2021-04-29 | 3 | Y | 0 | 2 | 2021-05-19 | 23 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1267 | P4 – Low
DRLE-RFI-0060 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – SE Redmond aerial guideway | Civil and systems drawings differ on grounding/bonding of retaining wall footing for stray-current control at SE Redmond aerial guideway. Request governing detail and responsibility for installation. | Project Engineer | 2021-05-12 | 7 | Routine | N | N | N | 4 | Design-Build EOR / ST Design Review | 3 | 2021-05-24 | 11 | N | 4 | 1 | 2021-05-24 | 11 | Closed | 0 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 742 | P3 – Medium
DRLE-RFI-0061 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | City of Redmond comment on critical areas permit – Marymoor Village parking garage | City of Redmond review comments on the critical areas permit require changes to the drilled shaft cap at Marymoor Village parking garage. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2021-05-12 | 7 | Expedite | N | Y | N | 0 | WSDOT / ST Third-Party Mgmt | 2 | 2021-05-25 | 13 | N | 6 | 1 | 2021-05-25 | 13 | Closed | 4 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 592 | P3 – Medium
DRLE-RFI-0062 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – platform edge slab sequence at SE Redmond aerial guideway | Erection of the platform edge slab as drawn conflicts with adjacent work and access limits at SE Redmond aerial guideway. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Superintendent | 2021-05-13 | 7 | Routine | N | N | N | 0 | Design-Build EOR / ST Design Review | 2 | 2021-05-31 | 16 | N | 9 | 2 | 2021-06-15 | 33 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1268 | P4 – Low
DRLE-RFI-0063 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Grounding/bonding and stray-current detail – Marymoor Village parking garage | Civil and systems drawings differ on grounding/bonding of column reinforcement for stray-current control at Marymoor Village parking garage. Request governing detail and responsibility for installation. | Design Manager | 2021-05-24 | 7 | Routine | N | Y | Y | 8 | Design-Build EOR / ST Design Review | 4 | 2021-05-28 | 4 | Y | 0 | 1 | 2021-05-28 | 4 | Closed | 10 | 8 | 0 |  |  | N |  | 0 | 0 | 0 | 8 | 413 | P3 – Medium
DRLE-RFI-0064 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Stormwater facility revision – Marymoor Park interface | Field conditions at Marymoor Park interface require changes to temporary erosion and sediment control or stormwater facility per C-229. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2021-05-25 | 7 | Routine | N | N | N | 7 | Design-Build EOR / ST Design Review | 1 | 2021-05-31 | 6 | Y | 0 | 1 | 2021-05-31 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1269 | P4 – Low
DRLE-RFI-0065 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | King County Parks comment on critical areas permit – Marymoor Park interface | King County Parks review comments on the critical areas permit require changes to the column reinforcement at Marymoor Park interface. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2021-05-27 | 7 | Routine | N | Y | N | 4 | City of Redmond / ST Third-Party Mgmt | 3 | 2021-06-07 | 11 | N | 4 | 1 | 2021-06-07 | 11 | Closed | 6 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 593 | P3 – Medium
DRLE-RFI-0066 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Redmond Way (SR 202) crossing: buried concrete debris and an old foundation | During excavation at Redmond Way (SR 202) crossing (Sta. 1873+86) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or M-148. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Project Engineer | 2021-05-27 | 7 | Routine | N | N | N | 4 | Design-Build EOR / ST Design Review | 2 | 2021-06-03 | 7 | Y | 0 | 1 | 2021-06-03 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1270 | P4 – Low
DRLE-RFI-0067 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – Redmond Way (SR 202) crossing | Systems contractor requires 3-in. PVC conduit stub-ups for traction power feeder at Redmond Way (SR 202) crossing not provided in civil C-315. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2021-05-31 | 7 | Routine | N | Y | N | 1 | Design-Build EOR / ST Design Review | 1 | 2021-06-21 | 21 | N | 14 | 1 | 2021-06-21 | 21 | Closed | 7 | 0 | 12 |  |  | N |  | 0 | 0 | 0 | 2.7 | 496 | P3 – Medium
DRLE-RFI-0068 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Track slab/expansion joint interface – Leary Way crossing | Track layout at Sta. 1774+90 (Leary Way crossing) differs from the track-structure interface drawing S-644. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Manager | 2021-06-09 | 7 | Urgent | N | N | Y | 5 | Design-Build EOR / ST Design Review | 2 | 2021-06-10 | 1 | Y | 0 | 1 | 2021-06-10 | 1 | Closed | 0 | 2 | 0 |  |  | N |  | 0 | 0 | 0 | 2 | 531 | P3 – Medium
DRLE-RFI-0069 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Special trackwork layout – Marymoor Park interface | Track layout at Sta. 1375+06 (Marymoor Park interface) differs from the track-structure interface drawing A-493. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Manager | 2021-06-10 | 7 | Routine | Y | Y | N | 1 | Design-Build EOR / ST Design Review | 2 | 2021-06-14 | 4 | Y | 0 | 1 | 2021-06-14 | 4 | Closed | 5 | 0 | 2 | 139000 | 260000 | N |  | 0 | 0 | 0 | 0.4 | 743 | P3 – Medium
DRLE-RFI-0070 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Grounding/bonding and stray-current detail – Sammamish River bridge | Civil and systems drawings differ on grounding/bonding of bearing pad/embed plate for stray-current control at Sammamish River bridge. Request governing detail and responsibility for installation. | Project Engineer | 2021-06-21 | 7 | Routine | N | Y | N | 2 | Design-Build EOR / ST Design Review | 3 | 2021-07-06 | 15 | N | 8 | 1 | 2021-07-06 | 15 | Closed | 3 | 0 | 6 |  |  | Y | DRLE-CO-014 | 162400 | 61510 | 0.2 | 39.4 | 251 | P2 – High
DRLE-RFI-0071 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 24-in. sanitary sewer at Marymoor Village Station | Potholing at Sta. 1082+35 located a 24-in. sanitary sewer in conflict with the proposed guideway girder diaphragm. Utility is not shown on A-200. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Project Engineer | 2021-06-24 | 7 | Routine | N | Y | N | 4 | Design-Build EOR / ST Design Review | 1 | 2021-07-09 | 15 | N | 8 | 1 | 2021-07-09 | 15 | Closed | 7 | 0 | 11 |  |  | N |  | 0 | 0 | 0 | 2.4 | 500 | P3 – Medium
DRLE-RFI-0072 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – SE Redmond aerial guideway | M-365 shows a 18 ft-1 in. dimension for the retaining wall footing; structural sheet S-720 shows a different value. Request clarification before fabrication/rebar release. | Project Engineer | 2021-06-28 | 7 | Urgent | N | N | Y | 6 | Design-Build EOR / ST Design Review | 1 | 2021-06-30 | 2 | Y | 0 | 2 | 2021-07-12 | 14 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1271 | P4 – Low
DRLE-RFI-0073 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Downtown Redmond Station: abandoned timber piles | During excavation at Downtown Redmond Station (Sta. 1981+54) the contractor encountered abandoned timber piles, not shown on the GBR or C-221. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Scheduler | 2021-06-28 | 7 | Routine | Y | Y | N | 2 | Design-Build EOR / ST Design Review | 1 | 2021-07-06 | 8 | N | 1 | 1 | 2021-07-06 | 8 | Closed | 7 | 0 | 6 | 195000 | 365000 | N |  | 0 | 0 | 0 | 1.3 | 570 | P3 – Medium
DRLE-RFI-0074 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Grounding/bonding and stray-current detail – Redmond Way (SR 202) crossing | Civil and systems drawings differ on grounding/bonding of bearing pad/embed plate for stray-current control at Redmond Way (SR 202) crossing. Request governing detail and responsibility for installation. | Project Manager | 2021-06-28 | 7 | Urgent | Y | Y | N | 1 | Design-Build EOR / ST Design Review | 4 | 2021-07-02 | 4 | Y | 0 | 1 | 2021-07-02 | 4 | Closed | 3 | 0 | 1 | 343000 | 640000 | Y | DRLE-CO-013 | 981500 | 685400 | 1 | 46.9 | 108 | P1 – Critical
DRLE-RFI-0075 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Marymoor Village parking garage: soft lacustrine silt below design subgrade | During excavation at Marymoor Village parking garage (Sta. 1295+39) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or C-226. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Superintendent | 2021-07-02 | 7 | Routine | N | Y | N | 1 | Design-Build EOR / ST Design Review | 2 | 2021-07-05 | 2 | Y | 0 | 1 | 2021-07-05 | 2 | Closed | 4 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 682 | P3 – Medium
DRLE-RFI-0076 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | WSDOT comment on building permit – Marymoor Park interface | WSDOT review comments on the building permit require changes to the duct bank encasement at Marymoor Park interface. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2021-07-05 | 7 | Routine | N | Y | Y | 8 | WSDOT / ST Third-Party Mgmt | 5 | 2021-07-12 | 5 | Y | 0 | 2 | 2021-07-21 | 16 | Closed | 6 | 3 | 0 |  |  | N |  | 0 | 0 | 0 | 3 | 485 | P3 – Medium
DRLE-RFI-0077 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with fiber communications duct bank at Downtown Redmond Station | Potholing at Sta. 2370+74 located a fiber communications duct bank in conflict with the proposed pedestrian ramp. Utility is not shown on E-318. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Project Engineer | 2021-07-05 | 7 | Routine | N | Y | N | 3 | Design-Build EOR / ST Design Review | 2 | 2021-07-09 | 4 | Y | 0 | 1 | 2021-07-09 | 4 | Closed | 5 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 812 | P4 – Low
DRLE-RFI-0078 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Art embed coordination – Marymoor Village parking garage | Request to clarify finish/connection detail on S-373 at Marymoor Village parking garage. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Manager | 2021-07-06 | 7 | Routine | N | N | N | 4 | Design-Build EOR / ST Design Review | 2 | 2021-07-09 | 3 | Y | 0 | 1 | 2021-07-09 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1272 | P4 – Low
DRLE-RFI-0079 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with abandoned utility vault at Marymoor Park interface | Potholing at Sta. 1174+74 located a abandoned utility vault in conflict with the proposed column reinforcement. Utility is not shown on C-538. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Scheduler | 2021-07-08 | 7 | Routine | Y | Y | Y | 7 | Design-Build EOR / ST Design Review | 2 | 2021-07-12 | 4 | Y | 0 | 1 | 2021-07-12 | 4 | Closed | 3 | 3 | 0 | 89000 | 167000 | Y | DRLE-CO-016 | 146120 | 116840 | 2.2 | 43.9 | 162 | P2 – High
DRLE-RFI-0080 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – retaining wall footing and duct bank encasement at Marymoor Village Station | Interference between retaining wall footing and duct bank encasement at Marymoor Village Station per S-301. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Field Engineer | 2021-07-12 | 7 | Expedite | Y | N | N | 0 | Design-Build EOR / ST Design Review | 1 | 2021-07-23 | 11 | N | 4 | 1 | 2021-07-23 | 11 | Closed | 0 | 0 | 0 | 1565000 | 2921000 | N |  | 0 | 0 | 0 | 0 | 1273 | P4 – Low
DRLE-RFI-0081 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – retaining wall footing at Marymoor Park interface | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-519 for smoke control damper at Marymoor Park interface. Request direction on compliant detail. | Project Manager | 2021-07-22 | 7 | Expedite | N | N | N | 6 | Design-Build EOR / ST Design Review | 2 | 2021-07-27 | 5 | Y | 0 | 1 | 2021-07-27 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1274 | P4 – Low
DRLE-RFI-0082 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Wetland/stream buffer protection – Redmond Way (SR 202) crossing | Field conditions at Redmond Way (SR 202) crossing require changes to temporary erosion and sediment control or stormwater facility per M-509. Request direction considering critical-areas conditions and permit requirements. | Project Manager | 2021-07-22 | 7 | Routine | N | N | N | 8 | Design-Build EOR / ST Design Review | 2 | 2021-08-09 | 17 | N | 10 | 1 | 2021-08-09 | 17 | Closed | 0 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 683 | P3 – Medium
DRLE-RFI-0083 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Direct fixation fastener spacing at Sta. 1325+12 | Track layout at Sta. 1325+12 (Redmond Way (SR 202) crossing) differs from the track-structure interface drawing S-579. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Engineer | 2021-07-26 | 7 | Routine | N | N | Y | 4 | Design-Build EOR / ST Design Review | 1 | 2021-08-02 | 5 | Y | 0 | 1 | 2021-08-02 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1275 | P4 – Low
DRLE-RFI-0084 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Night work and noise variance – Marymoor Village Station | Contractor requests approval of an alternate traffic/staging plan at Marymoor Village Station: revised haul route. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Project Engineer | 2021-08-02 | 7 | Routine | N | N | Y | 1 | Design-Build EOR / ST Design Review | 3 | 2021-08-06 | 4 | Y | 0 | 1 | 2021-08-06 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1276 | P4 – Low
DRLE-RFI-0085 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – Sammamish River bridge | Civil and systems drawings differ on grounding/bonding of station canopy support for stray-current control at Sammamish River bridge. Request governing detail and responsibility for installation. | Project Engineer | 2021-08-02 | 7 | Routine | Y | Y | Y | 0 | Design-Build EOR / ST Design Review | 1 | 2021-08-09 | 6 | Y | 0 | 1 | 2021-08-09 | 6 | Closed | 7 | 4 | 0 | 164000 | 307000 | N |  | 0 | 0 | 0 | 4 | 463 | P3 – Medium
DRLE-RFI-0086 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | King County Parks comment on right-of-way use permit – Bear Creek crossing | King County Parks review comments on the right-of-way use permit require changes to the pedestrian ramp at Bear Creek crossing. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2021-08-03 | 7 | Urgent | N | Y | N | 0 | WSDOT / ST Third-Party Mgmt | 1 | 2021-08-09 | 6 | Y | 0 | 1 | 2021-08-09 | 6 | Closed | 7 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 744 | P3 – Medium
DRLE-RFI-0087 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – galvanized steel handrail | Contractor requests approval to substitute galvanized steel handrail for stainless steel handrail on work at Downtown Redmond Station, citing procurement lead time. Product data attached. | Field Engineer | 2021-08-03 | 7 | Routine | N | N | N | 8 | Design-Build EOR / ST Design Review | 4 | 2021-08-09 | 5 | Y | 0 | 2 | 2021-08-27 | 24 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1277 | P4 – Low
DRLE-RFI-0088 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – station canopy support at SE Redmond aerial guideway | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-815 for smoke control damper at SE Redmond aerial guideway. Request direction on compliant detail. | Scheduler | 2021-08-03 | 7 | Urgent | N | N | Y | 5 | Design-Build EOR / ST Design Review | 3 | 2021-08-06 | 3 | Y | 0 | 1 | 2021-08-06 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1278 | P4 – Low
DRLE-RFI-0089 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at Sammamish River bridge, citing procurement lead time. Product data attached. | Project Engineer | 2021-08-20 | 7 | Routine | N | N | N | 2 | Design-Build EOR / ST Design Review | 1 | 2021-08-23 | 3 | Y | 0 | 1 | 2021-08-23 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1279 | P4 – Low
DRLE-RFI-0090 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – alternate LED luminaire | Contractor requests approval to substitute alternate LED luminaire for specified LED luminaire on work at Sammamish River bridge, citing procurement lead time. Product data attached. | Field Engineer | 2021-08-30 | 7 | Urgent | N | N | N | 6 | Design-Build EOR / ST Design Review | 1 | 2021-09-07 | 8 | N | 1 | 1 | 2021-09-07 | 8 | Closed | 0 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 813 | P4 – Low
DRLE-RFI-0091 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with fiber communications duct bank at Marymoor Park interface | Potholing at Sta. 2184+75 located a fiber communications duct bank in conflict with the proposed drilled shaft cap. Utility is not shown on E-197. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2021-09-07 | 7 | Routine | Y | Y | N | 1 | Design-Build EOR / ST Design Review | 1 | 2021-09-20 | 11 | N | 4 | 2 | 2021-09-30 | 23 | Closed | 15 | 0 | 11 | 1855000 | 3463000 | N |  | 0 | 0 | 0 | 2.4 | 501 | P3 – Medium
DRLE-RFI-0092 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | In-water work window – Leary Way crossing | Field conditions at Leary Way crossing require changes to temporary erosion and sediment control or stormwater facility per C-592. Request direction considering critical-areas conditions and permit requirements. | Field Engineer | 2021-09-09 | 7 | Urgent | Y | Y | N | 5 | Design-Build EOR / ST Design Review | 1 | 2021-09-13 | 3 | Y | 0 | 1 | 2021-09-13 | 3 | Closed | 4 | 0 | 2 | 177000 | 331000 | N |  | 0 | 0 | 0 | 0.4 | 745 | P3 – Medium
DRLE-RFI-0093 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Embedded conduit stub-ups – Downtown Redmond Station | Systems contractor requires 3-in. PVC conduit stub-ups for fiber backbone at Downtown Redmond Station not provided in civil M-702. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2021-09-13 | 7 | Expedite | N | Y | N | 7 | Design-Build EOR / ST Design Review | 2 | 2021-09-20 | 6 | Y | 0 | 1 | 2021-09-20 | 6 | Closed | 4 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 684 | P3 – Medium
DRLE-RFI-0094 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Wetland/stream buffer protection – Marymoor Park interface | Field conditions at Marymoor Park interface require changes to temporary erosion and sediment control or stormwater facility per C-840. Request direction considering critical-areas conditions and permit requirements. | Project Manager | 2021-09-16 | 7 | Routine | Y | Y | N | 4 | Design-Build EOR / ST Design Review | 3 | 2021-09-27 | 9 | N | 2 | 2 | 2021-10-11 | 23 | Closed | 11 | 0 | 5 | 209000 | 390000 | N |  | 0 | 0 | 0 | 1.1 | 594 | P3 – Medium
DRLE-RFI-0095 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Night work and noise variance – Marymoor Village parking garage | Contractor requests approval of an alternate traffic/staging plan at Marymoor Village parking garage: extended night closure. Existing work restrictions limit production; requests ST/King County Parks concurrence. | Design Manager | 2021-09-20 | 7 | Urgent | N | N | Y | 0 | Design-Build EOR / ST Design Review | 3 | 2021-09-23 | 3 | Y | 0 | 1 | 2021-09-23 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1280 | P4 – Low
DRLE-RFI-0096 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with abandoned utility vault at Leary Way crossing | Potholing at Sta. 2346+93 located a abandoned utility vault in conflict with the proposed retaining wall footing. Utility is not shown on M-310. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Field Engineer | 2021-09-21 | 7 | Routine | Y | Y | N | 2 | Design-Build EOR / ST Design Review | 2 | 2021-09-29 | 8 | N | 1 | 1 | 2021-09-29 | 8 | Closed | 2 | 0 | 1 | 947000 | 1767000 | Y | DRLE-CO-015 | 930900 | 0 | 0 | 0.2 | 814 | P4 – Low
DRLE-RFI-0097 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Crane staging in right-of-way – Marymoor Village Station | Contractor requests approval of an alternate traffic/staging plan at Marymoor Village Station: crane pick over active roadway. Existing work restrictions limit production; requests ST/King County Parks concurrence. | Superintendent | 2021-09-22 | 7 | Routine | Y | Y | N | 8 | Design-Build EOR / ST Design Review | 1 | 2021-09-27 | 4 | Y | 0 | 1 | 2021-09-27 | 4 | Closed | 1 | 0 | 0 | 22000 | 41000 | N |  | 0 | 0 | 0 | 0 | 1281 | P4 – Low
DRLE-RFI-0098 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Grounding/bonding and stray-current detail – Bear Creek crossing | Civil and systems drawings differ on grounding/bonding of duct bank encasement for stray-current control at Bear Creek crossing. Request governing detail and responsibility for installation. | Project Manager | 2021-09-27 | 7 | Routine | Y | N | N | 1 | Design-Build EOR / ST Design Review | 1 | 2021-10-06 | 9 | N | 2 | 2 | 2021-10-15 | 18 | Closed | 0 | 0 | 0 | 397000 | 740000 | N |  | 0 | 0 | 0 | 0 | 1282 | P4 – Low
DRLE-RFI-0099 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with PSE distribution duct bank at Leary Way crossing | Potholing at Sta. 1578+85 located a PSE distribution duct bank in conflict with the proposed guideway girder diaphragm. Utility is not shown on C-621. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Scheduler | 2021-10-05 | 7 | Routine | Y | Y | N | 8 | Design-Build EOR / ST Design Review | 2 | 2021-10-12 | 7 | Y | 0 | 1 | 2021-10-12 | 7 | Closed | 4 | 0 | 2 | 374000 | 697000 | Y | DRLE-CO-016 | 314580 | 251560 | 4.8 | 44.9 | 140 | P2 – High
DRLE-RFI-0100 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 8-in. high-pressure gas main at Downtown Redmond Station | Potholing at Sta. 2360+97 located a 8-in. high-pressure gas main in conflict with the proposed guideway girder diaphragm. Utility is not shown on E-827. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Design Manager | 2021-10-11 | 7 | Routine | N | Y | N | 4 | Design-Build EOR / ST Design Review | 1 | 2021-10-22 | 11 | N | 4 | 1 | 2021-10-22 | 11 | Closed | 6 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 640 | P3 – Medium
DRLE-RFI-0101 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 8-in. high-pressure gas main at Downtown Redmond Station | Potholing at Sta. 1758+48 located a 8-in. high-pressure gas main in conflict with the proposed stair core wall. Utility is not shown on S-860. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Superintendent | 2021-10-14 | 7 | Expedite | N | Y | N | 7 | Design-Build EOR / ST Design Review | 1 | 2021-10-20 | 6 | Y | 0 | 1 | 2021-10-20 | 6 | Closed | 3 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 815 | P4 – Low
DRLE-RFI-0102 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Crane staging in right-of-way – SE Redmond aerial guideway | Contractor requests approval of an alternate traffic/staging plan at SE Redmond aerial guideway: temporary lane shift. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Scheduler | 2021-10-20 | 7 | Expedite | N | N | N | 1 | Design-Build EOR / ST Design Review | 3 | 2021-10-25 | 3 | Y | 0 | 1 | 2021-10-25 | 3 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1283 | P4 – Low
DRLE-RFI-0103 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Clarify spec requirement – SE Redmond aerial guideway | Request clarification of 01 25 00 Substitution Procedures and S-618: dimension/notes appear inconsistent or omitted for the work at SE Redmond aerial guideway. | Scheduler | 2021-10-28 | 7 | Routine | N | N | N | 0 | Design-Build EOR / ST Design Review | 2 | 2021-11-04 | 7 | Y | 0 | 1 | 2021-11-04 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1284 | P4 – Low
DRLE-RFI-0104 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with PSE distribution duct bank at Marymoor Village parking garage | Potholing at Sta. 1915+04 located a PSE distribution duct bank in conflict with the proposed station canopy support. Utility is not shown on M-746. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Scheduler | 2021-10-29 | 7 | Expedite | Y | N | N | 8 | Design-Build EOR / ST Design Review | 1 | 2021-11-09 | 11 | N | 4 | 2 | 2021-11-16 | 18 | Closed | 0 | 0 | 0 | 100000 | 187000 | N |  | 0 | 0 | 0 | 0 | 1285 | P4 – Low
DRLE-RFI-0105 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – platform edge slab and stair core wall at Sammamish River bridge | Interference between platform edge slab and stair core wall at Sammamish River bridge per M-846. Required clearance of 7 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Field Engineer | 2021-11-01 | 7 | Routine | N | Y | N | 4 | Design-Build EOR / ST Design Review | 2 | 2021-11-10 | 9 | N | 2 | 1 | 2021-11-10 | 9 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 816 | P4 – Low
DRLE-RFI-0106 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – station canopy support at Marymoor Village parking garage | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-399 for fire alarm device layout at Marymoor Village parking garage. Request direction on compliant detail. | Scheduler | 2021-11-01 | 7 | Expedite | Y | N | N | 6 | Design-Build EOR / ST Design Review | 2 | 2021-11-15 | 12 | N | 5 | 1 | 2021-11-15 | 12 | Closed | 0 | 0 | 0 | 241000 | 450000 | Y | DRLE-CO-018 | 369800 | 263700 | 0 | 43 | 178 | P2 – High
DRLE-RFI-0107 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – Marymoor Village parking garage | Civil and systems drawings differ on grounding/bonding of drilled shaft cap for stray-current control at Marymoor Village parking garage. Request governing detail and responsibility for installation. | Superintendent | 2021-11-08 | 7 | Routine | N | Y | Y | 2 | Design-Build EOR / ST Design Review | 2 | 2021-11-19 | 11 | N | 4 | 1 | 2021-11-19 | 11 | Closed | 7 | 4 | 0 |  |  | N |  | 0 | 0 | 0 | 4 | 464 | P3 – Medium
DRLE-RFI-0108 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Sammamish River bridge: soft lacustrine silt below design subgrade | During excavation at Sammamish River bridge (Sta. 2393+70) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or S-731. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Field Engineer | 2021-11-10 | 7 | Routine | Y | Y | Y | 1 | Design-Build EOR / ST Design Review | 1 | 2021-11-12 | 2 | Y | 0 | 1 | 2021-11-12 | 2 | Closed | 3 | 3 | 0 | 352000 | 658000 | Y | DRLE-CO-017 | 273500 | 273500 | 2 | 46.8 | 111 | P2 – High
DRLE-RFI-0109 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | In-water work window – Downtown Redmond Station | Field conditions at Downtown Redmond Station require changes to temporary erosion and sediment control or stormwater facility per E-291. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2021-11-17 | 7 | Routine | Y | Y | N | 2 | Design-Build EOR / ST Design Review | 3 | 2021-12-17 | 30 | N | 23 | 1 | 2021-12-17 | 30 | Closed | 4 | 0 | 2 | 58000 | 108000 | Y | DRLE-CO-022 | 73900 | 44800 | 2 | 38 | 276 | P2 – High
DRLE-RFI-0110 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Dimensional discrepancy – Redmond Way (SR 202) crossing | C-591 shows a 38 ft-0 in. dimension for the guideway girder diaphragm; structural sheet S-639 shows a different value. Request clarification before fabrication/rebar release. | Project Engineer | 2021-11-22 | 7 | Routine | Y | N | Y | 2 | Design-Build EOR / ST Design Review | 1 | 2021-11-26 | 4 | Y | 0 | 2 | 2021-12-17 | 25 | Closed | 0 | 0 | 0 | 238000 | 444000 | Y | DRLE-CO-019 | 163200 | 64800 | 0 | 38.2 | 272 | P2 – High
DRLE-RFI-0111 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at Marymoor Village parking garage: perched groundwater | During excavation at Marymoor Village parking garage (Sta. 1024+34) the contractor encountered perched groundwater at approx. elevation 176 ft, not shown on the GBR or E-185. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Field Engineer | 2021-11-24 | 7 | Expedite | Y | Y | N | 2 | Design-Build EOR / ST Design Review | 4 | 2021-12-09 | 15 | N | 8 | 1 | 2021-12-09 | 15 | Closed | 5 | 0 | 6 | 791000 | 1476000 | Y | DRLE-CO-021 | 1398300 | 957200 | 3 | 49.8 | 64 | P1 – Critical
DRLE-RFI-0112 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Signal Case location conflict at Sta. 2012+04 | Proposed signal case foundation location at Sta. 2012+04 conflicts with drilled shaft cap; offset of 4 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Field Engineer | 2021-11-24 | 7 | Routine | Y | Y | Y | 6 | Design-Build EOR / ST Design Review | 4 | 2021-12-02 | 8 | N | 1 | 1 | 2021-12-02 | 8 | Closed | 3 | 2 | 0 | 58000 | 108000 | N |  | 0 | 0 | 0 | 2 | 532 | P3 – Medium
DRLE-RFI-0113 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | Property owner access/restoration requirement – Leary Way crossing | Adjacent property owner has requested additional restoration and access provisions at Leary Way crossing beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Field Engineer | 2021-11-29 | 7 | Routine | Y | Y | Y | 0 | City of Redmond / ST Third-Party Mgmt | 3 | 2021-12-07 | 8 | N | 1 | 1 | 2021-12-07 | 8 | Closed | 3 | 2 | 0 | 294000 | 549000 | N |  | 0 | 0 | 0 | 2 | 533 | P3 – Medium
DRLE-RFI-0114 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with fiber communications duct bank at Marymoor Park interface | Potholing at Sta. 2220+01 located a fiber communications duct bank in conflict with the proposed stair core wall. Utility is not shown on A-796. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Field Engineer | 2021-11-30 | 7 | Routine | Y | Y | N | 2 | Design-Build EOR / ST Design Review | 2 | 2021-12-07 | 7 | Y | 0 | 1 | 2021-12-07 | 7 | Closed | 6 | 0 | 4 | 140000 | 261000 | N |  | 0 | 0 | 0 | 0.9 | 641 | P3 – Medium
DRLE-RFI-0115 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – guideway girder diaphragm at Bear Creek crossing | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-893 for fire alarm device layout at Bear Creek crossing. Request direction on compliant detail. | Project Engineer | 2021-12-03 | 7 | Urgent | Y | N | Y | 2 | Design-Build EOR / ST Design Review | 3 | 2021-12-07 | 4 | Y | 0 | 2 | 2021-12-14 | 11 | Closed | 0 | 0 | 0 | 10000 | 19000 | Y | DRLE-CO-020 | 21800 | 8100 | 0 | 31 | 339 | P2 – High
DRLE-RFI-0116 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Crane staging in right-of-way – Marymoor Park interface | Contractor requests approval of an alternate traffic/staging plan at Marymoor Park interface: extended night closure. Existing work restrictions limit production; requests ST/King County Parks concurrence. | Design Manager | 2021-12-08 | 7 | Routine | N | Y | N | 7 | Design-Build EOR / ST Design Review | 1 | 2021-12-16 | 8 | N | 1 | 1 | 2021-12-16 | 8 | Closed | 1 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 817 | P4 – Low
DRLE-RFI-0117 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Embedded conduit stub-ups – Leary Way crossing | Systems contractor requires 2-in. PVC conduit stub-ups for signal case at Leary Way crossing not provided in civil S-649. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2021-12-17 | 7 | Routine | N | Y | Y | 4 | Design-Build EOR / ST Design Review | 2 | 2021-12-24 | 7 | Y | 0 | 1 | 2021-12-24 | 7 | Closed | 3 | 2 | 0 |  |  | N |  | 0 | 0 | 0 | 2 | 534 | P3 – Medium
DRLE-RFI-0118 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at Sammamish River bridge, citing procurement lead time. Product data attached. | Superintendent | 2021-12-20 | 7 | Urgent | N | N | N | 0 | Design-Build EOR / ST Design Review | 2 | 2021-12-27 | 5 | Y | 0 | 1 | 2021-12-27 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1286 | P4 – Low
DRLE-RFI-0119 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | TESC modification – Downtown Redmond Station | Field conditions at Downtown Redmond Station require changes to temporary erosion and sediment control or stormwater facility per A-157. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2021-12-23 | 7 | Routine | Y | Y | N | 7 | Design-Build EOR / ST Design Review | 1 | 2021-12-31 | 8 | N | 1 | 1 | 2021-12-31 | 8 | Closed | 1 | 0 | 2 | 572000 | 1068000 | N |  | 0 | 0 | 0 | 0.4 | 746 | P3 – Medium
DRLE-RFI-0120 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at Marymoor Village Station, citing procurement lead time. Product data attached. | Scheduler | 2021-12-24 | 7 | Routine | Y | N | N | 1 | Design-Build EOR / ST Design Review | 3 | 2021-12-30 | 6 | Y | 0 | 1 | 2021-12-30 | 6 | Closed | 0 | 0 | 0 | 15000 | 28000 | N |  | 0 | 0 | 0 | 0 | 1287 | P4 – Low
DRLE-RFI-0121 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Constructability – bearing pad/embed plate sequence at Sammamish River bridge | Erection of the bearing pad/embed plate as drawn conflicts with adjacent work and access limits at Sammamish River bridge. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Project Engineer | 2021-12-27 | 7 | Routine | Y | Y | N | 5 | Design-Build EOR / ST Design Review | 1 | 2021-12-29 | 2 | Y | 0 | 1 | 2021-12-29 | 2 | Closed | 4 | 0 | 3 | 31000 | 57000 | Y | DRLE-CO-023 | 30800 | 22300 | 2 | 35.8 | 307 | P2 – High
DRLE-RFI-0122 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Canopy/glazing connection – Bear Creek crossing | Request to clarify finish/connection detail on S-885 at Bear Creek crossing. Includes coordination with art program embeds and handrail sleeves as applicable. | Superintendent | 2021-12-28 | 7 | Expedite | N | Y | N | 2 | Design-Build EOR / ST Design Review | 1 | 2022-01-03 | 4 | Y | 0 | 1 | 2022-01-03 | 4 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 818 | P4 – Low
DRLE-RFI-0123 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – column reinforcement and station canopy support at Marymoor Village parking garage | Interference between column reinforcement and station canopy support at Marymoor Village parking garage per S-247. Required clearance of 2 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2022-01-03 | 7 | Routine | N | Y | N | 5 | Design-Build EOR / ST Design Review | 3 | 2022-01-17 | 13 | N | 6 | 2 | 2022-02-01 | 29 | Closed | 6 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 595 | P3 – Medium
DRLE-RFI-0124 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | Stormwater facility revision – Downtown Redmond Station | Field conditions at Downtown Redmond Station require changes to temporary erosion and sediment control or stormwater facility per M-652. Request direction considering critical-areas conditions and permit requirements. | Project Manager | 2022-01-04 | 7 | Routine | N | Y | N | 7 | Design-Build EOR / ST Design Review | 1 | 2022-01-11 | 7 | Y | 0 | 1 | 2022-01-11 | 7 | Closed | 11 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 596 | P3 – Medium
DRLE-RFI-0125 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Special trackwork layout – Marymoor Village parking garage | Track layout at Sta. 1174+35 (Marymoor Village parking garage) differs from the track-structure interface drawing M-114. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2022-01-10 | 7 | Routine | N | Y | N | 5 | Design-Build EOR / ST Design Review | 2 | 2022-01-19 | 9 | N | 2 | 2 | 2022-02-07 | 26 | Closed | 7 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 685 | P3 – Medium
DRLE-RFI-0126 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Station finish detail – Leary Way crossing | Request to clarify finish/connection detail on S-243 at Leary Way crossing. Includes coordination with art program embeds and handrail sleeves as applicable. | Superintendent | 2022-01-11 | 7 | Routine | Y | N | Y | 1 | Design-Build EOR / ST Design Review | 1 | 2022-01-18 | 7 | Y | 0 | 1 | 2022-01-18 | 7 | Closed | 0 | 0 | 0 | 143000 | 266000 | N |  | 0 | 0 | 0 | 0 | 1288 | P4 – Low
DRLE-RFI-0127 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Stormwater facility revision – Redmond Way (SR 202) crossing | Field conditions at Redmond Way (SR 202) crossing require changes to temporary erosion and sediment control or stormwater facility per A-590. Request direction considering critical-areas conditions and permit requirements. | Scheduler | 2022-01-17 | 7 | Urgent | Y | Y | Y | 1 | Design-Build EOR / ST Design Review | 3 | 2022-01-24 | 7 | Y | 0 | 1 | 2022-01-24 | 7 | Closed | 8 | 2 | 0 | 56000 | 104000 | Y | DRLE-CO-024 | 79600 | 63400 | 4 | 41.4 | 209 | P2 – High
DRLE-RFI-0128 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Marymoor Park interface | Systems contractor requires 3-in. PVC conduit stub-ups for SCADA cabinet at Marymoor Park interface not provided in civil E-694. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2022-01-18 | 7 | Routine | N | N | N | 3 | Design-Build EOR / ST Design Review | 1 | 2022-01-27 | 9 | N | 2 | 1 | 2022-01-27 | 9 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1289 | P4 – Low
DRLE-RFI-0129 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Fiber Backbone location conflict at Sta. 1945+15 | Proposed fiber backbone foundation location at Sta. 1945+15 conflicts with guideway girder diaphragm; offset of 11 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2022-01-20 | 7 | Routine | N | N | Y | 2 | Design-Build EOR / ST Design Review | 4 | 2022-02-07 | 17 | N | 10 | 1 | 2022-02-07 | 17 | Closed | 0 | 3 | 0 |  |  | N |  | 0 | 0 | 0 | 3 | 486 | P3 – Medium
DRLE-RFI-0130 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – Downtown Redmond Station | Civil and systems drawings differ on grounding/bonding of guideway girder diaphragm for stray-current control at Downtown Redmond Station. Request governing detail and responsibility for installation. | Design Manager | 2022-01-21 | 7 | Routine | N | Y | N | 6 | Design-Build EOR / ST Design Review | 4 | 2022-01-31 | 9 | N | 2 | 2 | 2022-02-07 | 17 | Closed | 9 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 642 | P3 – Medium
DRLE-RFI-0131 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Embedded conduit stub-ups – Sammamish River bridge | Systems contractor requires 5-in. PVC conduit stub-ups for traction power feeder at Sammamish River bridge not provided in civil S-676. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Project Engineer | 2022-01-24 | 7 | Routine | Y | N | N | 7 | Design-Build EOR / ST Design Review | 3 | 2022-01-31 | 6 | Y | 0 | 2 | 2022-02-07 | 12 | Closed | 0 | 0 | 0 | 59000 | 109000 | N |  | 0 | 0 | 0 | 0 | 1290 | P4 – Low
DRLE-RFI-0132 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at Marymoor Village Station, citing procurement lead time. Product data attached. | Field Engineer | 2022-01-24 | 7 | Routine | N | N | N | 2 | Design-Build EOR / ST Design Review | 1 | 2022-01-31 | 5 | Y | 0 | 1 | 2022-01-31 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1291 | P4 – Low
DRLE-RFI-0133 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with fiber communications duct bank at Marymoor Village parking garage | Potholing at Sta. 2256+33 located a fiber communications duct bank in conflict with the proposed station canopy support. Utility is not shown on S-661. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Project Engineer | 2022-01-25 | 7 | Routine | Y | N | N | 8 | Design-Build EOR / ST Design Review | 1 | 2022-02-01 | 7 | Y | 0 | 1 | 2022-02-01 | 7 | Closed | 0 | 0 | 0 | 74000 | 138000 | Y | DRLE-CO-025 | 87100 | 0 | 0 | 0 | 1292 | P4 – Low
DRLE-RFI-0134 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with abandoned utility vault at Leary Way crossing | Potholing at Sta. 1274+45 located a abandoned utility vault in conflict with the proposed duct bank encasement. Utility is not shown on E-222. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Project Engineer | 2022-01-28 | 7 | Expedite | Y | N | N | 6 | Design-Build EOR / ST Design Review | 1 | 2022-02-04 | 7 | Y | 0 | 1 | 2022-02-04 | 7 | Closed | 0 | 0 | 0 | 2122000 | 3961000 | Y | DRLE-CO-026 | 680280 | 632950 | 2.9 | 47 | 106 | P1 – Critical
DRLE-RFI-0135 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – alternate epoxy-coated rebar supplier | Contractor requests approval to substitute alternate epoxy-coated rebar supplier for specified epoxy-coated rebar on work at Marymoor Village Station, citing procurement lead time. Product data attached. | Project Engineer | 2022-02-07 | 7 | Routine | N | N | N | 1 | Design-Build EOR / ST Design Review | 2 | 2022-02-15 | 8 | N | 1 | 1 | 2022-02-15 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1293 | P4 – Low
DRLE-RFI-0136 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – stair core wall and pedestrian ramp at Marymoor Village parking garage | Interference between stair core wall and pedestrian ramp at Marymoor Village parking garage per M-769. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2022-02-10 | 7 | Routine | N | Y | Y | 6 | Design-Build EOR / ST Design Review | 1 | 2022-02-15 | 5 | Y | 0 | 1 | 2022-02-15 | 5 | Closed | 16 | 12 | 0 |  |  | N |  | 0 | 0 | 0 | 12 | 382 | P3 – Medium
DRLE-RFI-0137 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 24-in. sanitary sewer at Bear Creek crossing | Potholing at Sta. 2390+21 located a 24-in. sanitary sewer in conflict with the proposed stair core wall. Utility is not shown on A-870. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Project Manager | 2022-02-14 | 7 | Urgent | Y | Y | Y | 5 | Design-Build EOR / ST Design Review | 4 | 2022-02-17 | 3 | Y | 0 | 2 | 2022-03-07 | 21 | Closed | 5 | 3 | 0 | 23000 | 43000 | Y | DRLE-CO-026 | 21120 | 19650 | 0.1 | 37.1 | 291 | P2 – High
DRLE-RFI-0138 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 8-in. high-pressure gas main at Redmond Way (SR 202) crossing | Potholing at Sta. 1652+48 located a 8-in. high-pressure gas main in conflict with the proposed column reinforcement. Utility is not shown on S-840. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Field Engineer | 2022-02-17 | 7 | Routine | N | Y | N | 7 | Design-Build EOR / ST Design Review | 2 | 2022-03-03 | 14 | N | 7 | 1 | 2022-03-03 | 14 | Closed | 7 | 0 | 8 |  |  | N |  | 0 | 0 | 0 | 1.8 | 546 | P3 – Medium
DRLE-RFI-0139 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bear Creek crossing: perched groundwater | During excavation at Bear Creek crossing (Sta. 2064+63) the contractor encountered perched groundwater at approx. elevation 209 ft, not shown on the GBR or M-699. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Project Engineer | 2022-02-18 | 7 | Routine | Y | Y | N | 6 | Design-Build EOR / ST Design Review | 1 | 2022-02-23 | 5 | Y | 0 | 1 | 2022-02-23 | 5 | Closed | 20 | 0 | 12 | 103000 | 193000 | N |  | 0 | 0 | 0 | 2.7 | 497 | P3 – Medium
DRLE-RFI-0140 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on critical areas permit – Sammamish River bridge | WSDOT review comments on the critical areas permit require changes to the duct bank encasement at Sammamish River bridge. Request direction on scope impacts and whether comments are within the contract requirements. | Project Manager | 2022-03-10 | 7 | Expedite | N | Y | N | 3 | City of Redmond / ST Third-Party Mgmt | 5 | 2022-03-24 | 14 | N | 7 | 1 | 2022-03-24 | 14 | Closed | 14 | 0 | 7 |  |  | N |  | 0 | 0 | 0 | 1.6 | 560 | P3 – Medium
DRLE-RFI-0141 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Stormwater facility revision – Leary Way crossing | Field conditions at Leary Way crossing require changes to temporary erosion and sediment control or stormwater facility per S-332. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2022-03-11 | 7 | Expedite | Y | Y | Y | 6 | Design-Build EOR / ST Design Review | 2 | 2022-03-21 | 8 | N | 1 | 1 | 2022-03-21 | 8 | Closed | 8 | 5 | 0 | 819000 | 1528000 | N |  | 0 | 0 | 0 | 5 | 446 | P3 – Medium
DRLE-RFI-0142 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | King County Parks comment on clearing and grading permit – Bear Creek crossing | King County Parks review comments on the clearing and grading permit require changes to the column reinforcement at Bear Creek crossing. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2022-03-11 | 7 | Routine | N | Y | N | 0 | King County Parks / ST Third-Party Mgmt | 4 | 2022-03-25 | 14 | N | 7 | 1 | 2022-03-25 | 14 | Closed | 13 | 0 | 11 |  |  | N |  | 0 | 0 | 0 | 2.4 | 502 | P3 – Medium
DRLE-RFI-0143 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – Redmond Way (SR 202) crossing | Systems contractor requires 3-in. PVC conduit stub-ups for traction power feeder at Redmond Way (SR 202) crossing not provided in civil C-384. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Scheduler | 2022-03-17 | 7 | Routine | N | Y | N | 0 | Design-Build EOR / ST Design Review | 2 | 2022-03-28 | 9 | N | 2 | 1 | 2022-03-28 | 9 | Closed | 3 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 819 | P4 – Low
DRLE-RFI-0144 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Grounding/bonding and stray-current detail – Marymoor Park interface | Civil and systems drawings differ on grounding/bonding of platform edge slab for stray-current control at Marymoor Park interface. Request governing detail and responsibility for installation. | Field Engineer | 2022-03-21 | 7 | Routine | N | N | N | 2 | Design-Build EOR / ST Design Review | 1 | 2022-03-28 | 5 | Y | 0 | 1 | 2022-03-28 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1294 | P4 – Low
DRLE-RFI-0145 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Crane staging in right-of-way – Marymoor Park interface | Contractor requests approval of an alternate traffic/staging plan at Marymoor Park interface: temporary lane shift. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Design Manager | 2022-03-28 | 7 | Expedite | Y | N | N | 5 | Design-Build EOR / ST Design Review | 2 | 2022-04-01 | 4 | Y | 0 | 1 | 2022-04-01 | 4 | Closed | 0 | 0 | 0 | 31000 | 57000 | N |  | 0 | 0 | 0 | 0 | 1295 | P4 – Low
DRLE-RFI-0146 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Property owner access/restoration requirement – Sammamish River bridge | Adjacent property owner has requested additional restoration and access provisions at Sammamish River bridge beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Project Engineer | 2022-04-01 | 7 | Urgent | N | N | Y | 5 | City of Redmond / ST Third-Party Mgmt | 2 | 2022-04-11 | 8 | N | 1 | 1 | 2022-04-11 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1296 | P4 – Low
DRLE-RFI-0147 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 24-in. sanitary sewer at Bear Creek crossing | Potholing at Sta. 1033+57 located a 24-in. sanitary sewer in conflict with the proposed stair core wall. Utility is not shown on C-789. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Field Engineer | 2022-04-05 | 7 | Routine | Y | N | N | 3 | Design-Build EOR / ST Design Review | 1 | 2022-04-08 | 3 | Y | 0 | 1 | 2022-04-08 | 3 | Closed | 0 | 0 | 0 | 29000 | 55000 | Y | DRLE-CO-027 | 27100 | 0 | 0 | 0 | 1297 | P4 – Low
DRLE-RFI-0148 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – SE Redmond aerial guideway | Systems contractor requires 5-in. PVC conduit stub-ups for tunnel emergency phone at SE Redmond aerial guideway not provided in civil C-730. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Design Manager | 2022-04-15 | 7 | Routine | N | N | N | 1 | Design-Build EOR / ST Design Review | 4 | 2022-05-02 | 15 | N | 8 | 2 | 2022-05-16 | 29 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1298 | P4 – Low
DRLE-RFI-0149 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Property owner access/restoration requirement – Marymoor Village parking garage | Adjacent property owner has requested additional restoration and access provisions at Marymoor Village parking garage beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Field Engineer | 2022-04-19 | 7 | Routine | N | Y | N | 3 | City of Redmond / ST Third-Party Mgmt | 4 | 2022-04-25 | 4 | Y | 0 | 1 | 2022-04-25 | 4 | Closed | 2 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 747 | P3 – Medium
DRLE-RFI-0150 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Property owner access/restoration requirement – Sammamish River bridge | Adjacent property owner has requested additional restoration and access provisions at Sammamish River bridge beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Design Manager | 2022-04-25 | 7 | Expedite | N | N | Y | 7 | WSDOT / ST Third-Party Mgmt | 3 | 2022-05-05 | 10 | N | 3 | 1 | 2022-05-05 | 10 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1299 | P4 – Low
DRLE-RFI-0151 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Marymoor Park interface: an unmapped abandoned storm line | During excavation at Marymoor Park interface (Sta. 1840+35) the contractor encountered an unmapped abandoned storm line, not shown on the GBR or E-548. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Superintendent | 2022-04-27 | 7 | Expedite | Y | Y | N | 3 | Design-Build EOR / ST Design Review | 1 | 2022-05-04 | 7 | Y | 0 | 1 | 2022-05-04 | 7 | Closed | 8 | 0 | 5 | 1505000 | 2809000 | N |  | 0 | 0 | 0 | 1.1 | 597 | P3 – Medium
DRLE-RFI-0152 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Night work and noise variance – Leary Way crossing | Contractor requests approval of an alternate traffic/staging plan at Leary Way crossing: temporary lane shift. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Project Engineer | 2022-05-02 | 7 | Routine | Y | Y | N | 7 | Design-Build EOR / ST Design Review | 1 | 2022-05-09 | 5 | Y | 0 | 2 | 2022-05-23 | 21 | Closed | 3 | 0 | 2 | 45000 | 85000 | Y | DRLE-CO-028 | 57100 | 45200 | 3 | 38.4 | 268 | P2 – High
DRLE-RFI-0153 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 30-in. storm drain at Sammamish River bridge | Potholing at Sta. 1296+77 located a 30-in. storm drain in conflict with the proposed bearing pad/embed plate. Utility is not shown on S-529. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2022-05-02 | 7 | Routine | Y | Y | N | 3 | Design-Build EOR / ST Design Review | 2 | 2022-05-10 | 8 | N | 1 | 1 | 2022-05-10 | 8 | Closed | 2 | 0 | 1 | 178000 | 333000 | N |  | 0 | 0 | 0 | 0.2 | 820 | P4 – Low
DRLE-RFI-0154 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | King County Parks comment on critical areas permit – SE Redmond aerial guideway | King County Parks review comments on the critical areas permit require changes to the stair core wall at SE Redmond aerial guideway. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2022-05-05 | 7 | Routine | N | Y | N | 1 | WSDOT / ST Third-Party Mgmt | 2 | 2022-05-12 | 7 | Y | 0 | 1 | 2022-05-12 | 7 | Closed | 8 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 643 | P3 – Medium
DRLE-RFI-0155 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with PSE distribution duct bank at Downtown Redmond Station | Potholing at Sta. 2305+03 located a PSE distribution duct bank in conflict with the proposed stair core wall. Utility is not shown on C-261. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Project Manager | 2022-05-09 | 7 | Urgent | Y | Y | Y | 4 | Design-Build EOR / ST Design Review | 1 | 2022-05-12 | 3 | Y | 0 | 1 | 2022-05-12 | 3 | Closed | 17 | 6 | 0 | 42000 | 79000 | N |  | 0 | 0 | 0 | 6 | 428 | P3 – Medium
DRLE-RFI-0156 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Station finish detail – Sammamish River bridge | Request to clarify finish/connection detail on A-528 at Sammamish River bridge. Includes coordination with art program embeds and handrail sleeves as applicable. | Superintendent | 2022-05-10 | 7 | Expedite | N | N | N | 7 | Design-Build EOR / ST Design Review | 1 | 2022-05-12 | 2 | Y | 0 | 1 | 2022-05-12 | 2 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1300 | P4 – Low
DRLE-RFI-0157 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | Property owner access/restoration requirement – Downtown Redmond Station | Adjacent property owner has requested additional restoration and access provisions at Downtown Redmond Station beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Design Manager | 2022-05-16 | 7 | Routine | N | N | N | 6 | City of Redmond / ST Third-Party Mgmt | 3 | 2022-05-25 | 9 | N | 2 | 1 | 2022-05-25 | 9 | Closed | 0 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 821 | P4 – Low
DRLE-RFI-0158 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Station finish detail – Bear Creek crossing | Request to clarify finish/connection detail on C-768 at Bear Creek crossing. Includes coordination with art program embeds and handrail sleeves as applicable. | Superintendent | 2022-05-16 | 7 | Routine | N | N | N | 1 | Design-Build EOR / ST Design Review | 1 | 2022-05-23 | 5 | Y | 0 | 1 | 2022-05-23 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1301 | P4 – Low
DRLE-RFI-0159 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with fiber communications duct bank at Leary Way crossing | Potholing at Sta. 1637+43 located a fiber communications duct bank in conflict with the proposed guideway girder diaphragm. Utility is not shown on A-762. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Project Engineer | 2022-05-26 | 7 | Routine | N | N | N | 5 | Design-Build EOR / ST Design Review | 1 | 2022-05-30 | 4 | Y | 0 | 1 | 2022-05-30 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1302 | P4 – Low
DRLE-RFI-0160 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – retaining wall footing at Sammamish River bridge | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-638 for emergency stair pressurization at Sammamish River bridge. Request direction on compliant detail. | Project Engineer | 2022-05-30 | 7 | Routine | N | Y | N | 4 | Design-Build EOR / ST Design Review | 5 | 2022-06-06 | 7 | Y | 0 | 1 | 2022-06-06 | 7 | Closed | 4 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 686 | P3 – Medium
DRLE-RFI-0161 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Drawing/spec discrepancy – SE Redmond aerial guideway | Request clarification of 00 72 00 General Conditions and A-727: dimension/notes appear inconsistent or omitted for the work at SE Redmond aerial guideway. | Superintendent | 2022-05-31 | 7 | Expedite | N | N | N | 6 | Design-Build EOR / ST Design Review | 2 | 2022-06-06 | 4 | Y | 0 | 1 | 2022-06-06 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1303 | P4 – Low
DRLE-RFI-0162 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 12-in. ductile iron water main at SE Redmond aerial guideway | Potholing at Sta. 981+32 located a 12-in. ductile iron water main in conflict with the proposed platform edge slab. Utility is not shown on E-542. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Project Manager | 2022-06-06 | 7 | Routine | N | Y | N | 5 | Design-Build EOR / ST Design Review | 1 | 2022-06-13 | 6 | Y | 0 | 1 | 2022-06-13 | 6 | Closed | 9 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 644 | P3 – Medium
DRLE-RFI-0163 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 12-in. ductile iron water main at Marymoor Village Station | Potholing at Sta. 1734+38 located a 12-in. ductile iron water main in conflict with the proposed stair core wall. Utility is not shown on S-884. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Field Engineer | 2022-06-24 | 7 | Expedite | N | N | N | 8 | Design-Build EOR / ST Design Review | 1 | 2022-06-28 | 4 | Y | 0 | 1 | 2022-06-28 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1304 | P4 – Low
DRLE-RFI-0164 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Ocs Pole location conflict at Sta. 941+66 | Proposed OCS pole foundation location at Sta. 941+66 conflicts with pedestrian ramp; offset of 11 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2022-06-30 | 7 | Routine | Y | N | Y | 7 | Design-Build EOR / ST Design Review | 2 | 2022-07-07 | 7 | Y | 0 | 1 | 2022-07-07 | 7 | Closed | 0 | 0 | 0 | 37000 | 70000 | Y | DRLE-CO-029 | 78800 | 60200 | 0 | 37.9 | 278 | P2 – High
DRLE-RFI-0165 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Dimensional discrepancy – Redmond Way (SR 202) crossing | A-343 shows a 13 ft-4 in. dimension for the retaining wall footing; structural sheet S-341 shows a different value. Request clarification before fabrication/rebar release. | Scheduler | 2022-07-08 | 7 | Routine | Y | Y | N | 6 | Design-Build EOR / ST Design Review | 2 | 2022-07-13 | 5 | Y | 0 | 1 | 2022-07-13 | 5 | Closed | 7 | 0 | 3 | 293000 | 547000 | Y | DRLE-CO-030 | 391900 | 275900 | 4 | 45.2 | 137 | P2 – High
DRLE-RFI-0166 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | Property owner access/restoration requirement – Redmond Way (SR 202) crossing | Adjacent property owner has requested additional restoration and access provisions at Redmond Way (SR 202) crossing beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Scheduler | 2022-07-11 | 7 | Routine | N | Y | N | 2 | WSDOT / ST Third-Party Mgmt | 3 | 2022-07-25 | 13 | N | 6 | 1 | 2022-07-25 | 13 | Closed | 5 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 687 | P3 – Medium
DRLE-RFI-0167 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | In-water work window – Redmond Way (SR 202) crossing | Field conditions at Redmond Way (SR 202) crossing require changes to temporary erosion and sediment control or stormwater facility per S-564. Request direction considering critical-areas conditions and permit requirements. | Project Engineer | 2022-07-21 | 7 | Expedite | N | Y | N | 8 | Design-Build EOR / ST Design Review | 1 | 2022-07-25 | 3 | Y | 0 | 1 | 2022-07-25 | 3 | Closed | 2 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1305 | P4 – Low
DRLE-RFI-0168 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | In-water work window – Marymoor Village Station | Field conditions at Marymoor Village Station require changes to temporary erosion and sediment control or stormwater facility per E-843. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2022-07-27 | 7 | Routine | N | Y | N | 7 | Design-Build EOR / ST Design Review | 3 | 2022-08-01 | 5 | Y | 0 | 1 | 2022-08-01 | 5 | Closed | 5 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 645 | P3 – Medium
DRLE-RFI-0169 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Canopy/glazing connection – Leary Way crossing | Request to clarify finish/connection detail on M-876 at Leary Way crossing. Includes coordination with art program embeds and handrail sleeves as applicable. | Field Engineer | 2022-08-01 | 7 | Expedite | Y | N | N | 6 | Design-Build EOR / ST Design Review | 1 | 2022-08-05 | 4 | Y | 0 | 1 | 2022-08-05 | 4 | Closed | 0 | 0 | 0 | 84000 | 157000 | Y | DRLE-CO-031 | 85200 | 67500 | 0 | 38.3 | 270 | P2 – High
DRLE-RFI-0170 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Property owner access/restoration requirement – Redmond Way (SR 202) crossing | Adjacent property owner has requested additional restoration and access provisions at Redmond Way (SR 202) crossing beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Project Engineer | 2022-08-02 | 7 | Routine | N | Y | Y | 7 | City of Redmond / ST Third-Party Mgmt | 2 | 2022-08-30 | 28 | N | 21 | 2 | 2022-09-12 | 40 | Closed | 3 | 2 | 0 |  |  | N |  | 0 | 0 | 0 | 2 | 535 | P3 – Medium
DRLE-RFI-0171 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Crane staging in right-of-way – Downtown Redmond Station | Contractor requests approval of an alternate traffic/staging plan at Downtown Redmond Station: temporary lane shift. Existing work restrictions limit production; requests ST/City of Redmond concurrence. | Design Manager | 2022-08-10 | 7 | Routine | Y | N | N | 6 | Design-Build EOR / ST Design Review | 1 | 2022-08-12 | 2 | Y | 0 | 1 | 2022-08-12 | 2 | Closed | 0 | 0 | 0 | 118000 | 220000 | N |  | 0 | 0 | 0 | 0 | 1306 | P4 – Low
DRLE-RFI-0172 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Canopy/glazing connection – Sammamish River bridge | Request to clarify finish/connection detail on E-197 at Sammamish River bridge. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2022-08-12 | 7 | Routine | N | N | N | 0 | Design-Build EOR / ST Design Review | 1 | 2022-08-15 | 3 | Y | 0 | 1 | 2022-08-15 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1307 | P4 – Low
DRLE-RFI-0173 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with fiber communications duct bank at Downtown Redmond Station | Potholing at Sta. 1279+90 located a fiber communications duct bank in conflict with the proposed column reinforcement. Utility is not shown on S-516. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Project Manager | 2022-08-15 | 7 | Routine | Y | N | N | 6 | Design-Build EOR / ST Design Review | 1 | 2022-09-01 | 17 | N | 10 | 1 | 2022-09-01 | 17 | Closed | 0 | 0 | 3 | 298000 | 556000 | Y | DRLE-CO-032 | 252400 | 0 | 0 | 0.7 | 688 | P3 – Medium
DRLE-RFI-0174 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at SE Redmond aerial guideway: loose granular fill below planned bearing elevation | During excavation at SE Redmond aerial guideway (Sta. 1621+43) the contractor encountered loose granular fill below planned bearing elevation, not shown on the GBR or S-326. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Project Engineer | 2022-08-24 | 7 | Routine | Y | N | Y | 5 | Design-Build EOR / ST Design Review | 3 | 2022-09-01 | 8 | N | 1 | 1 | 2022-09-01 | 8 | Closed | 0 | 0 | 0 | 1158000 | 2162000 | N |  | 0 | 0 | 0 | 0 | 1308 | P4 – Low
DRLE-RFI-0175 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with abandoned utility vault at Leary Way crossing | Potholing at Sta. 2395+79 located a abandoned utility vault in conflict with the proposed drilled shaft cap. Utility is not shown on C-794. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Field Engineer | 2022-08-29 | 7 | Routine | N | Y | N | 4 | Design-Build EOR / ST Design Review | 1 | 2022-09-26 | 28 | N | 21 | 1 | 2022-09-26 | 28 | Closed | 6 | 0 | 14 |  |  | N |  | 0 | 0 | 0 | 3.1 | 471 | P3 – Medium
DRLE-RFI-0176 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Haul route revision – Sammamish River bridge | Contractor requests approval of an alternate traffic/staging plan at Sammamish River bridge: temporary lane shift. Existing work restrictions limit production; requests ST/King County Parks concurrence. | Project Engineer | 2022-08-29 | 7 | Urgent | Y | N | N | 5 | Design-Build EOR / ST Design Review | 2 | 2022-09-05 | 6 | Y | 0 | 1 | 2022-09-05 | 6 | Closed | 0 | 0 | 0 | 201000 | 375000 | N |  | 0 | 0 | 0 | 0 | 1309 | P4 – Low
DRLE-RFI-0177 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – recycled-content fly ash blend | Contractor requests approval to substitute recycled-content fly ash blend for Type IL cement mix on work at Marymoor Park interface, citing procurement lead time. Product data attached. | Field Engineer | 2022-08-29 | 7 | Routine | N | N | N | 4 | Design-Build EOR / ST Design Review | 2 | 2022-09-05 | 6 | Y | 0 | 1 | 2022-09-05 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1310 | P4 – Low
DRLE-RFI-0178 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – drilled shaft cap and stair core wall at Sammamish River bridge | Interference between drilled shaft cap and stair core wall at Sammamish River bridge per C-693. Required clearance of 4 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Engineer | 2022-09-06 | 7 | Routine | N | N | N | 3 | Design-Build EOR / ST Design Review | 1 | 2022-09-16 | 10 | N | 3 | 1 | 2022-09-16 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1311 | P4 – Low
DRLE-RFI-0179 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – duct bank encasement and platform edge slab at Leary Way crossing | Interference between duct bank encasement and platform edge slab at Leary Way crossing per A-329. Required clearance of 3 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Scheduler | 2022-09-12 | 7 | Routine | N | N | N | 3 | Design-Build EOR / ST Design Review | 4 | 2022-09-15 | 3 | Y | 0 | 1 | 2022-09-15 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1312 | P4 – Low
DRLE-RFI-0180 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | TESC modification – Leary Way crossing | Field conditions at Leary Way crossing require changes to temporary erosion and sediment control or stormwater facility per M-367. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2022-09-12 | 7 | Expedite | N | Y | N | 5 | Design-Build EOR / ST Design Review | 1 | 2022-09-16 | 4 | Y | 0 | 1 | 2022-09-16 | 4 | Closed | 1 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1313 | P4 – Low
DRLE-RFI-0181 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with fiber communications duct bank at Leary Way crossing | Potholing at Sta. 1627+24 located a fiber communications duct bank in conflict with the proposed pedestrian ramp. Utility is not shown on M-446. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Field Engineer | 2022-09-12 | 7 | Expedite | Y | Y | N | 0 | Design-Build EOR / ST Design Review | 1 | 2022-09-15 | 3 | Y | 0 | 1 | 2022-09-15 | 3 | Closed | 3 | 0 | 2 | 1220000 | 2278000 | Y | DRLE-CO-036 | 2021270 | 1444730 | 3.2 | 50.4 | 53 | P1 – Critical
DRLE-RFI-0182 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Stormwater facility revision – Marymoor Village parking garage | Field conditions at Marymoor Village parking garage require changes to temporary erosion and sediment control or stormwater facility per A-169. Request direction considering critical-areas conditions and permit requirements. | Project Engineer | 2022-09-22 | 7 | Expedite | Y | Y | N | 1 | Design-Build EOR / ST Design Review | 2 | 2022-09-28 | 6 | Y | 0 | 1 | 2022-09-28 | 6 | Closed | 3 | 0 | 2 | 255000 | 476000 | N |  | 0 | 0 | 0 | 0.4 | 748 | P3 – Medium
DRLE-RFI-0183 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – stair core wall at SE Redmond aerial guideway | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-407 for emergency stair pressurization at SE Redmond aerial guideway. Request direction on compliant detail. | Scheduler | 2022-09-22 | 7 | Routine | N | N | N | 2 | Design-Build EOR / ST Design Review | 2 | 2022-09-30 | 8 | N | 1 | 1 | 2022-09-30 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1314 | P4 – Low
DRLE-RFI-0184 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – galvanized steel handrail | Contractor requests approval to substitute galvanized steel handrail for stainless steel handrail on work at SE Redmond aerial guideway, citing procurement lead time. Product data attached. | Scheduler | 2022-09-22 | 7 | Expedite | N | N | Y | 5 | Design-Build EOR / ST Design Review | 2 | 2022-09-27 | 5 | Y | 0 | 1 | 2022-09-27 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1315 | P4 – Low
DRLE-RFI-0185 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – retaining wall footing at Bear Creek crossing | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-572 for smoke control damper at Bear Creek crossing. Request direction on compliant detail. | Field Engineer | 2022-09-26 | 7 | Routine | N | N | N | 5 | Design-Build EOR / ST Design Review | 1 | 2022-10-05 | 9 | N | 2 | 1 | 2022-10-05 | 9 | Closed | 0 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 822 | P4 – Low
DRLE-RFI-0186 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Grounding/bonding and stray-current detail – Leary Way crossing | Civil and systems drawings differ on grounding/bonding of stair core wall for stray-current control at Leary Way crossing. Request governing detail and responsibility for installation. | Design Manager | 2022-10-03 | 7 | Routine | N | N | N | 3 | Design-Build EOR / ST Design Review | 1 | 2022-10-12 | 9 | N | 2 | 1 | 2022-10-12 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1316 | P4 – Low
DRLE-RFI-0187 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with abandoned utility vault at Bear Creek crossing | Potholing at Sta. 962+17 located a abandoned utility vault in conflict with the proposed stair core wall. Utility is not shown on M-232. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Scheduler | 2022-10-10 | 7 | Expedite | Y | Y | N | 7 | Design-Build EOR / ST Design Review | 2 | 2022-10-14 | 4 | Y | 0 | 1 | 2022-10-14 | 4 | Closed | 3 | 0 | 2 | 300000 | 560000 | Y | DRLE-CO-033 | 537920 | 0 | 0 | 0.4 | 749 | P3 – Medium
DRLE-RFI-0188 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Art embed coordination – Marymoor Village Station | Request to clarify finish/connection detail on A-138 at Marymoor Village Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Scheduler | 2022-10-11 | 7 | Routine | N | Y | N | 2 | Design-Build EOR / ST Design Review | 1 | 2022-10-17 | 4 | Y | 0 | 1 | 2022-10-17 | 4 | Closed | 1 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1317 | P4 – Low
DRLE-RFI-0189 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with fiber communications duct bank at Downtown Redmond Station | Potholing at Sta. 1352+93 located a fiber communications duct bank in conflict with the proposed station canopy support. Utility is not shown on M-808. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Scheduler | 2022-10-11 | 7 | Urgent | Y | Y | N | 1 | Design-Build EOR / ST Design Review | 2 | 2022-10-14 | 3 | Y | 0 | 1 | 2022-10-14 | 3 | Closed | 9 | 0 | 4 | 170000 | 317000 | Y | DRLE-CO-033 | 242980 | 0 | 0 | 0.9 | 646 | P3 – Medium
DRLE-RFI-0190 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Lane closure window request – Marymoor Village Station | Contractor requests approval of an alternate traffic/staging plan at Marymoor Village Station: crane pick over active roadway. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Project Engineer | 2022-10-26 | 7 | Routine | N | N | N | 7 | Design-Build EOR / ST Design Review | 1 | 2022-10-31 | 5 | Y | 0 | 1 | 2022-10-31 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1318 | P4 – Low
DRLE-RFI-0191 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with PSE distribution duct bank at Sammamish River bridge | Potholing at Sta. 1373+19 located a PSE distribution duct bank in conflict with the proposed station canopy support. Utility is not shown on S-327. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Manager | 2022-10-26 | 7 | Routine | Y | N | Y | 0 | Design-Build EOR / ST Design Review | 1 | 2022-11-02 | 7 | Y | 0 | 1 | 2022-11-02 | 7 | Closed | 0 | 0 | 0 | 189000 | 352000 | Y | DRLE-CO-034 | 209270 | 188280 | 1 | 42.2 | 198 | P2 – High
DRLE-RFI-0192 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Night work and noise variance – Leary Way crossing | Contractor requests approval of an alternate traffic/staging plan at Leary Way crossing: crane pick over active roadway. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Superintendent | 2022-10-31 | 7 | Routine | N | N | N | 1 | Design-Build EOR / ST Design Review | 3 | 2022-11-09 | 9 | N | 2 | 1 | 2022-11-09 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1319 | P4 – Low
DRLE-RFI-0193 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Special trackwork layout – SE Redmond aerial guideway | Track layout at Sta. 1480+71 (SE Redmond aerial guideway) differs from the track-structure interface drawing M-422. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2022-11-04 | 7 | Urgent | N | Y | N | 8 | Design-Build EOR / ST Design Review | 1 | 2022-11-07 | 3 | Y | 0 | 1 | 2022-11-07 | 3 | Closed | 1 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 823 | P4 – Low
DRLE-RFI-0194 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 24-in. sanitary sewer at Downtown Redmond Station | Potholing at Sta. 1892+05 located a 24-in. sanitary sewer in conflict with the proposed drilled shaft cap. Utility is not shown on M-821. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Design Manager | 2022-11-07 | 7 | Urgent | Y | N | N | 5 | Design-Build EOR / ST Design Review | 2 | 2022-11-14 | 6 | Y | 0 | 1 | 2022-11-14 | 6 | Closed | 0 | 0 | 0 | 1266000 | 2363000 | Y | DRLE-CO-034 | 982900 | 884340 | 4.5 | 48.7 | 79 | P1 – Critical
DRLE-RFI-0195 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with PSE distribution duct bank at SE Redmond aerial guideway | Potholing at Sta. 1848+66 located a PSE distribution duct bank in conflict with the proposed drilled shaft cap. Utility is not shown on S-291. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Project Manager | 2022-11-11 | 7 | Urgent | Y | Y | N | 8 | Design-Build EOR / ST Design Review | 2 | 2022-11-16 | 5 | Y | 0 | 1 | 2022-11-16 | 5 | Closed | 10 | 0 | 5 | 109000 | 204000 | Y | DRLE-CO-034 | 126130 | 113480 | 0.6 | 41.4 | 210 | P2 – High
DRLE-RFI-0196 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – platform edge slab and column reinforcement at Marymoor Park interface | Interference between platform edge slab and column reinforcement at Marymoor Park interface per S-739. Required clearance of 2 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Manager | 2022-11-23 | 7 | Expedite | Y | Y | N | 5 | Design-Build EOR / ST Design Review | 1 | 2022-11-28 | 4 | Y | 0 | 1 | 2022-11-28 | 4 | Closed | 6 | 0 | 2 | 114000 | 212000 | Y | DRLE-CO-035 | 166500 | 0 | 0 | 0.4 | 750 | P3 – Medium
DRLE-RFI-0197 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Art embed coordination – Leary Way crossing | Request to clarify finish/connection detail on C-887 at Leary Way crossing. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2022-11-28 | 7 | Routine | N | N | N | 1 | Design-Build EOR / ST Design Review | 2 | 2022-12-05 | 5 | Y | 0 | 1 | 2022-12-05 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1320 | P4 – Low
DRLE-RFI-0198 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | WSDOT comment on building permit – Marymoor Village parking garage | WSDOT review comments on the building permit require changes to the duct bank encasement at Marymoor Village parking garage. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2022-11-29 | 7 | Expedite | N | Y | N | 5 | City of Redmond / ST Third-Party Mgmt | 2 | 2022-12-08 | 9 | N | 2 | 2 | 2022-12-26 | 27 | Closed | 11 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 598 | P3 – Medium
DRLE-RFI-0199 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 12-in. ductile iron water main at Bear Creek crossing | Potholing at Sta. 1784+03 located a 12-in. ductile iron water main in conflict with the proposed station canopy support. Utility is not shown on C-289. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Superintendent | 2022-12-05 | 7 | Routine | N | Y | N | 1 | Design-Build EOR / ST Design Review | 2 | 2022-12-14 | 9 | N | 2 | 1 | 2022-12-14 | 9 | Closed | 3 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 751 | P3 – Medium
DRLE-RFI-0200 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Station finish detail – SE Redmond aerial guideway | Request to clarify finish/connection detail on M-685 at SE Redmond aerial guideway. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2022-12-05 | 7 | Urgent | N | N | N | 7 | Design-Build EOR / ST Design Review | 1 | 2022-12-07 | 2 | Y | 0 | 1 | 2022-12-07 | 2 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1321 | P4 – Low
DRLE-RFI-0201 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Art embed coordination – Leary Way crossing | Request to clarify finish/connection detail on C-734 at Leary Way crossing. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2022-12-06 | 7 | Routine | N | N | N | 6 | Design-Build EOR / ST Design Review | 4 | 2022-12-09 | 3 | Y | 0 | 1 | 2022-12-09 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1322 | P4 – Low
DRLE-RFI-0202 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with PSE distribution duct bank at Bear Creek crossing | Potholing at Sta. 2319+77 located a PSE distribution duct bank in conflict with the proposed bearing pad/embed plate. Utility is not shown on M-618. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2022-12-07 | 7 | Urgent | Y | Y | N | 2 | Design-Build EOR / ST Design Review | 1 | 2022-12-12 | 4 | Y | 0 | 1 | 2022-12-12 | 4 | Closed | 3 | 0 | 1 | 814000 | 1519000 | Y | DRLE-CO-036 | 532730 | 380770 | 0.8 | 44.8 | 142 | P2 – High
DRLE-RFI-0203 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 8-in. high-pressure gas main at Downtown Redmond Station | Potholing at Sta. 977+19 located a 8-in. high-pressure gas main in conflict with the proposed drilled shaft cap. Utility is not shown on C-795. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Engineer | 2022-12-19 | 7 | Routine | Y | Y | Y | 2 | Design-Build EOR / ST Design Review | 3 | 2022-12-26 | 7 | Y | 0 | 1 | 2022-12-26 | 7 | Closed | 4 | 2 | 0 | 1806000 | 3372000 | Y | DRLE-CO-037 | 1006300 | 866500 | 1 | 49.5 | 68 | P1 – Critical
DRLE-RFI-0204 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | City of Redmond comment on critical areas permit – Sammamish River bridge | City of Redmond review comments on the critical areas permit require changes to the platform edge slab at Sammamish River bridge. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2022-12-21 | 7 | Routine | Y | Y | Y | 0 | WSDOT / ST Third-Party Mgmt | 3 | 2023-01-02 | 10 | N | 3 | 1 | 2023-01-02 | 10 | Closed | 12 | 10 | 0 | 1108000 | 2068000 | N |  | 0 | 0 | 0 | 10 | 396 | P3 – Medium
DRLE-RFI-0205 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at SE Redmond aerial guideway: loose granular fill below planned bearing elevation | During excavation at SE Redmond aerial guideway (Sta. 2295+36) the contractor encountered loose granular fill below planned bearing elevation, not shown on the GBR or M-593. Work in the area is suspended. Requests direction on over-excavation limits and replacement fill and confirmation of DSC entitlement. | Design Manager | 2022-12-26 | 7 | Expedite | N | Y | Y | 1 | Design-Build EOR / ST Design Review | 3 | 2023-01-02 | 5 | Y | 0 | 1 | 2023-01-02 | 5 | Closed | 6 | 3 | 0 |  |  | N |  | 0 | 0 | 0 | 3 | 487 | P3 – Medium
DRLE-RFI-0206 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Constructability – retaining wall footing sequence at Leary Way crossing | Erection of the retaining wall footing as drawn conflicts with adjacent work and access limits at Leary Way crossing. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Project Engineer | 2022-12-27 | 7 | Urgent | Y | Y | N | 5 | Design-Build EOR / ST Design Review | 1 | 2022-12-29 | 2 | Y | 0 | 1 | 2022-12-29 | 2 | Closed | 4 | 0 | 1 | 251000 | 469000 | N |  | 0 | 0 | 0 | 0.2 | 824 | P4 – Low
DRLE-RFI-0207 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Crane staging in right-of-way – Leary Way crossing | Contractor requests approval of an alternate traffic/staging plan at Leary Way crossing: temporary lane shift. Existing work restrictions limit production; requests ST/City of Redmond concurrence. | Project Engineer | 2022-12-30 | 7 | Routine | N | Y | Y | 5 | Design-Build EOR / ST Design Review | 1 | 2023-01-03 | 4 | Y | 0 | 1 | 2023-01-03 | 4 | Closed | 11 | 4 | 0 |  |  | N |  | 0 | 0 | 0 | 4 | 465 | P3 – Medium
DRLE-RFI-0208 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – drilled shaft cap at Leary Way crossing | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-106 for standpipe connection at Leary Way crossing. Request direction on compliant detail. | Superintendent | 2023-01-06 | 7 | Routine | N | N | N | 2 | Design-Build EOR / ST Design Review | 3 | 2023-01-12 | 6 | Y | 0 | 1 | 2023-01-12 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1323 | P4 – Low
DRLE-RFI-0209 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Track slab/expansion joint interface – Sammamish River bridge | Track layout at Sta. 1834+01 (Sammamish River bridge) differs from the track-structure interface drawing M-410. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2023-01-09 | 7 | Expedite | N | N | N | 8 | Design-Build EOR / ST Design Review | 1 | 2023-01-12 | 3 | Y | 0 | 1 | 2023-01-12 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1324 | P4 – Low
DRLE-RFI-0210 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Marymoor Park interface: abandoned timber piles | During excavation at Marymoor Park interface (Sta. 1189+39) the contractor encountered abandoned timber piles, not shown on the GBR or E-690. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Design Manager | 2023-01-09 | 7 | Routine | Y | N | Y | 1 | Design-Build EOR / ST Design Review | 1 | 2023-01-16 | 7 | Y | 0 | 1 | 2023-01-16 | 7 | Closed | 0 | 0 | 0 | 5395000 | 10070000 | Y | DRLE-CO-038 | 5199900 | 0 | 0 | 0 | 1325 | P4 – Low
DRLE-RFI-0211 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | King County Parks comment on right-of-way use permit – Leary Way crossing | King County Parks review comments on the right-of-way use permit require changes to the retaining wall footing at Leary Way crossing. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2023-01-16 | 7 | Routine | N | N | N | 5 | King County Parks / ST Third-Party Mgmt | 4 | 2023-01-23 | 7 | Y | 0 | 1 | 2023-01-23 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1326 | P4 – Low
DRLE-RFI-0212 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bear Creek crossing: loose granular fill below planned bearing elevation | During excavation at Bear Creek crossing (Sta. 1584+25) the contractor encountered loose granular fill below planned bearing elevation, not shown on the GBR or C-402. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Project Manager | 2023-01-16 | 7 | Routine | Y | Y | N | 2 | Design-Build EOR / ST Design Review | 2 | 2023-01-25 | 9 | N | 2 | 2 | 2023-02-14 | 29 | Closed | 1 | 0 | 1 | 129000 | 240000 | Y | DRLE-CO-039 | 314900 | 225200 | 1 | 43 | 179 | P2 – High
DRLE-RFI-0213 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | King County Parks comment on right-of-way use permit – Marymoor Village parking garage | King County Parks review comments on the right-of-way use permit require changes to the stair core wall at Marymoor Village parking garage. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2023-01-20 | 7 | Routine | Y | Y | N | 3 | King County Parks / ST Third-Party Mgmt | 2 | 2023-01-26 | 6 | Y | 0 | 2 | 2023-02-14 | 25 | Closed | 4 | 0 | 3 | 217000 | 405000 | Y | DRLE-CO-040 | 236200 | 67500 | 1 | 39.3 | 254 | P2 – High
DRLE-RFI-0214 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Station finish detail – SE Redmond aerial guideway | Request to clarify finish/connection detail on E-216 at SE Redmond aerial guideway. Includes coordination with art program embeds and handrail sleeves as applicable. | Scheduler | 2023-01-23 | 7 | Routine | N | N | N | 0 | Design-Build EOR / ST Design Review | 2 | 2023-02-01 | 9 | N | 2 | 1 | 2023-02-01 | 9 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1327 | P4 – Low
DRLE-RFI-0215 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Grounding/bonding and stray-current detail – Downtown Redmond Station | Civil and systems drawings differ on grounding/bonding of drilled shaft cap for stray-current control at Downtown Redmond Station. Request governing detail and responsibility for installation. | Field Engineer | 2023-01-30 | 7 | Routine | N | Y | N | 6 | Design-Build EOR / ST Design Review | 4 | 2023-02-06 | 5 | Y | 0 | 1 | 2023-02-06 | 5 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 825 | P4 – Low
DRLE-RFI-0216 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Station finish detail – Redmond Way (SR 202) crossing | Request to clarify finish/connection detail on A-646 at Redmond Way (SR 202) crossing. Includes coordination with art program embeds and handrail sleeves as applicable. | Project Engineer | 2023-02-03 | 7 | Expedite | N | Y | N | 0 | Design-Build EOR / ST Design Review | 5 | 2023-02-06 | 3 | Y | 0 | 1 | 2023-02-06 | 3 | Closed | 1 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 826 | P4 – Low
DRLE-RFI-0217 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | Property owner access/restoration requirement – Leary Way crossing | Adjacent property owner has requested additional restoration and access provisions at Leary Way crossing beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Superintendent | 2023-02-06 | 7 | Urgent | Y | Y | Y | 2 | King County Parks / ST Third-Party Mgmt | 2 | 2023-02-17 | 11 | N | 4 | 1 | 2023-02-17 | 11 | Closed | 12 | 8 | 0 | 19000 | 35000 | N |  | 0 | 0 | 0 | 8 | 414 | P3 – Medium
DRLE-RFI-0218 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Special trackwork layout – Redmond Way (SR 202) crossing | Track layout at Sta. 2300+81 (Redmond Way (SR 202) crossing) differs from the track-structure interface drawing A-196. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Field Engineer | 2023-02-06 | 7 | Expedite | N | N | Y | 5 | Design-Build EOR / ST Design Review | 1 | 2023-02-09 | 3 | Y | 0 | 1 | 2023-02-09 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1328 | P4 – Low
DRLE-RFI-0219 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Downtown Redmond Station | Systems contractor requires 3-in. PVC conduit stub-ups for tunnel emergency phone at Downtown Redmond Station not provided in civil C-568. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2023-02-06 | 7 | Routine | N | Y | N | 1 | Design-Build EOR / ST Design Review | 2 | 2023-02-20 | 12 | N | 5 | 1 | 2023-02-20 | 12 | Closed | 1 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1329 | P4 – Low
DRLE-RFI-0220 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Stormwater facility revision – Marymoor Village Station | Field conditions at Marymoor Village Station require changes to temporary erosion and sediment control or stormwater facility per E-808. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2023-02-08 | 7 | Urgent | N | Y | N | 1 | Design-Build EOR / ST Design Review | 3 | 2023-02-13 | 5 | Y | 0 | 1 | 2023-02-13 | 5 | Closed | 17 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 647 | P3 – Medium
DRLE-RFI-0221 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with fiber communications duct bank at Leary Way crossing | Potholing at Sta. 2079+45 located a fiber communications duct bank in conflict with the proposed retaining wall footing. Utility is not shown on S-351. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Project Engineer | 2023-02-08 | 7 | Routine | Y | Y | N | 2 | Design-Build EOR / ST Design Review | 1 | 2023-02-13 | 4 | Y | 0 | 2 | 2023-02-24 | 16 | Closed | 8 | 0 | 5 | 361000 | 675000 | Y | DRLE-CO-041 | 430800 | 308800 | 4 | 46 | 124 | P2 – High
DRLE-RFI-0222 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – guideway girder diaphragm at Marymoor Village parking garage | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-732 for fire alarm device layout at Marymoor Village parking garage. Request direction on compliant detail. | Design Manager | 2023-02-16 | 7 | Routine | N | Y | N | 6 | Design-Build EOR / ST Design Review | 3 | 2023-02-23 | 7 | Y | 0 | 1 | 2023-02-23 | 7 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1330 | P4 – Low
DRLE-RFI-0223 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Canopy/glazing connection – SE Redmond aerial guideway | Request to clarify finish/connection detail on A-600 at SE Redmond aerial guideway. Includes coordination with art program embeds and handrail sleeves as applicable. | Superintendent | 2023-02-20 | 7 | Expedite | N | N | N | 8 | Design-Build EOR / ST Design Review | 1 | 2023-02-27 | 7 | Y | 0 | 1 | 2023-02-27 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1331 | P4 – Low
DRLE-RFI-0224 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – recycled-content fly ash blend | Contractor requests approval to substitute recycled-content fly ash blend for Type IL cement mix on work at Marymoor Village parking garage, citing procurement lead time. Product data attached. | Field Engineer | 2023-02-27 | 7 | Routine | Y | Y | N | 3 | Design-Build EOR / ST Design Review | 1 | 2023-03-06 | 6 | Y | 0 | 1 | 2023-03-06 | 6 | Closed | 1 | 0 | 1 | 11000 | 20000 | Y | DRLE-CO-042 | 22900 | 15800 | 0 | 33.5 | 323 | P2 – High
DRLE-RFI-0225 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Stormwater facility revision – Leary Way crossing | Field conditions at Leary Way crossing require changes to temporary erosion and sediment control or stormwater facility per E-406. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2023-03-03 | 7 | Routine | Y | N | N | 7 | Design-Build EOR / ST Design Review | 2 | 2023-03-28 | 25 | N | 18 | 2 | 2023-04-10 | 38 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1332 | P4 – Low
DRLE-RFI-0226 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – pedestrian ramp at Sammamish River bridge | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-574 for standpipe connection at Sammamish River bridge. Request direction on compliant detail. | Design Manager | 2023-03-22 | 7 | Routine | Y | Y | Y | 2 | Design-Build EOR / ST Design Review | 1 | 2023-04-04 | 13 | N | 6 | 1 | 2023-04-04 | 13 | Closed | 11 | 9 | 0 | 110000 | 206000 | N |  | 0 | 0 | 0 | 9 | 405 | P3 – Medium
DRLE-RFI-0227 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | Property owner access/restoration requirement – Leary Way crossing | Adjacent property owner has requested additional restoration and access provisions at Leary Way crossing beyond the right-of-way agreement. Contractor requests direction from Sound Transit before proceeding. | Field Engineer | 2023-03-24 | 7 | Urgent | N | N | Y | 4 | WSDOT / ST Third-Party Mgmt | 4 | 2023-04-24 | 30 | N | 23 | 1 | 2023-04-24 | 30 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1333 | P4 – Low
DRLE-RFI-0228 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Lane closure window request – Marymoor Park interface | Contractor requests approval of an alternate traffic/staging plan at Marymoor Park interface: crane pick over active roadway. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Design Manager | 2023-03-27 | 7 | Routine | N | Y | N | 0 | Design-Build EOR / ST Design Review | 4 | 2023-04-03 | 5 | Y | 0 | 1 | 2023-04-03 | 5 | Closed | 8 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 752 | P3 – Medium
DRLE-RFI-0229 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | City of Redmond comment on building permit – Bear Creek crossing | City of Redmond review comments on the building permit require changes to the duct bank encasement at Bear Creek crossing. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2023-03-28 | 7 | Urgent | N | Y | N | 6 | WSDOT / ST Third-Party Mgmt | 4 | 2023-04-03 | 5 | Y | 0 | 2 | 2023-04-17 | 20 | Closed | 10 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 648 | P3 – Medium
DRLE-RFI-0230 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Leary Way crossing | Systems contractor requires 4-in. PVC conduit stub-ups for traction power feeder at Leary Way crossing not provided in civil M-305. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2023-04-03 | 7 | Expedite | Y | Y | N | 6 | Design-Build EOR / ST Design Review | 2 | 2023-04-19 | 16 | N | 9 | 1 | 2023-04-19 | 16 | Closed | 2 | 0 | 3 | 163000 | 304000 | Y | DRLE-CO-047 | 233580 | 208290 | 1 | 43.2 | 175 | P2 – High
DRLE-RFI-0231 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Ocs Pole location conflict at Sta. 2367+50 | Proposed OCS pole foundation location at Sta. 2367+50 conflicts with pedestrian ramp; offset of 4 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2023-04-07 | 7 | Routine | Y | Y | N | 4 | Design-Build EOR / ST Design Review | 5 | 2023-05-08 | 31 | N | 24 | 1 | 2023-05-08 | 31 | Closed | 3 | 0 | 2 | 280000 | 523000 | Y | DRLE-CO-044 | 301600 | 301600 | 2 | 44.6 | 147 | P2 – High
DRLE-RFI-0232 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Signal Case location conflict at Sta. 1090+41 | Proposed signal case foundation location at Sta. 1090+41 conflicts with guideway girder diaphragm; offset of 8 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Project Engineer | 2023-04-11 | 7 | Routine | Y | N | N | 2 | Design-Build EOR / ST Design Review | 5 | 2023-04-24 | 12 | N | 5 | 1 | 2023-04-24 | 12 | Closed | 0 | 0 | 2 | 68000 | 127000 | N |  | 0 | 0 | 0 | 0.4 | 753 | P3 – Medium
DRLE-RFI-0233 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Signal Case location conflict at Sta. 922+77 | Proposed signal case foundation location at Sta. 922+77 conflicts with drilled shaft cap; offset of 7 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2023-04-17 | 7 | Routine | N | N | Y | 8 | Design-Build EOR / ST Design Review | 2 | 2023-04-25 | 8 | N | 1 | 1 | 2023-04-25 | 8 | Closed | 0 | 1 | 0 |  |  | N |  | 0 | 0 | 0 | 1 | 615 | P3 – Medium
DRLE-RFI-0234 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Redmond Way (SR 202) crossing: soft lacustrine silt below design subgrade | During excavation at Redmond Way (SR 202) crossing (Sta. 1648+61) the contractor encountered soft lacustrine silt below design subgrade, not shown on the GBR or A-728. Work in the area is suspended. Requests direction on dewatering approach and discharge treatment and confirmation of DSC entitlement. | Superintendent | 2023-04-17 | 7 | Expedite | Y | Y | N | 5 | Design-Build EOR / ST Design Review | 2 | 2023-04-21 | 4 | Y | 0 | 1 | 2023-04-21 | 4 | Closed | 4 | 0 | 3 | 1128000 | 2106000 | Y | DRLE-CO-043 | 985300 | 536800 | 2 | 46.8 | 112 | P2 – High
DRLE-RFI-0235 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Night work and noise variance – Downtown Redmond Station | Contractor requests approval of an alternate traffic/staging plan at Downtown Redmond Station: crane pick over active roadway. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Field Engineer | 2023-04-18 | 7 | Urgent | N | N | N | 5 | Design-Build EOR / ST Design Review | 2 | 2023-04-24 | 5 | Y | 0 | 2 | 2023-05-02 | 14 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1334 | P4 – Low
DRLE-RFI-0236 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | City of Redmond comment on critical areas permit – Marymoor Park interface | City of Redmond review comments on the critical areas permit require changes to the platform edge slab at Marymoor Park interface. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2023-04-24 | 7 | Routine | N | Y | N | 2 | WSDOT / ST Third-Party Mgmt | 3 | 2023-05-12 | 18 | N | 11 | 1 | 2023-05-12 | 18 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 827 | P4 – Low
DRLE-RFI-0237 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Night work and noise variance – Sammamish River bridge | Contractor requests approval of an alternate traffic/staging plan at Sammamish River bridge: temporary lane shift. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Scheduler | 2023-04-25 | 7 | Routine | N | N | Y | 5 | Design-Build EOR / ST Design Review | 1 | 2023-04-27 | 2 | Y | 0 | 1 | 2023-04-27 | 2 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1335 | P4 – Low
DRLE-RFI-0238 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 32 10 00 Pavements | City of Redmond comment on street improvement permit – Redmond Way (SR 202) crossing | City of Redmond review comments on the street improvement permit require changes to the guideway girder diaphragm at Redmond Way (SR 202) crossing. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2023-04-28 | 7 | Routine | N | N | Y | 3 | King County Parks / ST Third-Party Mgmt | 3 | 2023-05-15 | 16 | N | 9 | 2 | 2023-05-23 | 25 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1336 | P4 – Low
DRLE-RFI-0239 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – retaining wall footing at SE Redmond aerial guideway | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-741 for smoke control damper at SE Redmond aerial guideway. Request direction on compliant detail. | Design Manager | 2023-05-01 | 7 | Expedite | Y | Y | N | 3 | Design-Build EOR / ST Design Review | 4 | 2023-05-15 | 14 | N | 7 | 1 | 2023-05-15 | 14 | Closed | 19 | 0 | 11 | 370000 | 691000 | N |  | 0 | 0 | 0 | 2.4 | 503 | P3 – Medium
DRLE-RFI-0240 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at Marymoor Park interface, citing procurement lead time. Product data attached. | Field Engineer | 2023-05-11 | 7 | Expedite | N | N | N | 6 | Design-Build EOR / ST Design Review | 3 | 2023-05-15 | 4 | Y | 0 | 1 | 2023-05-15 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1337 | P4 – Low
DRLE-RFI-0241 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Lane closure window request – Marymoor Village parking garage | Contractor requests approval of an alternate traffic/staging plan at Marymoor Village parking garage: temporary lane shift. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Design Manager | 2023-05-22 | 7 | Routine | N | Y | N | 8 | Design-Build EOR / ST Design Review | 2 | 2023-05-29 | 5 | Y | 0 | 1 | 2023-05-29 | 5 | Closed | 4 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 828 | P4 – Low
DRLE-RFI-0242 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Track slab/expansion joint interface – SE Redmond aerial guideway | Track layout at Sta. 1860+70 (SE Redmond aerial guideway) differs from the track-structure interface drawing C-874. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Scheduler | 2023-05-29 | 7 | Routine | N | N | N | 5 | Design-Build EOR / ST Design Review | 2 | 2023-06-02 | 4 | Y | 0 | 1 | 2023-06-02 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1338 | P4 – Low
DRLE-RFI-0243 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | SPC | Spec / Drawing Clarification | General | 01 25 00 Substitution Procedures | Missing dimension on A-162 | Request clarification of 01 33 00 Submittal Procedures and A-162: dimension/notes appear inconsistent or omitted for the work at Sammamish River bridge. | Field Engineer | 2023-05-30 | 7 | Routine | N | N | N | 3 | Design-Build EOR / ST Design Review | 1 | 2023-06-01 | 2 | Y | 0 | 1 | 2023-06-01 | 2 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1339 | P4 – Low
DRLE-RFI-0244 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Embedded conduit stub-ups – Marymoor Village Station | Systems contractor requires 3-in. PVC conduit stub-ups for tunnel emergency phone at Marymoor Village Station not provided in civil E-410. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2023-05-30 | 7 | Routine | Y | Y | N | 7 | Design-Build EOR / ST Design Review | 2 | 2023-06-08 | 9 | N | 2 | 1 | 2023-06-08 | 9 | Closed | 6 | 0 | 3 | 5000 | 9000 | N |  | 0 | 0 | 0 | 0.7 | 689 | P3 – Medium
DRLE-RFI-0245 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | WSDOT comment on street improvement permit – Sammamish River bridge | WSDOT review comments on the street improvement permit require changes to the stair core wall at Sammamish River bridge. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2023-05-31 | 7 | Routine | Y | N | Y | 1 | King County Parks / ST Third-Party Mgmt | 1 | 2023-06-13 | 13 | N | 6 | 1 | 2023-06-13 | 13 | Closed | 0 | 0 | 0 | 143000 | 266000 | Y | DRLE-CO-045 | 163700 | 104200 | 0 | 39.8 | 243 | P2 – High
DRLE-RFI-0246 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Traction Power Feeder location conflict at Sta. 1496+21 | Proposed traction power feeder foundation location at Sta. 1496+21 conflicts with station canopy support; offset of 9 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Superintendent | 2023-06-07 | 7 | Routine | Y | Y | N | 7 | Design-Build EOR / ST Design Review | 2 | 2023-06-15 | 8 | N | 1 | 2 | 2023-06-21 | 14 | Closed | 1 | 0 | 0 | 214000 | 399000 | Y | DRLE-CO-046 | 261700 | 184600 | 0 | 41.8 | 204 | P2 – High
DRLE-RFI-0247 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – station canopy support at Downtown Redmond Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-557 for emergency stair pressurization at Downtown Redmond Station. Request direction on compliant detail. | Scheduler | 2023-06-22 | 7 | Routine | Y | N | N | 0 | Design-Build EOR / ST Design Review | 1 | 2023-07-03 | 11 | N | 4 | 1 | 2023-07-03 | 11 | Closed | 0 | 0 | 1 | 175000 | 327000 | N |  | 0 | 0 | 0 | 0.2 | 829 | P4 – Low
DRLE-RFI-0248 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Signal Case location conflict at Sta. 1030+47 | Proposed signal case foundation location at Sta. 1030+47 conflicts with pedestrian ramp; offset of 9 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Design Manager | 2023-06-23 | 7 | Routine | Y | N | N | 1 | Design-Build EOR / ST Design Review | 2 | 2023-07-03 | 8 | N | 1 | 1 | 2023-07-03 | 8 | Closed | 0 | 0 | 0 | 201000 | 374000 | Y | DRLE-CO-047 | 243020 | 216710 | 1 | 42.7 | 187 | P2 – High
DRLE-RFI-0249 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Art embed coordination – SE Redmond aerial guideway | Request to clarify finish/connection detail on E-881 at SE Redmond aerial guideway. Includes coordination with art program embeds and handrail sleeves as applicable. | Scheduler | 2023-06-26 | 7 | Routine | N | N | N | 3 | Design-Build EOR / ST Design Review | 4 | 2023-07-04 | 8 | N | 1 | 1 | 2023-07-04 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1340 | P4 – Low
DRLE-RFI-0250 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 8-in. high-pressure gas main at Redmond Way (SR 202) crossing | Potholing at Sta. 1998+77 located a 8-in. high-pressure gas main in conflict with the proposed drilled shaft cap. Utility is not shown on E-114. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2023-07-03 | 7 | Urgent | Y | Y | N | 7 | Design-Build EOR / ST Design Review | 4 | 2023-07-14 | 11 | N | 4 | 2 | 2023-08-04 | 32 | Closed | 2 | 0 | 1 | 464000 | 866000 | Y | DRLE-CO-048 | 931000 | 683800 | 1 | 46.9 | 109 | P1 – Critical
DRLE-RFI-0251 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | ARC | Architectural / Finishes / Station Elements | Architectural | 09 90 00 Painting and Coating | Canopy/glazing connection – Sammamish River bridge | Request to clarify finish/connection detail on E-182 at Sammamish River bridge. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2023-07-04 | 7 | Urgent | Y | Y | Y | 3 | Design-Build EOR / ST Design Review | 2 | 2023-07-05 | 1 | Y | 0 | 2 | 2023-07-11 | 7 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1341 | P4 – Low
DRLE-RFI-0252 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Direct fixation fastener spacing at Sta. 2194+86 | Track layout at Sta. 2194+86 (Marymoor Village Station) differs from the track-structure interface drawing E-758. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Design Manager | 2023-07-06 | 7 | Expedite | N | N | N | 6 | Design-Build EOR / ST Design Review | 1 | 2023-07-13 | 7 | Y | 0 | 1 | 2023-07-13 | 7 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1342 | P4 – Low
DRLE-RFI-0253 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | TESC modification – Downtown Redmond Station | Field conditions at Downtown Redmond Station require changes to temporary erosion and sediment control or stormwater facility per C-385. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2023-07-07 | 7 | Routine | Y | N | N | 6 | Design-Build EOR / ST Design Review | 5 | 2023-07-17 | 8 | N | 1 | 2 | 2023-07-28 | 21 | Closed | 0 | 0 | 0 | 36000 | 67000 | Y | DRLE-CO-049 | 82600 | 44700 | 0 | 36.9 | 294 | P2 – High
DRLE-RFI-0254 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on building permit – Redmond Way (SR 202) crossing | WSDOT review comments on the building permit require changes to the guideway girder diaphragm at Redmond Way (SR 202) crossing. Request direction on scope impacts and whether comments are within the contract requirements. | Project Engineer | 2023-07-10 | 7 | Routine | Y | Y | N | 3 | WSDOT / ST Third-Party Mgmt | 4 | 2023-08-07 | 27 | N | 20 | 2 | 2023-08-21 | 41 | Closed | 2 | 0 | 10 | 722000 | 1348000 | N |  | 0 | 0 | 0 | 2.2 | 509 | P3 – Medium
DRLE-RFI-0255 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – platform edge slab and pedestrian ramp at SE Redmond aerial guideway | Interference between platform edge slab and pedestrian ramp at SE Redmond aerial guideway per A-373. Required clearance of 2 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Project Engineer | 2023-07-10 | 7 | Routine | N | Y | N | 1 | Design-Build EOR / ST Design Review | 2 | 2023-07-17 | 7 | Y | 0 | 1 | 2023-07-17 | 7 | Closed | 1 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1343 | P4 – Low
DRLE-RFI-0256 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Rail Bonding location conflict at Sta. 1478+09 | Proposed rail bonding foundation location at Sta. 1478+09 conflicts with station canopy support; offset of 9 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Field Engineer | 2023-07-12 | 7 | Routine | N | Y | N | 7 | Design-Build EOR / ST Design Review | 1 | 2023-07-19 | 7 | Y | 0 | 1 | 2023-07-19 | 7 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 830 | P4 – Low
DRLE-RFI-0257 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Wetland/stream buffer protection – SE Redmond aerial guideway | Field conditions at SE Redmond aerial guideway require changes to temporary erosion and sediment control or stormwater facility per E-468. Request direction considering critical-areas conditions and permit requirements. | Scheduler | 2023-07-18 | 7 | Routine | N | Y | N | 5 | Design-Build EOR / ST Design Review | 3 | 2023-08-07 | 18 | N | 11 | 1 | 2023-08-07 | 18 | Closed | 3 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 599 | P3 – Medium
DRLE-RFI-0258 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Marymoor Village parking garage | Systems contractor requires 5-in. PVC conduit stub-ups for OCS pole at Marymoor Village parking garage not provided in civil C-886. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2023-07-19 | 7 | Routine | N | Y | Y | 5 | Design-Build EOR / ST Design Review | 2 | 2023-07-26 | 7 | Y | 0 | 1 | 2023-07-26 | 7 | Closed | 17 | 13 | 0 |  |  | N |  | 0 | 0 | 0 | 13 | 375 | P3 – Medium
DRLE-RFI-0259 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – pedestrian ramp at Marymoor Park interface | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and C-870 for standpipe connection at Marymoor Park interface. Request direction on compliant detail. | Project Manager | 2023-07-20 | 7 | Routine | Y | N | N | 7 | Design-Build EOR / ST Design Review | 3 | 2023-08-01 | 12 | N | 5 | 2 | 2023-08-21 | 31 | Closed | 0 | 0 | 1 | 1034000 | 1931000 | N |  | 0 | 0 | 0 | 0.2 | 831 | P4 – Low
DRLE-RFI-0260 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Station finish detail – SE Redmond aerial guideway | Request to clarify finish/connection detail on E-822 at SE Redmond aerial guideway. Includes coordination with art program embeds and handrail sleeves as applicable. | Superintendent | 2023-07-20 | 7 | Expedite | N | N | N | 6 | Design-Build EOR / ST Design Review | 1 | 2023-07-24 | 3 | Y | 0 | 1 | 2023-07-24 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1344 | P4 – Low
DRLE-RFI-0261 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | Wetland/stream buffer protection – Leary Way crossing | Field conditions at Leary Way crossing require changes to temporary erosion and sediment control or stormwater facility per M-542. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2023-07-21 | 7 | Expedite | Y | Y | N | 5 | Design-Build EOR / ST Design Review | 2 | 2023-07-25 | 4 | Y | 0 | 2 | 2023-08-11 | 21 | Closed | 7 | 0 | 2 | 23000 | 43000 | N |  | 0 | 0 | 0 | 0.4 | 754 | P4 – Low
DRLE-RFI-0262 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Embedded conduit stub-ups – Marymoor Village Station | Systems contractor requires 3-in. PVC conduit stub-ups for signal case at Marymoor Village Station not provided in civil S-675. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Field Engineer | 2023-07-31 | 7 | Routine | N | Y | N | 7 | Design-Build EOR / ST Design Review | 3 | 2023-08-23 | 23 | N | 16 | 1 | 2023-08-23 | 23 | Closed | 7 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 600 | P3 – Medium
DRLE-RFI-0263 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – bearing pad/embed plate at Downtown Redmond Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-685 for emergency stair pressurization at Downtown Redmond Station. Request direction on compliant detail. | Scheduler | 2023-07-31 | 7 | Urgent | N | Y | Y | 8 | Design-Build EOR / ST Design Review | 2 | 2023-08-07 | 6 | Y | 0 | 1 | 2023-08-07 | 6 | Closed | 5 | 3 | 0 |  |  | N |  | 0 | 0 | 0 | 3 | 488 | P3 – Medium
DRLE-RFI-0264 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – station canopy support at Downtown Redmond Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-450 for fire alarm device layout at Downtown Redmond Station. Request direction on compliant detail. | Design Manager | 2023-08-01 | 7 | Routine | N | N | N | 3 | Design-Build EOR / ST Design Review | 2 | 2023-08-09 | 8 | N | 1 | 1 | 2023-08-09 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1345 | P4 – Low
DRLE-RFI-0265 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 24-in. sanitary sewer at SE Redmond aerial guideway | Potholing at Sta. 2391+84 located a 24-in. sanitary sewer in conflict with the proposed guideway girder diaphragm. Utility is not shown on S-794. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Design Manager | 2023-08-07 | 7 | Routine | N | Y | Y | 2 | Design-Build EOR / ST Design Review | 1 | 2023-08-14 | 7 | Y | 0 | 2 | 2023-08-29 | 22 | Closed | 3 | 1 | 0 |  |  | N |  | 0 | 0 | 0 | 1 | 616 | P3 – Medium
DRLE-RFI-0266 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | DES | Design Conflict / Constructability | Structural | 03 21 00 Reinforcing Steel | Interference – retaining wall footing and stair core wall at Marymoor Village Station | Interference between retaining wall footing and stair core wall at Marymoor Village Station per A-429. Required clearance of 5 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Scheduler | 2023-08-11 | 7 | Urgent | N | Y | N | 6 | Design-Build EOR / ST Design Review | 1 | 2023-08-15 | 4 | Y | 0 | 2 | 2023-08-30 | 19 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 832 | P4 – Low
DRLE-RFI-0267 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | WSDOT comment on building permit – Marymoor Village parking garage | WSDOT review comments on the building permit require changes to the stair core wall at Marymoor Village parking garage. Request direction on scope impacts and whether comments are within the contract requirements. | Design Manager | 2023-08-23 | 7 | Routine | Y | Y | Y | 4 | City of Redmond / ST Third-Party Mgmt | 3 | 2023-09-07 | 15 | N | 8 | 2 | 2023-09-22 | 30 | Closed | 4 | 6 | 0 | 22000 | 40000 | N |  | 0 | 0 | 0 | 6 | 429 | P3 – Medium
DRLE-RFI-0268 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Tunnel Emergency Phone location conflict at Sta. 1801+16 | Proposed tunnel emergency phone foundation location at Sta. 1801+16 conflicts with platform edge slab; offset of 7 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Project Engineer | 2023-08-23 | 7 | Expedite | Y | N | N | 1 | Design-Build EOR / ST Design Review | 2 | 2023-08-28 | 5 | Y | 0 | 1 | 2023-08-28 | 5 | Closed | 0 | 0 | 0 | 366000 | 683000 | N |  | 0 | 0 | 0 | 0 | 1346 | P4 – Low
DRLE-RFI-0269 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 35 00 Special Procedures | Lane closure window request – Leary Way crossing | Contractor requests approval of an alternate traffic/staging plan at Leary Way crossing: revised haul route. Existing work restrictions limit production; requests ST/WSDOT concurrence. | Field Engineer | 2023-09-05 | 7 | Routine | N | Y | N | 1 | Design-Build EOR / ST Design Review | 3 | 2023-09-08 | 3 | Y | 0 | 1 | 2023-09-08 | 3 | Closed | 11 | 0 | 4 |  |  | N |  | 0 | 0 | 0 | 0.9 | 649 | P3 – Medium
DRLE-RFI-0270 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 19 Dewatering | Unforeseen condition at SE Redmond aerial guideway: buried concrete debris and an old foundation | During excavation at SE Redmond aerial guideway (Sta. 1966+84) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or A-688. Work in the area is suspended. Requests direction on testing/disposal protocol and confirmation of DSC entitlement. | Project Engineer | 2023-09-06 | 7 | Urgent | Y | N | N | 3 | Design-Build EOR / ST Design Review | 2 | 2023-09-13 | 7 | Y | 0 | 1 | 2023-09-13 | 7 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1347 | P4 – Low
DRLE-RFI-0271 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | TESC modification – Sammamish River bridge | Field conditions at Sammamish River bridge require changes to temporary erosion and sediment control or stormwater facility per A-704. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2023-09-06 | 7 | Routine | N | Y | N | 1 | Design-Build EOR / ST Design Review | 3 | 2023-09-20 | 14 | N | 7 | 1 | 2023-09-20 | 14 | Closed | 2 | 0 | 2 |  |  | Y | DRLE-CO-050 | 243200 | 179000 | 1 | 42.5 | 190 | P2 – High
DRLE-RFI-0272 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 12-in. ductile iron water main at Leary Way crossing | Potholing at Sta. 2004+36 located a 12-in. ductile iron water main in conflict with the proposed column reinforcement. Utility is not shown on C-655. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Project Engineer | 2023-09-08 | 7 | Routine | Y | Y | N | 5 | Design-Build EOR / ST Design Review | 3 | 2023-09-14 | 6 | Y | 0 | 1 | 2023-09-14 | 6 | Closed | 5 | 0 | 4 | 4107000 | 7667000 | N |  | 0 | 0 | 0 | 0.9 | 650 | P3 – Medium
DRLE-RFI-0273 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Grounding/bonding and stray-current detail – Downtown Redmond Station | Civil and systems drawings differ on grounding/bonding of duct bank encasement for stray-current control at Downtown Redmond Station. Request governing detail and responsibility for installation. | Design Manager | 2023-09-19 | 7 | Urgent | N | N | Y | 4 | Design-Build EOR / ST Design Review | 4 | 2023-09-22 | 3 | Y | 0 | 1 | 2023-09-22 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1348 | P4 – Low
DRLE-RFI-0274 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | MAT | Material / Submittal / Substitution | General | 05 12 00 Structural Steel | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at Marymoor Village Station, citing procurement lead time. Product data attached. | Project Engineer | 2023-09-21 | 7 | Routine | N | N | N | 1 | Design-Build EOR / ST Design Review | 1 | 2023-09-29 | 8 | N | 1 | 1 | 2023-09-29 | 8 | Closed | 0 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 833 | P4 – Low
DRLE-RFI-0275 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – retaining wall footing and stair core wall at Bear Creek crossing | Interference between retaining wall footing and stair core wall at Bear Creek crossing per C-828. Required clearance of 8 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2023-09-22 | 7 | Urgent | Y | Y | Y | 8 | Design-Build EOR / ST Design Review | 1 | 2023-09-26 | 4 | Y | 0 | 1 | 2023-09-26 | 4 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1349 | P4 – Low
DRLE-RFI-0276 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with PSE distribution duct bank at Marymoor Village Station | Potholing at Sta. 1787+76 located a PSE distribution duct bank in conflict with the proposed duct bank encasement. Utility is not shown on M-243. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Design Manager | 2023-10-10 | 7 | Routine | Y | Y | Y | 4 | Design-Build EOR / ST Design Review | 1 | 2023-10-23 | 13 | N | 6 | 1 | 2023-10-23 | 13 | Closed | 5 | 5 | 0 | 47000 | 88000 | Y | DRLE-CO-055 | 52780 | 49080 | 1.9 | 42.9 | 182 | P2 – High
DRLE-RFI-0277 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 8-in. high-pressure gas main at Marymoor Village Station | Potholing at Sta. 1821+32 located a 8-in. high-pressure gas main in conflict with the proposed drilled shaft cap. Utility is not shown on A-118. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Project Engineer | 2023-10-17 | 7 | Expedite | N | Y | N | 3 | Design-Build EOR / ST Design Review | 1 | 2023-10-20 | 3 | Y | 0 | 1 | 2023-10-20 | 3 | Closed | 4 | 0 | 3 |  |  | Y | DRLE-CO-051 | 59400 | 31900 | 1 | 36.7 | 295 | P2 – High
DRLE-RFI-0278 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | TRK | Trackwork / Track-Structure Interface | Track | 34 11 33 Direct Fixation Track | Direct fixation fastener spacing at Sta. 1145+36 | Track layout at Sta. 1145+36 (SE Redmond aerial guideway) differs from the track-structure interface drawing M-726. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Superintendent | 2023-10-23 | 7 | Routine | N | N | N | 3 | Design-Build EOR / ST Design Review | 1 | 2023-10-30 | 5 | Y | 0 | 1 | 2023-10-30 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1350 | P4 – Low
DRLE-RFI-0279 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 55 00 Traffic Control | Crane staging in right-of-way – SE Redmond aerial guideway | Contractor requests approval of an alternate traffic/staging plan at SE Redmond aerial guideway: temporary lane shift. Existing work restrictions limit production; requests ST/City of Redmond concurrence. | Scheduler | 2023-10-30 | 7 | Routine | N | N | N | 3 | Design-Build EOR / ST Design Review | 2 | 2023-11-02 | 3 | Y | 0 | 1 | 2023-11-02 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1351 | P4 – Low
DRLE-RFI-0280 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | King County Parks comment on right-of-way use permit – Leary Way crossing | King County Parks review comments on the right-of-way use permit require changes to the retaining wall footing at Leary Way crossing. Request direction on scope impacts and whether comments are within the contract requirements. | Project Manager | 2023-11-03 | 7 | Expedite | N | N | Y | 1 | King County Parks / ST Third-Party Mgmt | 4 | 2023-11-09 | 6 | Y | 0 | 1 | 2023-11-09 | 6 | Closed | 0 | 5 | 0 |  |  | N |  | 0 | 0 | 0 | 5 | 447 | P3 – Medium
DRLE-RFI-0281 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – pedestrian ramp at Redmond Way (SR 202) crossing | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-764 for egress width at Redmond Way (SR 202) crossing. Request direction on compliant detail. | Superintendent | 2023-11-06 | 7 | Routine | N | N | N | 5 | Design-Build EOR / ST Design Review | 4 | 2023-11-14 | 8 | N | 1 | 1 | 2023-11-14 | 8 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1352 | P4 – Low
DRLE-RFI-0282 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 01 57 00 Temporary Controls | TESC modification – Marymoor Park interface | Field conditions at Marymoor Park interface require changes to temporary erosion and sediment control or stormwater facility per C-766. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2023-11-08 | 7 | Routine | Y | Y | N | 8 | Design-Build EOR / ST Design Review | 2 | 2023-11-15 | 7 | Y | 0 | 1 | 2023-11-15 | 7 | Closed | 4 | 0 | 1 | 42000 | 78000 | Y | DRLE-CO-053 | 47000 | 0 | 0 | 0.2 | 834 | P4 – Low
DRLE-RFI-0283 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Lane closure window request – Sammamish River bridge | Contractor requests approval of an alternate traffic/staging plan at Sammamish River bridge: extended night closure. Existing work restrictions limit production; requests ST/City of Redmond concurrence. | Superintendent | 2023-11-13 | 7 | Urgent | N | N | N | 4 | Design-Build EOR / ST Design Review | 2 | 2023-11-14 | 1 | Y | 0 | 1 | 2023-11-14 | 1 | Closed | 0 | 0 | 0 |  |  | Y | DRLE-CO-052 | 16900 | 10200 | 0 | 31.8 | 336 | P2 – High
DRLE-RFI-0284 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – duct bank encasement and retaining wall footing at Marymoor Village Station | Interference between duct bank encasement and retaining wall footing at Marymoor Village Station per S-833. Required clearance of 6 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2023-11-20 | 7 | Routine | Y | Y | N | 4 | Design-Build EOR / ST Design Review | 2 | 2023-11-27 | 5 | Y | 0 | 1 | 2023-11-27 | 5 | Closed | 7 | 0 | 5 | 87000 | 162000 | Y | DRLE-CO-054 | 165840 | 93170 | 2.3 | 41.3 | 213 | P2 – High
DRLE-RFI-0285 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Sammamish River bridge | C-331 shows a 33 ft-0 in. dimension for the stair core wall; structural sheet S-289 shows a different value. Request clarification before fabrication/rebar release. | Superintendent | 2023-11-27 | 7 | Urgent | Y | Y | Y | 1 | Design-Build EOR / ST Design Review | 2 | 2023-11-29 | 2 | Y | 0 | 1 | 2023-11-29 | 2 | Closed | 11 | 7 | 0 | 168000 | 314000 | Y | DRLE-CO-054 | 189960 | 106730 | 2.7 | 47.8 | 95 | P1 – Critical
DRLE-RFI-0286 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | WSDOT comment on building permit – Marymoor Village Station | WSDOT review comments on the building permit require changes to the platform edge slab at Marymoor Village Station. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2023-12-06 | 7 | Routine | N | N | N | 6 | King County Parks / ST Third-Party Mgmt | 1 | 2023-12-18 | 10 | N | 3 | 1 | 2023-12-18 | 10 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1353 | P4 – Low
DRLE-RFI-0287 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 8-in. high-pressure gas main at Marymoor Village parking garage | Potholing at Sta. 1321+84 located a 8-in. high-pressure gas main in conflict with the proposed platform edge slab. Utility is not shown on S-110. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Scheduler | 2023-12-11 | 7 | Expedite | Y | Y | Y | 6 | Design-Build EOR / ST Design Review | 3 | 2023-12-18 | 5 | Y | 0 | 1 | 2023-12-18 | 5 | Closed | 5 | 2 | 0 | 194000 | 363000 | Y | DRLE-CO-056 | 293160 | 232280 | 2.4 | 45.4 | 133 | P2 – High
DRLE-RFI-0288 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Wetland/stream buffer protection – Marymoor Park interface | Field conditions at Marymoor Park interface require changes to temporary erosion and sediment control or stormwater facility per M-249. Request direction considering critical-areas conditions and permit requirements. | Project Engineer | 2023-12-11 | 7 | Routine | N | Y | N | 2 | Design-Build EOR / ST Design Review | 1 | 2023-12-19 | 8 | N | 1 | 1 | 2023-12-19 | 8 | Closed | 12 | 0 | 9 |  |  | N |  | 0 | 0 | 0 | 2 | 536 | P3 – Medium
DRLE-RFI-0289 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 28 31 00 Fire Detection and Alarm | NFPA 130 requirement – duct bank encasement at Bear Creek crossing | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and M-211 for egress width at Bear Creek crossing. Request direction on compliant detail. | Scheduler | 2023-12-21 | 7 | Routine | N | Y | N | 5 | Design-Build EOR / ST Design Review | 1 | 2024-01-01 | 9 | N | 2 | 1 | 2024-01-01 | 9 | Closed | 2 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 755 | P4 – Low
DRLE-RFI-0290 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | King County Parks comment on street improvement permit – Marymoor Village Station | King County Parks review comments on the street improvement permit require changes to the guideway girder diaphragm at Marymoor Village Station. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2023-12-22 | 7 | Routine | N | Y | N | 0 | City of Redmond / ST Third-Party Mgmt | 1 | 2023-12-29 | 7 | Y | 0 | 1 | 2023-12-29 | 7 | Closed | 15 | 0 | 11 |  |  | N |  | 0 | 0 | 0 | 2.4 | 504 | P3 – Medium
DRLE-RFI-0291 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – galvanized steel handrail | Contractor requests approval to substitute galvanized steel handrail for stainless steel handrail on work at Marymoor Park interface, citing procurement lead time. Product data attached. | Superintendent | 2023-12-25 | 7 | Expedite | N | N | N | 6 | Design-Build EOR / ST Design Review | 2 | 2023-12-29 | 4 | Y | 0 | 1 | 2023-12-29 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1354 | P4 – Low
DRLE-RFI-0292 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 24-in. sanitary sewer at Leary Way crossing | Potholing at Sta. 1125+08 located a 24-in. sanitary sewer in conflict with the proposed stair core wall. Utility is not shown on E-501. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Project Manager | 2024-01-01 | 7 | Urgent | Y | Y | Y | 0 | Design-Build EOR / ST Design Review | 1 | 2024-01-03 | 2 | Y | 0 | 2 | 2024-01-15 | 13 | Closed | 6 | 4 | 0 | 106000 | 199000 | Y | DRLE-CO-055 | 78950 | 73430 | 2.8 | 43.5 | 169 | P2 – High
DRLE-RFI-0293 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | King County Parks comment on right-of-way use permit – SE Redmond aerial guideway | King County Parks review comments on the right-of-way use permit require changes to the guideway girder diaphragm at SE Redmond aerial guideway. Request direction on scope impacts and whether comments are within the contract requirements. | Field Engineer | 2024-01-11 | 7 | Expedite | Y | Y | N | 8 | City of Redmond / ST Third-Party Mgmt | 3 | 2024-01-25 | 14 | N | 7 | 1 | 2024-01-25 | 14 | Closed | 12 | 0 | 7 | 505000 | 942000 | N |  | 0 | 0 | 0 | 1.6 | 561 | P3 – Medium
DRLE-RFI-0294 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with PSE distribution duct bank at Marymoor Village parking garage | Potholing at Sta. 2044+15 located a PSE distribution duct bank in conflict with the proposed stair core wall. Utility is not shown on E-629. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Superintendent | 2024-01-11 | 7 | Expedite | Y | Y | Y | 5 | Design-Build EOR / ST Design Review | 1 | 2024-01-19 | 8 | N | 1 | 1 | 2024-01-19 | 8 | Closed | 9 | 6 | 0 | 299000 | 559000 | Y | DRLE-CO-055 | 351170 | 326590 | 12.4 | 53.9 | 31 | P1 – Critical
DRLE-RFI-0295 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 41 00 Regulatory Requirements | King County Parks comment on critical areas permit – Marymoor Village Station | King County Parks review comments on the critical areas permit require changes to the drilled shaft cap at Marymoor Village Station. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2024-01-29 | 7 | Routine | N | N | N | 7 | King County Parks / ST Third-Party Mgmt | 2 | 2024-02-09 | 11 | N | 4 | 1 | 2024-02-09 | 11 | Closed | 0 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 756 | P4 – Low
DRLE-RFI-0296 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with fiber communications duct bank at Bear Creek crossing | Potholing at Sta. 2225+84 located a fiber communications duct bank in conflict with the proposed column reinforcement. Utility is not shown on A-592. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Superintendent | 2024-01-29 | 7 | Urgent | Y | Y | N | 5 | Design-Build EOR / ST Design Review | 2 | 2024-02-05 | 6 | Y | 0 | 1 | 2024-02-05 | 6 | Closed | 4 | 0 | 3 | 583000 | 1088000 | Y | DRLE-CO-056 | 702640 | 556720 | 5.6 | 48.1 | 91 | P1 – Critical
DRLE-RFI-0297 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | SPC | Spec / Drawing Clarification | General | 00 72 00 General Conditions | Drawing/spec discrepancy – Redmond Way (SR 202) crossing | Request clarification of 00 72 00 General Conditions and S-785: dimension/notes appear inconsistent or omitted for the work at Redmond Way (SR 202) crossing. | Field Engineer | 2024-01-31 | 7 | Routine | N | N | N | 3 | Design-Build EOR / ST Design Review | 1 | 2024-02-05 | 3 | Y | 0 | 1 | 2024-02-05 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1355 | P4 – Low
DRLE-RFI-0298 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 23 34 00 Ventilation | NFPA 130 requirement – retaining wall footing at Downtown Redmond Station | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and S-302 for emergency stair pressurization at Downtown Redmond Station. Request direction on compliant detail. | Field Engineer | 2024-02-06 | 7 | Routine | Y | Y | Y | 4 | Design-Build EOR / ST Design Review | 2 | 2024-02-16 | 10 | N | 3 | 2 | 2024-02-28 | 22 | Closed | 20 | 9 | 0 | 1110000 | 2072000 | Y | DRLE-CO-057 | 1625200 | 1105500 | 10 | 60.3 | 17 | P1 – Critical
DRLE-RFI-0299 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 12-in. ductile iron water main at SE Redmond aerial guideway | Potholing at Sta. 1605+32 located a 12-in. ductile iron water main in conflict with the proposed stair core wall. Utility is not shown on M-599. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Field Engineer | 2024-02-07 | 7 | Routine | N | Y | Y | 5 | Design-Build EOR / ST Design Review | 2 | 2024-02-15 | 8 | N | 1 | 1 | 2024-02-15 | 8 | Closed | 19 | 14 | 0 |  |  | N |  | 0 | 0 | 0 | 14 | 374 | P3 – Medium
DRLE-RFI-0300 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Tunnel Emergency Phone location conflict at Sta. 1920+22 | Proposed tunnel emergency phone foundation location at Sta. 1920+22 conflicts with column reinforcement; offset of 8 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Project Manager | 2024-02-09 | 7 | Expedite | N | Y | N | 0 | Design-Build EOR / ST Design Review | 3 | 2024-02-15 | 6 | Y | 0 | 1 | 2024-02-15 | 6 | Closed | 6 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 690 | P3 – Medium
DRLE-RFI-0301 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | MOT | Staging / MOT / Access / Sequencing | Traffic/Civil | 01 14 00 Work Restrictions | Night work and noise variance – SE Redmond aerial guideway | Contractor requests approval of an alternate traffic/staging plan at SE Redmond aerial guideway: extended night closure. Existing work restrictions limit production; requests ST/City of Redmond concurrence. | Scheduler | 2024-02-09 | 7 | Routine | N | Y | N | 0 | Design-Build EOR / ST Design Review | 3 | 2024-02-12 | 3 | Y | 0 | 1 | 2024-02-12 | 3 | Closed | 3 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 757 | P4 – Low
DRLE-RFI-0302 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 8-in. high-pressure gas main at Downtown Redmond Station | Potholing at Sta. 2016+65 located a 8-in. high-pressure gas main in conflict with the proposed column reinforcement. Utility is not shown on M-378. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Scheduler | 2024-02-12 | 7 | Routine | Y | Y | N | 1 | Design-Build EOR / ST Design Review | 2 | 2024-02-19 | 6 | Y | 0 | 1 | 2024-02-19 | 6 | Closed | 7 | 0 | 4 | 871000 | 1625000 | N |  | 0 | 0 | 0 | 0.9 | 651 | P3 – Medium
DRLE-RFI-0303 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Special trackwork layout – Marymoor Village Station | Track layout at Sta. 1181+79 (Marymoor Village Station) differs from the track-structure interface drawing S-440. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Superintendent | 2024-02-20 | 7 | Expedite | N | Y | N | 0 | Design-Build EOR / ST Design Review | 2 | 2024-02-23 | 3 | Y | 0 | 1 | 2024-02-23 | 3 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 835 | P4 – Low
DRLE-RFI-0304 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | City of Redmond comment on street improvement permit – Marymoor Park interface | City of Redmond review comments on the street improvement permit require changes to the column reinforcement at Marymoor Park interface. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2024-02-22 | 7 | Expedite | Y | Y | N | 5 | City of Redmond / ST Third-Party Mgmt | 3 | 2024-02-26 | 4 | Y | 0 | 1 | 2024-02-26 | 4 | Closed | 5 | 0 | 2 | 185000 | 345000 | Y | DRLE-CO-058 | 151800 | 63400 | 1 | 38.9 | 257 | P2 – High
DRLE-RFI-0305 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 30-in. storm drain at Downtown Redmond Station | Potholing at Sta. 1848+34 located a 30-in. storm drain in conflict with the proposed bearing pad/embed plate. Utility is not shown on E-850. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Design Manager | 2024-03-13 | 7 | Urgent | N | N | Y | 5 | Design-Build EOR / ST Design Review | 1 | 2024-03-18 | 4 | Y | 0 | 1 | 2024-03-18 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1356 | P4 – Low
DRLE-RFI-0306 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 24-in. sanitary sewer at Bear Creek crossing | Potholing at Sta. 1098+05 located a 24-in. sanitary sewer in conflict with the proposed duct bank encasement. Utility is not shown on M-300. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Superintendent | 2024-03-20 | 7 | Routine | Y | Y | N | 6 | Design-Build EOR / ST Design Review | 3 | 2024-03-25 | 4 | Y | 0 | 1 | 2024-03-25 | 4 | Closed | 8 | 0 | 5 | 372000 | 694000 | N |  | 0 | 0 | 0 | 1.1 | 601 | P3 – Medium
DRLE-RFI-0307 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | TRK | Trackwork / Track-Structure Interface | Track | 34 11 00 Track Construction | Special trackwork layout – Bear Creek crossing | Track layout at Sta. 1825+93 (Bear Creek crossing) differs from the track-structure interface drawing E-180. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Scheduler | 2024-03-27 | 7 | Expedite | N | Y | N | 5 | Design-Build EOR / ST Design Review | 2 | 2024-04-02 | 6 | Y | 0 | 1 | 2024-04-02 | 6 | Closed | 4 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 836 | P4 – Low
DRLE-RFI-0308 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | DES | Design Conflict / Constructability | Structural | 03 30 00 Cast-in-Place Concrete | Interference – duct bank encasement and bearing pad/embed plate at Downtown Redmond Station | Interference between duct bank encasement and bearing pad/embed plate at Downtown Redmond Station per M-211. Required clearance of 2 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Design Manager | 2024-04-17 | 7 | Urgent | Y | Y | Y | 8 | Design-Build EOR / ST Design Review | 1 | 2024-04-23 | 6 | Y | 0 | 2 | 2024-05-03 | 16 | Closed | 8 | 8 | 0 | 215000 | 401000 | Y | DRLE-CO-059 | 372500 | 0 | 0 | 8 | 415 | P3 – Medium
DRLE-RFI-0309 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Downtown Redmond Station: an unmapped abandoned storm line | During excavation at Downtown Redmond Station (Sta. 1910+82) the contractor encountered an unmapped abandoned storm line, not shown on the GBR or A-564. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Superintendent | 2024-05-08 | 7 | Routine | Y | Y | N | 2 | Design-Build EOR / ST Design Review | 2 | 2024-05-13 | 3 | Y | 0 | 1 | 2024-05-13 | 3 | Closed | 7 | 0 | 2 | 102000 | 190000 | Y | DRLE-CO-060 | 154300 | 84300 | 2 | 40.2 | 231 | P2 – High
DRLE-RFI-0310 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at Redmond Way (SR 202) crossing, citing procurement lead time. Product data attached. | Project Manager | 2024-05-13 | 7 | Routine | Y | N | N | 6 | Design-Build EOR / ST Design Review | 2 | 2024-05-17 | 4 | Y | 0 | 1 | 2024-05-17 | 4 | Closed | 0 | 0 | 0 | 4000 | 8000 | N |  | 0 | 0 | 0 | 0 | 1357 | P4 – Low
DRLE-RFI-0311 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Interference – retaining wall footing and guideway girder diaphragm at Marymoor Park interface | Interference between retaining wall footing and guideway girder diaphragm at Marymoor Park interface per E-519. Required clearance of 6 in. cannot be maintained. Request revised detail or approval of proposed field modification. | Superintendent | 2024-05-20 | 7 | Routine | Y | Y | N | 7 | Design-Build EOR / ST Design Review | 1 | 2024-05-27 | 5 | Y | 0 | 1 | 2024-05-27 | 5 | Closed | 2 | 0 | 1 | 338000 | 630000 | Y | DRLE-CO-061 | 400300 | 248000 | 0 | 43 | 180 | P2 – High
DRLE-RFI-0312 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | Stormwater facility revision – Downtown Redmond Station | Field conditions at Downtown Redmond Station require changes to temporary erosion and sediment control or stormwater facility per E-250. Request direction considering critical-areas conditions and permit requirements. | Scheduler | 2024-05-22 | 7 | Routine | N | N | N | 1 | Design-Build EOR / ST Design Review | 1 | 2024-06-17 | 26 | N | 19 | 1 | 2024-06-17 | 26 | Closed | 0 | 0 | 11 |  |  | N |  | 0 | 0 | 0 | 2.4 | 505 | P3 – Medium
DRLE-RFI-0313 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Constructability – platform edge slab sequence at Sammamish River bridge | Erection of the platform edge slab as drawn conflicts with adjacent work and access limits at Sammamish River bridge. Contractor proposes alternate sequence and temporary support; requests design review and approval. | Project Engineer | 2024-05-28 | 7 | Routine | N | N | N | 0 | Design-Build EOR / ST Design Review | 4 | 2024-06-03 | 5 | Y | 0 | 1 | 2024-06-03 | 5 | Closed | 0 | 0 | 0 |  |  | Y | DRLE-CO-062 | 110600 | 58200 | 0 | 37.8 | 279 | P2 – High
DRLE-RFI-0314 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Signal Case location conflict at Sta. 1836+86 | Proposed signal case foundation location at Sta. 1836+86 conflicts with column reinforcement; offset of 13 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Project Engineer | 2024-05-30 | 7 | Urgent | N | N | Y | 7 | Design-Build EOR / ST Design Review | 5 | 2024-06-10 | 9 | N | 2 | 1 | 2024-06-10 | 9 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1358 | P4 – Low
DRLE-RFI-0315 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 33 40 00 Stormwater Utilities | In-water work window – Bear Creek crossing | Field conditions at Bear Creek crossing require changes to temporary erosion and sediment control or stormwater facility per M-324. Request direction considering critical-areas conditions and permit requirements. | Superintendent | 2024-06-03 | 7 | Routine | N | N | Y | 7 | Design-Build EOR / ST Design Review | 2 | 2024-06-10 | 5 | Y | 0 | 1 | 2024-06-10 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1359 | P4 – Low
DRLE-RFI-0316 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 8-in. high-pressure gas main at Bear Creek crossing | Potholing at Sta. 1357+73 located a 8-in. high-pressure gas main in conflict with the proposed drilled shaft cap. Utility is not shown on E-395. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Scheduler | 2024-06-10 | 7 | Routine | N | Y | N | 5 | Design-Build EOR / ST Design Review | 2 | 2024-06-13 | 3 | Y | 0 | 1 | 2024-06-13 | 3 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 837 | P4 – Low
DRLE-RFI-0317 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with 12-in. ductile iron water main at Marymoor Village parking garage | Potholing at Sta. 2368+11 located a 12-in. ductile iron water main in conflict with the proposed bearing pad/embed plate. Utility is not shown on M-425. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Design Manager | 2024-06-24 | 7 | Urgent | Y | Y | N | 7 | Design-Build EOR / ST Design Review | 2 | 2024-06-28 | 4 | Y | 0 | 1 | 2024-06-28 | 4 | Closed | 1 | 0 | 1 | 3446000 | 6433000 | Y | DRLE-CO-063 | 4126900 | 2986000 | 0 | 50.2 | 54 | P1 – Critical
DRLE-RFI-0318 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – galvanized steel handrail | Contractor requests approval to substitute galvanized steel handrail for stainless steel handrail on work at Marymoor Park interface, citing procurement lead time. Product data attached. | Superintendent | 2024-07-23 | 7 | Routine | N | Y | N | 3 | Design-Build EOR / ST Design Review | 1 | 2024-07-31 | 8 | N | 1 | 2 | 2024-08-19 | 27 | Closed | 6 | 0 | 3 |  |  | N |  | 0 | 0 | 0 | 0.7 | 691 | P3 – Medium
DRLE-RFI-0319 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | FLS | Fire-Life-Safety / MEP / Tunnel Systems | MEP/FLS | 21 13 00 Fire Suppression | NFPA 130 requirement – platform edge slab at Sammamish River bridge | Contractor identifies a conflict between NFPA 130 egress/ventilation requirements and A-134 for standpipe connection at Sammamish River bridge. Request direction on compliant detail. | Design Manager | 2024-08-19 | 7 | Routine | N | N | N | 3 | Design-Build EOR / ST Design Review | 1 | 2024-08-23 | 4 | Y | 0 | 1 | 2024-08-23 | 4 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1360 | P4 – Low
DRLE-RFI-0320 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Bear Creek crossing: buried concrete debris and an old foundation | During excavation at Bear Creek crossing (Sta. 2341+55) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or S-348. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Project Engineer | 2024-08-23 | 7 | Routine | Y | N | Y | 1 | Design-Build EOR / ST Design Review | 1 | 2024-08-26 | 2 | Y | 0 | 1 | 2024-08-26 | 2 | Closed | 0 | 0 | 0 | 100000 | 187000 | Y | DRLE-CO-064 | 202700 | 163500 | 0 | 41.4 | 211 | P2 – High
DRLE-RFI-0321 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at Sammamish River bridge, citing procurement lead time. Product data attached. | Design Manager | 2024-08-28 | 7 | Routine | N | N | N | 4 | Design-Build EOR / ST Design Review | 1 | 2024-09-03 | 6 | Y | 0 | 1 | 2024-09-03 | 6 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1361 | P4 – Low
DRLE-RFI-0322 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | SPC | Spec / Drawing Clarification | General | 01 33 00 Submittal Procedures | Clarify spec requirement – Bear Creek crossing | Request clarification of 01 33 00 Submittal Procedures and M-652: dimension/notes appear inconsistent or omitted for the work at Bear Creek crossing. | Scheduler | 2024-09-05 | 7 | Expedite | N | N | N | 8 | Design-Build EOR / ST Design Review | 2 | 2024-09-09 | 3 | Y | 0 | 1 | 2024-09-09 | 3 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1362 | P4 – Low
DRLE-RFI-0323 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 50 00 Excavation Support | Unforeseen condition at Leary Way crossing: abandoned timber piles | During excavation at Leary Way crossing (Sta. 1200+04) the contractor encountered abandoned timber piles, not shown on the GBR or E-380. Work in the area is suspended. Requests direction on revised bearing elevation and foundation detail and confirmation of DSC entitlement. | Design Manager | 2024-09-09 | 7 | Expedite | N | Y | Y | 1 | Design-Build EOR / ST Design Review | 2 | 2024-09-18 | 9 | N | 2 | 1 | 2024-09-18 | 9 | Closed | 9 | 3 | 0 |  |  | N |  | 0 | 0 | 0 | 3 | 489 | P3 – Medium
DRLE-RFI-0324 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Sammamish River bridge | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 27 10 00 Communications | Embedded conduit stub-ups – Sammamish River bridge | Systems contractor requires 4-in. PVC conduit stub-ups for tunnel emergency phone at Sammamish River bridge not provided in civil C-691. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Superintendent | 2024-09-12 | 7 | Routine | N | Y | N | 3 | Design-Build EOR / ST Design Review | 6 | 2024-09-26 | 14 | N | 7 | 1 | 2024-09-26 | 14 | Closed | 3 | 0 | 5 |  |  | N |  | 0 | 0 | 0 | 1.1 | 602 | P3 – Medium
DRLE-RFI-0325 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village parking garage | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | City of Redmond comment on right-of-way use permit – Marymoor Village parking garage | City of Redmond review comments on the right-of-way use permit require changes to the retaining wall footing at Marymoor Village parking garage. Request direction on scope impacts and whether comments are within the contract requirements. | Scheduler | 2024-09-24 | 7 | Routine | N | N | N | 2 | WSDOT / ST Third-Party Mgmt | 4 | 2024-10-04 | 10 | N | 3 | 2 | 2024-10-14 | 19 | Closed | 0 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 758 | P4 – Low
DRLE-RFI-0326 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | SE Redmond aerial guideway | 3P | Third-Party / Permit / ROW Requirement | Permitting/Civil | 01 14 00 Work Restrictions | WSDOT comment on street improvement permit – SE Redmond aerial guideway | WSDOT review comments on the street improvement permit require changes to the stair core wall at SE Redmond aerial guideway. Request direction on scope impacts and whether comments are within the contract requirements. | Superintendent | 2024-09-26 | 7 | Routine | Y | N | N | 1 | City of Redmond / ST Third-Party Mgmt | 1 | 2024-09-30 | 4 | Y | 0 | 1 | 2024-09-30 | 4 | Closed | 0 | 0 | 0 | 161000 | 301000 | Y | DRLE-CO-065 | 283200 | 0 | 0 | 0 | 1363 | P4 – Low
DRLE-RFI-0327 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 41 00 Train Control/Signals | Tunnel Emergency Phone location conflict at Sta. 1509+37 | Proposed tunnel emergency phone foundation location at Sta. 1509+37 conflicts with platform edge slab; offset of 5 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Project Engineer | 2024-10-02 | 7 | Routine | N | Y | N | 6 | Design-Build EOR / ST Design Review | 4 | 2024-10-10 | 8 | N | 1 | 1 | 2024-10-10 | 8 | Closed | 4 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 759 | P4 – Low
DRLE-RFI-0328 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 21 00 Traction Power | Signal Case location conflict at Sta. 1466+83 | Proposed signal case foundation location at Sta. 1466+83 conflicts with station canopy support; offset of 10 ft needed to maintain clearance envelope. Request revised location and design confirmation. | Scheduler | 2024-10-03 | 7 | Routine | N | Y | Y | 4 | Design-Build EOR / ST Design Review | 2 | 2024-10-11 | 8 | N | 1 | 1 | 2024-10-11 | 8 | Closed | 19 | 12 | 0 |  |  | N |  | 0 | 0 | 0 | 12 | 383 | P3 – Medium
DRLE-RFI-0329 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Downtown Redmond Station | ARC | Architectural / Finishes / Station Elements | Architectural | 05 50 00 Metal Fabrications | Station finish detail – Downtown Redmond Station | Request to clarify finish/connection detail on A-346 at Downtown Redmond Station. Includes coordination with art program embeds and handrail sleeves as applicable. | Design Manager | 2024-10-07 | 7 | Routine | Y | N | N | 7 | Design-Build EOR / ST Design Review | 3 | 2024-10-14 | 7 | Y | 0 | 1 | 2024-10-14 | 7 | Closed | 0 | 0 | 0 | 58000 | 108000 | N |  | 0 | 0 | 0 | 0 | 1364 | P4 – Low
DRLE-RFI-0330 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | MAT | Material / Submittal / Substitution | General | 01 33 00 Submittal Procedures | Substitution request – alternate LED luminaire | Contractor requests approval to substitute alternate LED luminaire for specified LED luminaire on work at Redmond Way (SR 202) crossing, citing procurement lead time. Product data attached. | Field Engineer | 2024-10-08 | 7 | Expedite | Y | N | N | 3 | Design-Build EOR / ST Design Review | 3 | 2024-10-14 | 6 | Y | 0 | 1 | 2024-10-14 | 6 | Closed | 0 | 0 | 0 | 33000 | 61000 | N |  | 0 | 0 | 0 | 0 | 1365 | P4 – Low
DRLE-RFI-0331 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | MAT | Material / Submittal / Substitution | General | 03 30 00 Cast-in-Place Concrete | Substitution request – precast trench drain | Contractor requests approval to substitute precast trench drain for cast-in-place trench drain on work at Leary Way crossing, citing procurement lead time. Product data attached. | Superintendent | 2024-10-10 | 7 | Routine | N | N | N | 1 | Design-Build EOR / ST Design Review | 2 | 2024-10-14 | 3 | Y | 0 | 2 | 2024-11-01 | 22 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1366 | P4 – Low
DRLE-RFI-0332 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | DES | Design Conflict / Constructability | Structural | 05 12 00 Structural Steel | Dimensional discrepancy – Marymoor Park interface | E-211 shows a 27 ft-0 in. dimension for the retaining wall footing; structural sheet S-767 shows a different value. Request clarification before fabrication/rebar release. | Project Engineer | 2024-11-05 | 7 | Routine | Y | N | N | 8 | Design-Build EOR / ST Design Review | 1 | 2024-11-13 | 8 | N | 1 | 1 | 2024-11-13 | 8 | Closed | 0 | 0 | 0 | 2096000 | 3913000 | N |  | 0 | 0 | 0 | 0 | 1367 | P4 – Low
DRLE-RFI-0333 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | TRK | Trackwork / Track-Structure Interface | Track | 34 11 36 Special Trackwork | Special trackwork layout – Marymoor Park interface | Track layout at Sta. 1895+53 (Marymoor Park interface) differs from the track-structure interface drawing E-732. Contractor requests confirmation of fastener spacing, rail joint or expansion-joint treatment and slab elevation tolerance. | Project Engineer | 2024-11-08 | 7 | Expedite | N | N | N | 8 | Design-Build EOR / ST Design Review | 2 | 2024-11-19 | 11 | N | 4 | 1 | 2024-11-19 | 11 | Closed | 0 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 838 | P4 – Low
DRLE-RFI-0334 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Park interface | ARC | Architectural / Finishes / Station Elements | Architectural | 08 44 00 Curtain Wall/Glazing | Art embed coordination – Marymoor Park interface | Request to clarify finish/connection detail on M-797 at Marymoor Park interface. Includes coordination with art program embeds and handrail sleeves as applicable. | Scheduler | 2024-11-18 | 7 | Routine | N | N | N | 4 | Design-Build EOR / ST Design Review | 1 | 2024-11-25 | 5 | Y | 0 | 1 | 2024-11-25 | 5 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1368 | P4 – Low
DRLE-RFI-0335 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | ENV | Environmental / Stormwater / Critical Areas | Civil/Environmental | 31 25 00 Erosion and Sediment Control | Wetland/stream buffer protection – Bear Creek crossing | Field conditions at Bear Creek crossing require changes to temporary erosion and sediment control or stormwater facility per M-512. Request direction considering critical-areas conditions and permit requirements. | Design Manager | 2024-11-27 | 7 | Routine | N | Y | N | 2 | Design-Build EOR / ST Design Review | 2 | 2024-12-03 | 6 | Y | 0 | 1 | 2024-12-03 | 6 | Closed | 2 | 0 | 1 |  |  | N |  | 0 | 0 | 0 | 0.2 | 839 | P4 – Low
DRLE-RFI-0336 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Leary Way crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 05 00 Common Work for Utilities | Conflict with 12-in. ductile iron water main at Leary Way crossing | Potholing at Sta. 1045+74 located a 12-in. ductile iron water main in conflict with the proposed column reinforcement. Utility is not shown on S-134. Contractor requests direction on relocation, redesign, or protection in place, and coordination with WSDOT. | Field Engineer | 2024-12-30 | 7 | Routine | Y | Y | N | 0 | Design-Build EOR / ST Design Review | 4 | 2025-01-02 | 3 | Y | 0 | 1 | 2025-01-02 | 3 | Closed | 11 | 0 | 8 | 326000 | 608000 | Y | DRLE-CO-066 | 353700 | 190000 | 3 | 44.7 | 145 | P2 – High
DRLE-RFI-0337 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Bear Creek crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 30 00 Sanitary Sewerage | Conflict with PSE distribution duct bank at Bear Creek crossing | Potholing at Sta. 1169+24 located a PSE distribution duct bank in conflict with the proposed station canopy support. Utility is not shown on E-379. Contractor requests direction on relocation, redesign, or protection in place, and coordination with City of Redmond. | Project Engineer | 2025-01-01 | 7 | Expedite | N | N | N | 4 | Design-Build EOR / ST Design Review | 2 | 2025-01-06 | 5 | Y | 0 | 2 | 2025-01-27 | 24 | Closed | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1369 | P4 – Low
DRLE-RFI-0338 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Redmond Way (SR 202) crossing | UTL | Utility Conflict / Relocation | Civil/Utilities | 33 11 00 Water Utility | Conflict with 8-in. high-pressure gas main at Redmond Way (SR 202) crossing | Potholing at Sta. 2143+69 located a 8-in. high-pressure gas main in conflict with the proposed bearing pad/embed plate. Utility is not shown on E-194. Contractor requests direction on relocation, redesign, or protection in place, and coordination with King County Parks. | Field Engineer | 2025-01-01 | 7 | Expedite | Y | Y | N | 8 | Design-Build EOR / ST Design Review | 1 | 2025-01-06 | 3 | Y | 0 | 2 | 2025-01-10 | 9 | Void/Withdrawn | 0 | 0 | 0 |  |  | N |  | 0 | 0 | 0 | 0 | 1370 | P4 – Low
DRLE-RFI-0339 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | DSC | Differing Site Conditions / Geotechnical | Geotechnical | 31 23 00 Excavation and Fill | Unforeseen condition at Marymoor Village Station: buried concrete debris and an old foundation | During excavation at Marymoor Village Station (Sta. 1615+29) the contractor encountered buried concrete debris and an old foundation, not shown on the GBR or E-732. Work in the area is suspended. Requests direction on temporary shoring modification and confirmation of DSC entitlement. | Design Manager | 2025-02-04 | 7 | Routine | Y | Y | N | 8 | Design-Build EOR / ST Design Review | 3 | 2025-02-10 | 5 | Y | 0 | 1 | 2025-02-10 | 5 | Closed | 17 | 0 | 13 | 145000 | 271000 | Y | DRLE-CO-067 | 382500 | 204400 | 5 | 46.7 | 114 | P2 – High
DRLE-RFI-0340 | DRLE | Downtown Redmond Link Extension | Stacy Witbeck/Kuney, JV | Marymoor Village Station | SYS | Systems Interface (TPSS/OCS/Signals/Comms) | Systems | 34 23 00 Overhead Contact System | Embedded conduit stub-ups – Marymoor Village Station | Systems contractor requires 3-in. PVC conduit stub-ups for tunnel emergency phone at Marymoor Village Station not provided in civil E-591. Request confirmation of locations and coordination of installation prior to the next concrete pour. | Project Manager | 2025-02-27 | 7 | Routine | N | Y | N | 1 | Design-Build EOR / ST Design Review | 1 | 2025-03-06 | 7 | Y | 0 | 2 | 2025-03-12 | 13 | Closed | 5 | 0 | 2 |  |  | N |  | 0 | 0 | 0 | 0.4 | 760 | P4 – Low

## Change_Orders
co_id | pco_id | package_id | project | change_type | dominant_content_category | linked_rfi_count | primary_rfi_id | linked_rfi_ids | notice_of_change_date | pricing_submitted_date | executed_or_closed_date | days_notice_to_pricing | days_pricing_to_close | days_notice_to_close | requested_cost_usd | time_requested_days | dispute_path | funding_source | outcome
DRLE-CO-001 | DRLE-PCO-001 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | DRLE-RFI-0003 | DRLE-RFI-0003 | 2020-01-03 | 2020-01-21 | 2020-04-20 | 18 | 90 | 108 | 762000 | 0 | None | N/A | Rejected – Contractor Responsibility / No Merit
DRLE-CO-002 | DRLE-PCO-002 | DRLE | Downtown Redmond Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | DRLE-RFI-0004 | DRLE-RFI-0004 | 2020-01-27 | 2020-02-13 | 2021-03-08 | 17 | 389 | 406 | 52600 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
DRLE-CO-003 | DRLE-PCO-003 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | DRLE-RFI-0010 | DRLE-RFI-0010 | 2020-04-06 | 2020-04-24 | 2020-08-28 | 18 | 126 | 144 | 150100 | 4 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
DRLE-CO-004 | DRLE-PCO-004 | DRLE | Downtown Redmond Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | DRLE-RFI-0011 | DRLE-RFI-0011 | 2020-04-13 | 2020-05-01 | 2020-08-03 | 18 | 94 | 112 | 550100 | 8 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-005 | DRLE-PCO-005 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | DRLE-RFI-0009 | DRLE-RFI-0009; DRLE-RFI-0012 | 2020-05-01 | 2020-06-01 | 2020-08-31 | 31 | 91 | 122 | 2290500 | 13 | None | Project contingency (within baseline budget) | Executed – As Requested
DRLE-CO-006 | DRLE-PCO-006 | DRLE | Downtown Redmond Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | DRLE-RFI-0014 | DRLE-RFI-0014 | 2020-05-15 | 2020-07-16 | 2020-09-11 | 62 | 57 | 119 | 10300 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-007 | DRLE-PCO-007 | DRLE | Downtown Redmond Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | DRLE-RFI-0025 | DRLE-RFI-0025 | 2020-08-19 | 2020-09-25 | 2020-11-24 | 37 | 60 | 97 | 186400 | 2 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-008 | DRLE-PCO-008 | DRLE | Downtown Redmond Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | DRLE-RFI-0024 | DRLE-RFI-0024 | 2020-08-26 | 2020-10-12 | 2021-03-11 | 47 | 150 | 197 | 284700 | 15 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
DRLE-CO-009 | DRLE-PCO-009 | DRLE | Downtown Redmond Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | DRLE-RFI-0033 | DRLE-RFI-0033 | 2020-10-09 | 2020-12-30 | 2021-06-14 | 82 | 166 | 248 | 396500 | 1 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-010 | DRLE-PCO-010 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | DRLE-RFI-0034 | DRLE-RFI-0034 | 2020-10-26 | 2020-11-23 | 2021-03-18 | 28 | 115 | 143 | 62400 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
DRLE-CO-011 | DRLE-PCO-011 | DRLE | Downtown Redmond Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | DRLE-RFI-0036 | DRLE-RFI-0036 | 2020-10-28 | 2020-11-12 | 2021-01-06 | 15 | 55 | 70 | 777600 | 3 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
DRLE-CO-012 | DRLE-PCO-012 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | DRLE-RFI-0042 | DRLE-RFI-0042 | 2021-01-11 | 2021-02-01 | 2021-05-10 | 21 | 98 | 119 | 121500 | 7 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-013 | DRLE-PCO-013 | DRLE | Downtown Redmond Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | DRLE-RFI-0074 | DRLE-RFI-0074 | 2021-07-09 | 2021-08-09 | 2021-09-20 | 31 | 42 | 73 | 981500 | 3 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-014 | DRLE-PCO-014 | DRLE | Downtown Redmond Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 2 | DRLE-RFI-0056 | DRLE-RFI-0056; DRLE-RFI-0070 | 2021-07-15 | 2021-11-03 | 2022-01-12 | 111 | 70 | 181 | 914300 | 5 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
DRLE-CO-015 | DRLE-PCO-015 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | DRLE-RFI-0096 | DRLE-RFI-0096 | 2021-09-30 | 2021-10-25 | 2021-12-28 | 25 | 64 | 89 | 930900 | 1 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
DRLE-CO-016 | DRLE-PCO-016 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | DRLE-RFI-0079 | DRLE-RFI-0079; DRLE-RFI-0099 | 2021-10-18 | 2021-12-27 | 2022-03-18 | 70 | 81 | 151 | 460700 | 8 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-017 | DRLE-PCO-017 | DRLE | Downtown Redmond Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | DRLE-RFI-0108 | DRLE-RFI-0108 | 2021-11-19 | 2021-11-30 | 2022-05-16 | 11 | 167 | 178 | 273500 | 2 | None | Project contingency (within baseline budget) | Executed – As Requested
DRLE-CO-018 | DRLE-PCO-018 | DRLE | Downtown Redmond Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | DRLE-RFI-0106 | DRLE-RFI-0106 | 2021-11-24 | 2021-12-06 | 2022-02-03 | 12 | 59 | 71 | 369800 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-019 | DRLE-PCO-019 | DRLE | Downtown Redmond Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | DRLE-RFI-0110 | DRLE-RFI-0110 | 2021-12-07 | 2021-12-22 | 2022-02-11 | 15 | 51 | 66 | 163200 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-020 | DRLE-PCO-020 | DRLE | Downtown Redmond Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | DRLE-RFI-0115 | DRLE-RFI-0115 | 2021-12-09 | 2022-01-17 | 2022-02-23 | 39 | 37 | 76 | 21800 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-021 | DRLE-PCO-021 | DRLE | Downtown Redmond Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | DRLE-RFI-0111 | DRLE-RFI-0111 | 2021-12-21 | 2022-01-20 | 2022-05-24 | 30 | 124 | 154 | 1398300 | 4 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
DRLE-CO-022 | DRLE-PCO-022 | DRLE | Downtown Redmond Link Extension | Regulatory / Permit Condition | Environmental / Stormwater / Critical Areas | 1 | DRLE-RFI-0109 | DRLE-RFI-0109 | 2021-12-29 | 2022-01-31 | 2022-09-05 | 33 | 217 | 250 | 73900 | 4 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
DRLE-CO-023 | DRLE-PCO-023 | DRLE | Downtown Redmond Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | DRLE-RFI-0121 | DRLE-RFI-0121 | 2022-01-10 | 2022-02-04 | 2022-04-25 | 25 | 80 | 105 | 30800 | 4 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-024 | DRLE-PCO-024 | DRLE | Downtown Redmond Link Extension | Regulatory / Permit Condition | Environmental / Stormwater / Critical Areas | 1 | DRLE-RFI-0127 | DRLE-RFI-0127 | 2022-01-31 | 2022-03-08 | 2022-06-20 | 36 | 104 | 140 | 79600 | 7 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
DRLE-CO-025 | DRLE-PCO-025 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | DRLE-RFI-0133 | DRLE-RFI-0133 | 2022-02-14 | 2022-02-28 | 2022-03-29 | 14 | 29 | 43 | 87100 | 0 | None | N/A | Withdrawn by Contractor
DRLE-CO-026 | DRLE-PCO-026 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | DRLE-RFI-0134 | DRLE-RFI-0134; DRLE-RFI-0137 | 2022-02-21 | 2022-03-16 | 2022-05-30 | 23 | 75 | 98 | 701400 | 4 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-027 | DRLE-PCO-027 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | DRLE-RFI-0147 | DRLE-RFI-0147 | 2022-04-08 | 2022-05-09 | 2022-07-18 | 31 | 70 | 101 | 27100 | 0 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
DRLE-CO-028 | DRLE-PCO-028 | DRLE | Downtown Redmond Link Extension | Owner-Directed / Work Restriction | Staging / MOT / Access / Sequencing | 1 | DRLE-RFI-0152 | DRLE-RFI-0152 | 2022-05-23 | 2022-07-11 | 2022-09-05 | 49 | 56 | 105 | 57100 | 3 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-029 | DRLE-PCO-029 | DRLE | Downtown Redmond Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | DRLE-RFI-0164 | DRLE-RFI-0164 | 2022-07-14 | 2022-08-22 | 2022-11-07 | 39 | 77 | 116 | 78800 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-030 | DRLE-PCO-030 | DRLE | Downtown Redmond Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | DRLE-RFI-0165 | DRLE-RFI-0165 | 2022-07-20 | 2022-08-15 | 2022-10-03 | 26 | 49 | 75 | 391900 | 5 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-031 | DRLE-PCO-031 | DRLE | Downtown Redmond Link Extension | Owner-Directed | Architectural / Finishes / Station Elements | 1 | DRLE-RFI-0169 | DRLE-RFI-0169 | 2022-08-09 | 2022-08-29 | 2022-10-10 | 20 | 42 | 62 | 85200 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-032 | DRLE-PCO-032 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | DRLE-RFI-0173 | DRLE-RFI-0173 | 2022-09-05 | 2022-09-29 | 2023-01-30 | 24 | 123 | 147 | 252400 | 0 | None | N/A | Rejected – Contractor Responsibility / No Merit
DRLE-CO-033 | DRLE-PCO-033 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | DRLE-RFI-0187 | DRLE-RFI-0187; DRLE-RFI-0189 | 2022-10-24 | 2022-12-12 | 2023-02-01 | 49 | 51 | 100 | 780900 | 12 | None | N/A | Rejected – Contractor Responsibility / No Merit
DRLE-CO-034 | DRLE-PCO-034 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 3 | DRLE-RFI-0191 | DRLE-RFI-0191; DRLE-RFI-0194; DRLE-RFI-0195 | 2022-11-21 | 2022-12-21 | 2023-02-20 | 30 | 61 | 91 | 1318300 | 8 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-035 | DRLE-PCO-035 | DRLE | Downtown Redmond Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | DRLE-RFI-0196 | DRLE-RFI-0196 | 2022-11-29 | 2023-01-25 | 2023-03-24 | 57 | 58 | 115 | 166500 | 4 | None | N/A | Rejected – Contractor Responsibility / No Merit
DRLE-CO-036 | DRLE-PCO-036 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | DRLE-RFI-0181 | DRLE-RFI-0181; DRLE-RFI-0202 | 2022-12-19 | 2023-03-02 | 2023-08-17 | 73 | 168 | 241 | 2554000 | 5 | Dispute Review Board | Project contingency (within baseline budget) | Escalated to DRB – Partial Award
DRLE-CO-037 | DRLE-PCO-037 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | DRLE-RFI-0203 | DRLE-RFI-0203 | 2022-12-28 | 2023-02-24 | 2023-07-24 | 58 | 150 | 208 | 1006300 | 2 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-038 | DRLE-PCO-038 | DRLE | Downtown Redmond Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | DRLE-RFI-0210 | DRLE-RFI-0210 | 2023-01-25 | 2023-02-27 | 2023-05-15 | 33 | 77 | 110 | 5199900 | 0 | None | N/A | Withdrawn by Contractor
DRLE-CO-039 | DRLE-PCO-039 | DRLE | Downtown Redmond Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | DRLE-RFI-0212 | DRLE-RFI-0212 | 2023-01-25 | 2023-02-08 | 2023-09-06 | 14 | 210 | 224 | 314900 | 1 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-040 | DRLE-PCO-040 | DRLE | Downtown Redmond Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | DRLE-RFI-0213 | DRLE-RFI-0213 | 2023-01-30 | 2023-02-13 | 2023-09-08 | 14 | 207 | 221 | 236200 | 2 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
DRLE-CO-041 | DRLE-PCO-041 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | DRLE-RFI-0221 | DRLE-RFI-0221 | 2023-02-13 | 2023-04-18 | 2023-05-29 | 64 | 41 | 105 | 430800 | 6 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-042 | DRLE-PCO-042 | DRLE | Downtown Redmond Link Extension | Contractor-Requested | Material / Submittal / Substitution | 1 | DRLE-RFI-0224 | DRLE-RFI-0224 | 2023-03-13 | 2023-04-17 | 2023-05-24 | 35 | 37 | 72 | 22900 | 0 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
DRLE-CO-043 | DRLE-PCO-043 | DRLE | Downtown Redmond Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | DRLE-RFI-0234 | DRLE-RFI-0234 | 2023-04-28 | 2023-06-19 | 2024-02-05 | 52 | 231 | 283 | 985300 | 4 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
DRLE-CO-044 | DRLE-PCO-044 | DRLE | Downtown Redmond Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | DRLE-RFI-0231 | DRLE-RFI-0231 | 2023-05-22 | 2023-06-12 | 2023-09-20 | 21 | 100 | 121 | 301600 | 3 | None | Project contingency (within baseline budget) | Executed – As Requested
DRLE-CO-045 | DRLE-PCO-045 | DRLE | Downtown Redmond Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | DRLE-RFI-0245 | DRLE-RFI-0245 | 2023-06-19 | 2023-07-31 | 2023-10-12 | 42 | 73 | 115 | 163700 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-046 | DRLE-PCO-046 | DRLE | Downtown Redmond Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | DRLE-RFI-0246 | DRLE-RFI-0246 | 2023-06-22 | 2023-07-17 | 2023-10-16 | 25 | 91 | 116 | 261700 | 1 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-047 | DRLE-PCO-047 | DRLE | Downtown Redmond Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 2 | DRLE-RFI-0230 | DRLE-RFI-0230; DRLE-RFI-0248 | 2023-07-10 | 2023-08-08 | 2023-10-26 | 29 | 79 | 108 | 476600 | 2 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-048 | DRLE-PCO-048 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | DRLE-RFI-0250 | DRLE-RFI-0250 | 2023-07-14 | 2023-08-11 | 2023-10-12 | 28 | 62 | 90 | 931000 | 2 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-049 | DRLE-PCO-049 | DRLE | Downtown Redmond Link Extension | Regulatory / Permit Condition | Environmental / Stormwater / Critical Areas | 1 | DRLE-RFI-0253 | DRLE-RFI-0253 | 2023-07-31 | 2023-09-11 | 2023-10-17 | 42 | 36 | 78 | 82600 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-050 | DRLE-PCO-050 | DRLE | Downtown Redmond Link Extension | Regulatory / Permit Condition | Environmental / Stormwater / Critical Areas | 1 | DRLE-RFI-0271 | DRLE-RFI-0271 | 2023-09-22 | 2023-10-05 | 2024-03-05 | 13 | 152 | 165 | 243200 | 1 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
DRLE-CO-051 | DRLE-PCO-051 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | DRLE-RFI-0277 | DRLE-RFI-0277 | 2023-11-03 | 2023-11-27 | 2024-01-29 | 24 | 63 | 87 | 59400 | 4 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-052 | DRLE-PCO-052 | DRLE | Downtown Redmond Link Extension | Owner-Directed / Work Restriction | Staging / MOT / Access / Sequencing | 1 | DRLE-RFI-0283 | DRLE-RFI-0283 | 2023-11-20 | 2024-01-26 | 2024-05-27 | 67 | 122 | 189 | 16900 | 0 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
DRLE-CO-053 | DRLE-PCO-053 | DRLE | Downtown Redmond Link Extension | Regulatory / Permit Condition | Environmental / Stormwater / Critical Areas | 1 | DRLE-RFI-0282 | DRLE-RFI-0282 | 2023-11-22 | 2023-12-11 | 2024-02-01 | 19 | 52 | 71 | 47000 | 3 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
DRLE-CO-054 | DRLE-PCO-054 | DRLE | Downtown Redmond Link Extension | Design Error/Omission | Design Conflict / Constructability | 2 | DRLE-RFI-0284 | DRLE-RFI-0284; DRLE-RFI-0285 | 2023-12-06 | 2023-12-18 | 2024-03-18 | 12 | 91 | 103 | 355800 | 12 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-055 | DRLE-PCO-055 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 3 | DRLE-RFI-0276 | DRLE-RFI-0276; DRLE-RFI-0292; DRLE-RFI-0294 | 2024-01-19 | 2024-02-14 | 2024-04-30 | 26 | 76 | 102 | 482900 | 23 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-056 | DRLE-PCO-056 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | DRLE-RFI-0287 | DRLE-RFI-0287; DRLE-RFI-0296 | 2024-02-05 | 2024-03-08 | 2024-06-21 | 32 | 105 | 137 | 995800 | 9 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-057 | DRLE-PCO-057 | DRLE | Downtown Redmond Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | DRLE-RFI-0298 | DRLE-RFI-0298 | 2024-02-23 | 2024-03-15 | 2024-04-30 | 21 | 46 | 67 | 1625200 | 14 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-058 | DRLE-PCO-058 | DRLE | Downtown Redmond Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | DRLE-RFI-0304 | DRLE-RFI-0304 | 2024-03-04 | 2024-04-08 | 2024-07-29 | 35 | 112 | 147 | 151800 | 4 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
DRLE-CO-059 | DRLE-PCO-059 | DRLE | Downtown Redmond Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | DRLE-RFI-0308 | DRLE-RFI-0308 | 2024-05-06 | 2024-06-13 | 2024-09-11 | 38 | 90 | 128 | 372500 | 7 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
DRLE-CO-060 | DRLE-PCO-060 | DRLE | Downtown Redmond Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | DRLE-RFI-0309 | DRLE-RFI-0309 | 2024-05-27 | 2024-07-08 | 2024-10-16 | 42 | 100 | 142 | 154300 | 6 | Dispute Review Board | Project contingency (within baseline budget) | Escalated to DRB – Partial Award
DRLE-CO-061 | DRLE-PCO-061 | DRLE | Downtown Redmond Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | DRLE-RFI-0311 | DRLE-RFI-0311 | 2024-06-07 | 2024-07-31 | 2024-12-26 | 54 | 148 | 202 | 400300 | 1 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-062 | DRLE-PCO-062 | DRLE | Downtown Redmond Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | DRLE-RFI-0313 | DRLE-RFI-0313 | 2024-06-17 | 2024-07-22 | 2024-09-30 | 35 | 70 | 105 | 110600 | 0 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
DRLE-CO-063 | DRLE-PCO-063 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | DRLE-RFI-0317 | DRLE-RFI-0317 | 2024-07-05 | 2024-08-22 | 2024-12-17 | 48 | 117 | 165 | 4126900 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
DRLE-CO-064 | DRLE-PCO-064 | DRLE | Downtown Redmond Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | DRLE-RFI-0320 | DRLE-RFI-0320 | 2024-09-05 | 2024-10-07 | 2025-01-09 | 32 | 94 | 126 | 202700 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-065 | DRLE-PCO-065 | DRLE | Downtown Redmond Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | DRLE-RFI-0326 | DRLE-RFI-0326 | 2024-10-03 | 2024-10-30 | 2025-01-01 | 27 | 63 | 90 | 283200 | 0 | None | N/A | Rejected – Contractor Responsibility / No Merit
DRLE-CO-066 | DRLE-PCO-066 | DRLE | Downtown Redmond Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | DRLE-RFI-0336 | DRLE-RFI-0336 | 2025-01-06 | 2025-01-31 | 2025-04-22 | 25 | 81 | 106 | 353700 | 7 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
DRLE-CO-067 | DRLE-PCO-067 | DRLE | Downtown Redmond Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | DRLE-RFI-0339 | DRLE-RFI-0339 | 2025-02-17 | 2025-04-23 | 2025-07-16 | 65 | 84 | 149 | 382500 | 12 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-001 | E320-PCO-001 | E320 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E320-RFI-0004 | E320-RFI-0004 | 2016-12-01 | 2016-12-26 | 2017-03-15 | 25 | 79 | 104 | 103900 | 0 | Dispute Review Board | Project contingency (within baseline budget) | Escalated to DRB – Partial Award
E320-CO-002 | E320-PCO-002 | E320 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E320-RFI-0009 | E320-RFI-0009 | 2017-01-31 | 2017-02-24 | 2017-04-26 | 24 | 61 | 85 | 162700 | 0 | None | N/A | Withdrawn by Contractor
E320-CO-003 | E320-PCO-003 | E320 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 2 | E320-RFI-0014 | E320-RFI-0014; E320-RFI-0018 | 2017-04-17 | 2017-05-12 | 2017-07-24 | 25 | 73 | 98 | 186900 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E320-CO-004 | E320-PCO-004 | E320 | East Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | E320-RFI-0020 | E320-RFI-0020 | 2017-05-05 | 2017-05-17 | 2017-08-14 | 12 | 89 | 101 | 33200 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E320-CO-005 | E320-PCO-005 | E320 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E320-RFI-0026 | E320-RFI-0026 | 2017-08-14 | 2017-09-01 | 2017-10-30 | 18 | 59 | 77 | 17400 | 2 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-006 | E320-PCO-006 | E320 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | E320-RFI-0027 | E320-RFI-0027; E320-RFI-0029 | 2017-09-12 | 2017-10-03 | 2017-12-13 | 21 | 71 | 92 | 523300 | 20 | None | Project contingency (within baseline budget) | Executed – As Requested
E320-CO-007 | E320-PCO-007 | E320 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 2 | E320-RFI-0030 | E320-RFI-0030; E320-RFI-0033 | 2017-09-27 | 2017-10-18 | 2017-12-11 | 21 | 54 | 75 | 151400 | 17 | None | Project contingency (within baseline budget) | Executed – As Requested
E320-CO-008 | E320-PCO-008 | E320 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E320-RFI-0034 | E320-RFI-0034 | 2017-10-30 | 2017-11-24 | 2017-12-12 | 25 | 18 | 43 | 32200 | 0 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E320-CO-009 | E320-PCO-009 | E320 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E320-RFI-0040 | E320-RFI-0040 | 2017-11-24 | 2017-12-04 | 2019-03-18 | 10 | 469 | 479 | 34500 | 0 | Dispute Review Board | Project contingency (within baseline budget) | Escalated to DRB – Partial Award
E320-CO-010 | E320-PCO-010 | E320 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E320-RFI-0039 | E320-RFI-0039 | 2017-12-01 | 2017-12-18 | 2018-03-12 | 17 | 84 | 101 | 114600 | 5 | None | Project contingency (within baseline budget) | Executed – As Requested
E320-CO-011 | E320-PCO-011 | E320 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | E320-RFI-0042 | E320-RFI-0042; E320-RFI-0043 | 2018-01-09 | 2018-02-16 | 2018-04-20 | 38 | 63 | 101 | 386600 | 28 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E320-CO-012 | E320-PCO-012 | E320 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 2 | E320-RFI-0038 | E320-RFI-0038; E320-RFI-0047 | 2018-01-29 | 2018-02-23 | 2018-04-24 | 25 | 60 | 85 | 2807200 | 31 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-013 | E320-PCO-013 | E320 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E320-RFI-0049 | E320-RFI-0049 | 2018-02-21 | 2018-03-26 | 2018-07-02 | 33 | 98 | 131 | 42100 | 0 | Dispute Review Board | Project contingency (within baseline budget) | Escalated to DRB – Partial Award
E320-CO-014 | E320-PCO-014 | E320 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E320-RFI-0055 | E320-RFI-0055 | 2018-03-27 | 2018-04-24 | 2018-06-21 | 28 | 58 | 86 | 463100 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E320-CO-015 | E320-PCO-015 | E320 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E320-RFI-0058 | E320-RFI-0058 | 2018-04-23 | 2018-06-14 | 2018-11-08 | 52 | 147 | 199 | 120600 | 2 | Dispute Review Board | Project contingency (within baseline budget) | Escalated to DRB – Partial Award
E320-CO-016 | E320-PCO-016 | E320 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E320-RFI-0062 | E320-RFI-0062 | 2018-05-07 | 2018-07-02 | 2018-07-25 | 56 | 23 | 79 | 34800 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-017 | E320-PCO-017 | E320 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E320-RFI-0064 | E320-RFI-0064 | 2018-05-14 | 2018-06-06 | 2018-08-27 | 23 | 82 | 105 | 38200 | 12 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-018 | E320-PCO-018 | E320 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E320-RFI-0063 | E320-RFI-0063 | 2018-05-18 | 2018-06-13 | 2018-09-06 | 26 | 85 | 111 | 265800 | 3 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E320-CO-019 | E320-PCO-019 | E320 | East Link Extension | Owner-Directed / Work Restriction | Staging / MOT / Access / Sequencing | 2 | E320-RFI-0067 | E320-RFI-0067; E320-RFI-0068 | 2018-06-15 | 2018-07-05 | 2018-09-14 | 20 | 71 | 91 | 175800 | 44 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
E320-CO-020 | E320-PCO-020 | E320 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E320-RFI-0078 | E320-RFI-0078 | 2018-09-21 | 2018-12-03 | 2019-04-22 | 73 | 140 | 213 | 134600 | 2 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-021 | E320-PCO-021 | E320 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 2 | E320-RFI-0073 | E320-RFI-0073; E320-RFI-0077 | 2018-10-01 | 2018-10-29 | 2019-01-14 | 28 | 77 | 105 | 800000 | 26 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-022 | E320-PCO-022 | E320 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E320-RFI-0082 | E320-RFI-0082 | 2018-10-29 | 2018-11-26 | 2019-01-28 | 28 | 63 | 91 | 124600 | 6 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-023 | E320-PCO-023 | E320 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E320-RFI-0081 | E320-RFI-0081 | 2018-11-05 | 2018-12-05 | 2019-02-14 | 30 | 71 | 101 | 252200 | 2 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-024 | E320-PCO-024 | E320 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | E320-RFI-0086 | E320-RFI-0086; E320-RFI-0088 | 2018-12-17 | 2019-01-07 | 2019-03-04 | 21 | 56 | 77 | 119500 | 6 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E320-CO-025 | E320-PCO-025 | E320 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E320-RFI-0092 | E320-RFI-0092 | 2019-02-11 | 2019-03-18 | 2019-10-07 | 35 | 203 | 238 | 2685700 | 31 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E320-CO-026 | E320-PCO-026 | E320 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E320-RFI-0101 | E320-RFI-0101 | 2019-05-16 | 2019-06-18 | 2019-09-23 | 33 | 97 | 130 | 211700 | 0 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
E320-CO-027 | E320-PCO-027 | E320 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 2 | E320-RFI-0096 | E320-RFI-0096; E320-RFI-0100 | 2019-05-20 | 2019-07-10 | 2019-11-11 | 51 | 124 | 175 | 34900 | 5 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E320-CO-028 | E320-PCO-028 | E320 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E320-RFI-0103 | E320-RFI-0103 | 2019-05-27 | 2019-06-26 | 2019-11-08 | 30 | 135 | 165 | 117200 | 15 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-029 | E320-PCO-029 | E320 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E320-RFI-0111 | E320-RFI-0111 | 2019-09-04 | 2019-09-30 | 2019-12-31 | 26 | 92 | 118 | 721100 | 8 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-030 | E320-PCO-030 | E320 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E320-RFI-0120 | E320-RFI-0120 | 2019-12-12 | 2019-12-27 | 2020-04-27 | 15 | 122 | 137 | 43400 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-031 | E320-PCO-031 | E320 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E320-RFI-0121 | E320-RFI-0121 | 2019-12-24 | 2020-01-17 | 2020-02-21 | 24 | 35 | 59 | 537000 | 7 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-032 | E320-PCO-032 | E320 | East Link Extension | Owner-Directed / Work Restriction | Staging / MOT / Access / Sequencing | 1 | E320-RFI-0123 | E320-RFI-0123 | 2019-12-30 | 2020-01-27 | 2020-03-11 | 28 | 44 | 72 | 68700 | 7 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-033 | E320-PCO-033 | E320 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E320-RFI-0124 | E320-RFI-0124 | 2020-01-03 | 2020-01-24 | 2020-02-27 | 21 | 34 | 55 | 38700 | 7 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-034 | E320-PCO-034 | E320 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E320-RFI-0122 | E320-RFI-0122 | 2020-01-06 | 2020-01-16 | 2020-03-16 | 10 | 60 | 70 | 384500 | 3 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-035 | E320-PCO-035 | E320 | East Link Extension | Design Error/Omission | Trackwork / Track-Structure Interface | 1 | E320-RFI-0126 | E320-RFI-0126 | 2020-01-28 | 2020-02-17 | 2020-04-09 | 20 | 52 | 72 | 71500 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E320-CO-036 | E320-PCO-036 | E320 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E320-RFI-0129 | E320-RFI-0129 | 2020-02-24 | 2020-03-09 | 2020-05-18 | 14 | 70 | 84 | 340900 | 18 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E320-CO-037 | E320-PCO-037 | E320 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E320-RFI-0131 | E320-RFI-0131 | 2020-03-11 | 2020-05-04 | 2020-06-23 | 54 | 50 | 104 | 125800 | 5 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
E320-CO-038 | E320-PCO-038 | E320 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E320-RFI-0134 | E320-RFI-0134 | 2020-04-10 | 2020-05-25 | 2020-07-16 | 45 | 52 | 97 | 268400 | 11 | None | N/A | Rejected – Contractor Responsibility / No Merit
E320-CO-039 | E320-PCO-039 | E320 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 2 | E320-RFI-0132 | E320-RFI-0132; E320-RFI-0137 | 2020-04-28 | 2020-05-20 | 2020-10-16 | 22 | 149 | 171 | 1394300 | 11 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E320-CO-040 | E320-PCO-040 | E320 | East Link Extension | Regulatory / Permit Condition | Environmental / Stormwater / Critical Areas | 1 | E320-RFI-0139 | E320-RFI-0139 | 2020-06-01 | 2020-07-03 | 2020-09-25 | 32 | 84 | 116 | 86200 | 12 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-041 | E320-PCO-041 | E320 | East Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | E320-RFI-0143 | E320-RFI-0143 | 2020-08-19 | 2020-09-09 | 2021-08-18 | 21 | 343 | 364 | 63900 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E320-CO-042 | E320-PCO-042 | E320 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E320-RFI-0144 | E320-RFI-0144 | 2020-08-31 | 2020-10-12 | 2020-11-16 | 42 | 35 | 77 | 2333100 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E320-CO-043 | E320-PCO-043 | E320 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E320-RFI-0145 | E320-RFI-0145 | 2020-10-14 | 2020-11-13 | 2021-01-19 | 30 | 67 | 97 | 255900 | 14 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E320-CO-044 | E320-PCO-044 | E320 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E320-RFI-0150 | E320-RFI-0150 | 2021-04-26 | 2021-07-13 | 2021-09-23 | 78 | 72 | 150 | 66200 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E330-CO-001 | E330-PCO-001 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E330-RFI-0001 | E330-RFI-0001 | 2016-06-08 | 2016-07-13 | 2016-08-08 | 35 | 26 | 61 | 83500 | 0 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E330-CO-002 | E330-PCO-002 | E330 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E330-RFI-0002 | E330-RFI-0002 | 2016-07-26 | 2016-09-07 | 2016-11-24 | 43 | 78 | 121 | 75100 | 14 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E330-CO-003 | E330-PCO-003 | E330 | East Link Extension | Owner-Directed / Work Restriction | Staging / MOT / Access / Sequencing | 1 | E330-RFI-0006 | E330-RFI-0006 | 2016-10-21 | 2016-10-31 | 2017-02-07 | 10 | 99 | 109 | 9200 | 5 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E330-CO-004 | E330-PCO-004 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E330-RFI-0012 | E330-RFI-0012 | 2017-01-27 | 2017-02-10 | 2017-08-22 | 14 | 193 | 207 | 1239900 | 10 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E330-CO-005 | E330-PCO-005 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | E330-RFI-0010 | E330-RFI-0010; E330-RFI-0014 | 2017-03-06 | 2017-04-10 | 2017-10-18 | 35 | 191 | 226 | 2116000 | 6 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E330-CO-006 | E330-PCO-006 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 3 | E330-RFI-0015 | E330-RFI-0015; E330-RFI-0016; E330-RFI-0017 | 2017-03-28 | 2017-04-10 | 2017-07-17 | 13 | 98 | 111 | 540300 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E330-CO-007 | E330-PCO-007 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E330-RFI-0022 | E330-RFI-0022 | 2017-05-22 | 2017-06-14 | 2017-07-26 | 23 | 42 | 65 | 69800 | 3 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
E330-CO-008 | E330-PCO-008 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | E330-RFI-0019 | E330-RFI-0019; E330-RFI-0023 | 2017-06-07 | 2017-06-20 | 2017-10-26 | 13 | 128 | 141 | 247100 | 7 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E330-CO-009 | E330-PCO-009 | E330 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E330-RFI-0025 | E330-RFI-0025 | 2017-06-26 | 2017-07-26 | 2017-09-04 | 30 | 40 | 70 | 107500 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E330-CO-010 | E330-PCO-010 | E330 | East Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | E330-RFI-0027 | E330-RFI-0027 | 2017-07-24 | 2017-08-14 | 2017-11-06 | 21 | 84 | 105 | 98200 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E330-CO-011 | E330-PCO-011 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 2 | E330-RFI-0024 | E330-RFI-0024; E330-RFI-0029 | 2017-08-15 | 2017-09-26 | 2017-12-08 | 42 | 73 | 115 | 1911600 | 21 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
E330-CO-012 | E330-PCO-012 | E330 | East Link Extension | Regulatory / Permit Condition | Environmental / Stormwater / Critical Areas | 1 | E330-RFI-0035 | E330-RFI-0035 | 2017-09-13 | 2017-10-11 | 2017-12-20 | 28 | 70 | 98 | 85000 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E330-CO-013 | E330-PCO-013 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E330-RFI-0038 | E330-RFI-0038 | 2017-09-22 | 2017-09-29 | 2017-12-28 | 7 | 90 | 97 | 106300 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E330-CO-014 | E330-PCO-014 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | E330-RFI-0042 | E330-RFI-0042; E330-RFI-0047 | 2017-11-08 | 2017-12-07 | 2018-02-12 | 29 | 67 | 96 | 386700 | 8 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E330-CO-015 | E330-PCO-015 | E330 | East Link Extension | Owner-Directed / Work Restriction | Staging / MOT / Access / Sequencing | 1 | E330-RFI-0048 | E330-RFI-0048 | 2017-11-13 | 2017-12-27 | 2018-02-20 | 44 | 55 | 99 | 40700 | 2 | None | Project contingency (within baseline budget) | Executed – As Requested
E330-CO-016 | E330-PCO-016 | E330 | East Link Extension | Owner-Directed / Work Restriction | Staging / MOT / Access / Sequencing | 1 | E330-RFI-0050 | E330-RFI-0050 | 2017-11-21 | 2017-12-19 | 2018-02-19 | 28 | 62 | 90 | 56500 | 3 | None | N/A | Rejected – Contractor Responsibility / No Merit
E330-CO-017 | E330-PCO-017 | E330 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E330-RFI-0054 | E330-RFI-0054 | 2017-12-25 | 2018-01-29 | 2018-03-19 | 35 | 49 | 84 | 263300 | 9 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E330-CO-018 | E330-PCO-018 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 3 | E330-RFI-0046 | E330-RFI-0046; E330-RFI-0053; E330-RFI-0055 | 2018-01-01 | 2018-03-12 | 2018-06-12 | 70 | 92 | 162 | 356700 | 10 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E330-CO-019 | E330-PCO-019 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E330-RFI-0056 | E330-RFI-0056 | 2018-01-08 | 2018-01-31 | 2018-03-30 | 23 | 58 | 81 | 112100 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E330-CO-020 | E330-PCO-020 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E330-RFI-0059 | E330-RFI-0059 | 2018-01-18 | 2018-02-26 | 2018-04-20 | 39 | 53 | 92 | 363100 | 10 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E330-CO-021 | E330-PCO-021 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E330-RFI-0061 | E330-RFI-0061 | 2018-02-20 | 2018-03-16 | 2018-05-07 | 24 | 52 | 76 | 283300 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E330-CO-022 | E330-PCO-022 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E330-RFI-0069 | E330-RFI-0069 | 2018-03-01 | 2018-04-24 | 2019-03-18 | 54 | 328 | 382 | 9800 | 12 | Dispute Review Board | Project contingency (within baseline budget) | Escalated to DRB – Partial Award
E330-CO-023 | E330-PCO-023 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E330-RFI-0067 | E330-RFI-0067 | 2018-03-12 | 2018-03-26 | 2018-06-12 | 14 | 78 | 92 | 564900 | 9 | None | N/A | Withdrawn by Contractor
E330-CO-024 | E330-PCO-024 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | E330-RFI-0077 | E330-RFI-0077; E330-RFI-0080 | 2018-07-03 | 2018-11-06 | 2019-03-11 | 126 | 125 | 251 | 676500 | 5 | None | N/A | Withdrawn by Contractor
E330-CO-025 | E330-PCO-025 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 2 | E330-RFI-0081 | E330-RFI-0081; E330-RFI-0083 | 2018-07-30 | 2018-09-24 | 2018-11-05 | 56 | 42 | 98 | 1267000 | 0 | None | N/A | Withdrawn by Contractor
E330-CO-026 | E330-PCO-026 | E330 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 2 | E330-RFI-0084 | E330-RFI-0084; E330-RFI-0085 | 2018-09-10 | 2018-11-13 | 2018-12-31 | 64 | 48 | 112 | 109600 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E330-CO-027 | E330-PCO-027 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 2 | E330-RFI-0082 | E330-RFI-0082; E330-RFI-0087 | 2018-09-21 | 2018-11-09 | 2018-12-19 | 49 | 40 | 89 | 1292200 | 18 | None | N/A | Rejected – Contractor Responsibility / No Merit
E330-CO-028 | E330-PCO-028 | E330 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E330-RFI-0089 | E330-RFI-0089 | 2018-10-19 | 2018-11-16 | 2019-05-31 | 28 | 196 | 224 | 103600 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E330-CO-029 | E330-PCO-029 | E330 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E330-RFI-0095 | E330-RFI-0095 | 2018-11-02 | 2018-12-10 | 2019-02-04 | 38 | 56 | 94 | 158000 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E330-CO-030 | E330-PCO-030 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E330-RFI-0097 | E330-RFI-0097 | 2018-11-23 | 2018-12-19 | 2019-02-15 | 26 | 58 | 84 | 37600 | 4 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E330-CO-031 | E330-PCO-031 | E330 | East Link Extension | Owner-Directed / Work Restriction | Staging / MOT / Access / Sequencing | 1 | E330-RFI-0103 | E330-RFI-0103 | 2019-01-03 | 2019-01-18 | 2019-07-31 | 15 | 194 | 209 | 154700 | 0 | None | Project contingency (within baseline budget) | Executed – As Requested
E330-CO-032 | E330-PCO-032 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 2 | E330-RFI-0093 | E330-RFI-0093; E330-RFI-0100 | 2019-01-04 | 2019-03-11 | 2019-05-09 | 66 | 59 | 125 | 8542200 | 34 | None | N/A | Withdrawn by Contractor
E330-CO-033 | E330-PCO-033 | E330 | East Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | E330-RFI-0114 | E330-RFI-0114 | 2019-03-15 | 2019-05-22 | 2020-07-21 | 68 | 426 | 494 | 8200 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E330-CO-034 | E330-PCO-034 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 2 | E330-RFI-0108 | E330-RFI-0108; E330-RFI-0121 | 2019-04-22 | 2019-06-24 | 2019-08-21 | 63 | 58 | 121 | 80100 | 53 | Dispute Review Board | Project contingency (within baseline budget) | Escalated to DRB – Partial Award
E330-CO-035 | E330-PCO-035 | E330 | East Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 2 | E330-RFI-0120 | E330-RFI-0120; E330-RFI-0123 | 2019-04-23 | 2019-05-27 | 2019-10-07 | 34 | 133 | 167 | 162700 | 0 | None | Project contingency (within baseline budget) | Executed – As Requested
E330-CO-036 | E330-PCO-036 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E330-RFI-0127 | E330-RFI-0127 | 2019-05-03 | 2019-05-27 | 2019-10-21 | 24 | 147 | 171 | 215300 | 0 | Dispute Review Board | Project contingency (within baseline budget) | Escalated to DRB – Partial Award
E330-CO-037 | E330-PCO-037 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E330-RFI-0125 | E330-RFI-0125 | 2019-05-09 | 2019-05-20 | 2019-06-28 | 11 | 39 | 50 | 180700 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E330-CO-038 | E330-PCO-038 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | E330-RFI-0129 | E330-RFI-0129; E330-RFI-0139 | 2019-09-20 | 2019-10-18 | 2019-12-09 | 28 | 52 | 80 | 346600 | 4 | None | Project contingency (within baseline budget) | Executed – As Requested
E330-CO-039 | E330-PCO-039 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 4 | E330-RFI-0128 | E330-RFI-0128; E330-RFI-0137; E330-RFI-0138; E330-RFI-0142 | 2019-11-04 | 2019-12-20 | 2020-03-23 | 46 | 94 | 140 | 1010300 | 12 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E330-CO-040 | E330-PCO-040 | E330 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E330-RFI-0150 | E330-RFI-0150 | 2020-01-29 | 2020-02-20 | 2020-05-04 | 22 | 74 | 96 | 209300 | 11 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E330-CO-041 | E330-PCO-041 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E330-RFI-0151 | E330-RFI-0151 | 2020-02-14 | 2020-03-19 | 2020-05-19 | 34 | 61 | 95 | 259200 | 9 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E330-CO-042 | E330-PCO-042 | E330 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E330-RFI-0154 | E330-RFI-0154 | 2020-04-01 | 2020-04-22 | 2020-06-22 | 21 | 61 | 82 | 1224200 | 1 | None | Project contingency (within baseline budget) | Executed – As Requested
E330-CO-043 | E330-PCO-043 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E330-RFI-0156 | E330-RFI-0156 | 2020-04-27 | 2020-08-11 | 2020-10-07 | 106 | 57 | 163 | 497600 | 4 | None | N/A | Withdrawn by Contractor
E330-CO-044 | E330-PCO-044 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E330-RFI-0163 | E330-RFI-0163 | 2020-06-01 | 2020-06-19 | 2020-08-03 | 18 | 45 | 63 | 206700 | 21 | None | Project contingency (within baseline budget) | Executed – As Requested
E330-CO-045 | E330-PCO-045 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E330-RFI-0166 | E330-RFI-0166 | 2020-07-02 | 2020-07-30 | 2021-01-14 | 28 | 168 | 196 | 285600 | 22 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E330-CO-046 | E330-PCO-046 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E330-RFI-0168 | E330-RFI-0168 | 2020-09-22 | 2020-10-12 | 2021-08-18 | 20 | 310 | 330 | 285900 | 6 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E330-CO-047 | E330-PCO-047 | E330 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E330-RFI-0169 | E330-RFI-0169 | 2020-11-11 | 2020-12-14 | 2021-08-16 | 33 | 245 | 278 | 543900 | 4 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E330-CO-048 | E330-PCO-048 | E330 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E330-RFI-0170 | E330-RFI-0170 | 2020-12-14 | 2020-12-30 | 2021-02-15 | 16 | 47 | 63 | 422100 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-001 | E335-PCO-001 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0004 | E335-RFI-0004 | 2017-05-24 | 2017-06-27 | 2017-09-06 | 34 | 71 | 105 | 53200 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-002 | E335-PCO-002 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0005 | E335-RFI-0005 | 2017-07-10 | 2017-08-30 | 2017-09-19 | 51 | 20 | 71 | 626800 | 5 | None | Project contingency (within baseline budget) | Executed – As Requested
E335-CO-003 | E335-PCO-003 | E335 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E335-RFI-0010 | E335-RFI-0010 | 2017-11-27 | 2017-12-29 | 2018-03-19 | 32 | 80 | 112 | 312300 | 5 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-004 | E335-PCO-004 | E335 | East Link Extension | Design Error/Omission | Trackwork / Track-Structure Interface | 1 | E335-RFI-0011 | E335-RFI-0011 | 2017-11-27 | 2018-01-10 | 2018-07-04 | 44 | 175 | 219 | 14700 | 0 | None | Project contingency (within baseline budget) | Executed – As Requested
E335-CO-005 | E335-PCO-005 | E335 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E335-RFI-0013 | E335-RFI-0013 | 2018-01-09 | 2018-01-22 | 2018-04-03 | 13 | 71 | 84 | 106700 | 16 | None | Project contingency (within baseline budget) | Executed – As Requested
E335-CO-006 | E335-PCO-006 | E335 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E335-RFI-0014 | E335-RFI-0014 | 2018-03-01 | 2018-03-26 | 2018-09-11 | 25 | 169 | 194 | 536700 | 25 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E335-CO-007 | E335-PCO-007 | E335 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E335-RFI-0018 | E335-RFI-0018 | 2018-03-20 | 2018-04-27 | 2018-07-19 | 38 | 83 | 121 | 399300 | 7 | None | Project contingency (within baseline budget) | Executed – As Requested
E335-CO-008 | E335-PCO-008 | E335 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E335-RFI-0020 | E335-RFI-0020 | 2018-03-23 | 2018-05-04 | 2018-06-18 | 42 | 45 | 87 | 45600 | 0 | None | N/A | Withdrawn by Contractor
E335-CO-009 | E335-PCO-009 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0022 | E335-RFI-0022 | 2018-04-23 | 2018-06-11 | 2018-09-17 | 49 | 98 | 147 | 1325100 | 2 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-010 | E335-PCO-010 | E335 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E335-RFI-0025 | E335-RFI-0025 | 2018-04-23 | 2018-05-09 | 2018-06-20 | 16 | 42 | 58 | 1941600 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-011 | E335-PCO-011 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 2 | E335-RFI-0031 | E335-RFI-0031; E335-RFI-0038 | 2018-10-15 | 2018-11-29 | 2019-05-06 | 45 | 158 | 203 | 4554800 | 4 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-012 | E335-PCO-012 | E335 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E335-RFI-0043 | E335-RFI-0043 | 2018-12-25 | 2019-01-07 | 2019-02-01 | 13 | 25 | 38 | 166800 | 4 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E335-CO-013 | E335-PCO-013 | E335 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E335-RFI-0046 | E335-RFI-0046 | 2019-01-28 | 2019-03-04 | 2019-06-05 | 35 | 93 | 128 | 426800 | 20 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-014 | E335-PCO-014 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0051 | E335-RFI-0051 | 2019-02-18 | 2019-05-16 | 2019-10-24 | 87 | 161 | 248 | 259600 | 26 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-015 | E335-PCO-015 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0052 | E335-RFI-0052 | 2019-02-18 | 2019-04-29 | 2019-06-06 | 70 | 38 | 108 | 137600 | 5 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
E335-CO-016 | E335-PCO-016 | E335 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E335-RFI-0055 | E335-RFI-0055 | 2019-03-12 | 2019-03-25 | 2019-04-24 | 13 | 30 | 43 | 1804700 | 3 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-017 | E335-PCO-017 | E335 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E335-RFI-0061 | E335-RFI-0061 | 2019-04-17 | 2019-06-05 | 2019-09-19 | 49 | 106 | 155 | 1214700 | 3 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-018 | E335-PCO-018 | E335 | East Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | E335-RFI-0064 | E335-RFI-0064 | 2019-04-19 | 2019-06-11 | 2019-10-01 | 53 | 112 | 165 | 134600 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-019 | E335-PCO-019 | E335 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 2 | E335-RFI-0071 | E335-RFI-0071; E335-RFI-0072 | 2019-05-30 | 2019-06-24 | 2019-08-19 | 25 | 56 | 81 | 147800 | 10 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E335-CO-020 | E335-PCO-020 | E335 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E335-RFI-0073 | E335-RFI-0073 | 2019-05-30 | 2019-06-17 | 2019-10-04 | 18 | 109 | 127 | 20200 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-021 | E335-PCO-021 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0077 | E335-RFI-0077 | 2019-07-02 | 2019-08-27 | 2019-09-30 | 56 | 34 | 90 | 259900 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-022 | E335-PCO-022 | E335 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 2 | E335-RFI-0069 | E335-RFI-0069; E335-RFI-0083 | 2019-07-22 | 2019-08-05 | 2019-09-30 | 14 | 56 | 70 | 564600 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-023 | E335-PCO-023 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 3 | E335-RFI-0062 | E335-RFI-0062; E335-RFI-0075; E335-RFI-0086 | 2019-08-15 | 2019-10-07 | 2019-12-12 | 53 | 66 | 119 | 3463100 | 5 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-024 | E335-PCO-024 | E335 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E335-RFI-0091 | E335-RFI-0091 | 2019-09-20 | 2019-10-02 | 2020-01-23 | 12 | 113 | 125 | 184700 | 42 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-025 | E335-PCO-025 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 2 | E335-RFI-0097 | E335-RFI-0097; E335-RFI-0099 | 2019-11-04 | 2019-12-16 | 2020-01-10 | 42 | 25 | 67 | 969000 | 8 | None | N/A | Withdrawn by Contractor
E335-CO-026 | E335-PCO-026 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 2 | E335-RFI-0093 | E335-RFI-0093; E335-RFI-0109 | 2019-12-23 | 2020-03-11 | 2020-05-04 | 79 | 54 | 133 | 185500 | 14 | None | Project contingency (within baseline budget) | Executed – As Requested
E335-CO-027 | E335-PCO-027 | E335 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E335-RFI-0113 | E335-RFI-0113 | 2020-01-07 | 2020-02-17 | 2020-04-14 | 41 | 57 | 98 | 207600 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-028 | E335-PCO-028 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0114 | E335-RFI-0114 | 2020-02-07 | 2020-02-24 | 2020-06-10 | 17 | 107 | 124 | 268400 | 0 | Dispute Review Board | Project contingency (within baseline budget) | Escalated to DRB – Partial Award
E335-CO-029 | E335-PCO-029 | E335 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 2 | E335-RFI-0108 | E335-RFI-0108; E335-RFI-0115 | 2020-02-17 | 2020-04-13 | 2020-11-04 | 56 | 205 | 261 | 633300 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-030 | E335-PCO-030 | E335 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E335-RFI-0119 | E335-RFI-0119 | 2020-03-16 | 2020-04-13 | 2020-10-20 | 28 | 190 | 218 | 45200 | 4 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-031 | E335-PCO-031 | E335 | East Link Extension | Design Clarification | Spec / Drawing Clarification | 1 | E335-RFI-0124 | E335-RFI-0124 | 2020-04-09 | 2020-05-15 | 2020-09-09 | 36 | 117 | 153 | 16100 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-032 | E335-PCO-032 | E335 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E335-RFI-0125 | E335-RFI-0125 | 2020-04-20 | 2020-05-21 | 2020-09-28 | 31 | 130 | 161 | 673100 | 8 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-033 | E335-PCO-033 | E335 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E335-RFI-0139 | E335-RFI-0139 | 2020-07-02 | 2020-07-27 | 2020-10-19 | 25 | 84 | 109 | 40000 | 8 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-034 | E335-PCO-034 | E335 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E335-RFI-0142 | E335-RFI-0142 | 2020-07-08 | 2020-08-06 | 2020-09-07 | 29 | 32 | 61 | 1113500 | 5 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
E335-CO-035 | E335-PCO-035 | E335 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E335-RFI-0144 | E335-RFI-0144 | 2020-07-17 | 2020-08-11 | 2020-10-13 | 25 | 63 | 88 | 46800 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-036 | E335-PCO-036 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0153 | E335-RFI-0153 | 2020-09-17 | 2020-10-08 | 2020-12-10 | 21 | 63 | 84 | 60200 | 5 | None | Project contingency (within baseline budget) | Executed – As Requested
E335-CO-037 | E335-PCO-037 | E335 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 2 | E335-RFI-0167 | E335-RFI-0167; E335-RFI-0168 | 2020-12-31 | 2021-01-15 | 2021-03-01 | 15 | 45 | 60 | 1327600 | 74 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-038 | E335-PCO-038 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0176 | E335-RFI-0176 | 2021-02-23 | 2021-05-05 | 2021-12-06 | 71 | 215 | 286 | 48900 | 18 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-039 | E335-PCO-039 | E335 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 4 | E335-RFI-0171 | E335-RFI-0171; E335-RFI-0172; E335-RFI-0177; E335-RFI-0178 | 2021-03-22 | 2021-05-11 | 2021-11-01 | 50 | 174 | 224 | 4447000 | 35 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-040 | E335-PCO-040 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 2 | E335-RFI-0174 | E335-RFI-0174; E335-RFI-0179 | 2021-04-09 | 2021-05-24 | 2021-12-29 | 45 | 219 | 264 | 574700 | 32 | None | Project contingency (within baseline budget) | Executed – As Requested
E335-CO-041 | E335-PCO-041 | E335 | East Link Extension | Owner-Directed | Architectural / Finishes / Station Elements | 1 | E335-RFI-0185 | E335-RFI-0185 | 2021-06-14 | 2021-07-21 | 2021-10-04 | 37 | 75 | 112 | 19700 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-042 | E335-PCO-042 | E335 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E335-RFI-0188 | E335-RFI-0188 | 2021-07-01 | 2021-08-19 | 2021-10-01 | 49 | 43 | 92 | 402000 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-043 | E335-PCO-043 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0189 | E335-RFI-0189 | 2021-07-20 | 2021-08-30 | 2021-12-28 | 41 | 120 | 161 | 297600 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-044 | E335-PCO-044 | E335 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E335-RFI-0193 | E335-RFI-0193 | 2021-09-17 | 2021-10-13 | 2021-12-13 | 26 | 61 | 87 | 30800 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-045 | E335-PCO-045 | E335 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | E335-RFI-0196 | E335-RFI-0196; E335-RFI-0200 | 2021-10-18 | 2021-11-22 | 2022-01-10 | 35 | 49 | 84 | 1450400 | 7 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-046 | E335-PCO-046 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 2 | E335-RFI-0204 | E335-RFI-0204; E335-RFI-0209 | 2021-11-29 | 2021-12-14 | 2022-01-20 | 15 | 37 | 52 | 2179800 | 3 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-047 | E335-PCO-047 | E335 | East Link Extension | Owner-Directed | Architectural / Finishes / Station Elements | 1 | E335-RFI-0214 | E335-RFI-0214 | 2021-12-28 | 2022-02-04 | 2022-06-10 | 38 | 126 | 164 | 49600 | 0 | None | N/A | Rejected – Contractor Responsibility / No Merit
E335-CO-048 | E335-PCO-048 | E335 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E335-RFI-0216 | E335-RFI-0216 | 2022-01-17 | 2022-02-02 | 2022-05-12 | 16 | 99 | 115 | 251100 | 34 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-049 | E335-PCO-049 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0217 | E335-RFI-0217 | 2022-01-17 | 2022-01-25 | 2022-03-04 | 8 | 38 | 46 | 498700 | 9 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-050 | E335-PCO-050 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0218 | E335-RFI-0218 | 2022-01-17 | 2022-03-08 | 2022-06-24 | 50 | 108 | 158 | 604600 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-051 | E335-PCO-051 | E335 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E335-RFI-0223 | E335-RFI-0223 | 2022-02-11 | 2022-02-24 | 2022-04-28 | 13 | 63 | 76 | 163700 | 25 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-052 | E335-PCO-052 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 2 | E335-RFI-0211 | E335-RFI-0211; E335-RFI-0226 | 2022-03-01 | 2022-04-11 | 2023-07-14 | 41 | 459 | 500 | 329700 | 16 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-053 | E335-PCO-053 | E335 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E335-RFI-0227 | E335-RFI-0227 | 2022-04-07 | 2022-04-25 | 2022-05-27 | 18 | 32 | 50 | 1302200 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E335-CO-054 | E335-PCO-054 | E335 | East Link Extension | Owner-Directed / Work Restriction | Staging / MOT / Access / Sequencing | 1 | E335-RFI-0234 | E335-RFI-0234 | 2022-04-18 | 2022-05-09 | 2022-05-31 | 21 | 22 | 43 | 77500 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-055 | E335-PCO-055 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0239 | E335-RFI-0239 | 2022-07-05 | 2022-09-23 | 2022-11-16 | 80 | 54 | 134 | 73700 | 0 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
E335-CO-056 | E335-PCO-056 | E335 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E335-RFI-0248 | E335-RFI-0248 | 2022-10-10 | 2022-11-21 | 2023-03-07 | 42 | 106 | 148 | 135400 | 0 | None | N/A | Rejected – Contractor Responsibility / No Merit
E335-CO-057 | E335-PCO-057 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0249 | E335-RFI-0249 | 2022-10-26 | 2022-12-05 | 2023-05-29 | 40 | 175 | 215 | 193000 | 6 | None | N/A | Withdrawn by Contractor
E335-CO-058 | E335-PCO-058 | E335 | East Link Extension | Regulatory / Permit Condition | Environmental / Stormwater / Critical Areas | 1 | E335-RFI-0254 | E335-RFI-0254 | 2023-01-20 | 2023-02-06 | 2023-04-05 | 17 | 58 | 75 | 607600 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E335-CO-059 | E335-PCO-059 | E335 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E335-RFI-0259 | E335-RFI-0259 | 2023-03-14 | 2023-03-31 | 2023-06-19 | 17 | 80 | 97 | 450400 | 0 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E340-CO-001 | E340-PCO-001 | E340 | East Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | E340-RFI-0004 | E340-RFI-0004 | 2017-12-15 | 2018-01-16 | 2018-04-12 | 32 | 86 | 118 | 30500 | 0 | None | Project contingency (within baseline budget) | Executed – As Requested
E340-CO-002 | E340-PCO-002 | E340 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E340-RFI-0005 | E340-RFI-0005 | 2017-12-28 | 2018-02-09 | 2019-04-01 | 43 | 416 | 459 | 110100 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E340-CO-003 | E340-PCO-003 | E340 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E340-RFI-0008 | E340-RFI-0008 | 2018-02-26 | 2018-03-15 | 2018-05-07 | 17 | 53 | 70 | 104000 | 14 | None | Project contingency (within baseline budget) | Executed – As Requested
E340-CO-004 | E340-PCO-004 | E340 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E340-RFI-0010 | E340-RFI-0010 | 2018-04-03 | 2018-05-18 | 2018-11-06 | 45 | 172 | 217 | 434900 | 3 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E340-CO-005 | E340-PCO-005 | E340 | East Link Extension | Owner-Directed / Work Restriction | Staging / MOT / Access / Sequencing | 1 | E340-RFI-0011 | E340-RFI-0011 | 2018-04-16 | 2018-05-31 | 2018-07-02 | 45 | 32 | 77 | 38000 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E340-CO-006 | E340-PCO-006 | E340 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E340-RFI-0016 | E340-RFI-0016 | 2018-05-14 | 2018-06-11 | 2018-12-06 | 28 | 178 | 206 | 180400 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E340-CO-007 | E340-PCO-007 | E340 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E340-RFI-0017 | E340-RFI-0017 | 2018-06-13 | 2018-06-27 | 2018-08-10 | 14 | 44 | 58 | 221400 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E340-CO-008 | E340-PCO-008 | E340 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E340-RFI-0022 | E340-RFI-0022 | 2018-09-24 | 2018-10-15 | 2019-02-08 | 21 | 116 | 137 | 637900 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E340-CO-009 | E340-PCO-009 | E340 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E340-RFI-0021 | E340-RFI-0021 | 2018-09-25 | 2018-10-26 | 2019-02-25 | 31 | 122 | 153 | 12100 | 9 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E340-CO-010 | E340-PCO-010 | E340 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E340-RFI-0023 | E340-RFI-0023 | 2018-10-09 | 2018-11-26 | 2019-05-21 | 48 | 176 | 224 | 23600 | 2 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E340-CO-011 | E340-PCO-011 | E340 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E340-RFI-0027 | E340-RFI-0027 | 2018-10-18 | 2018-11-21 | 2019-02-13 | 34 | 84 | 118 | 54700 | 0 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E340-CO-012 | E340-PCO-012 | E340 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E340-RFI-0028 | E340-RFI-0028 | 2018-10-29 | 2018-12-05 | 2019-09-23 | 37 | 292 | 329 | 643700 | 8 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E340-CO-013 | E340-PCO-013 | E340 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E340-RFI-0037 | E340-RFI-0037 | 2019-02-25 | 2019-04-01 | 2019-08-01 | 35 | 122 | 157 | 74500 | 0 | None | Project contingency (within baseline budget) | Executed – As Requested
E340-CO-014 | E340-PCO-014 | E340 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | E340-RFI-0036 | E340-RFI-0036; E340-RFI-0039 | 2019-03-21 | 2019-04-25 | 2019-09-11 | 35 | 139 | 174 | 381300 | 14 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E340-CO-015 | E340-PCO-015 | E340 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E340-RFI-0042 | E340-RFI-0042 | 2019-04-16 | 2019-05-14 | 2019-11-20 | 28 | 190 | 218 | 48800 | 8 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E340-CO-016 | E340-PCO-016 | E340 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 3 | E340-RFI-0030 | E340-RFI-0030; E340-RFI-0038; E340-RFI-0047 | 2019-06-12 | 2019-08-05 | 2020-01-02 | 54 | 150 | 204 | 2248700 | 25 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E340-CO-017 | E340-PCO-017 | E340 | East Link Extension | Owner-Directed / Work Restriction | Staging / MOT / Access / Sequencing | 1 | E340-RFI-0054 | E340-RFI-0054 | 2019-10-09 | 2019-11-06 | 2020-01-15 | 28 | 70 | 98 | 67300 | 4 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E340-CO-018 | E340-PCO-018 | E340 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 2 | E340-RFI-0051 | E340-RFI-0051; E340-RFI-0055 | 2019-10-29 | 2019-12-05 | 2020-02-04 | 37 | 61 | 98 | 1950400 | 3 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E340-CO-019 | E340-PCO-019 | E340 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E340-RFI-0060 | E340-RFI-0060 | 2019-11-27 | 2019-12-20 | 2020-07-15 | 23 | 208 | 231 | 172700 | 6 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E340-CO-020 | E340-PCO-020 | E340 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E340-RFI-0064 | E340-RFI-0064 | 2020-01-13 | 2020-01-31 | 2020-08-31 | 18 | 213 | 231 | 351600 | 14 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E340-CO-021 | E340-PCO-021 | E340 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E340-RFI-0071 | E340-RFI-0071 | 2020-03-06 | 2020-05-06 | 2020-07-13 | 61 | 68 | 129 | 212100 | 0 | None | N/A | Withdrawn by Contractor
E340-CO-022 | E340-PCO-022 | E340 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E340-RFI-0077 | E340-RFI-0077 | 2020-05-27 | 2020-07-21 | 2020-08-24 | 55 | 34 | 89 | 45600 | 0 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E340-CO-023 | E340-PCO-023 | E340 | East Link Extension | Design Error/Omission | Trackwork / Track-Structure Interface | 1 | E340-RFI-0080 | E340-RFI-0080 | 2020-08-03 | 2020-08-24 | 2020-11-06 | 21 | 74 | 95 | 191300 | 0 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
E340-CO-024 | E340-PCO-024 | E340 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E340-RFI-0081 | E340-RFI-0081 | 2020-08-03 | 2020-08-24 | 2021-01-29 | 21 | 158 | 179 | 255100 | 2 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E340-CO-025 | E340-PCO-025 | E340 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E340-RFI-0082 | E340-RFI-0082 | 2020-09-23 | 2020-10-27 | 2021-04-05 | 34 | 160 | 194 | 651600 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E340-CO-026 | E340-PCO-026 | E340 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E340-RFI-0083 | E340-RFI-0083 | 2020-10-07 | 2020-10-27 | 2021-03-11 | 20 | 135 | 155 | 68400 | 2 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E340-CO-027 | E340-PCO-027 | E340 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E340-RFI-0086 | E340-RFI-0086 | 2020-11-16 | 2021-01-28 | 2021-05-31 | 73 | 123 | 196 | 73400 | 10 | None | Project contingency (within baseline budget) | Executed – As Requested
E340-CO-028 | E340-PCO-028 | E340 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E340-RFI-0087 | E340-RFI-0087 | 2020-11-24 | 2020-12-17 | 2021-03-29 | 23 | 102 | 125 | 33800 | 0 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E360-CO-001 | E360-PCO-001 | E360 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E360-RFI-0005 | E360-RFI-0005 | 2017-02-27 | 2017-03-13 | 2017-06-15 | 14 | 94 | 108 | 25700 | 18 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-002 | E360-PCO-002 | E360 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E360-RFI-0008 | E360-RFI-0008 | 2017-03-22 | 2017-04-17 | 2017-10-05 | 26 | 171 | 197 | 2029700 | 3 | Dispute Review Board | Project contingency (within baseline budget) | Escalated to DRB – Partial Award
E360-CO-003 | E360-PCO-003 | E360 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E360-RFI-0011 | E360-RFI-0011 | 2017-06-12 | 2017-08-07 | 2017-09-18 | 56 | 42 | 98 | 70700 | 12 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-004 | E360-PCO-004 | E360 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E360-RFI-0012 | E360-RFI-0012 | 2017-06-28 | 2017-08-07 | 2017-12-14 | 40 | 129 | 169 | 185100 | 2 | None | N/A | Withdrawn by Contractor
E360-CO-005 | E360-PCO-005 | E360 | East Link Extension | Design Clarification | Spec / Drawing Clarification | 1 | E360-RFI-0013 | E360-RFI-0013 | 2017-06-30 | 2017-07-17 | 2017-10-09 | 17 | 84 | 101 | 33900 | 0 | None | Project contingency (within baseline budget) | Executed – As Requested
E360-CO-006 | E360-PCO-006 | E360 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E360-RFI-0014 | E360-RFI-0014 | 2017-08-02 | 2017-09-04 | 2017-09-29 | 33 | 25 | 58 | 129600 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-007 | E360-PCO-007 | E360 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E360-RFI-0015 | E360-RFI-0015 | 2017-08-14 | 2017-10-10 | 2017-12-06 | 57 | 57 | 114 | 182300 | 10 | None | Project contingency (within baseline budget) | Executed – As Requested
E360-CO-008 | E360-PCO-008 | E360 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E360-RFI-0017 | E360-RFI-0017 | 2017-08-14 | 2017-09-14 | 2018-02-19 | 31 | 158 | 189 | 115300 | 24 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E360-CO-009 | E360-PCO-009 | E360 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E360-RFI-0020 | E360-RFI-0020 | 2017-08-28 | 2017-10-26 | 2017-12-27 | 59 | 62 | 121 | 240900 | 3 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-010 | E360-PCO-010 | E360 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E360-RFI-0022 | E360-RFI-0022 | 2017-10-10 | 2017-11-06 | 2018-02-14 | 27 | 100 | 127 | 72400 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E360-CO-011 | E360-PCO-011 | E360 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E360-RFI-0023 | E360-RFI-0023 | 2017-10-19 | 2017-11-06 | 2018-01-08 | 18 | 63 | 81 | 29400 | 45 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-012 | E360-PCO-012 | E360 | East Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | E360-RFI-0025 | E360-RFI-0025 | 2017-10-26 | 2017-12-28 | 2018-08-02 | 63 | 217 | 280 | 946300 | 0 | None | N/A | Withdrawn by Contractor
E360-CO-013 | E360-PCO-013 | E360 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E360-RFI-0033 | E360-RFI-0033 | 2018-02-26 | 2018-04-03 | 2018-06-08 | 36 | 66 | 102 | 3336300 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-014 | E360-PCO-014 | E360 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E360-RFI-0038 | E360-RFI-0038 | 2018-03-27 | 2018-05-15 | 2018-08-06 | 49 | 83 | 132 | 5182700 | 23 | None | N/A | Withdrawn by Contractor
E360-CO-015 | E360-PCO-015 | E360 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E360-RFI-0043 | E360-RFI-0043 | 2018-06-04 | 2018-07-02 | 2019-03-15 | 28 | 256 | 284 | 237200 | 0 | None | Project contingency (within baseline budget) | Executed – As Requested
E360-CO-016 | E360-PCO-016 | E360 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E360-RFI-0051 | E360-RFI-0051 | 2018-09-11 | 2018-11-08 | 2018-12-03 | 58 | 25 | 83 | 2131300 | 7 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E360-CO-017 | E360-PCO-017 | E360 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 2 | E360-RFI-0052 | E360-RFI-0052; E360-RFI-0055 | 2018-11-05 | 2019-01-03 | 2019-03-18 | 59 | 74 | 133 | 585100 | 4 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-018 | E360-PCO-018 | E360 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E360-RFI-0057 | E360-RFI-0057 | 2018-11-20 | 2018-12-27 | 2019-07-29 | 37 | 214 | 251 | 748600 | 4 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E360-CO-019 | E360-PCO-019 | E360 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E360-RFI-0058 | E360-RFI-0058 | 2018-12-04 | 2018-12-13 | 2019-01-21 | 9 | 39 | 48 | 479900 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-020 | E360-PCO-020 | E360 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E360-RFI-0075 | E360-RFI-0075 | 2019-03-18 | 2019-04-01 | 2019-07-04 | 14 | 94 | 108 | 3229000 | 4 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E360-CO-021 | E360-PCO-021 | E360 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E360-RFI-0077 | E360-RFI-0077 | 2019-04-03 | 2019-04-26 | 2019-07-31 | 23 | 96 | 119 | 132500 | 11 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-022 | E360-PCO-022 | E360 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E360-RFI-0082 | E360-RFI-0082 | 2019-05-23 | 2019-07-29 | 2019-11-04 | 67 | 98 | 165 | 287200 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-023 | E360-PCO-023 | E360 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | E360-RFI-0076 | E360-RFI-0076; E360-RFI-0087 | 2019-06-12 | 2019-07-23 | 2019-10-04 | 41 | 73 | 114 | 3274100 | 11 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
E360-CO-024 | E360-PCO-024 | E360 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E360-RFI-0084 | E360-RFI-0084 | 2019-06-12 | 2019-06-24 | 2019-08-02 | 12 | 39 | 51 | 287800 | 0 | None | Project contingency (within baseline budget) | Executed – As Requested
E360-CO-025 | E360-PCO-025 | E360 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E360-RFI-0105 | E360-RFI-0105 | 2019-11-22 | 2019-12-16 | 2020-02-26 | 24 | 72 | 96 | 328700 | 13 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E360-CO-026 | E360-PCO-026 | E360 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E360-RFI-0108 | E360-RFI-0108 | 2019-12-09 | 2019-12-30 | 2021-05-06 | 21 | 493 | 514 | 193700 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E360-CO-027 | E360-PCO-027 | E360 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E360-RFI-0110 | E360-RFI-0110 | 2019-12-19 | 2020-01-13 | 2020-08-10 | 25 | 210 | 235 | 1827200 | 3 | None | N/A | Rejected – Contractor Responsibility / No Merit
E360-CO-028 | E360-PCO-028 | E360 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | E360-RFI-0107 | E360-RFI-0107; E360-RFI-0114 | 2020-02-26 | 2020-04-14 | 2020-07-07 | 48 | 84 | 132 | 653300 | 9 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-029 | E360-PCO-029 | E360 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E360-RFI-0116 | E360-RFI-0116 | 2020-03-05 | 2020-04-06 | 2020-06-02 | 32 | 57 | 89 | 341100 | 31 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-030 | E360-PCO-030 | E360 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E360-RFI-0117 | E360-RFI-0117 | 2020-03-23 | 2020-04-30 | 2020-07-16 | 38 | 77 | 115 | 503200 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E360-CO-031 | E360-PCO-031 | E360 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E360-RFI-0118 | E360-RFI-0118 | 2020-03-27 | 2020-05-18 | 2020-08-27 | 52 | 101 | 153 | 4826600 | 7 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-032 | E360-PCO-032 | E360 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E360-RFI-0120 | E360-RFI-0120 | 2020-04-22 | 2020-06-22 | 2020-08-18 | 61 | 57 | 118 | 2569600 | 4 | None | N/A | Withdrawn by Contractor
E360-CO-033 | E360-PCO-033 | E360 | East Link Extension | Regulatory / Permit Condition | Environmental / Stormwater / Critical Areas | 1 | E360-RFI-0124 | E360-RFI-0124 | 2020-06-24 | 2020-08-31 | 2020-11-05 | 68 | 66 | 134 | 1823900 | 19 | None | N/A | Rejected – Contractor Responsibility / No Merit
E360-CO-034 | E360-PCO-034 | E360 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E360-RFI-0125 | E360-RFI-0125 | 2020-07-06 | 2020-07-27 | 2020-09-21 | 21 | 56 | 77 | 182400 | 2 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E360-CO-035 | E360-PCO-035 | E360 | East Link Extension | Contractor-Requested | Material / Submittal / Substitution | 1 | E360-RFI-0129 | E360-RFI-0129 | 2020-09-28 | 2020-10-20 | 2020-12-07 | 22 | 48 | 70 | 59100 | 1 | None | Project contingency (within baseline budget) | Executed – As Requested
E360-CO-036 | E360-PCO-036 | E360 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E360-RFI-0134 | E360-RFI-0134 | 2020-11-06 | 2020-11-23 | 2020-12-29 | 17 | 36 | 53 | 1487900 | 7 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-037 | E360-PCO-037 | E360 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E360-RFI-0135 | E360-RFI-0135 | 2020-12-30 | 2021-03-15 | 2021-08-04 | 75 | 142 | 217 | 1014400 | 0 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E360-CO-038 | E360-PCO-038 | E360 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E360-RFI-0136 | E360-RFI-0136 | 2021-01-18 | 2021-02-08 | 2021-04-30 | 21 | 81 | 102 | 374400 | 25 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-039 | E360-PCO-039 | E360 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E360-RFI-0139 | E360-RFI-0139 | 2021-03-15 | 2021-04-05 | 2021-09-15 | 21 | 163 | 184 | 2301800 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E360-CO-040 | E360-PCO-040 | E360 | East Link Extension | Regulatory / Permit Condition | Environmental / Stormwater / Critical Areas | 1 | E360-RFI-0138 | E360-RFI-0138 | 2021-03-17 | 2021-05-03 | 2021-07-06 | 47 | 64 | 111 | 950600 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-001 | E750-PCO-001 | E750 | East Link Extension | Contractor-Requested | Material / Submittal / Substitution | 1 | E750-RFI-0001 | E750-RFI-0001 | 2018-04-13 | 2018-05-08 | 2018-07-09 | 25 | 62 | 87 | 14900 | 0 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E750-CO-002 | E750-PCO-002 | E750 | East Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | E750-RFI-0006 | E750-RFI-0006 | 2018-08-16 | 2018-10-04 | 2018-12-25 | 49 | 82 | 131 | 1842700 | 0 | None | N/A | Withdrawn by Contractor
E750-CO-003 | E750-PCO-003 | E750 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E750-RFI-0005 | E750-RFI-0005 | 2018-08-22 | 2018-10-04 | 2018-11-12 | 43 | 39 | 82 | 137900 | 11 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-004 | E750-PCO-004 | E750 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E750-RFI-0008 | E750-RFI-0008 | 2018-09-10 | 2018-11-15 | 2019-06-17 | 66 | 214 | 280 | 51000 | 4 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-005 | E750-PCO-005 | E750 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 2 | E750-RFI-0020 | E750-RFI-0020; E750-RFI-0023 | 2019-04-15 | 2019-06-11 | 2019-07-24 | 57 | 43 | 100 | 1016600 | 133 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-006 | E750-PCO-006 | E750 | East Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | E750-RFI-0024 | E750-RFI-0024 | 2019-05-03 | 2019-06-05 | 2019-09-27 | 33 | 114 | 147 | 82700 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-007 | E750-PCO-007 | E750 | East Link Extension | Design Error/Omission | Trackwork / Track-Structure Interface | 1 | E750-RFI-0036 | E750-RFI-0036 | 2019-07-23 | 2019-08-30 | 2019-12-04 | 38 | 96 | 134 | 239500 | 2 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E750-CO-008 | E750-PCO-008 | E750 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E750-RFI-0037 | E750-RFI-0037 | 2019-08-13 | 2019-10-01 | 2019-11-26 | 49 | 56 | 105 | 1678000 | 0 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E750-CO-009 | E750-PCO-009 | E750 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 4 | E750-RFI-0028 | E750-RFI-0028; E750-RFI-0030; E750-RFI-0033; E750-RFI-0042 | 2019-09-20 | 2019-09-27 | 2020-01-20 | 7 | 115 | 122 | 558100 | 102 | None | Project contingency (within baseline budget) | Executed – As Requested
E750-CO-010 | E750-PCO-010 | E750 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E750-RFI-0052 | E750-RFI-0052 | 2019-12-02 | 2020-01-13 | 2020-08-03 | 42 | 203 | 245 | 120900 | 7 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E750-CO-011 | E750-PCO-011 | E750 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E750-RFI-0063 | E750-RFI-0063 | 2020-03-02 | 2020-03-10 | 2020-07-20 | 8 | 132 | 140 | 1091600 | 13 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E750-CO-012 | E750-PCO-012 | E750 | East Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | E750-RFI-0071 | E750-RFI-0071 | 2020-04-16 | 2020-05-05 | 2020-07-02 | 19 | 58 | 77 | 2081600 | 3 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-013 | E750-PCO-013 | E750 | East Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | E750-RFI-0075 | E750-RFI-0075 | 2020-06-01 | 2020-07-30 | 2020-11-11 | 59 | 104 | 163 | 248100 | 0 | None | Project contingency (within baseline budget) | Executed – As Requested
E750-CO-014 | E750-PCO-014 | E750 | East Link Extension | Owner-Directed / Work Restriction | Staging / MOT / Access / Sequencing | 1 | E750-RFI-0083 | E750-RFI-0083 | 2020-07-27 | 2020-09-21 | 2021-03-02 | 56 | 162 | 218 | 68400 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E750-CO-015 | E750-PCO-015 | E750 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E750-RFI-0096 | E750-RFI-0096 | 2020-09-24 | 2020-10-16 | 2021-03-03 | 22 | 138 | 160 | 125700 | 3 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-016 | E750-PCO-016 | E750 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E750-RFI-0106 | E750-RFI-0106 | 2020-12-07 | 2021-01-12 | 2021-03-23 | 36 | 70 | 106 | 2110600 | 0 | None | N/A | Rejected – Contractor Responsibility / No Merit
E750-CO-017 | E750-PCO-017 | E750 | East Link Extension | Third-Party Requirement | Third-Party / Permit / ROW Requirement | 1 | E750-RFI-0111 | E750-RFI-0111 | 2020-12-14 | 2021-01-15 | 2021-03-16 | 32 | 60 | 92 | 164300 | 32 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-018 | E750-PCO-018 | E750 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E750-RFI-0108 | E750-RFI-0108 | 2020-12-15 | 2021-01-18 | 2021-08-24 | 34 | 218 | 252 | 795300 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-019 | E750-PCO-019 | E750 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E750-RFI-0114 | E750-RFI-0114 | 2021-02-22 | 2021-04-06 | 2021-06-09 | 43 | 64 | 107 | 519300 | 17 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-020 | E750-PCO-020 | E750 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E750-RFI-0117 | E750-RFI-0117 | 2021-03-15 | 2021-03-29 | 2021-07-05 | 14 | 98 | 112 | 200400 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-021 | E750-PCO-021 | E750 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E750-RFI-0118 | E750-RFI-0118 | 2021-03-19 | 2021-04-26 | 2021-06-07 | 38 | 42 | 80 | 507900 | 3 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-022 | E750-PCO-022 | E750 | East Link Extension | Owner-Directed / Work Restriction | Staging / MOT / Access / Sequencing | 1 | E750-RFI-0128 | E750-RFI-0128 | 2021-05-11 | 2021-06-02 | 2021-11-11 | 22 | 162 | 184 | 957100 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-023 | E750-PCO-023 | E750 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E750-RFI-0129 | E750-RFI-0129 | 2021-05-14 | 2021-06-14 | 2021-08-02 | 31 | 49 | 80 | 1351100 | 13 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E750-CO-024 | E750-PCO-024 | E750 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E750-RFI-0142 | E750-RFI-0142 | 2021-08-02 | 2021-09-22 | 2021-12-10 | 51 | 79 | 130 | 809600 | 21 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E750-CO-025 | E750-PCO-025 | E750 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E750-RFI-0140 | E750-RFI-0140 | 2021-08-06 | 2021-10-11 | 2022-01-11 | 66 | 92 | 158 | 1236400 | 24 | None | Project contingency (within baseline budget) | Executed – As Requested
E750-CO-026 | E750-PCO-026 | E750 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E750-RFI-0152 | E750-RFI-0152 | 2021-09-15 | 2021-10-22 | 2022-01-05 | 37 | 75 | 112 | 952900 | 0 | Executive Management | N/A | Rejected – Contractor Responsibility / No Merit
E750-CO-027 | E750-PCO-027 | E750 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 2 | E750-RFI-0138 | E750-RFI-0138; E750-RFI-0147 | 2021-09-30 | 2021-11-08 | 2022-05-25 | 39 | 198 | 237 | 2644300 | 10 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E750-CO-028 | E750-PCO-028 | E750 | East Link Extension | Design Error/Omission | Trackwork / Track-Structure Interface | 1 | E750-RFI-0158 | E750-RFI-0158 | 2021-10-21 | 2021-11-03 | 2021-12-20 | 13 | 47 | 60 | 205300 | 0 | None | Project contingency (within baseline budget) | Executed – As Requested
E750-CO-029 | E750-PCO-029 | E750 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 2 | E750-RFI-0165 | E750-RFI-0165; E750-RFI-0168 | 2022-01-24 | 2022-03-07 | 2022-08-08 | 42 | 154 | 196 | 4650000 | 17 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-030 | E750-PCO-030 | E750 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E750-RFI-0171 | E750-RFI-0171 | 2022-02-07 | 2022-04-11 | 2022-10-24 | 63 | 196 | 259 | 695100 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E750-CO-031 | E750-PCO-031 | E750 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E750-RFI-0174 | E750-RFI-0174 | 2022-03-28 | 2022-04-25 | 2022-07-01 | 28 | 67 | 95 | 2475400 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E750-CO-032 | E750-PCO-032 | E750 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E750-RFI-0176 | E750-RFI-0176 | 2022-03-29 | 2022-04-26 | 2022-06-24 | 28 | 59 | 87 | 700900 | 28 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-033 | E750-PCO-033 | E750 | East Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | E750-RFI-0179 | E750-RFI-0179 | 2022-05-09 | 2022-07-25 | 2022-09-01 | 77 | 38 | 115 | 2090600 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-034 | E750-PCO-034 | E750 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E750-RFI-0181 | E750-RFI-0181 | 2022-05-27 | 2022-06-20 | 2022-11-24 | 24 | 157 | 181 | 144100 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E750-CO-035 | E750-PCO-035 | E750 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E750-RFI-0188 | E750-RFI-0188 | 2022-08-22 | 2022-09-14 | 2022-10-31 | 23 | 47 | 70 | 238400 | 12 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-036 | E750-PCO-036 | E750 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E750-RFI-0186 | E750-RFI-0186 | 2022-08-23 | 2022-09-15 | 2022-11-07 | 23 | 53 | 76 | 1578200 | 12 | None | Project contingency (within baseline budget) | Executed – Partial (Revised Scope)
E750-CO-037 | E750-PCO-037 | E750 | East Link Extension | Design Error/Omission (Interface) | Systems Interface (TPSS/OCS/Signals/Comms) | 1 | E750-RFI-0197 | E750-RFI-0197 | 2023-02-07 | 2023-03-13 | 2023-10-03 | 34 | 204 | 238 | 2431400 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E750-CO-038 | E750-PCO-038 | E750 | East Link Extension | Differing Site Condition | Differing Site Conditions / Geotechnical | 1 | E750-RFI-0204 | E750-RFI-0204 | 2023-03-22 | 2023-04-17 | 2023-08-09 | 26 | 114 | 140 | 2809000 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E750-CO-039 | E750-PCO-039 | E750 | East Link Extension | Differing Site Condition (Utility) | Utility Conflict / Relocation | 1 | E750-RFI-0205 | E750-RFI-0205 | 2023-04-06 | 2023-04-24 | 2023-07-10 | 18 | 77 | 95 | 3873100 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement
E750-CO-040 | E750-PCO-040 | E750 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E750-RFI-0209 | E750-RFI-0209 | 2023-06-16 | 2023-07-10 | 2023-11-28 | 24 | 141 | 165 | 3230100 | 0 | None | Project contingency (within baseline budget) | Executed – Negotiated Reduction
E750-CO-041 | E750-PCO-041 | E750 | East Link Extension | Design Error/Omission | Design Conflict / Constructability | 1 | E750-RFI-0217 | E750-RFI-0217 | 2023-10-24 | 2023-11-27 | 2024-02-19 | 34 | 84 | 118 | 782100 | 0 | None | Project contingency (within baseline budget) | Executed – As Requested
E750-CO-042 | E750-PCO-042 | E750 | East Link Extension | Owner-Directed / Code Compliance | Fire-Life-Safety / MEP / Tunnel Systems | 1 | E750-RFI-0218 | E750-RFI-0218 | 2023-11-20 | 2023-12-18 | 2024-04-08 | 28 | 112 | 140 | 1475300 | 0 | Executive Management | Project contingency (within baseline budget) | Resolved via Global Settlement

## CO_Outcomes
co_id | package_id | outcome | outcome_date | requested_cost_usd | final_approved_cost_usd | pct_of_request_approved | cost_reduction_usd | time_requested_days | time_granted_days | pct_time_granted | contingency_drawn_usd | cumulative_time_granted_pkg_days | pct_of_contract_base
DRLE-CO-001 | DRLE | Rejected – Contractor Responsibility / No Merit | 2020-04-20 | 762000 | 0 | 0% | 762000 | 0 | 0 | 0% | 0 | 0 | 0
DRLE-CO-002 | DRLE | Resolved via Global Settlement | 2021-03-08 | 52600 | 26000 | 49.4% | 26600 | 0 | 0 | 0% | 26000 | 0 | 0.004
DRLE-CO-003 | DRLE | Resolved via Global Settlement | 2020-08-28 | 150100 | 96200 | 64.1% | 53900 | 4 | 3 | 75% | 96200 | 3 | 0.013
DRLE-CO-004 | DRLE | Executed – Negotiated Reduction | 2020-08-03 | 550100 | 393300 | 71.5% | 156800 | 8 | 5 | 62.5% | 393300 | 8 | 0.055
DRLE-CO-005 | DRLE | Executed – As Requested | 2020-08-31 | 2290500 | 2290500 | 100% | 0 | 13 | 13 | 100% | 2290500 | 21 | 0.318
DRLE-CO-006 | DRLE | Executed – Negotiated Reduction | 2020-09-11 | 10300 | 5400 | 52.4% | 4900 | 0 | 0 | 0% | 5400 | 21 | 0.001
DRLE-CO-007 | DRLE | Executed – Negotiated Reduction | 2020-11-24 | 186400 | 148800 | 79.8% | 37600 | 2 | 2 | 100% | 148800 | 23 | 0.021
DRLE-CO-008 | DRLE | Rejected – Contractor Responsibility / No Merit | 2021-03-11 | 284700 | 0 | 0% | 284700 | 15 | 0 | 0% | 0 | 23 | 0
DRLE-CO-009 | DRLE | Executed – Negotiated Reduction | 2021-06-14 | 396500 | 211800 | 53.4% | 184700 | 1 | 0 | 0% | 211800 | 23 | 0.029
DRLE-CO-010 | DRLE | Resolved via Global Settlement | 2021-03-18 | 62400 | 40500 | 64.9% | 21900 | 0 | 0 | 0% | 40500 | 23 | 0.006
DRLE-CO-011 | DRLE | Resolved via Global Settlement | 2021-01-06 | 777600 | 600500 | 77.2% | 177100 | 3 | 1 | 33.3% | 600500 | 24 | 0.083
DRLE-CO-012 | DRLE | Executed – Negotiated Reduction | 2021-05-10 | 121500 | 49500 | 40.7% | 72000 | 7 | 2 | 28.6% | 49500 | 26 | 0.007
DRLE-CO-013 | DRLE | Executed – Negotiated Reduction | 2021-09-20 | 981500 | 685400 | 69.8% | 296100 | 3 | 1 | 33.3% | 685400 | 27 | 0.095
DRLE-CO-014 | DRLE | Resolved via Global Settlement | 2022-01-12 | 914300 | 346300 | 37.9% | 568000 | 5 | 1 | 20% | 346300 | 28 | 0.048
DRLE-CO-015 | DRLE | Rejected – Contractor Responsibility / No Merit | 2021-12-28 | 930900 | 0 | 0% | 930900 | 1 | 0 | 0% | 0 | 28 | 0
DRLE-CO-016 | DRLE | Executed – Negotiated Reduction | 2022-03-18 | 460700 | 368400 | 80% | 92300 | 8 | 7 | 87.5% | 368400 | 35 | 0.051
DRLE-CO-017 | DRLE | Executed – As Requested | 2022-05-16 | 273500 | 273500 | 100% | 0 | 2 | 2 | 100% | 273500 | 37 | 0.038
DRLE-CO-018 | DRLE | Executed – Negotiated Reduction | 2022-02-03 | 369800 | 263700 | 71.3% | 106100 | 0 | 0 | 0% | 263700 | 37 | 0.037
DRLE-CO-019 | DRLE | Executed – Negotiated Reduction | 2022-02-11 | 163200 | 64800 | 39.7% | 98400 | 0 | 0 | 0% | 64800 | 37 | 0.009
DRLE-CO-020 | DRLE | Executed – Negotiated Reduction | 2022-02-23 | 21800 | 8100 | 37.2% | 13700 | 0 | 0 | 0% | 8100 | 37 | 0.001
DRLE-CO-021 | DRLE | Resolved via Global Settlement | 2022-05-24 | 1398300 | 957200 | 68.5% | 441100 | 4 | 3 | 75% | 957200 | 40 | 0.133
DRLE-CO-022 | DRLE | Resolved via Global Settlement | 2022-09-05 | 73900 | 44800 | 60.6% | 29100 | 4 | 2 | 50% | 44800 | 42 | 0.006
DRLE-CO-023 | DRLE | Executed – Negotiated Reduction | 2022-04-25 | 30800 | 22300 | 72.4% | 8500 | 4 | 2 | 50% | 22300 | 44 | 0.003
DRLE-CO-024 | DRLE | Executed – Partial (Revised Scope) | 2022-06-20 | 79600 | 63400 | 79.6% | 16200 | 7 | 4 | 57.1% | 63400 | 48 | 0.009
DRLE-CO-025 | DRLE | Withdrawn by Contractor | 2022-03-29 | 87100 | 0 | 0% | 87100 | 0 | 0 | 0% | 0 | 48 | 0
DRLE-CO-026 | DRLE | Executed – Negotiated Reduction | 2022-05-30 | 701400 | 652600 | 93% | 48800 | 4 | 3 | 75% | 652600 | 51 | 0.091
DRLE-CO-027 | DRLE | Rejected – Contractor Responsibility / No Merit | 2022-07-18 | 27100 | 0 | 0% | 27100 | 0 | 0 | 0% | 0 | 51 | 0
DRLE-CO-028 | DRLE | Executed – Negotiated Reduction | 2022-09-05 | 57100 | 45200 | 79.2% | 11900 | 3 | 3 | 100% | 45200 | 54 | 0.006
DRLE-CO-029 | DRLE | Executed – Negotiated Reduction | 2022-11-07 | 78800 | 60200 | 76.4% | 18600 | 0 | 0 | 0% | 60200 | 54 | 0.008
DRLE-CO-030 | DRLE | Executed – Negotiated Reduction | 2022-10-03 | 391900 | 275900 | 70.4% | 116000 | 5 | 4 | 80% | 275900 | 58 | 0.038
DRLE-CO-031 | DRLE | Executed – Negotiated Reduction | 2022-10-10 | 85200 | 67500 | 79.2% | 17700 | 0 | 0 | 0% | 67500 | 58 | 0.009
DRLE-CO-032 | DRLE | Rejected – Contractor Responsibility / No Merit | 2023-01-30 | 252400 | 0 | 0% | 252400 | 0 | 0 | 0% | 0 | 58 | 0
DRLE-CO-033 | DRLE | Rejected – Contractor Responsibility / No Merit | 2023-02-01 | 780900 | 0 | 0% | 780900 | 12 | 0 | 0% | 0 | 58 | 0
DRLE-CO-034 | DRLE | Executed – Negotiated Reduction | 2023-02-20 | 1318300 | 1186100 | 90% | 132200 | 8 | 6 | 75% | 1186100 | 64 | 0.165
DRLE-CO-035 | DRLE | Rejected – Contractor Responsibility / No Merit | 2023-03-24 | 166500 | 0 | 0% | 166500 | 4 | 0 | 0% | 0 | 64 | 0
DRLE-CO-036 | DRLE | Escalated to DRB – Partial Award | 2023-08-17 | 2554000 | 1825500 | 71.5% | 728500 | 5 | 4 | 80% | 1825500 | 68 | 0.254
DRLE-CO-037 | DRLE | Executed – Negotiated Reduction | 2023-07-24 | 1006300 | 866500 | 86.1% | 139800 | 2 | 1 | 50% | 866500 | 69 | 0.12
DRLE-CO-038 | DRLE | Withdrawn by Contractor | 2023-05-15 | 5199900 | 0 | 0% | 5199900 | 0 | 0 | 0% | 0 | 69 | 0
DRLE-CO-039 | DRLE | Executed – Negotiated Reduction | 2023-09-06 | 314900 | 225200 | 71.5% | 89700 | 1 | 1 | 100% | 225200 | 70 | 0.031
DRLE-CO-040 | DRLE | Executed – Partial (Revised Scope) | 2023-09-08 | 236200 | 67500 | 28.6% | 168700 | 2 | 1 | 50% | 67500 | 71 | 0.009
DRLE-CO-041 | DRLE | Executed – Negotiated Reduction | 2023-05-29 | 430800 | 308800 | 71.7% | 122000 | 6 | 4 | 66.7% | 308800 | 75 | 0.043
DRLE-CO-042 | DRLE | Executed – Partial (Revised Scope) | 2023-05-24 | 22900 | 15800 | 69% | 7100 | 0 | 0 | 0% | 15800 | 75 | 0.002
DRLE-CO-043 | DRLE | Resolved via Global Settlement | 2024-02-05 | 985300 | 536800 | 54.5% | 448500 | 4 | 2 | 50% | 536800 | 77 | 0.075
DRLE-CO-044 | DRLE | Executed – As Requested | 2023-09-20 | 301600 | 301600 | 100% | 0 | 3 | 2 | 66.7% | 301600 | 79 | 0.042
DRLE-CO-045 | DRLE | Executed – Negotiated Reduction | 2023-10-12 | 163700 | 104200 | 63.7% | 59500 | 0 | 0 | 0% | 104200 | 79 | 0.014
DRLE-CO-046 | DRLE | Executed – Negotiated Reduction | 2023-10-16 | 261700 | 184600 | 70.5% | 77100 | 1 | 0 | 0% | 184600 | 79 | 0.026
DRLE-CO-047 | DRLE | Executed – Negotiated Reduction | 2023-10-26 | 476600 | 425000 | 89.2% | 51600 | 2 | 2 | 100% | 425000 | 81 | 0.059
DRLE-CO-048 | DRLE | Executed – Negotiated Reduction | 2023-10-12 | 931000 | 683800 | 73.4% | 247200 | 2 | 1 | 50% | 683800 | 82 | 0.095
DRLE-CO-049 | DRLE | Executed – Negotiated Reduction | 2023-10-17 | 82600 | 44700 | 54.1% | 37900 | 0 | 0 | 0% | 44700 | 82 | 0.006
DRLE-CO-050 | DRLE | Executed – Partial (Revised Scope) | 2024-03-05 | 243200 | 179000 | 73.6% | 64200 | 1 | 1 | 100% | 179000 | 83 | 0.025
DRLE-CO-051 | DRLE | Executed – Negotiated Reduction | 2024-01-29 | 59400 | 31900 | 53.7% | 27500 | 4 | 1 | 25% | 31900 | 84 | 0.004
DRLE-CO-052 | DRLE | Executed – Partial (Revised Scope) | 2024-05-27 | 16900 | 10200 | 60.4% | 6700 | 0 | 0 | 0% | 10200 | 84 | 0.001
DRLE-CO-053 | DRLE | Rejected – Contractor Responsibility / No Merit | 2024-02-01 | 47000 | 0 | 0% | 47000 | 3 | 0 | 0% | 0 | 84 | 0
DRLE-CO-054 | DRLE | Executed – Negotiated Reduction | 2024-03-18 | 355800 | 199900 | 56.2% | 155900 | 12 | 5 | 41.7% | 199900 | 89 | 0.028
DRLE-CO-055 | DRLE | Executed – Negotiated Reduction | 2024-04-30 | 482900 | 449100 | 93% | 33800 | 23 | 17 | 73.9% | 449100 | 106 | 0.062
DRLE-CO-056 | DRLE | Executed – Negotiated Reduction | 2024-06-21 | 995800 | 789000 | 79.2% | 206800 | 9 | 8 | 88.9% | 789000 | 114 | 0.11
DRLE-CO-057 | DRLE | Executed – Negotiated Reduction | 2024-04-30 | 1625200 | 1105500 | 68% | 519700 | 14 | 10 | 71.4% | 1105500 | 124 | 0.154
DRLE-CO-058 | DRLE | Resolved via Global Settlement | 2024-07-29 | 151800 | 63400 | 41.8% | 88400 | 4 | 1 | 25% | 63400 | 125 | 0.009
DRLE-CO-059 | DRLE | Rejected – Contractor Responsibility / No Merit | 2024-09-11 | 372500 | 0 | 0% | 372500 | 7 | 0 | 0% | 0 | 125 | 0
DRLE-CO-060 | DRLE | Escalated to DRB – Partial Award | 2024-10-16 | 154300 | 84300 | 54.6% | 70000 | 6 | 2 | 33.3% | 84300 | 127 | 0.012
DRLE-CO-061 | DRLE | Executed – Negotiated Reduction | 2024-12-26 | 400300 | 248000 | 62% | 152300 | 1 | 0 | 0% | 248000 | 127 | 0.034
DRLE-CO-062 | DRLE | Executed – Partial (Revised Scope) | 2024-09-30 | 110600 | 58200 | 52.6% | 52400 | 0 | 0 | 0% | 58200 | 127 | 0.008
DRLE-CO-063 | DRLE | Resolved via Global Settlement | 2024-12-17 | 4126900 | 2986000 | 72.4% | 1140900 | 0 | 0 | 0% | 2986000 | 127 | 0.415
DRLE-CO-064 | DRLE | Executed – Negotiated Reduction | 2025-01-09 | 202700 | 163500 | 80.7% | 39200 | 0 | 0 | 0% | 163500 | 127 | 0.023
DRLE-CO-065 | DRLE | Rejected – Contractor Responsibility / No Merit | 2025-01-01 | 283200 | 0 | 0% | 283200 | 0 | 0 | 0% | 0 | 127 | 0
DRLE-CO-066 | DRLE | Executed – Negotiated Reduction | 2025-04-22 | 353700 | 190000 | 53.7% | 163700 | 7 | 3 | 42.9% | 190000 | 130 | 0.026
DRLE-CO-067 | DRLE | Executed – Negotiated Reduction | 2025-07-16 | 382500 | 204400 | 53.4% | 178100 | 12 | 5 | 41.7% | 204400 | 135 | 0.028
E320-CO-001 | E320 | Escalated to DRB – Partial Award | 2017-03-15 | 103900 | 44100 | 42.4% | 59800 | 0 | 0 | 0% | 44100 | 0 | 0.023
E320-CO-002 | E320 | Withdrawn by Contractor | 2017-04-26 | 162700 | 0 | 0% | 162700 | 0 | 0 | 0% | 0 | 0 | 0
E320-CO-003 | E320 | Resolved via Global Settlement | 2017-07-24 | 186900 | 95100 | 50.9% | 91800 | 0 | 0 | 0% | 95100 | 0 | 0.05
E320-CO-004 | E320 | Resolved via Global Settlement | 2017-08-14 | 33200 | 15600 | 47% | 17600 | 0 | 0 | 0% | 15600 | 0 | 0.008
E320-CO-005 | E320 | Executed – Negotiated Reduction | 2017-10-30 | 17400 | 11100 | 63.8% | 6300 | 2 | 1 | 50% | 11100 | 1 | 0.006
E320-CO-006 | E320 | Executed – As Requested | 2017-12-13 | 523300 | 523300 | 100% | 0 | 20 | 19 | 95% | 523300 | 20 | 0.275
E320-CO-007 | E320 | Executed – As Requested | 2017-12-11 | 151400 | 151400 | 100% | 0 | 17 | 11 | 64.7% | 151400 | 31 | 0.08
E320-CO-008 | E320 | Executed – Partial (Revised Scope) | 2017-12-12 | 32200 | 19000 | 59% | 13200 | 0 | 0 | 0% | 19000 | 31 | 0.01
E320-CO-009 | E320 | Escalated to DRB – Partial Award | 2019-03-18 | 34500 | 23800 | 69% | 10700 | 0 | 0 | 0% | 23800 | 31 | 0.013
E320-CO-010 | E320 | Executed – As Requested | 2018-03-12 | 114600 | 114600 | 100% | 0 | 5 | 5 | 100% | 114600 | 36 | 0.06
E320-CO-011 | E320 | Executed – Partial (Revised Scope) | 2018-04-20 | 386600 | 246900 | 63.9% | 139700 | 28 | 16 | 57.1% | 246900 | 52 | 0.13
E320-CO-012 | E320 | Executed – Negotiated Reduction | 2018-04-24 | 2807200 | 2456200 | 87.5% | 351000 | 31 | 27 | 87.1% | 2456200 | 79 | 1.293
E320-CO-013 | E320 | Escalated to DRB – Partial Award | 2018-07-02 | 42100 | 13900 | 33% | 28200 | 0 | 0 | 0% | 13900 | 79 | 0.007
E320-CO-014 | E320 | Resolved via Global Settlement | 2018-06-21 | 463100 | 157000 | 33.9% | 306100 | 0 | 0 | 0% | 157000 | 79 | 0.083
E320-CO-015 | E320 | Escalated to DRB – Partial Award | 2018-11-08 | 120600 | 84200 | 69.8% | 36400 | 2 | 1 | 50% | 84200 | 80 | 0.044
E320-CO-016 | E320 | Executed – Negotiated Reduction | 2018-07-25 | 34800 | 28500 | 81.9% | 6300 | 0 | 0 | 0% | 28500 | 80 | 0.015
E320-CO-017 | E320 | Executed – Negotiated Reduction | 2018-08-27 | 38200 | 35100 | 91.9% | 3100 | 12 | 7 | 58.3% | 35100 | 87 | 0.018
E320-CO-018 | E320 | Executed – Partial (Revised Scope) | 2018-09-06 | 265800 | 212200 | 79.8% | 53600 | 3 | 2 | 66.7% | 212200 | 89 | 0.112
E320-CO-019 | E320 | Rejected – Contractor Responsibility / No Merit | 2018-09-14 | 175800 | 0 | 0% | 175800 | 44 | 0 | 0% | 0 | 89 | 0
E320-CO-020 | E320 | Executed – Negotiated Reduction | 2019-04-22 | 134600 | 97800 | 72.7% | 36800 | 2 | 1 | 50% | 97800 | 90 | 0.051
E320-CO-021 | E320 | Executed – Negotiated Reduction | 2019-01-14 | 800000 | 603900 | 75.5% | 196100 | 26 | 15 | 57.7% | 603900 | 105 | 0.318
E320-CO-022 | E320 | Executed – Negotiated Reduction | 2019-01-28 | 124600 | 89900 | 72.2% | 34700 | 6 | 3 | 50% | 89900 | 108 | 0.047
E320-CO-023 | E320 | Executed – Negotiated Reduction | 2019-02-14 | 252200 | 155700 | 61.7% | 96500 | 2 | 1 | 50% | 155700 | 109 | 0.082
E320-CO-024 | E320 | Resolved via Global Settlement | 2019-03-04 | 119500 | 74300 | 62.2% | 45200 | 6 | 3 | 50% | 74300 | 112 | 0.039
E320-CO-025 | E320 | Resolved via Global Settlement | 2019-10-07 | 2685700 | 1478500 | 55.1% | 1207200 | 31 | 15 | 48.4% | 1478500 | 127 | 0.778
E320-CO-026 | E320 | Rejected – Contractor Responsibility / No Merit | 2019-09-23 | 211700 | 0 | 0% | 211700 | 0 | 0 | 0% | 0 | 127 | 0
E320-CO-027 | E320 | Resolved via Global Settlement | 2019-11-11 | 34900 | 8200 | 23.5% | 26700 | 5 | 1 | 20% | 8200 | 128 | 0.004
E320-CO-028 | E320 | Executed – Negotiated Reduction | 2019-11-08 | 117200 | 53100 | 45.3% | 64100 | 15 | 5 | 33.3% | 53100 | 133 | 0.028
E320-CO-029 | E320 | Executed – Negotiated Reduction | 2019-12-31 | 721100 | 546600 | 75.8% | 174500 | 8 | 5 | 62.5% | 546600 | 138 | 0.288
E320-CO-030 | E320 | Executed – Negotiated Reduction | 2020-04-27 | 43400 | 30100 | 69.4% | 13300 | 0 | 0 | 0% | 30100 | 138 | 0.016
E320-CO-031 | E320 | Executed – Negotiated Reduction | 2020-02-21 | 537000 | 405000 | 75.4% | 132000 | 7 | 4 | 57.1% | 405000 | 142 | 0.213
E320-CO-032 | E320 | Executed – Negotiated Reduction | 2020-03-11 | 68700 | 39600 | 57.6% | 29100 | 7 | 4 | 57.1% | 39600 | 146 | 0.021
E320-CO-033 | E320 | Executed – Negotiated Reduction | 2020-02-27 | 38700 | 27500 | 71.1% | 11200 | 7 | 3 | 42.9% | 27500 | 149 | 0.014
E320-CO-034 | E320 | Executed – Negotiated Reduction | 2020-03-16 | 384500 | 249900 | 65% | 134600 | 3 | 1 | 33.3% | 249900 | 150 | 0.132
E320-CO-035 | E320 | Resolved via Global Settlement | 2020-04-09 | 71500 | 50700 | 70.9% | 20800 | 0 | 0 | 0% | 50700 | 150 | 0.027
E320-CO-036 | E320 | Resolved via Global Settlement | 2020-05-18 | 340900 | 205600 | 60.3% | 135300 | 18 | 12 | 66.7% | 205600 | 162 | 0.108
E320-CO-037 | E320 | Rejected – Contractor Responsibility / No Merit | 2020-06-23 | 125800 | 0 | 0% | 125800 | 5 | 0 | 0% | 0 | 162 | 0
E320-CO-038 | E320 | Rejected – Contractor Responsibility / No Merit | 2020-07-16 | 268400 | 0 | 0% | 268400 | 11 | 0 | 0% | 0 | 162 | 0
E320-CO-039 | E320 | Resolved via Global Settlement | 2020-10-16 | 1394300 | 565400 | 40.6% | 828900 | 11 | 3 | 27.3% | 565400 | 165 | 0.298
E320-CO-040 | E320 | Executed – Negotiated Reduction | 2020-09-25 | 86200 | 72900 | 84.6% | 13300 | 12 | 7 | 58.3% | 72900 | 172 | 0.038
E320-CO-041 | E320 | Resolved via Global Settlement | 2021-08-18 | 63900 | 34500 | 54% | 29400 | 0 | 0 | 0% | 34500 | 172 | 0.018
E320-CO-042 | E320 | Resolved via Global Settlement | 2020-11-16 | 2333100 | 1239400 | 53.1% | 1093700 | 0 | 0 | 0% | 1239400 | 172 | 0.652
E320-CO-043 | E320 | Executed – Negotiated Reduction | 2021-01-19 | 255900 | 164400 | 64.2% | 91500 | 14 | 6 | 42.9% | 164400 | 178 | 0.087
E320-CO-044 | E320 | Resolved via Global Settlement | 2021-09-23 | 66200 | 25200 | 38.1% | 41000 | 0 | 0 | 0% | 25200 | 178 | 0.013
E330-CO-001 | E330 | Executed – Partial (Revised Scope) | 2016-08-08 | 83500 | 61700 | 73.9% | 21800 | 0 | 0 | 0% | 61700 | 0 | 0.051
E330-CO-002 | E330 | Executed – Negotiated Reduction | 2016-11-24 | 75100 | 44200 | 58.9% | 30900 | 14 | 5 | 35.7% | 44200 | 5 | 0.036
E330-CO-003 | E330 | Resolved via Global Settlement | 2017-02-07 | 9200 | 5400 | 58.7% | 3800 | 5 | 2 | 40% | 5400 | 7 | 0.004
E330-CO-004 | E330 | Executed – Partial (Revised Scope) | 2017-08-22 | 1239900 | 957100 | 77.2% | 282800 | 10 | 6 | 60% | 957100 | 13 | 0.788
E330-CO-005 | E330 | Executed – Negotiated Reduction | 2017-10-18 | 2116000 | 1058000 | 50% | 1058000 | 6 | 2 | 33.3% | 1058000 | 15 | 0.871
E330-CO-006 | E330 | Resolved via Global Settlement | 2017-07-17 | 540300 | 406600 | 75.3% | 133700 | 0 | 0 | 0% | 406600 | 15 | 0.335
E330-CO-007 | E330 | Rejected – Contractor Responsibility / No Merit | 2017-07-26 | 69800 | 0 | 0% | 69800 | 3 | 0 | 0% | 0 | 15 | 0
E330-CO-008 | E330 | Executed – Negotiated Reduction | 2017-10-26 | 247100 | 169700 | 68.7% | 77400 | 7 | 5 | 71.4% | 169700 | 20 | 0.14
E330-CO-009 | E330 | Executed – Negotiated Reduction | 2017-09-04 | 107500 | 88300 | 82.1% | 19200 | 0 | 0 | 0% | 88300 | 20 | 0.073
E330-CO-010 | E330 | Resolved via Global Settlement | 2017-11-06 | 98200 | 32300 | 32.9% | 65900 | 0 | 0 | 0% | 32300 | 20 | 0.027
E330-CO-011 | E330 | Rejected – Contractor Responsibility / No Merit | 2017-12-08 | 1911600 | 0 | 0% | 1911600 | 21 | 0 | 0% | 0 | 20 | 0
E330-CO-012 | E330 | Resolved via Global Settlement | 2017-12-20 | 85000 | 39100 | 46% | 45900 | 0 | 0 | 0% | 39100 | 20 | 0.032
E330-CO-013 | E330 | Executed – Negotiated Reduction | 2017-12-28 | 106300 | 78400 | 73.8% | 27900 | 0 | 0 | 0% | 78400 | 20 | 0.065
E330-CO-014 | E330 | Executed – Negotiated Reduction | 2018-02-12 | 386700 | 226100 | 58.5% | 160600 | 8 | 5 | 62.5% | 226100 | 25 | 0.186
E330-CO-015 | E330 | Executed – As Requested | 2018-02-20 | 40700 | 40700 | 100% | 0 | 2 | 1 | 50% | 40700 | 26 | 0.034
E330-CO-016 | E330 | Rejected – Contractor Responsibility / No Merit | 2018-02-19 | 56500 | 0 | 0% | 56500 | 3 | 0 | 0% | 0 | 26 | 0
E330-CO-017 | E330 | Executed – Negotiated Reduction | 2018-03-19 | 263300 | 215500 | 81.8% | 47800 | 9 | 5 | 55.6% | 215500 | 31 | 0.177
E330-CO-018 | E330 | Executed – Negotiated Reduction | 2018-06-12 | 356700 | 211100 | 59.2% | 145600 | 10 | 6 | 60% | 211100 | 37 | 0.174
E330-CO-019 | E330 | Resolved via Global Settlement | 2018-03-30 | 112100 | 70100 | 62.5% | 42000 | 0 | 0 | 0% | 70100 | 37 | 0.058
E330-CO-020 | E330 | Executed – Negotiated Reduction | 2018-04-20 | 363100 | 265000 | 73% | 98100 | 10 | 6 | 60% | 265000 | 43 | 0.218
E330-CO-021 | E330 | Resolved via Global Settlement | 2018-05-07 | 283300 | 118100 | 41.7% | 165200 | 0 | 0 | 0% | 118100 | 43 | 0.097
E330-CO-022 | E330 | Escalated to DRB – Partial Award | 2019-03-18 | 9800 | 6900 | 70.4% | 2900 | 12 | 7 | 58.3% | 6900 | 50 | 0.006
E330-CO-023 | E330 | Withdrawn by Contractor | 2018-06-12 | 564900 | 0 | 0% | 564900 | 9 | 0 | 0% | 0 | 50 | 0
E330-CO-024 | E330 | Withdrawn by Contractor | 2019-03-11 | 676500 | 0 | 0% | 676500 | 5 | 0 | 0% | 0 | 50 | 0
E330-CO-025 | E330 | Withdrawn by Contractor | 2018-11-05 | 1267000 | 0 | 0% | 1267000 | 0 | 0 | 0% | 0 | 50 | 0
E330-CO-026 | E330 | Executed – Negotiated Reduction | 2018-12-31 | 109600 | 95800 | 87.4% | 13800 | 0 | 0 | 0% | 95800 | 50 | 0.079
E330-CO-027 | E330 | Rejected – Contractor Responsibility / No Merit | 2018-12-19 | 1292200 | 0 | 0% | 1292200 | 18 | 0 | 0% | 0 | 50 | 0
E330-CO-028 | E330 | Resolved via Global Settlement | 2019-05-31 | 103600 | 65500 | 63.2% | 38100 | 0 | 0 | 0% | 65500 | 50 | 0.054
E330-CO-029 | E330 | Executed – Negotiated Reduction | 2019-02-04 | 158000 | 115600 | 73.2% | 42400 | 0 | 0 | 0% | 115600 | 50 | 0.095
E330-CO-030 | E330 | Executed – Negotiated Reduction | 2019-02-15 | 37600 | 26500 | 70.5% | 11100 | 4 | 3 | 75% | 26500 | 53 | 0.022
E330-CO-031 | E330 | Executed – As Requested | 2019-07-31 | 154700 | 154700 | 100% | 0 | 0 | 0 | 0% | 154700 | 53 | 0.127
E330-CO-032 | E330 | Withdrawn by Contractor | 2019-05-09 | 8542200 | 0 | 0% | 8542200 | 34 | 0 | 0% | 0 | 53 | 0
E330-CO-033 | E330 | Resolved via Global Settlement | 2020-07-21 | 8200 | 3200 | 39% | 5000 | 0 | 0 | 0% | 3200 | 53 | 0.003
E330-CO-034 | E330 | Escalated to DRB – Partial Award | 2019-08-21 | 80100 | 38400 | 47.9% | 41700 | 53 | 27 | 50.9% | 38400 | 80 | 0.032
E330-CO-035 | E330 | Executed – As Requested | 2019-10-07 | 162700 | 162700 | 100% | 0 | 0 | 0 | 0% | 162700 | 80 | 0.134
E330-CO-036 | E330 | Escalated to DRB – Partial Award | 2019-10-21 | 215300 | 103600 | 48.1% | 111700 | 0 | 0 | 0% | 103600 | 80 | 0.085
E330-CO-037 | E330 | Resolved via Global Settlement | 2019-06-28 | 180700 | 132900 | 73.5% | 47800 | 0 | 0 | 0% | 132900 | 80 | 0.109
E330-CO-038 | E330 | Executed – As Requested | 2019-12-09 | 346600 | 346600 | 100% | 0 | 4 | 3 | 75% | 346600 | 83 | 0.285
E330-CO-039 | E330 | Resolved via Global Settlement | 2020-03-23 | 1010300 | 605600 | 59.9% | 404700 | 12 | 4 | 33.3% | 605600 | 87 | 0.499
E330-CO-040 | E330 | Resolved via Global Settlement | 2020-05-04 | 209300 | 71100 | 34% | 138200 | 11 | 4 | 36.4% | 71100 | 91 | 0.059
E330-CO-041 | E330 | Executed – Negotiated Reduction | 2020-05-19 | 259200 | 142700 | 55.1% | 116500 | 9 | 3 | 33.3% | 142700 | 94 | 0.118
E330-CO-042 | E330 | Executed – As Requested | 2020-06-22 | 1224200 | 1224200 | 100% | 0 | 1 | 1 | 100% | 1224200 | 95 | 1.008
E330-CO-043 | E330 | Withdrawn by Contractor | 2020-10-07 | 497600 | 0 | 0% | 497600 | 4 | 0 | 0% | 0 | 95 | 0
E330-CO-044 | E330 | Executed – As Requested | 2020-08-03 | 206700 | 206700 | 100% | 0 | 21 | 21 | 100% | 206700 | 116 | 0.17
E330-CO-045 | E330 | Executed – Negotiated Reduction | 2021-01-14 | 285600 | 184100 | 64.5% | 101500 | 22 | 10 | 45.5% | 184100 | 126 | 0.152
E330-CO-046 | E330 | Resolved via Global Settlement | 2021-08-18 | 285900 | 158400 | 55.4% | 127500 | 6 | 3 | 50% | 158400 | 129 | 0.13
E330-CO-047 | E330 | Resolved via Global Settlement | 2021-08-16 | 543900 | 382000 | 70.2% | 161900 | 4 | 2 | 50% | 382000 | 131 | 0.315
E330-CO-048 | E330 | Executed – Negotiated Reduction | 2021-02-15 | 422100 | 186600 | 44.2% | 235500 | 0 | 0 | 0% | 186600 | 131 | 0.154
E335-CO-001 | E335 | Executed – Negotiated Reduction | 2017-09-06 | 53200 | 46800 | 88% | 6400 | 0 | 0 | 0% | 46800 | 0 | 0.016
E335-CO-002 | E335 | Executed – As Requested | 2017-09-19 | 626800 | 626800 | 100% | 0 | 5 | 3 | 60% | 626800 | 3 | 0.22
E335-CO-003 | E335 | Executed – Negotiated Reduction | 2018-03-19 | 312300 | 178800 | 57.3% | 133500 | 5 | 3 | 60% | 178800 | 6 | 0.063
E335-CO-004 | E335 | Executed – As Requested | 2018-07-04 | 14700 | 14700 | 100% | 0 | 0 | 0 | 0% | 14700 | 6 | 0.005
E335-CO-005 | E335 | Executed – As Requested | 2018-04-03 | 106700 | 106700 | 100% | 0 | 16 | 10 | 62.5% | 106700 | 16 | 0.037
E335-CO-006 | E335 | Executed – Partial (Revised Scope) | 2018-09-11 | 536700 | 455900 | 84.9% | 80800 | 25 | 23 | 92% | 455900 | 39 | 0.16
E335-CO-007 | E335 | Executed – As Requested | 2018-07-19 | 399300 | 399300 | 100% | 0 | 7 | 7 | 100% | 399300 | 46 | 0.14
E335-CO-008 | E335 | Withdrawn by Contractor | 2018-06-18 | 45600 | 0 | 0% | 45600 | 0 | 0 | 0% | 0 | 46 | 0
E335-CO-009 | E335 | Resolved via Global Settlement | 2018-09-17 | 1325100 | 1033400 | 78% | 291700 | 2 | 2 | 100% | 1033400 | 48 | 0.363
E335-CO-010 | E335 | Resolved via Global Settlement | 2018-06-20 | 1941600 | 619600 | 31.9% | 1322000 | 0 | 0 | 0% | 619600 | 48 | 0.217
E335-CO-011 | E335 | Executed – Negotiated Reduction | 2019-05-06 | 4554800 | 4103600 | 90.1% | 451200 | 4 | 4 | 100% | 4103600 | 52 | 1.44
E335-CO-012 | E335 | Executed – Partial (Revised Scope) | 2019-02-01 | 166800 | 74100 | 44.4% | 92700 | 4 | 1 | 25% | 74100 | 53 | 0.026
E335-CO-013 | E335 | Resolved via Global Settlement | 2019-06-05 | 426800 | 299300 | 70.1% | 127500 | 20 | 12 | 60% | 299300 | 65 | 0.105
E335-CO-014 | E335 | Resolved via Global Settlement | 2019-10-24 | 259600 | 127300 | 49% | 132300 | 26 | 15 | 57.7% | 127300 | 80 | 0.045
E335-CO-015 | E335 | Rejected – Contractor Responsibility / No Merit | 2019-06-06 | 137600 | 0 | 0% | 137600 | 5 | 0 | 0% | 0 | 80 | 0
E335-CO-016 | E335 | Executed – Negotiated Reduction | 2019-04-24 | 1804700 | 1182700 | 65.5% | 622000 | 3 | 2 | 66.7% | 1182700 | 82 | 0.415
E335-CO-017 | E335 | Resolved via Global Settlement | 2019-09-19 | 1214700 | 537200 | 44.2% | 677500 | 3 | 1 | 33.3% | 537200 | 83 | 0.188
E335-CO-018 | E335 | Resolved via Global Settlement | 2019-10-01 | 134600 | 89000 | 66.1% | 45600 | 0 | 0 | 0% | 89000 | 83 | 0.031
E335-CO-019 | E335 | Executed – Partial (Revised Scope) | 2019-08-19 | 147800 | 44600 | 30.2% | 103200 | 10 | 3 | 30% | 44600 | 86 | 0.016
E335-CO-020 | E335 | Resolved via Global Settlement | 2019-10-04 | 20200 | 11200 | 55.4% | 9000 | 0 | 0 | 0% | 11200 | 86 | 0.004
E335-CO-021 | E335 | Executed – Negotiated Reduction | 2019-09-30 | 259900 | 221900 | 85.4% | 38000 | 0 | 0 | 0% | 221900 | 86 | 0.078
E335-CO-022 | E335 | Resolved via Global Settlement | 2019-09-30 | 564600 | 496500 | 87.9% | 68100 | 0 | 0 | 0% | 496500 | 86 | 0.174
E335-CO-023 | E335 | Executed – Negotiated Reduction | 2019-12-12 | 3463100 | 2435500 | 70.3% | 1027600 | 5 | 3 | 60% | 2435500 | 89 | 0.855
E335-CO-024 | E335 | Executed – Negotiated Reduction | 2020-01-23 | 184700 | 131700 | 71.3% | 53000 | 42 | 26 | 61.9% | 131700 | 115 | 0.046
E335-CO-025 | E335 | Withdrawn by Contractor | 2020-01-10 | 969000 | 0 | 0% | 969000 | 8 | 0 | 0% | 0 | 115 | 0
E335-CO-026 | E335 | Executed – As Requested | 2020-05-04 | 185500 | 185500 | 100% | 0 | 14 | 12 | 85.7% | 185500 | 127 | 0.065
E335-CO-027 | E335 | Executed – Negotiated Reduction | 2020-04-14 | 207600 | 149900 | 72.2% | 57700 | 0 | 0 | 0% | 149900 | 127 | 0.053
E335-CO-028 | E335 | Escalated to DRB – Partial Award | 2020-06-10 | 268400 | 114500 | 42.7% | 153900 | 0 | 0 | 0% | 114500 | 127 | 0.04
E335-CO-029 | E335 | Executed – Negotiated Reduction | 2020-11-04 | 633300 | 553900 | 87.5% | 79400 | 0 | 0 | 0% | 553900 | 127 | 0.194
E335-CO-030 | E335 | Resolved via Global Settlement | 2020-10-20 | 45200 | 21200 | 46.9% | 24000 | 4 | 2 | 50% | 21200 | 129 | 0.007
E335-CO-031 | E335 | Executed – Negotiated Reduction | 2020-09-09 | 16100 | 15300 | 95% | 800 | 0 | 0 | 0% | 15300 | 129 | 0.005
E335-CO-032 | E335 | Resolved via Global Settlement | 2020-09-28 | 673100 | 256700 | 38.1% | 416400 | 8 | 3 | 37.5% | 256700 | 132 | 0.09
E335-CO-033 | E335 | Executed – Negotiated Reduction | 2020-10-19 | 40000 | 29800 | 74.5% | 10200 | 8 | 4 | 50% | 29800 | 136 | 0.01
E335-CO-034 | E335 | Rejected – Contractor Responsibility / No Merit | 2020-09-07 | 1113500 | 0 | 0% | 1113500 | 5 | 0 | 0% | 0 | 136 | 0
E335-CO-035 | E335 | Resolved via Global Settlement | 2020-10-13 | 46800 | 16100 | 34.4% | 30700 | 0 | 0 | 0% | 16100 | 136 | 0.006
E335-CO-036 | E335 | Executed – As Requested | 2020-12-10 | 60200 | 60200 | 100% | 0 | 5 | 4 | 80% | 60200 | 140 | 0.021
E335-CO-037 | E335 | Resolved via Global Settlement | 2021-03-01 | 1327600 | 889700 | 67% | 437900 | 74 | 51 | 68.9% | 889700 | 191 | 0.312
E335-CO-038 | E335 | Resolved via Global Settlement | 2021-12-06 | 48900 | 24200 | 49.5% | 24700 | 18 | 9 | 50% | 24200 | 200 | 0.008
E335-CO-039 | E335 | Resolved via Global Settlement | 2021-11-01 | 4447000 | 3509500 | 78.9% | 937500 | 35 | 20 | 57.1% | 3509500 | 220 | 1.231
E335-CO-040 | E335 | Executed – As Requested | 2021-12-29 | 574700 | 574700 | 100% | 0 | 32 | 23 | 71.9% | 574700 | 243 | 0.202
E335-CO-041 | E335 | Executed – Negotiated Reduction | 2021-10-04 | 19700 | 9400 | 47.7% | 10300 | 0 | 0 | 0% | 9400 | 243 | 0.003
E335-CO-042 | E335 | Executed – Negotiated Reduction | 2021-10-01 | 402000 | 302100 | 75.1% | 99900 | 0 | 0 | 0% | 302100 | 243 | 0.106
E335-CO-043 | E335 | Executed – Negotiated Reduction | 2021-12-28 | 297600 | 168100 | 56.5% | 129500 | 0 | 0 | 0% | 168100 | 243 | 0.059
E335-CO-044 | E335 | Executed – Negotiated Reduction | 2021-12-13 | 30800 | 24800 | 80.5% | 6000 | 0 | 0 | 0% | 24800 | 243 | 0.009
E335-CO-045 | E335 | Executed – Negotiated Reduction | 2022-01-10 | 1450400 | 1089600 | 75.1% | 360800 | 7 | 6 | 85.7% | 1089600 | 249 | 0.382
E335-CO-046 | E335 | Executed – Negotiated Reduction | 2022-01-20 | 2179800 | 1510500 | 69.3% | 669300 | 3 | 2 | 66.7% | 1510500 | 251 | 0.53
E335-CO-047 | E335 | Rejected – Contractor Responsibility / No Merit | 2022-06-10 | 49600 | 0 | 0% | 49600 | 0 | 0 | 0% | 0 | 251 | 0
E335-CO-048 | E335 | Resolved via Global Settlement | 2022-05-12 | 251100 | 105100 | 41.9% | 146000 | 34 | 14 | 41.2% | 105100 | 265 | 0.037
E335-CO-049 | E335 | Executed – Negotiated Reduction | 2022-03-04 | 498700 | 343100 | 68.8% | 155600 | 9 | 4 | 44.4% | 343100 | 269 | 0.12
E335-CO-050 | E335 | Executed – Negotiated Reduction | 2022-06-24 | 604600 | 462600 | 76.5% | 142000 | 0 | 0 | 0% | 462600 | 269 | 0.162
E335-CO-051 | E335 | Resolved via Global Settlement | 2022-04-28 | 163700 | 70000 | 42.8% | 93700 | 25 | 12 | 48% | 70000 | 281 | 0.025
E335-CO-052 | E335 | Executed – Negotiated Reduction | 2023-07-14 | 329700 | 277400 | 84.1% | 52300 | 16 | 13 | 81.2% | 277400 | 294 | 0.097
E335-CO-053 | E335 | Resolved via Global Settlement | 2022-05-27 | 1302200 | 773700 | 59.4% | 528500 | 0 | 0 | 0% | 773700 | 294 | 0.271
E335-CO-054 | E335 | Executed – Negotiated Reduction | 2022-05-31 | 77500 | 48000 | 61.9% | 29500 | 0 | 0 | 0% | 48000 | 294 | 0.017
E335-CO-055 | E335 | Rejected – Contractor Responsibility / No Merit | 2022-11-16 | 73700 | 0 | 0% | 73700 | 0 | 0 | 0% | 0 | 294 | 0
E335-CO-056 | E335 | Rejected – Contractor Responsibility / No Merit | 2023-03-07 | 135400 | 0 | 0% | 135400 | 0 | 0 | 0% | 0 | 294 | 0
E335-CO-057 | E335 | Withdrawn by Contractor | 2023-05-29 | 193000 | 0 | 0% | 193000 | 6 | 0 | 0% | 0 | 294 | 0
E335-CO-058 | E335 | Executed – Negotiated Reduction | 2023-04-05 | 607600 | 495900 | 81.6% | 111700 | 0 | 0 | 0% | 495900 | 294 | 0.174
E335-CO-059 | E335 | Executed – Partial (Revised Scope) | 2023-06-19 | 450400 | 331900 | 73.7% | 118500 | 0 | 0 | 0% | 331900 | 294 | 0.116
E340-CO-001 | E340 | Executed – As Requested | 2018-04-12 | 30500 | 30500 | 100% | 0 | 0 | 0 | 0% | 30500 | 0 | 0.032
E340-CO-002 | E340 | Executed – Negotiated Reduction | 2019-04-01 | 110100 | 72000 | 65.4% | 38100 | 0 | 0 | 0% | 72000 | 0 | 0.076
E340-CO-003 | E340 | Executed – As Requested | 2018-05-07 | 104000 | 104000 | 100% | 0 | 14 | 11 | 78.6% | 104000 | 11 | 0.109
E340-CO-004 | E340 | Resolved via Global Settlement | 2018-11-06 | 434900 | 103500 | 23.8% | 331400 | 3 | 1 | 33.3% | 103500 | 12 | 0.109
E340-CO-005 | E340 | Executed – Negotiated Reduction | 2018-07-02 | 38000 | 25100 | 66.1% | 12900 | 0 | 0 | 0% | 25100 | 12 | 0.026
E340-CO-006 | E340 | Resolved via Global Settlement | 2018-12-06 | 180400 | 90100 | 49.9% | 90300 | 0 | 0 | 0% | 90100 | 12 | 0.095
E340-CO-007 | E340 | Resolved via Global Settlement | 2018-08-10 | 221400 | 108700 | 49.1% | 112700 | 0 | 0 | 0% | 108700 | 12 | 0.114
E340-CO-008 | E340 | Resolved via Global Settlement | 2019-02-08 | 637900 | 381900 | 59.9% | 256000 | 0 | 0 | 0% | 381900 | 12 | 0.402
E340-CO-009 | E340 | Executed – Negotiated Reduction | 2019-02-25 | 12100 | 4800 | 39.7% | 7300 | 9 | 2 | 22.2% | 4800 | 14 | 0.005
E340-CO-010 | E340 | Executed – Negotiated Reduction | 2019-05-21 | 23600 | 15800 | 66.9% | 7800 | 2 | 2 | 100% | 15800 | 16 | 0.017
E340-CO-011 | E340 | Executed – Partial (Revised Scope) | 2019-02-13 | 54700 | 49400 | 90.3% | 5300 | 0 | 0 | 0% | 49400 | 16 | 0.052
E340-CO-012 | E340 | Resolved via Global Settlement | 2019-09-23 | 643700 | 499700 | 77.6% | 144000 | 8 | 7 | 87.5% | 499700 | 23 | 0.526
E340-CO-013 | E340 | Executed – As Requested | 2019-08-01 | 74500 | 74500 | 100% | 0 | 0 | 0 | 0% | 74500 | 23 | 0.078
E340-CO-014 | E340 | Resolved via Global Settlement | 2019-09-11 | 381300 | 213100 | 55.9% | 168200 | 14 | 5 | 35.7% | 213100 | 28 | 0.224
E340-CO-015 | E340 | Executed – Partial (Revised Scope) | 2019-11-20 | 48800 | 31500 | 64.5% | 17300 | 8 | 5 | 62.5% | 31500 | 33 | 0.033
E340-CO-016 | E340 | Resolved via Global Settlement | 2020-01-02 | 2248700 | 1351800 | 60.1% | 896900 | 25 | 14 | 56% | 1351800 | 47 | 1.423
E340-CO-017 | E340 | Executed – Negotiated Reduction | 2020-01-15 | 67300 | 54600 | 81.1% | 12700 | 4 | 2 | 50% | 54600 | 49 | 0.057
E340-CO-018 | E340 | Resolved via Global Settlement | 2020-02-04 | 1950400 | 1331800 | 68.3% | 618600 | 3 | 2 | 66.7% | 1331800 | 51 | 1.402
E340-CO-019 | E340 | Resolved via Global Settlement | 2020-07-15 | 172700 | 42400 | 24.6% | 130300 | 6 | 1 | 16.7% | 42400 | 52 | 0.045
E340-CO-020 | E340 | Resolved via Global Settlement | 2020-08-31 | 351600 | 290900 | 82.7% | 60700 | 14 | 12 | 85.7% | 290900 | 64 | 0.306
E340-CO-021 | E340 | Withdrawn by Contractor | 2020-07-13 | 212100 | 0 | 0% | 212100 | 0 | 0 | 0% | 0 | 64 | 0
E340-CO-022 | E340 | Executed – Partial (Revised Scope) | 2020-08-24 | 45600 | 14300 | 31.4% | 31300 | 0 | 0 | 0% | 14300 | 64 | 0.015
E340-CO-023 | E340 | Rejected – Contractor Responsibility / No Merit | 2020-11-06 | 191300 | 0 | 0% | 191300 | 0 | 0 | 0% | 0 | 64 | 0
E340-CO-024 | E340 | Resolved via Global Settlement | 2021-01-29 | 255100 | 142900 | 56% | 112200 | 2 | 1 | 50% | 142900 | 65 | 0.15
E340-CO-025 | E340 | Resolved via Global Settlement | 2021-04-05 | 651600 | 524200 | 80.4% | 127400 | 0 | 0 | 0% | 524200 | 65 | 0.552
E340-CO-026 | E340 | Executed – Negotiated Reduction | 2021-03-11 | 68400 | 57000 | 83.3% | 11400 | 2 | 1 | 50% | 57000 | 66 | 0.06
E340-CO-027 | E340 | Executed – As Requested | 2021-05-31 | 73400 | 73400 | 100% | 0 | 10 | 7 | 70% | 73400 | 73 | 0.077
E340-CO-028 | E340 | Executed – Partial (Revised Scope) | 2021-03-29 | 33800 | 12200 | 36.1% | 21600 | 0 | 0 | 0% | 12200 | 73 | 0.013
E360-CO-001 | E360 | Executed – Negotiated Reduction | 2017-06-15 | 25700 | 20800 | 80.9% | 4900 | 18 | 12 | 66.7% | 20800 | 12 | 0.009
E360-CO-002 | E360 | Escalated to DRB – Partial Award | 2017-10-05 | 2029700 | 1062900 | 52.4% | 966800 | 3 | 1 | 33.3% | 1062900 | 13 | 0.472
E360-CO-003 | E360 | Executed – Negotiated Reduction | 2017-09-18 | 70700 | 63100 | 89.3% | 7600 | 12 | 10 | 83.3% | 63100 | 23 | 0.028
E360-CO-004 | E360 | Withdrawn by Contractor | 2017-12-14 | 185100 | 0 | 0% | 185100 | 2 | 0 | 0% | 0 | 23 | 0
E360-CO-005 | E360 | Executed – As Requested | 2017-10-09 | 33900 | 33900 | 100% | 0 | 0 | 0 | 0% | 33900 | 23 | 0.015
E360-CO-006 | E360 | Executed – Negotiated Reduction | 2017-09-29 | 129600 | 75900 | 58.6% | 53700 | 0 | 0 | 0% | 75900 | 23 | 0.034
E360-CO-007 | E360 | Executed – As Requested | 2017-12-06 | 182300 | 182300 | 100% | 0 | 10 | 9 | 90% | 182300 | 32 | 0.081
E360-CO-008 | E360 | Resolved via Global Settlement | 2018-02-19 | 115300 | 57100 | 49.5% | 58200 | 24 | 13 | 54.2% | 57100 | 45 | 0.025
E360-CO-009 | E360 | Executed – Negotiated Reduction | 2017-12-27 | 240900 | 156600 | 65% | 84300 | 3 | 2 | 66.7% | 156600 | 47 | 0.069
E360-CO-010 | E360 | Resolved via Global Settlement | 2018-02-14 | 72400 | 32500 | 44.9% | 39900 | 0 | 0 | 0% | 32500 | 47 | 0.014
E360-CO-011 | E360 | Executed – Negotiated Reduction | 2018-01-08 | 29400 | 22000 | 74.8% | 7400 | 45 | 24 | 53.3% | 22000 | 71 | 0.01
E360-CO-012 | E360 | Withdrawn by Contractor | 2018-08-02 | 946300 | 0 | 0% | 946300 | 0 | 0 | 0% | 0 | 71 | 0
E360-CO-013 | E360 | Executed – Negotiated Reduction | 2018-06-08 | 3336300 | 2288300 | 68.6% | 1048000 | 0 | 0 | 0% | 2288300 | 71 | 1.016
E360-CO-014 | E360 | Withdrawn by Contractor | 2018-08-06 | 5182700 | 0 | 0% | 5182700 | 23 | 0 | 0% | 0 | 71 | 0
E360-CO-015 | E360 | Executed – As Requested | 2019-03-15 | 237200 | 237200 | 100% | 0 | 0 | 0 | 0% | 237200 | 71 | 0.105
E360-CO-016 | E360 | Executed – Partial (Revised Scope) | 2018-12-03 | 2131300 | 488900 | 22.9% | 1642400 | 7 | 2 | 28.6% | 488900 | 73 | 0.217
E360-CO-017 | E360 | Executed – Negotiated Reduction | 2019-03-18 | 585100 | 283000 | 48.4% | 302100 | 4 | 2 | 50% | 283000 | 75 | 0.126
E360-CO-018 | E360 | Resolved via Global Settlement | 2019-07-29 | 748600 | 346100 | 46.2% | 402500 | 4 | 1 | 25% | 346100 | 76 | 0.154
E360-CO-019 | E360 | Executed – Negotiated Reduction | 2019-01-21 | 479900 | 332100 | 69.2% | 147800 | 0 | 0 | 0% | 332100 | 76 | 0.147
E360-CO-020 | E360 | Resolved via Global Settlement | 2019-07-04 | 3229000 | 1199600 | 37.2% | 2029400 | 4 | 1 | 25% | 1199600 | 77 | 0.532
E360-CO-021 | E360 | Executed – Negotiated Reduction | 2019-07-31 | 132500 | 77100 | 58.2% | 55400 | 11 | 6 | 54.5% | 77100 | 83 | 0.034
E360-CO-022 | E360 | Executed – Negotiated Reduction | 2019-11-04 | 287200 | 220200 | 76.7% | 67000 | 0 | 0 | 0% | 220200 | 83 | 0.098
E360-CO-023 | E360 | Rejected – Contractor Responsibility / No Merit | 2019-10-04 | 3274100 | 0 | 0% | 3274100 | 11 | 0 | 0% | 0 | 83 | 0
E360-CO-024 | E360 | Executed – As Requested | 2019-08-02 | 287800 | 287800 | 100% | 0 | 0 | 0 | 0% | 287800 | 83 | 0.128
E360-CO-025 | E360 | Resolved via Global Settlement | 2020-02-26 | 328700 | 206000 | 62.7% | 122700 | 13 | 5 | 38.5% | 206000 | 88 | 0.091
E360-CO-026 | E360 | Resolved via Global Settlement | 2021-05-06 | 193700 | 54900 | 28.3% | 138800 | 0 | 0 | 0% | 54900 | 88 | 0.024
E360-CO-027 | E360 | Rejected – Contractor Responsibility / No Merit | 2020-08-10 | 1827200 | 0 | 0% | 1827200 | 3 | 0 | 0% | 0 | 88 | 0
E360-CO-028 | E360 | Executed – Negotiated Reduction | 2020-07-07 | 653300 | 421900 | 64.6% | 231400 | 9 | 4 | 44.4% | 421900 | 92 | 0.187
E360-CO-029 | E360 | Executed – Negotiated Reduction | 2020-06-02 | 341100 | 193200 | 56.6% | 147900 | 31 | 20 | 64.5% | 193200 | 112 | 0.086
E360-CO-030 | E360 | Resolved via Global Settlement | 2020-07-16 | 503200 | 391900 | 77.9% | 111300 | 0 | 0 | 0% | 391900 | 112 | 0.174
E360-CO-031 | E360 | Executed – Negotiated Reduction | 2020-08-27 | 4826600 | 2032900 | 42.1% | 2793700 | 7 | 2 | 28.6% | 2032900 | 114 | 0.902
E360-CO-032 | E360 | Withdrawn by Contractor | 2020-08-18 | 2569600 | 0 | 0% | 2569600 | 4 | 0 | 0% | 0 | 114 | 0
E360-CO-033 | E360 | Rejected – Contractor Responsibility / No Merit | 2020-11-05 | 1823900 | 0 | 0% | 1823900 | 19 | 0 | 0% | 0 | 114 | 0
E360-CO-034 | E360 | Resolved via Global Settlement | 2020-09-21 | 182400 | 111000 | 60.9% | 71400 | 2 | 1 | 50% | 111000 | 115 | 0.049
E360-CO-035 | E360 | Executed – As Requested | 2020-12-07 | 59100 | 59100 | 100% | 0 | 1 | 1 | 100% | 59100 | 116 | 0.026
E360-CO-036 | E360 | Executed – Negotiated Reduction | 2020-12-29 | 1487900 | 940000 | 63.2% | 547900 | 7 | 5 | 71.4% | 940000 | 121 | 0.417
E360-CO-037 | E360 | Executed – Partial (Revised Scope) | 2021-08-04 | 1014400 | 744900 | 73.4% | 269500 | 0 | 0 | 0% | 744900 | 121 | 0.331
E360-CO-038 | E360 | Executed – Negotiated Reduction | 2021-04-30 | 374400 | 169200 | 45.2% | 205200 | 25 | 12 | 48% | 169200 | 133 | 0.075
E360-CO-039 | E360 | Executed – Negotiated Reduction | 2021-09-15 | 2301800 | 1360400 | 59.1% | 941400 | 0 | 0 | 0% | 1360400 | 133 | 0.604
E360-CO-040 | E360 | Executed – Negotiated Reduction | 2021-07-06 | 950600 | 494100 | 52% | 456500 | 0 | 0 | 0% | 494100 | 133 | 0.219
E750-CO-001 | E750 | Executed – Partial (Revised Scope) | 2018-07-09 | 14900 | 6200 | 41.6% | 8700 | 0 | 0 | 0% | 6200 | 0 | 0.002
E750-CO-002 | E750 | Withdrawn by Contractor | 2018-12-25 | 1842700 | 0 | 0% | 1842700 | 0 | 0 | 0% | 0 | 0 | 0
E750-CO-003 | E750 | Executed – Negotiated Reduction | 2018-11-12 | 137900 | 104800 | 76% | 33100 | 11 | 6 | 54.5% | 104800 | 6 | 0.029
E750-CO-004 | E750 | Executed – Negotiated Reduction | 2019-06-17 | 51000 | 40800 | 80% | 10200 | 4 | 2 | 50% | 40800 | 8 | 0.011
E750-CO-005 | E750 | Executed – Negotiated Reduction | 2019-07-24 | 1016600 | 796500 | 78.3% | 220100 | 133 | 104 | 78.2% | 796500 | 112 | 0.221
E750-CO-006 | E750 | Executed – Negotiated Reduction | 2019-09-27 | 82700 | 72800 | 88% | 9900 | 0 | 0 | 0% | 72800 | 112 | 0.02
E750-CO-007 | E750 | Resolved via Global Settlement | 2019-12-04 | 239500 | 188300 | 78.6% | 51200 | 2 | 2 | 100% | 188300 | 114 | 0.052
E750-CO-008 | E750 | Executed – Partial (Revised Scope) | 2019-11-26 | 1678000 | 661300 | 39.4% | 1016700 | 0 | 0 | 0% | 661300 | 114 | 0.184
E750-CO-009 | E750 | Executed – As Requested | 2020-01-20 | 558100 | 558100 | 100% | 0 | 102 | 66 | 64.7% | 558100 | 180 | 0.155
E750-CO-010 | E750 | Resolved via Global Settlement | 2020-08-03 | 120900 | 62400 | 51.6% | 58500 | 7 | 3 | 42.9% | 62400 | 183 | 0.017
E750-CO-011 | E750 | Resolved via Global Settlement | 2020-07-20 | 1091600 | 577200 | 52.9% | 514400 | 13 | 5 | 38.5% | 577200 | 188 | 0.16
E750-CO-012 | E750 | Executed – Negotiated Reduction | 2020-07-02 | 2081600 | 1822500 | 87.6% | 259100 | 3 | 3 | 100% | 1822500 | 191 | 0.506
E750-CO-013 | E750 | Executed – As Requested | 2020-11-11 | 248100 | 248100 | 100% | 0 | 0 | 0 | 0% | 248100 | 191 | 0.069
E750-CO-014 | E750 | Resolved via Global Settlement | 2021-03-02 | 68400 | 24000 | 35.1% | 44400 | 0 | 0 | 0% | 24000 | 191 | 0.007
E750-CO-015 | E750 | Executed – Negotiated Reduction | 2021-03-03 | 125700 | 83800 | 66.7% | 41900 | 3 | 2 | 66.7% | 83800 | 193 | 0.023
E750-CO-016 | E750 | Rejected – Contractor Responsibility / No Merit | 2021-03-23 | 2110600 | 0 | 0% | 2110600 | 0 | 0 | 0% | 0 | 193 | 0
E750-CO-017 | E750 | Executed – Negotiated Reduction | 2021-03-16 | 164300 | 108200 | 65.9% | 56100 | 32 | 24 | 75% | 108200 | 217 | 0.03
E750-CO-018 | E750 | Executed – Negotiated Reduction | 2021-08-24 | 795300 | 410900 | 51.7% | 384400 | 0 | 0 | 0% | 410900 | 217 | 0.114
E750-CO-019 | E750 | Executed – Negotiated Reduction | 2021-06-09 | 519300 | 367300 | 70.7% | 152000 | 17 | 8 | 47.1% | 367300 | 225 | 0.102
E750-CO-020 | E750 | Executed – Negotiated Reduction | 2021-07-05 | 200400 | 112600 | 56.2% | 87800 | 0 | 0 | 0% | 112600 | 225 | 0.031
E750-CO-021 | E750 | Executed – Negotiated Reduction | 2021-06-07 | 507900 | 401100 | 79% | 106800 | 3 | 2 | 66.7% | 401100 | 227 | 0.111
E750-CO-022 | E750 | Executed – Negotiated Reduction | 2021-11-11 | 957100 | 900700 | 94.1% | 56400 | 0 | 0 | 0% | 900700 | 227 | 0.25
E750-CO-023 | E750 | Executed – Partial (Revised Scope) | 2021-08-02 | 1351100 | 1032400 | 76.4% | 318700 | 13 | 10 | 76.9% | 1032400 | 237 | 0.287
E750-CO-024 | E750 | Executed – Partial (Revised Scope) | 2021-12-10 | 809600 | 622600 | 76.9% | 187000 | 21 | 11 | 52.4% | 622600 | 248 | 0.173
E750-CO-025 | E750 | Executed – As Requested | 2022-01-11 | 1236400 | 1236400 | 100% | 0 | 24 | 24 | 100% | 1236400 | 272 | 0.343
E750-CO-026 | E750 | Rejected – Contractor Responsibility / No Merit | 2022-01-05 | 952900 | 0 | 0% | 952900 | 0 | 0 | 0% | 0 | 272 | 0
E750-CO-027 | E750 | Resolved via Global Settlement | 2022-05-25 | 2644300 | 1054900 | 39.9% | 1589400 | 10 | 4 | 40% | 1054900 | 276 | 0.293
E750-CO-028 | E750 | Executed – As Requested | 2021-12-20 | 205300 | 205300 | 100% | 0 | 0 | 0 | 0% | 205300 | 276 | 0.057
E750-CO-029 | E750 | Executed – Negotiated Reduction | 2022-08-08 | 4650000 | 3562400 | 76.6% | 1087600 | 17 | 15 | 88.2% | 3562400 | 291 | 0.99
E750-CO-030 | E750 | Resolved via Global Settlement | 2022-10-24 | 695100 | 317800 | 45.7% | 377300 | 0 | 0 | 0% | 317800 | 291 | 0.088
E750-CO-031 | E750 | Resolved via Global Settlement | 2022-07-01 | 2475400 | 1457300 | 58.9% | 1018100 | 0 | 0 | 0% | 1457300 | 291 | 0.405
E750-CO-032 | E750 | Executed – Negotiated Reduction | 2022-06-24 | 700900 | 593700 | 84.7% | 107200 | 28 | 24 | 85.7% | 593700 | 315 | 0.165
E750-CO-033 | E750 | Executed – Negotiated Reduction | 2022-09-01 | 2090600 | 1025800 | 49.1% | 1064800 | 0 | 0 | 0% | 1025800 | 315 | 0.285
E750-CO-034 | E750 | Resolved via Global Settlement | 2022-11-24 | 144100 | 60100 | 41.7% | 84000 | 0 | 0 | 0% | 60100 | 315 | 0.017
E750-CO-035 | E750 | Executed – Negotiated Reduction | 2022-10-31 | 238400 | 143800 | 60.3% | 94600 | 12 | 8 | 66.7% | 143800 | 323 | 0.04
E750-CO-036 | E750 | Executed – Partial (Revised Scope) | 2022-11-07 | 1578200 | 1066100 | 67.6% | 512100 | 12 | 8 | 66.7% | 1066100 | 331 | 0.296
E750-CO-037 | E750 | Resolved via Global Settlement | 2023-10-03 | 2431400 | 2010500 | 82.7% | 420900 | 0 | 0 | 0% | 2010500 | 331 | 0.558
E750-CO-038 | E750 | Resolved via Global Settlement | 2023-08-09 | 2809000 | 1273600 | 45.3% | 1535400 | 0 | 0 | 0% | 1273600 | 331 | 0.354
E750-CO-039 | E750 | Resolved via Global Settlement | 2023-07-10 | 3873100 | 1680900 | 43.4% | 2192200 | 0 | 0 | 0% | 1680900 | 331 | 0.467
E750-CO-040 | E750 | Executed – Negotiated Reduction | 2023-11-28 | 3230100 | 1839900 | 57% | 1390200 | 0 | 0 | 0% | 1839900 | 331 | 0.511
E750-CO-041 | E750 | Executed – As Requested | 2024-02-19 | 782100 | 782100 | 100% | 0 | 0 | 0 | 0% | 782100 | 331 | 0.217
E750-CO-042 | E750 | Resolved via Global Settlement | 2024-04-08 | 1475300 | 1286800 | 87.2% | 188500 | 0 | 0 | 0% | 1286800 | 331 | 0.357

## RFI_CO_Link
rfi_id | co_id | allocation_share | allocated_requested_cost_usd | allocated_approved_cost_usd | allocated_time_days
DRLE-RFI-0003 | DRLE-CO-001 | 100% | 762000 | 0 | 0
DRLE-RFI-0004 | DRLE-CO-002 | 100% | 52600 | 26000 | 0
DRLE-RFI-0010 | DRLE-CO-003 | 100% | 150100 | 96200 | 3
DRLE-RFI-0011 | DRLE-CO-004 | 100% | 550100 | 393300 | 5
DRLE-RFI-0009 | DRLE-CO-005 | 2.56% | 58530 | 58530 | 0.3
DRLE-RFI-0012 | DRLE-CO-005 | 97.44% | 2231970 | 2231970 | 12.7
DRLE-RFI-0014 | DRLE-CO-006 | 100% | 10300 | 5400 | 0
DRLE-RFI-0025 | DRLE-CO-007 | 100% | 186400 | 148800 | 2
DRLE-RFI-0024 | DRLE-CO-008 | 100% | 284700 | 0 | 0
DRLE-RFI-0033 | DRLE-CO-009 | 100% | 396500 | 211800 | 0
DRLE-RFI-0034 | DRLE-CO-010 | 100% | 62400 | 40500 | 0
DRLE-RFI-0036 | DRLE-CO-011 | 100% | 777600 | 600500 | 1
DRLE-RFI-0042 | DRLE-CO-012 | 100% | 121500 | 49500 | 2
DRLE-RFI-0074 | DRLE-CO-013 | 100% | 981500 | 685400 | 1
DRLE-RFI-0056 | DRLE-CO-014 | 82.24% | 751900 | 284790 | 0.8
DRLE-RFI-0070 | DRLE-CO-014 | 17.76% | 162400 | 61510 | 0.2
DRLE-RFI-0096 | DRLE-CO-015 | 100% | 930900 | 0 | 0
DRLE-RFI-0079 | DRLE-CO-016 | 31.72% | 146120 | 116840 | 2.2
DRLE-RFI-0099 | DRLE-CO-016 | 68.28% | 314580 | 251560 | 4.8
DRLE-RFI-0108 | DRLE-CO-017 | 100% | 273500 | 273500 | 2
DRLE-RFI-0106 | DRLE-CO-018 | 100% | 369800 | 263700 | 0
DRLE-RFI-0110 | DRLE-CO-019 | 100% | 163200 | 64800 | 0
DRLE-RFI-0115 | DRLE-CO-020 | 100% | 21800 | 8100 | 0
DRLE-RFI-0111 | DRLE-CO-021 | 100% | 1398300 | 957200 | 3
DRLE-RFI-0109 | DRLE-CO-022 | 100% | 73900 | 44800 | 2
DRLE-RFI-0121 | DRLE-CO-023 | 100% | 30800 | 22300 | 2
DRLE-RFI-0127 | DRLE-CO-024 | 100% | 79600 | 63400 | 4
DRLE-RFI-0133 | DRLE-CO-025 | 100% | 87100 | 0 | 0
DRLE-RFI-0134 | DRLE-CO-026 | 96.99% | 680280 | 632950 | 2.9
DRLE-RFI-0137 | DRLE-CO-026 | 3.01% | 21120 | 19650 | 0.1
DRLE-RFI-0147 | DRLE-CO-027 | 100% | 27100 | 0 | 0
DRLE-RFI-0152 | DRLE-CO-028 | 100% | 57100 | 45200 | 3
DRLE-RFI-0164 | DRLE-CO-029 | 100% | 78800 | 60200 | 0
DRLE-RFI-0165 | DRLE-CO-030 | 100% | 391900 | 275900 | 4
DRLE-RFI-0169 | DRLE-CO-031 | 100% | 85200 | 67500 | 0
DRLE-RFI-0173 | DRLE-CO-032 | 100% | 252400 | 0 | 0
DRLE-RFI-0187 | DRLE-CO-033 | 68.88% | 537920 | 0 | 0
DRLE-RFI-0189 | DRLE-CO-033 | 31.12% | 242980 | 0 | 0
DRLE-RFI-0191 | DRLE-CO-034 | 15.87% | 209270 | 188280 | 1
DRLE-RFI-0194 | DRLE-CO-034 | 74.56% | 982900 | 884340 | 4.5
DRLE-RFI-0195 | DRLE-CO-034 | 9.57% | 126130 | 113480 | 0.6
DRLE-RFI-0196 | DRLE-CO-035 | 100% | 166500 | 0 | 0
DRLE-RFI-0181 | DRLE-CO-036 | 79.14% | 2021270 | 1444730 | 3.2
DRLE-RFI-0202 | DRLE-CO-036 | 20.86% | 532730 | 380770 | 0.8
DRLE-RFI-0203 | DRLE-CO-037 | 100% | 1006300 | 866500 | 1
DRLE-RFI-0210 | DRLE-CO-038 | 100% | 5199900 | 0 | 0
DRLE-RFI-0212 | DRLE-CO-039 | 100% | 314900 | 225200 | 1
DRLE-RFI-0213 | DRLE-CO-040 | 100% | 236200 | 67500 | 1
DRLE-RFI-0221 | DRLE-CO-041 | 100% | 430800 | 308800 | 4
DRLE-RFI-0224 | DRLE-CO-042 | 100% | 22900 | 15800 | 0
DRLE-RFI-0234 | DRLE-CO-043 | 100% | 985300 | 536800 | 2
DRLE-RFI-0231 | DRLE-CO-044 | 100% | 301600 | 301600 | 2
DRLE-RFI-0245 | DRLE-CO-045 | 100% | 163700 | 104200 | 0
DRLE-RFI-0246 | DRLE-CO-046 | 100% | 261700 | 184600 | 0
DRLE-RFI-0230 | DRLE-CO-047 | 49.01% | 233580 | 208290 | 1
DRLE-RFI-0248 | DRLE-CO-047 | 50.99% | 243020 | 216710 | 1
DRLE-RFI-0250 | DRLE-CO-048 | 100% | 931000 | 683800 | 1
DRLE-RFI-0253 | DRLE-CO-049 | 100% | 82600 | 44700 | 0
DRLE-RFI-0271 | DRLE-CO-050 | 100% | 243200 | 179000 | 1
DRLE-RFI-0277 | DRLE-CO-051 | 100% | 59400 | 31900 | 1
DRLE-RFI-0283 | DRLE-CO-052 | 100% | 16900 | 10200 | 0
DRLE-RFI-0282 | DRLE-CO-053 | 100% | 47000 | 0 | 0
DRLE-RFI-0284 | DRLE-CO-054 | 46.61% | 165840 | 93170 | 2.3
DRLE-RFI-0285 | DRLE-CO-054 | 53.39% | 189960 | 106730 | 2.7
DRLE-RFI-0276 | DRLE-CO-055 | 10.93% | 52780 | 49080 | 1.9
DRLE-RFI-0292 | DRLE-CO-055 | 16.35% | 78950 | 73430 | 2.8
DRLE-RFI-0294 | DRLE-CO-055 | 72.72% | 351170 | 326590 | 12.4
DRLE-RFI-0287 | DRLE-CO-056 | 29.44% | 293160 | 232280 | 2.4
DRLE-RFI-0296 | DRLE-CO-056 | 70.56% | 702640 | 556720 | 5.6
DRLE-RFI-0298 | DRLE-CO-057 | 100% | 1625200 | 1105500 | 10
DRLE-RFI-0304 | DRLE-CO-058 | 100% | 151800 | 63400 | 1
DRLE-RFI-0308 | DRLE-CO-059 | 100% | 372500 | 0 | 0
DRLE-RFI-0309 | DRLE-CO-060 | 100% | 154300 | 84300 | 2
DRLE-RFI-0311 | DRLE-CO-061 | 100% | 400300 | 248000 | 0
DRLE-RFI-0313 | DRLE-CO-062 | 100% | 110600 | 58200 | 0
DRLE-RFI-0317 | DRLE-CO-063 | 100% | 4126900 | 2986000 | 0
DRLE-RFI-0320 | DRLE-CO-064 | 100% | 202700 | 163500 | 0
DRLE-RFI-0326 | DRLE-CO-065 | 100% | 283200 | 0 | 0
DRLE-RFI-0336 | DRLE-CO-066 | 100% | 353700 | 190000 | 3
DRLE-RFI-0339 | DRLE-CO-067 | 100% | 382500 | 204400 | 5
E320-RFI-0004 | E320-CO-001 | 100% | 103900 | 44100 | 0
E320-RFI-0009 | E320-CO-002 | 100% | 162700 | 0 | 0
E320-RFI-0014 | E320-CO-003 | 4.21% | 7860 | 4000 | 0
E320-RFI-0018 | E320-CO-003 | 95.79% | 179040 | 91100 | 0
E320-RFI-0020 | E320-CO-004 | 100% | 33200 | 15600 | 0
E320-RFI-0026 | E320-CO-005 | 100% | 17400 | 11100 | 1
E320-RFI-0027 | E320-CO-006 | 59.21% | 309830 | 309830 | 11.2
E320-RFI-0029 | E320-CO-006 | 40.79% | 213470 | 213470 | 7.8
E320-RFI-0030 | E320-CO-007 | 62.85% | 95150 | 95150 | 6.9
E320-RFI-0033 | E320-CO-007 | 37.15% | 56250 | 56250 | 4.1
E320-RFI-0034 | E320-CO-008 | 100% | 32200 | 19000 | 0
E320-RFI-0040 | E320-CO-009 | 100% | 34500 | 23800 | 0
E320-RFI-0039 | E320-CO-010 | 100% | 114600 | 114600 | 5
E320-RFI-0042 | E320-CO-011 | 71.19% | 275210 | 175760 | 11.4
E320-RFI-0043 | E320-CO-011 | 28.81% | 111390 | 71140 | 4.6
E320-RFI-0038 | E320-CO-012 | 84.01% | 2358420 | 2063530 | 22.7
E320-RFI-0047 | E320-CO-012 | 15.99% | 448780 | 392670 | 4.3
E320-RFI-0049 | E320-CO-013 | 100% | 42100 | 13900 | 0
E320-RFI-0055 | E320-CO-014 | 100% | 463100 | 157000 | 0
E320-RFI-0058 | E320-CO-015 | 100% | 120600 | 84200 | 1
E320-RFI-0062 | E320-CO-016 | 100% | 34800 | 28500 | 0
E320-RFI-0064 | E320-CO-017 | 100% | 38200 | 35100 | 7
E320-RFI-0063 | E320-CO-018 | 100% | 265800 | 212200 | 2
E320-RFI-0067 | E320-CO-019 | 37.05% | 65130 | 0 | 0
E320-RFI-0068 | E320-CO-019 | 62.95% | 110670 | 0 | 0
E320-RFI-0078 | E320-CO-020 | 100% | 134600 | 97800 | 1
E320-RFI-0073 | E320-CO-021 | 49.44% | 395550 | 298590 | 7.4
E320-RFI-0077 | E320-CO-021 | 50.56% | 404450 | 305310 | 7.6
E320-RFI-0082 | E320-CO-022 | 100% | 124600 | 89900 | 3
E320-RFI-0081 | E320-CO-023 | 100% | 252200 | 155700 | 1
E320-RFI-0086 | E320-CO-024 | 51.05% | 61010 | 37930 | 1.5
E320-RFI-0088 | E320-CO-024 | 48.95% | 58490 | 36370 | 1.5
E320-RFI-0092 | E320-CO-025 | 100% | 2685700 | 1478500 | 15
E320-RFI-0101 | E320-CO-026 | 100% | 211700 | 0 | 0
E320-RFI-0096 | E320-CO-027 | 36.36% | 12690 | 2980 | 0.4
E320-RFI-0100 | E320-CO-027 | 63.64% | 22210 | 5220 | 0.6
E320-RFI-0103 | E320-CO-028 | 100% | 117200 | 53100 | 5
E320-RFI-0111 | E320-CO-029 | 100% | 721100 | 546600 | 5
E320-RFI-0120 | E320-CO-030 | 100% | 43400 | 30100 | 0
E320-RFI-0121 | E320-CO-031 | 100% | 537000 | 405000 | 4
E320-RFI-0123 | E320-CO-032 | 100% | 68700 | 39600 | 4
E320-RFI-0124 | E320-CO-033 | 100% | 38700 | 27500 | 3
E320-RFI-0122 | E320-CO-034 | 100% | 384500 | 249900 | 1
E320-RFI-0126 | E320-CO-035 | 100% | 71500 | 50700 | 0
E320-RFI-0129 | E320-CO-036 | 100% | 340900 | 205600 | 12
E320-RFI-0131 | E320-CO-037 | 100% | 125800 | 0 | 0
E320-RFI-0134 | E320-CO-038 | 100% | 268400 | 0 | 0
E320-RFI-0132 | E320-CO-039 | 74.79% | 1042790 | 422860 | 2.2
E320-RFI-0137 | E320-CO-039 | 25.21% | 351510 | 142540 | 0.8
E320-RFI-0139 | E320-CO-040 | 100% | 86200 | 72900 | 7
E320-RFI-0143 | E320-CO-041 | 100% | 63900 | 34500 | 0
E320-RFI-0144 | E320-CO-042 | 100% | 2333100 | 1239400 | 0
E320-RFI-0145 | E320-CO-043 | 100% | 255900 | 164400 | 6
E320-RFI-0150 | E320-CO-044 | 100% | 66200 | 25200 | 0
E330-RFI-0001 | E330-CO-001 | 100% | 83500 | 61700 | 0
E330-RFI-0002 | E330-CO-002 | 100% | 75100 | 44200 | 5
E330-RFI-0006 | E330-CO-003 | 100% | 9200 | 5400 | 2
E330-RFI-0012 | E330-CO-004 | 100% | 1239900 | 957100 | 6
E330-RFI-0010 | E330-CO-005 | 3.61% | 76420 | 38210 | 0.1
E330-RFI-0014 | E330-CO-005 | 96.39% | 2039580 | 1019790 | 1.9
E330-RFI-0015 | E330-CO-006 | 92.25% | 498420 | 375080 | 0
E330-RFI-0016 | E330-CO-006 | 3.07% | 16590 | 12480 | 0
E330-RFI-0017 | E330-CO-006 | 4.68% | 25290 | 19030 | 0
E330-RFI-0022 | E330-CO-007 | 100% | 69800 | 0 | 0
E330-RFI-0019 | E330-CO-008 | 52.8% | 130470 | 89600 | 2.6
E330-RFI-0023 | E330-CO-008 | 47.2% | 116630 | 80100 | 2.4
E330-RFI-0025 | E330-CO-009 | 100% | 107500 | 88300 | 0
E330-RFI-0027 | E330-CO-010 | 100% | 98200 | 32300 | 0
E330-RFI-0024 | E330-CO-011 | 21.03% | 402100 | 0 | 0
E330-RFI-0029 | E330-CO-011 | 78.97% | 1509500 | 0 | 0
E330-RFI-0035 | E330-CO-012 | 100% | 85000 | 39100 | 0
E330-RFI-0038 | E330-CO-013 | 100% | 106300 | 78400 | 0
E330-RFI-0042 | E330-CO-014 | 49.8% | 192580 | 112600 | 2.5
E330-RFI-0047 | E330-CO-014 | 50.2% | 194120 | 113500 | 2.5
E330-RFI-0048 | E330-CO-015 | 100% | 40700 | 40700 | 1
E330-RFI-0050 | E330-CO-016 | 100% | 56500 | 0 | 0
E330-RFI-0054 | E330-CO-017 | 100% | 263300 | 215500 | 5
E330-RFI-0046 | E330-CO-018 | 33.68% | 120130 | 71090 | 2
E330-RFI-0053 | E330-CO-018 | 15.86% | 56590 | 33490 | 1
E330-RFI-0055 | E330-CO-018 | 50.46% | 179990 | 106520 | 3
E330-RFI-0056 | E330-CO-019 | 100% | 112100 | 70100 | 0
E330-RFI-0059 | E330-CO-020 | 100% | 363100 | 265000 | 6
E330-RFI-0061 | E330-CO-021 | 100% | 283300 | 118100 | 0
E330-RFI-0069 | E330-CO-022 | 100% | 9800 | 6900 | 7
E330-RFI-0067 | E330-CO-023 | 100% | 564900 | 0 | 0
E330-RFI-0077 | E330-CO-024 | 8.96% | 60630 | 0 | 0
E330-RFI-0080 | E330-CO-024 | 91.04% | 615870 | 0 | 0
E330-RFI-0081 | E330-CO-025 | 61.66% | 781240 | 0 | 0
E330-RFI-0083 | E330-CO-025 | 38.34% | 485760 | 0 | 0
E330-RFI-0084 | E330-CO-026 | 59.18% | 64860 | 56700 | 0
E330-RFI-0085 | E330-CO-026 | 40.82% | 44740 | 39100 | 0
E330-RFI-0082 | E330-CO-027 | 16.85% | 217750 | 0 | 0
E330-RFI-0087 | E330-CO-027 | 83.15% | 1074450 | 0 | 0
E330-RFI-0089 | E330-CO-028 | 100% | 103600 | 65500 | 0
E330-RFI-0095 | E330-CO-029 | 100% | 158000 | 115600 | 0
E330-RFI-0097 | E330-CO-030 | 100% | 37600 | 26500 | 3
E330-RFI-0103 | E330-CO-031 | 100% | 154700 | 154700 | 0
E330-RFI-0093 | E330-CO-032 | 1.58% | 134700 | 0 | 0
E330-RFI-0100 | E330-CO-032 | 98.42% | 8407500 | 0 | 0
E330-RFI-0114 | E330-CO-033 | 100% | 8200 | 3200 | 0
E330-RFI-0108 | E330-CO-034 | 58.39% | 46770 | 22420 | 15.8
E330-RFI-0121 | E330-CO-034 | 41.61% | 33330 | 15980 | 11.2
E330-RFI-0120 | E330-CO-035 | 92.75% | 150900 | 150900 | 0
E330-RFI-0123 | E330-CO-035 | 7.25% | 11800 | 11800 | 0
E330-RFI-0127 | E330-CO-036 | 100% | 215300 | 103600 | 0
E330-RFI-0125 | E330-CO-037 | 100% | 180700 | 132900 | 0
E330-RFI-0129 | E330-CO-038 | 89.13% | 308910 | 308910 | 2.7
E330-RFI-0139 | E330-CO-038 | 10.87% | 37690 | 37690 | 0.3
E330-RFI-0128 | E330-CO-039 | 10.95% | 110630 | 66320 | 0.4
E330-RFI-0137 | E330-CO-039 | 50.62% | 511370 | 306530 | 2
E330-RFI-0138 | E330-CO-039 | 5.2% | 52570 | 31510 | 0.2
E330-RFI-0142 | E330-CO-039 | 33.23% | 335730 | 201250 | 1.3
E330-RFI-0150 | E330-CO-040 | 100% | 209300 | 71100 | 4
E330-RFI-0151 | E330-CO-041 | 100% | 259200 | 142700 | 3
E330-RFI-0154 | E330-CO-042 | 100% | 1224200 | 1224200 | 1
E330-RFI-0156 | E330-CO-043 | 100% | 497600 | 0 | 0
E330-RFI-0163 | E330-CO-044 | 100% | 206700 | 206700 | 21
E330-RFI-0166 | E330-CO-045 | 100% | 285600 | 184100 | 10
E330-RFI-0168 | E330-CO-046 | 100% | 285900 | 158400 | 3
E330-RFI-0169 | E330-CO-047 | 100% | 543900 | 382000 | 2
E330-RFI-0170 | E330-CO-048 | 100% | 422100 | 186600 | 0
E335-RFI-0004 | E335-CO-001 | 100% | 53200 | 46800 | 0
E335-RFI-0005 | E335-CO-002 | 100% | 626800 | 626800 | 3
E335-RFI-0010 | E335-CO-003 | 100% | 312300 | 178800 | 3
E335-RFI-0011 | E335-CO-004 | 100% | 14700 | 14700 | 0
E335-RFI-0013 | E335-CO-005 | 100% | 106700 | 106700 | 10
E335-RFI-0014 | E335-CO-006 | 100% | 536700 | 455900 | 23
E335-RFI-0018 | E335-CO-007 | 100% | 399300 | 399300 | 7
E335-RFI-0020 | E335-CO-008 | 100% | 45600 | 0 | 0
E335-RFI-0022 | E335-CO-009 | 100% | 1325100 | 1033400 | 2
E335-RFI-0025 | E335-CO-010 | 100% | 1941600 | 619600 | 0
E335-RFI-0031 | E335-CO-011 | 15.36% | 699680 | 630370 | 0.6
E335-RFI-0038 | E335-CO-011 | 84.64% | 3855120 | 3473230 | 3.4
E335-RFI-0043 | E335-CO-012 | 100% | 166800 | 74100 | 1
E335-RFI-0046 | E335-CO-013 | 100% | 426800 | 299300 | 12
E335-RFI-0051 | E335-CO-014 | 100% | 259600 | 127300 | 15
E335-RFI-0052 | E335-CO-015 | 100% | 137600 | 0 | 0
E335-RFI-0055 | E335-CO-016 | 100% | 1804700 | 1182700 | 2
E335-RFI-0061 | E335-CO-017 | 100% | 1214700 | 537200 | 1
E335-RFI-0064 | E335-CO-018 | 100% | 134600 | 89000 | 0
E335-RFI-0071 | E335-CO-019 | 42.3% | 62520 | 18870 | 1.3
E335-RFI-0072 | E335-CO-019 | 57.7% | 85280 | 25730 | 1.7
E335-RFI-0073 | E335-CO-020 | 100% | 20200 | 11200 | 0
E335-RFI-0077 | E335-CO-021 | 100% | 259900 | 221900 | 0
E335-RFI-0069 | E335-CO-022 | 20.19% | 114020 | 100260 | 0
E335-RFI-0083 | E335-CO-022 | 79.81% | 450580 | 396240 | 0
E335-RFI-0062 | E335-CO-023 | 5.5% | 190380 | 133890 | 0.2
E335-RFI-0075 | E335-CO-023 | 10.15% | 351420 | 247150 | 0.3
E335-RFI-0086 | E335-CO-023 | 84.35% | 2921290 | 2054460 | 2.5
E335-RFI-0091 | E335-CO-024 | 100% | 184700 | 131700 | 26
E335-RFI-0097 | E335-CO-025 | 59.84% | 579850 | 0 | 0
E335-RFI-0099 | E335-CO-025 | 40.16% | 389150 | 0 | 0
E335-RFI-0093 | E335-CO-026 | 19.83% | 36780 | 36780 | 2.4
E335-RFI-0109 | E335-CO-026 | 80.17% | 148720 | 148720 | 9.6
E335-RFI-0113 | E335-CO-027 | 100% | 207600 | 149900 | 0
E335-RFI-0114 | E335-CO-028 | 100% | 268400 | 114500 | 0
E335-RFI-0108 | E335-CO-029 | 80.3% | 508550 | 444790 | 0
E335-RFI-0115 | E335-CO-029 | 19.7% | 124750 | 109110 | 0
E335-RFI-0119 | E335-CO-030 | 100% | 45200 | 21200 | 2
E335-RFI-0124 | E335-CO-031 | 100% | 16100 | 15300 | 0
E335-RFI-0125 | E335-CO-032 | 100% | 673100 | 256700 | 3
E335-RFI-0139 | E335-CO-033 | 100% | 40000 | 29800 | 4
E335-RFI-0142 | E335-CO-034 | 100% | 1113500 | 0 | 0
E335-RFI-0144 | E335-CO-035 | 100% | 46800 | 16100 | 0
E335-RFI-0153 | E335-CO-036 | 100% | 60200 | 60200 | 4
E335-RFI-0167 | E335-CO-037 | 79.31% | 1052910 | 705610 | 40.4
E335-RFI-0168 | E335-CO-037 | 20.69% | 274690 | 184090 | 10.6
E335-RFI-0176 | E335-CO-038 | 100% | 48900 | 24200 | 9
E335-RFI-0171 | E335-CO-039 | 57.43% | 2554000 | 2015570 | 11.5
E335-RFI-0172 | E335-CO-039 | 3.54% | 157300 | 124140 | 0.7
E335-RFI-0177 | E335-CO-039 | 24.85% | 1104970 | 872030 | 5
E335-RFI-0178 | E335-CO-039 | 14.18% | 630730 | 497760 | 2.8
E335-RFI-0174 | E335-CO-040 | 9.26% | 53210 | 53210 | 2.1
E335-RFI-0179 | E335-CO-040 | 90.74% | 521490 | 521490 | 20.9
E335-RFI-0185 | E335-CO-041 | 100% | 19700 | 9400 | 0
E335-RFI-0188 | E335-CO-042 | 100% | 402000 | 302100 | 0
E335-RFI-0189 | E335-CO-043 | 100% | 297600 | 168100 | 0
E335-RFI-0193 | E335-CO-044 | 100% | 30800 | 24800 | 0
E335-RFI-0196 | E335-CO-045 | 99.02% | 1436120 | 1078880 | 5.9
E335-RFI-0200 | E335-CO-045 | 0.98% | 14280 | 10720 | 0.1
E335-RFI-0204 | E335-CO-046 | 92.54% | 2017280 | 1397880 | 1.9
E335-RFI-0209 | E335-CO-046 | 7.46% | 162520 | 112620 | 0.1
E335-RFI-0214 | E335-CO-047 | 100% | 49600 | 0 | 0
E335-RFI-0216 | E335-CO-048 | 100% | 251100 | 105100 | 14
E335-RFI-0217 | E335-CO-049 | 100% | 498700 | 343100 | 4
E335-RFI-0218 | E335-CO-050 | 100% | 604600 | 462600 | 0
E335-RFI-0223 | E335-CO-051 | 100% | 163700 | 70000 | 12
E335-RFI-0211 | E335-CO-052 | 64.39% | 212300 | 178620 | 8.4
E335-RFI-0226 | E335-CO-052 | 35.61% | 117400 | 98780 | 4.6
E335-RFI-0227 | E335-CO-053 | 100% | 1302200 | 773700 | 0
E335-RFI-0234 | E335-CO-054 | 100% | 77500 | 48000 | 0
E335-RFI-0239 | E335-CO-055 | 100% | 73700 | 0 | 0
E335-RFI-0248 | E335-CO-056 | 100% | 135400 | 0 | 0
E335-RFI-0249 | E335-CO-057 | 100% | 193000 | 0 | 0
E335-RFI-0254 | E335-CO-058 | 100% | 607600 | 495900 | 0
E335-RFI-0259 | E335-CO-059 | 100% | 450400 | 331900 | 0
E340-RFI-0004 | E340-CO-001 | 100% | 30500 | 30500 | 0
E340-RFI-0005 | E340-CO-002 | 100% | 110100 | 72000 | 0
E340-RFI-0008 | E340-CO-003 | 100% | 104000 | 104000 | 11
E340-RFI-0010 | E340-CO-004 | 100% | 434900 | 103500 | 1
E340-RFI-0011 | E340-CO-005 | 100% | 38000 | 25100 | 0
E340-RFI-0016 | E340-CO-006 | 100% | 180400 | 90100 | 0
E340-RFI-0017 | E340-CO-007 | 100% | 221400 | 108700 | 0
E340-RFI-0022 | E340-CO-008 | 100% | 637900 | 381900 | 0
E340-RFI-0021 | E340-CO-009 | 100% | 12100 | 4800 | 2
E340-RFI-0023 | E340-CO-010 | 100% | 23600 | 15800 | 2
E340-RFI-0027 | E340-CO-011 | 100% | 54700 | 49400 | 0
E340-RFI-0028 | E340-CO-012 | 100% | 643700 | 499700 | 7
E340-RFI-0037 | E340-CO-013 | 100% | 74500 | 74500 | 0
E340-RFI-0036 | E340-CO-014 | 6.7% | 25540 | 14280 | 0.3
E340-RFI-0039 | E340-CO-014 | 93.3% | 355760 | 198820 | 4.7
E340-RFI-0042 | E340-CO-015 | 100% | 48800 | 31500 | 5
E340-RFI-0030 | E340-CO-016 | 7.26% | 163200 | 98110 | 1
E340-RFI-0038 | E340-CO-016 | 33.97% | 763780 | 459140 | 4.8
E340-RFI-0047 | E340-CO-016 | 58.78% | 1321720 | 794550 | 8.2
E340-RFI-0054 | E340-CO-017 | 100% | 67300 | 54600 | 2
E340-RFI-0051 | E340-CO-018 | 1.88% | 36660 | 25030 | 0
E340-RFI-0055 | E340-CO-018 | 98.12% | 1913740 | 1306770 | 2
E340-RFI-0060 | E340-CO-019 | 100% | 172700 | 42400 | 1
E340-RFI-0064 | E340-CO-020 | 100% | 351600 | 290900 | 12
E340-RFI-0071 | E340-CO-021 | 100% | 212100 | 0 | 0
E340-RFI-0077 | E340-CO-022 | 100% | 45600 | 14300 | 0
E340-RFI-0080 | E340-CO-023 | 100% | 191300 | 0 | 0
E340-RFI-0081 | E340-CO-024 | 100% | 255100 | 142900 | 1
E340-RFI-0082 | E340-CO-025 | 100% | 651600 | 524200 | 0
E340-RFI-0083 | E340-CO-026 | 100% | 68400 | 57000 | 1
E340-RFI-0086 | E340-CO-027 | 100% | 73400 | 73400 | 7
E340-RFI-0087 | E340-CO-028 | 100% | 33800 | 12200 | 0
E360-RFI-0005 | E360-CO-001 | 100% | 25700 | 20800 | 12
E360-RFI-0008 | E360-CO-002 | 100% | 2029700 | 1062900 | 1
E360-RFI-0011 | E360-CO-003 | 100% | 70700 | 63100 | 10
E360-RFI-0012 | E360-CO-004 | 100% | 185100 | 0 | 0
E360-RFI-0013 | E360-CO-005 | 100% | 33900 | 33900 | 0
E360-RFI-0014 | E360-CO-006 | 100% | 129600 | 75900 | 0
E360-RFI-0015 | E360-CO-007 | 100% | 182300 | 182300 | 9
E360-RFI-0017 | E360-CO-008 | 100% | 115300 | 57100 | 13
E360-RFI-0020 | E360-CO-009 | 100% | 240900 | 156600 | 2
E360-RFI-0022 | E360-CO-010 | 100% | 72400 | 32500 | 0
E360-RFI-0023 | E360-CO-011 | 100% | 29400 | 22000 | 24
E360-RFI-0025 | E360-CO-012 | 100% | 946300 | 0 | 0
E360-RFI-0033 | E360-CO-013 | 100% | 3336300 | 2288300 | 0
E360-RFI-0038 | E360-CO-014 | 100% | 5182700 | 0 | 0
E360-RFI-0043 | E360-CO-015 | 100% | 237200 | 237200 | 0
E360-RFI-0051 | E360-CO-016 | 100% | 2131300 | 488900 | 2
E360-RFI-0052 | E360-CO-017 | 56.04% | 327910 | 158600 | 1.1
E360-RFI-0055 | E360-CO-017 | 43.96% | 257190 | 124400 | 0.9
E360-RFI-0057 | E360-CO-018 | 100% | 748600 | 346100 | 1
E360-RFI-0058 | E360-CO-019 | 100% | 479900 | 332100 | 0
E360-RFI-0075 | E360-CO-020 | 100% | 3229000 | 1199600 | 1
E360-RFI-0077 | E360-CO-021 | 100% | 132500 | 77100 | 6
E360-RFI-0082 | E360-CO-022 | 100% | 287200 | 220200 | 0
E360-RFI-0076 | E360-CO-023 | 30.5% | 998660 | 0 | 0
E360-RFI-0087 | E360-CO-023 | 69.5% | 2275440 | 0 | 0
E360-RFI-0084 | E360-CO-024 | 100% | 287800 | 287800 | 0
E360-RFI-0105 | E360-CO-025 | 100% | 328700 | 206000 | 5
E360-RFI-0108 | E360-CO-026 | 100% | 193700 | 54900 | 0
E360-RFI-0110 | E360-CO-027 | 100% | 1827200 | 0 | 0
E360-RFI-0107 | E360-CO-028 | 47.51% | 310380 | 200450 | 1.9
E360-RFI-0114 | E360-CO-028 | 52.49% | 342920 | 221450 | 2.1
E360-RFI-0116 | E360-CO-029 | 100% | 341100 | 193200 | 20
E360-RFI-0117 | E360-CO-030 | 100% | 503200 | 391900 | 0
E360-RFI-0118 | E360-CO-031 | 100% | 4826600 | 2032900 | 2
E360-RFI-0120 | E360-CO-032 | 100% | 2569600 | 0 | 0
E360-RFI-0124 | E360-CO-033 | 100% | 1823900 | 0 | 0
E360-RFI-0125 | E360-CO-034 | 100% | 182400 | 111000 | 1
E360-RFI-0129 | E360-CO-035 | 100% | 59100 | 59100 | 1
E360-RFI-0134 | E360-CO-036 | 100% | 1487900 | 940000 | 5
E360-RFI-0135 | E360-CO-037 | 100% | 1014400 | 744900 | 0
E360-RFI-0136 | E360-CO-038 | 100% | 374400 | 169200 | 12
E360-RFI-0139 | E360-CO-039 | 100% | 2301800 | 1360400 | 0
E360-RFI-0138 | E360-CO-040 | 100% | 950600 | 494100 | 0
E750-RFI-0001 | E750-CO-001 | 100% | 14900 | 6200 | 0
E750-RFI-0006 | E750-CO-002 | 100% | 1842700 | 0 | 0
E750-RFI-0005 | E750-CO-003 | 100% | 137900 | 104800 | 6
E750-RFI-0008 | E750-CO-004 | 100% | 51000 | 40800 | 2
E750-RFI-0020 | E750-CO-005 | 42.72% | 434320 | 340290 | 44.4
E750-RFI-0023 | E750-CO-005 | 57.28% | 582280 | 456210 | 59.6
E750-RFI-0024 | E750-CO-006 | 100% | 82700 | 72800 | 0
E750-RFI-0036 | E750-CO-007 | 100% | 239500 | 188300 | 2
E750-RFI-0037 | E750-CO-008 | 100% | 1678000 | 661300 | 0
E750-RFI-0028 | E750-CO-009 | 18.58% | 103680 | 103680 | 12.3
E750-RFI-0030 | E750-CO-009 | 31.76% | 177240 | 177240 | 21
E750-RFI-0033 | E750-CO-009 | 43.97% | 245380 | 245380 | 29
E750-RFI-0042 | E750-CO-009 | 5.7% | 31800 | 31800 | 3.8
E750-RFI-0052 | E750-CO-010 | 100% | 120900 | 62400 | 3
E750-RFI-0063 | E750-CO-011 | 100% | 1091600 | 577200 | 5
E750-RFI-0071 | E750-CO-012 | 100% | 2081600 | 1822500 | 3
E750-RFI-0075 | E750-CO-013 | 100% | 248100 | 248100 | 0
E750-RFI-0083 | E750-CO-014 | 100% | 68400 | 24000 | 0
E750-RFI-0096 | E750-CO-015 | 100% | 125700 | 83800 | 2
E750-RFI-0106 | E750-CO-016 | 100% | 2110600 | 0 | 0
E750-RFI-0111 | E750-CO-017 | 100% | 164300 | 108200 | 24
E750-RFI-0108 | E750-CO-018 | 100% | 795300 | 410900 | 0
E750-RFI-0114 | E750-CO-019 | 100% | 519300 | 367300 | 8
E750-RFI-0117 | E750-CO-020 | 100% | 200400 | 112600 | 0
E750-RFI-0118 | E750-CO-021 | 100% | 507900 | 401100 | 2
E750-RFI-0128 | E750-CO-022 | 100% | 957100 | 900700 | 0
E750-RFI-0129 | E750-CO-023 | 100% | 1351100 | 1032400 | 10
E750-RFI-0142 | E750-CO-024 | 100% | 809600 | 622600 | 11
E750-RFI-0140 | E750-CO-025 | 100% | 1236400 | 1236400 | 24
E750-RFI-0152 | E750-CO-026 | 100% | 952900 | 0 | 0
E750-RFI-0138 | E750-CO-027 | 39.07% | 1033130 | 412150 | 1.6
E750-RFI-0147 | E750-CO-027 | 60.93% | 1611170 | 642750 | 2.4
E750-RFI-0158 | E750-CO-028 | 100% | 205300 | 205300 | 0
E750-RFI-0165 | E750-CO-029 | 29.9% | 1390310 | 1065130 | 4.5
E750-RFI-0168 | E750-CO-029 | 70.1% | 3259690 | 2497270 | 10.5
E750-RFI-0171 | E750-CO-030 | 100% | 695100 | 317800 | 0
E750-RFI-0174 | E750-CO-031 | 100% | 2475400 | 1457300 | 0
E750-RFI-0176 | E750-CO-032 | 100% | 700900 | 593700 | 24
E750-RFI-0179 | E750-CO-033 | 100% | 2090600 | 1025800 | 0
E750-RFI-0181 | E750-CO-034 | 100% | 144100 | 60100 | 0
E750-RFI-0188 | E750-CO-035 | 100% | 238400 | 143800 | 8
E750-RFI-0186 | E750-CO-036 | 100% | 1578200 | 1066100 | 8
E750-RFI-0197 | E750-CO-037 | 100% | 2431400 | 2010500 | 0
E750-RFI-0204 | E750-CO-038 | 100% | 2809000 | 1273600 | 0
E750-RFI-0205 | E750-CO-039 | 100% | 3873100 | 1680900 | 0
E750-RFI-0209 | E750-CO-040 | 100% | 3230100 | 1839900 | 0
E750-RFI-0217 | E750-CO-041 | 100% | 782100 | 782100 | 0
E750-RFI-0218 | E750-CO-042 | 100% | 1475300 | 1286800 | 0

## Data_Dictionary
column(s) | description | available_at_submittal
rfi_id | Unique RFI number (package-RFI-seq) | Y
package_id | Contract package | Y
content_category_code / content_category | PRIMARY content classification (12 categories) – the variable under test | Y
location | Station/segment/structure | Y
spec_section | CSI-style spec section referenced | Y
subject / description | Free text as submitted | Y
submitted_date | Date submitted | Y
required_response_days | Contract response requirement (days) | Y
contractor_priority_flag | Routine/Expedite/Urgent set by contractor (noisy) | Y
contractor_claims_cost_impact / _schedule_impact | Contractor asserts impact at submittal | Y
on_critical_path_at_submittal | Scheduler flag: affected activity on critical path | Y
attachments / num_reviewers / assigned_reviewer | Routing metadata | Y
response_date, response_days_initial, response_on_time, days_overdue_initial | First response timing (calendar days) | N
revision_cycles, closed_date, response_days_final | Re-response after partial answers | N
status | Closed or Void/Withdrawn | N
schedule_impact_days_claimed | Contractor-claimed delay (days) | N
critical_path_delay_days_actual | Realized critical-path delay attributable to RFI | N
float_consumed_days_actual | Float consumed on non-critical activities | N
contractor_est_cost_low_usd / high | Contractor early estimate range when RFI raised (only if cost impact claimed) | N
led_to_change_order, linked_co_ids | Whether/which COs resulted | N
linked_requested_cost_usd, linked_approved_cost_usd, linked_time_granted_days | Cost/time allocated from COs to this RFI | N
impact_score_0_100, true_priority_rank, true_priority_tier | GROUND TRUTH label derived from outcomes – use as target, never as feature | N
Change_Orders.* | CO/PCO register: dates (notice, pricing, close), cycle times, requested cost, time requested, dispute path, funding | N
CO_Outcomes.* | Outcome, final approved cost/time, % of request, cumulative time granted per package (float erosion proxy) | N
RFI_CO_Link.* | Many-to-many link with cost/time allocation shares (sum to 1 per CO) | N